## 1_EXECUTIVE_DASHBOARD
PRODUCTION PLANNING - EXECUTIVE DASHBOARD (FIXED - ALL 8 STAGES) v2
Planning Period: Week 1-19 (19 weeks) ¦ Start Date: November 22, 2025
KEY PERFORMANCE METRICS
Metric | Value | Target | Status | Trend
Total Casting Volume | 1,788 tons | 15,200 tons | ✓ On Track | →
Average Weekly Casting | 94 tons/week | 800 tons/week | ✓ Good | →
Total Units Delivered | 2,827 units |  |  | →
Overall Fulfillment Rate | 99.4% | ≥90% | ✓ Excellent | ↑
On-Time Delivery Rate | 89.4% | ≥85% | ✓ Good | ↑
CRITICAL ALERTS & ACTION ITEMS
Priority | Issue | Impact | Action Required
🔴 CRITICAL | Unmet Demand | 22 units cannot be fulfilled | Increase capacity or extend timeline
🟡 WARNING | Casting capacity | 91% utilization | Monitor and plan backup
🟡 WARNING | Grinding capacity | 87% utilization | Monitor and plan backup
🟡 WARNING | Machining Stage 1 | 88% utilization | Monitor and plan backup
🟡 WARNING | Painting Stage 1 (Primer) | 91% utilization | Monitor and plan backup
🟡 WARNING | Painting Stage 2 (Intermediate) | 91% utilization | Monitor and plan backup
🟡 WARNING | Painting Stage 3 (Top Coat) | 91% utilization | Monitor and plan backup
🟡 WARNING | Big Line moulding capacity | 94% utilization | Monitor and plan backup
🟡 WARNING | Small Line moulding capacity | 89% utilization | Monitor and plan backup
CAPACITY UTILIZATION SUMMARY - ALL 8 PRODUCTION STAGES
Stage | Avg % | Max % | Status | Recommendation
Casting | 11.5% | 91.0% | 🟡 Warning | Plan additional resources
Grinding | 17.6% | 86.8% | 🟡 Warning | Plan additional resources
Machining Stage 1 (MC1) | 18.1% | 87.9% | 🟡 Warning | Plan additional resources
Machining Stage 2 (MC2) | 14.6% | 64.5% | 🟢 Healthy | Continue monitoring
Machining Stage 3 (MC3) | 3.7% | 25.0% | 🟢 Healthy | Continue monitoring
Painting Stage 1 - Primer (SP1) | 19.3% | 91.0% | 🟡 Warning | Plan additional resources
Painting Stage 2 - Intermediate (SP2) | 17.3% | 91.0% | 🟡 Warning | Plan additional resources
Painting Stage 3 - Top Coat (SP3) | 12.3% | 91.0% | 🟡 Warning | Plan additional resources
Big Line Moulding | 16.2% | 94.0% | 🟡 Warning | Plan additional resources
Small Line Moulding | 15.2% | 88.6% | 🟡 Warning | Plan additional resources

## 2_MASTER_SCHEDULE
MASTER SHIPMENT SCHEDULE - WITH SHIP DATES
Track all scheduled shipments with actual ship dates (distributed across working days Mon-Sat)
Week | Ship Date | Committed Date | Material Code | Customer | Sales Order | Quantity | Committed Week | Status | Early/Late | Notes
W1 | 2025-11-22 | 2025-11-22 | ARM-004-N | Unknown | 2526100558 | 4 | W1 | ✓ On-Time | 0
W1 | 2025-11-24 | 2025-11-22 | ARM-004-N | Unknown | 2526100561 | 1 | W1 | ✓ On-Time | 0
W1 | 2025-11-25 | 2025-11-22 | ARM-004-N | Unknown | 2526100562 | 5 | W1 | ✓ On-Time | 0
W1 | 2025-11-26 | 2025-11-22 | ARM-004-N | Unknown | 2526100563 | 7 | W1 | ✓ On-Time | 0
W1 | 2025-11-27 | 2025-11-22 | ARM-007 | Unknown | 2526100559 | 1 | W1 | ✓ On-Time | 0
W1 | 2025-11-28 | 2025-11-22 | ARM-007 | Unknown | 2526100560 | 2 | W1 | ✓ On-Time | 0
W1 | 2025-11-22 | 2025-11-22 | ARM-007 | Unknown | 2526100564 | 2 | W1 | ✓ On-Time | 0
W1 | 2025-11-24 | 2025-11-22 | ARM-007 | Unknown | 2526100565 | 4 | W1 | ✓ On-Time | 0
W1 | 2025-11-25 | 2025-11-22 | ARM-007 | Unknown | 2526100566 | 4 | W1 | ✓ On-Time | 0
W1 | 2025-11-26 | 2025-11-22 | ARM-007 | Unknown | 2526100569 | 1 | W1 | ✓ On-Time | 0
W1 | 2025-11-27 | 2025-11-22 | ATT-001 | Unknown | 2526201015 | 3 | W1 | ✓ On-Time | 0
W1 | 2025-11-28 | 2025-11-22 | ATT-001 | Unknown | 2526202952 | 3 | W1 | ✓ On-Time | 0
W1 | 2025-11-22 | 2025-11-22 | ATT-001 | Unknown | 2526202953 | 3 | W1 | ✓ On-Time | 0
W1 | 2025-11-24 | 2025-11-22 | ATT-002 | Unknown | 2526201015 | 5 | W1 | ✓ On-Time | 0
W1 | 2025-11-25 | 2025-11-22 | ATT-002 | Unknown | 2526202952 | 4 | W1 | ✓ On-Time | 0
W1 | 2025-11-26 | 2025-11-22 | ATT-002 | Unknown | 2526202953 | 4 | W1 | ✓ On-Time | 0
W1 | 2025-11-27 | 2025-11-22 | DGC-001 | Unknown | 2526202970 | 12 | W1 | ✓ On-Time | 0
W1 | 2025-11-28 | 2025-11-22 | DGC-001 | Unknown | 2526202971 | 12 | W1 | ✓ On-Time | 0
W1 | 2025-11-22 | 2025-11-22 | DGC-001 | Unknown | 2526203269 | 11 | W1 | ✓ On-Time | 0
W1 | 2025-11-24 | 2025-11-22 | DGC-001 | Unknown | 2526203270 | 7 | W1 | ✓ On-Time | 0
W1 | 2025-11-25 | 2025-11-29 | DGC-006 | Unknown | 2526203332 | 4 | W2 | ✓ On-Time | -1
W1 | 2025-11-26 | 2025-11-29 | DGC-012 | Unknown | 2526203271 | 14 | W2 | ✓ On-Time | -1
W1 | 2025-11-27 | 2025-11-22 | KBS-008 | Unknown | 2526500109 | 20 | W1 | ✓ On-Time | 0
W1 | 2025-11-28 | 2025-11-22 | KBS-009 | Unknown | 2526500114 | 18 | W1 | ✓ On-Time | 0
W1 | 2025-11-22 | 2025-11-22 | KBS-009 | Unknown | 2526500124 | 18 | W1 | ✓ On-Time | 0
W1 | 2025-11-24 | 2025-11-22 | KBS-010 | Unknown | 2526500115 | 8 | W1 | ✓ On-Time | 0
W1 | 2025-11-25 | 2025-11-22 | KBS-011 | Unknown | 2526500116 | 13 | W1 | ✓ On-Time | 0
W1 | 2025-11-26 | 2025-11-22 | KBS-012 | Unknown | 2526500083 | 1 | W1 | ✓ On-Time | 0
W1 | 2025-11-27 | 2025-11-29 | KBS-012 | Unknown | 2526500126 | 11 | W2 | ✓ On-Time | -1
W1 | 2025-11-28 | 2025-11-29 | KBS-012 | Unknown | 2526500127 | 10 | W2 | ✓ On-Time | -1
W1 | 2025-11-22 | 2025-11-22 | KBS-014 | Unknown | 2526500107 | 24 | W1 | ✓ On-Time | 0
W1 | 2025-11-24 | 2025-11-29 | KBS-014 | Unknown | 2526500130 | 24 | W2 | ✓ On-Time | -1
W1 | 2025-11-25 | 2025-11-22 | KBS-016 | Unknown | 2526500086 | 19 | W1 | ✓ On-Time | 0
W1 | 2025-11-26 | 2025-11-22 | KBS-016 | Unknown | 2526500104 | 19 | W1 | ✓ On-Time | 0
W1 | 2025-11-27 | 2025-11-22 | KBS-016 | Unknown | 2526500105 | 19 | W1 | ✓ On-Time | 0
W1 | 2025-11-28 | 2025-11-22 | KBS-017 | Unknown | 2526500087 | 5 | W1 | ✓ On-Time | 0
W1 | 2025-11-22 | 2025-11-22 | KBS-017 | Unknown | 2526500092 | 1 | W1 | ✓ On-Time | 0
W1 | 2025-11-24 | 2025-11-22 | KBS-017 | Unknown | 2526500094 | 15 | W1 | ✓ On-Time | 0
W1 | 2025-11-25 | 2025-11-22 | KBS-017 | Unknown | 2526500095 | 17 | W1 | ✓ On-Time | 0
W1 | 2025-11-26 | 2025-11-22 | KBS-017 | Unknown | 2526500096 | 14 | W1 | ✓ On-Time | 0
W1 | 2025-11-27 | 2025-11-22 | KBS-017 | Unknown | 2526500097 | 3 | W1 | ✓ On-Time | 0
W1 | 2025-11-28 | 2025-11-22 | KBS-018 | Unknown | 2526500091 | 8 | W1 | ✓ On-Time | 0
W1 | 2025-11-22 | 2025-11-22 | KBS-018 | Unknown | 2526500093 | 16 | W1 | ✓ On-Time | 0
W1 | 2025-11-24 | 2025-11-22 | LKK-01 | Unknown | 2526202458 | 2 | W1 | ✓ On-Time | 0
W1 | 2025-11-25 | 2025-11-22 | LKK-02 | Unknown | 2526202458 | 4 | W1 | ✓ On-Time | 0
W1 | 2025-11-26 | 2025-11-22 | LKK-03 | Unknown | 2526202458 | 3 | W1 | ✓ On-Time | 0
W1 | 2025-11-27 | 2025-11-22 | LKK-04 | Unknown | 2526202458 | 3 | W1 | ✓ On-Time | 0
W1 | 2025-11-28 | 2025-11-22 | LKK-05 | Unknown | 2526202458 | 4 | W1 | ✓ On-Time | 0
W1 | 2025-11-22 | 2025-11-22 | LKK-06 | Unknown | 2526202458 | 4 | W1 | ✓ On-Time | 0
W1 | 2025-11-24 | 2025-11-22 | LKK-10 | Unknown | 2526202459 | 2 | W1 | ✓ On-Time | 0
W1 | 2025-11-25 | 2025-11-22 | LKK-11 | Unknown | 2526202459 | 1 | W1 | ✓ On-Time | 0
W1 | 2025-11-26 | 2025-11-22 | LKK-12 | Unknown | 2526202459 | 10 | W1 | ✓ On-Time | 0
W1 | 2025-11-27 | 2025-11-29 | LKK-17 | Unknown | 2526203463 | 5 | W2 | ✓ On-Time | -1
W1 | 2025-11-28 | 2025-11-22 | MCB-007 | Unknown | 2526203284 | 1 | W1 | ✓ On-Time | 0
W1 | 2025-11-22 | 2025-11-22 | MCB-007 | Unknown | 2526203285 | 1 | W1 | ✓ On-Time | 0
W1 | 2025-11-24 | 2025-11-29 | MCB-008 | Unknown | 2526203153 | 3 | W2 | ✓ On-Time | -1
W1 | 2025-11-25 | 2025-11-29 | MCB-008 | Unknown | 2526203154 | 3 | W2 | ✓ On-Time | -1
W1 | 2025-11-26 | 2025-11-29 | MCB-008 | Unknown | 2526203164 | 2 | W2 | ✓ On-Time | -1
W1 | 2025-11-27 | 2025-11-22 | MCB-009 | Unknown | 2526203038 | 7 | W1 | ✓ On-Time | 0
W1 | 2025-11-28 | 2025-11-22 | MCB-009 | Unknown | 2526203139 | 6 | W1 | ✓ On-Time | 0
W1 | 2025-11-22 | 2025-11-29 | MCB-010 | Unknown | 2526203171 | 2 | W2 | ✓ On-Time | -1
W1 | 2025-11-24 | 2025-11-29 | MCB-010 | Unknown | 2526203172 | 2 | W2 | ✓ On-Time | -1
W1 | 2025-11-25 | 2025-11-29 | MCB-010 | Unknown | 2526203173 | 2 | W2 | ✓ On-Time | -1
W1 | 2025-11-26 | 2025-11-29 | MCB-010 | Unknown | 2526203174 | 2 | W2 | ✓ On-Time | -1
W1 | 2025-11-27 | 2025-11-29 | MCB-010 | Unknown | 2526203175 | 2 | W2 | ✓ On-Time | -1
W1 | 2025-11-28 | 2025-11-29 | MCB-010 | Unknown | 2526203176 | 1 | W2 | ✓ On-Time | -1
W1 | 2025-11-22 | 2025-11-29 | MCB-010 | Unknown | 2526203177 | 1 | W2 | ✓ On-Time | -1
W1 | 2025-11-24 | 2025-11-22 | MCB-HYG-016 | Unknown | 2526202705 | 4 | W1 | ✓ On-Time | 0
W1 | 2025-11-25 | 2025-11-22 | MCB-HYG-016 | Unknown | 2526202706 | 4 | W1 | ✓ On-Time | 0
W1 | 2025-11-26 | 2025-11-22 | MCB-HYG-016 | Unknown | 2526202707 | 4 | W1 | ✓ On-Time | 0
W1 | 2025-11-27 | 2025-11-22 | MCB-HYG-016 | Unknown | 2526202708 | 4 | W1 | ✓ On-Time | 0
W1 | 2025-11-28 | 2025-11-22 | MCB-HYG-023 | Unknown | 2526202788 | 6 | W1 | ✓ On-Time | 0
W1 | 2025-11-22 | 2025-11-22 | MCB-HYG-023 | Unknown | 2526202818 | 5 | W1 | ✓ On-Time | 0
W1 | 2025-11-24 | 2025-11-22 | MCB-HYG-026 | Unknown | 2526202474 | 5 | W1 | ✓ On-Time | 0
W1 | 2025-11-25 | 2025-11-22 | MCB-HYG-026 | Unknown | 2526202709 | 4 | W1 | ✓ On-Time | 0
W1 | 2025-11-26 | 2025-11-22 | MCB-JLG-014 | Unknown | 2526203279 | 6 | W1 | ✓ On-Time | 0
W1 | 2025-11-27 | 2025-11-22 | MCB-JLG-020 | Unknown | 2526203039 | 4 | W1 | ✓ On-Time | 0
W1 | 2025-11-28 | 2025-11-22 | MCB-JLG-020 | Unknown | 2526203143 | 4 | W1 | ✓ On-Time | 0
W1 | 2025-11-22 | 2025-11-29 | MCB-JLG-031 | Unknown | 2526201341 | 1 | W2 | ✓ On-Time | -1
W1 | 2025-11-24 | 2025-11-22 | MCB-JLG-046 | Unknown | 2526202810 | 3 | W1 | ✓ On-Time | 0
W1 | 2025-11-25 | 2025-11-22 | MCB-JLG-046 | Unknown | 2526202810 | 1 | W1 | ✓ On-Time | 0
W1 | 2025-11-26 | 2025-11-22 | MCB-JLG-047 | Unknown | 2526203057 | 9 | W1 | ✓ On-Time | 0
W1 | 2025-11-27 | 2025-11-22 | MCB-JLG-047 | Unknown | 2526203141 | 9 | W1 | ✓ On-Time | 0
W1 | 2025-11-28 | 2025-11-22 | NMS-H-001 | Unknown | 2526203092 | 13 | W1 | ✓ On-Time | 0
W1 | 2025-11-22 | 2025-11-22 | NMS-H-001 | Unknown | 2526203093 | 13 | W1 | ✓ On-Time | 0
W1 | 2025-11-24 | 2025-11-22 | NMS-V-003 | Unknown | 2526203094 | 10 | W1 | ✓ On-Time | 0
W1 | 2025-11-25 | 2025-11-22 | NMS-V-004 | Unknown | 2526202939 | 5 | W1 | ✓ On-Time | 0
W1 | 2025-11-26 | 2025-11-22 | NMS-V-004 | Unknown | 2526203090 | 4 | W1 | ✓ On-Time | 0
W1 | 2025-11-27 | 2025-11-22 | NMS-V-004 | Unknown | 2526203091 | 4 | W1 | ✓ On-Time | 0
W1 | 2025-11-28 | 2025-11-22 | TAS-GN-004 | Unknown | 2526202713 | 2 | W1 | ✓ On-Time | 0
W1 | 2025-11-22 | 2025-11-29 | TAS-GN-006 | Unknown | 2526201561 | 3 | W2 | ✓ On-Time | -1
W1 | 2025-11-24 | 2025-11-22 | TAS-GN-008 | Unknown | 2526201611 | 3 | W1 | ✓ On-Time | 0
W1 | 2025-11-25 | 2025-11-22 | TAS-GN-008 | Unknown | 2526201804 | 2 | W1 | ✓ On-Time | 0
W1 | 2025-11-26 | 2025-11-22 | TAS-GN-008 | Unknown | 2526202929 | 1 | W1 | ✓ On-Time | 0
W1 | 2025-11-27 | 2025-11-22 | UBC-018 | Unknown | 2526203023 | 18 | W1 | ✓ On-Time | 0
W1 | 2025-11-28 | 2025-11-22 | UBC-020 | Unknown | 2526202941 | 1 | W1 | ✓ On-Time | 0
W1 | 2025-11-22 | 2025-11-22 | UBC-020 | Unknown | 2526202947 | 3 | W1 | ✓ On-Time | 0
W1 | 2025-11-24 | 2025-11-22 | UBC-020 | Unknown | 2526203022 | 6 | W1 | ✓ On-Time | 0
W1 | 2025-11-25 | 2025-11-22 | UBC-020 | Unknown | 2526203022 | 6 | W1 | ✓ On-Time | 0
W1 | 2025-11-26 | 2025-11-22 | UBC-022 | Unknown | 2526202943 | 3 | W1 | ✓ On-Time | 0
W1 | 2025-11-27 | 2025-11-22 | UBC-022 | Unknown | 2526202943 | 3 | W1 | ✓ On-Time | 0
W1 | 2025-11-28 | 2025-11-22 | UBC-022 | Unknown | 2526203022 | 2 | W1 | ✓ On-Time | 0
W1 | 2025-11-22 | 2025-11-22 | UBC-022 | Unknown | 2526203022 | 2 | W1 | ✓ On-Time | 0
W1 | 2025-11-24 | 2025-11-22 | UBC-035 | Unknown | 2526100367 | 46 | W1 | ✓ On-Time | 0
W1 | 2025-11-25 | 2025-11-22 | UBC-046 | Unknown | 2526201681 | 7 | W1 | ✓ On-Time | 0
W1 | 2025-11-26 | 2025-11-22 | UBC-050 | Unknown | 2526202947 | 5 | W1 | ✓ On-Time | 0
W1 | 2025-11-27 | 2025-11-22 | UBC-050 | Unknown | 2526203022 | 3 | W1 | ✓ On-Time | 0
W1 | 2025-11-28 | 2025-11-22 | UBC-051 | Unknown | 2526202947 | 5 | W1 | ✓ On-Time | 0
W1 | 2025-11-22 | 2025-11-22 | UBC-051 | Unknown | 2526203022 | 3 | W1 | ✓ On-Time | 0
W1 | 2025-11-24 | 2025-11-29 | UBC-051 | Unknown | 2526203076 | 4 | W2 | ✓ On-Time | -1
W1 | 2025-11-25 | 2025-11-22 | UBC-062 | Unknown | 2526200576 | 2 | W1 | ✓ On-Time | 0
W1 | 2025-11-26 | 2025-11-22 | UBC-063 | Unknown | 2526200576 | 2 | W1 | ✓ On-Time | 0
W1 | 2025-11-27 | 2025-11-22 | UBC-064 | Unknown | 2526200576 | 2 | W1 | ✓ On-Time | 0
W1 | 2025-11-28 | 2025-11-22 | UBC-064 | Unknown | 2526203434 | 1 | W1 | ✓ On-Time | 0
W2 | 2025-11-29 | 2025-11-29 | ARM-007 | Unknown | 2526100567 | 4 | W2 | ✓ On-Time | 0
W2 | 2025-12-01 | 2025-11-29 | ATT-001 | Unknown | 2526201561 | 1 | W2 | ✓ On-Time | 0
W2 | 2025-12-02 | 2025-11-29 | DGC-001 | Unknown | 2526203271 | 38 | W2 | ✓ On-Time | 0
W2 | 2025-12-03 | 2025-11-29 | KBS-009 | Unknown | 2526500120 | 20 | W2 | ✓ On-Time | 0
W2 | 2025-12-04 | 2025-11-29 | KBS-011 | Unknown | 2526500122 | 15 | W2 | ✓ On-Time | 0
W2 | 2025-12-05 | 2025-11-29 | KBS-011 | Unknown | 2526500125 | 15 | W2 | ✓ On-Time | 0
W2 | 2025-11-29 | 2025-11-29 | KBS-017 | Unknown | 2526500098 | 22 | W2 | ✓ On-Time | 0
W2 | 2025-12-01 | 2025-11-29 | KBS-017 | Unknown | 2526500106 | 12 | W2 | ✓ On-Time | 0
W2 | 2025-12-02 | 2025-11-29 | LKK-01 | Unknown | 2526201561 | 2 | W2 | ✓ On-Time | 0
W2 | 2025-12-03 | 2025-11-29 | LKK-01 | Unknown | 2526202964 | 8 | W2 | ✓ On-Time | 0
W2 | 2025-12-04 | 2025-11-29 | LKK-02 | Unknown | 2526202964 | 8 | W2 | ✓ On-Time | 0
W2 | 2025-12-05 | 2025-12-06 | LKK-02 | Unknown | 2526202965 | 8 | W3 | ✓ On-Time | -1
W2 | 2025-11-29 | 2025-11-29 | LKK-03 | Unknown | 2526202964 | 8 | W2 | ✓ On-Time | 0
W2 | 2025-12-01 | 2025-12-06 | LKK-03 | Unknown | 2526202965 | 8 | W3 | ✓ On-Time | -1
W2 | 2025-12-02 | 2025-12-06 | LKK-031 | Unknown | 2526203464 | 3 | W3 | ✓ On-Time | -1
W2 | 2025-12-03 | 2025-12-06 | LKK-033 | Unknown | 2526203464 | 2 | W3 | ✓ On-Time | -1
W2 | 2025-12-04 | 2025-12-06 | LKK-034 | Unknown | 2526203464 | 1 | W3 | ✓ On-Time | -1
W2 | 2025-12-05 | 2025-11-29 | LKK-04 | Unknown | 2526203463 | 4 | W2 | ✓ On-Time | 0
W2 | 2025-11-29 | 2025-11-29 | LKK-05 | Unknown | 2526203463 | 4 | W2 | ✓ On-Time | 0
W2 | 2025-12-01 | 2025-11-29 | LKK-06 | Unknown | 2526203463 | 4 | W2 | ✓ On-Time | 0
W2 | 2025-12-02 | 2025-11-29 | LKK-16 | Unknown | 2526203463 | 12 | W2 | ✓ On-Time | 0
W2 | 2025-12-03 | 2025-11-29 | LKK-17 | Unknown | 2526203463 | 7 | W2 | ✓ On-Time | 0
W2 | 2025-12-04 | 2025-12-06 | MCB-007 | Unknown | 2526203256 | 4 | W3 | ✓ On-Time | -1
W2 | 2025-12-05 | 2025-12-06 | MCB-007 | Unknown | 2526203386 | 4 | W3 | ✓ On-Time | -1
W2 | 2025-11-29 | 2025-12-06 | MCB-007 | Unknown | 2526203387 | 4 | W3 | ✓ On-Time | -1
W2 | 2025-12-01 | 2025-12-06 | MCB-008 | Unknown | 2526203255 | 6 | W3 | ✓ On-Time | -1
W2 | 2025-12-02 | 2025-11-29 | MCB-009 | Unknown | 2526201341 | 7 | W2 | ✓ On-Time | 0
W2 | 2025-12-03 | 2025-11-29 | MCB-009 | Unknown | 2526203138 | 12 | W2 | ✓ On-Time | 0
W2 | 2025-12-04 | 2025-11-29 | MCB-010 | Unknown | 2526203171 | 3 | W2 | ✓ On-Time | 0
W2 | 2025-12-05 | 2025-11-29 | MCB-010 | Unknown | 2526203172 | 3 | W2 | ✓ On-Time | 0
W2 | 2025-11-29 | 2025-11-29 | MCB-010 | Unknown | 2526203173 | 3 | W2 | ✓ On-Time | 0
W2 | 2025-12-01 | 2025-11-29 | MCB-010 | Unknown | 2526203174 | 2 | W2 | ✓ On-Time | 0
W2 | 2025-12-02 | 2025-11-29 | MCB-010 | Unknown | 2526203175 | 2 | W2 | ✓ On-Time | 0
W2 | 2025-12-03 | 2025-11-29 | MCB-010 | Unknown | 2526203176 | 2 | W2 | ✓ On-Time | 0
W2 | 2025-12-04 | 2025-11-29 | MCB-010 | Unknown | 2526203177 | 2 | W2 | ✓ On-Time | 0
W2 | 2025-12-05 | 2025-11-29 | MCB-HYG-016 | Unknown | 2526202819 | 5 | W2 | ✓ On-Time | 0
W2 | 2025-11-29 | 2025-11-29 | MCB-HYG-016 | Unknown | 2526202820 | 5 | W2 | ✓ On-Time | 0
W2 | 2025-12-01 | 2025-11-29 | MCB-HYG-034 | Unknown | 2526201160 | 9 | W2 | ✓ On-Time | 0
W2 | 2025-12-02 | 2025-11-29 | MCB-JLG-014 | Unknown | 2526203131 | 1 | W2 | ✓ On-Time | 0
W2 | 2025-12-03 | 2025-11-29 | MCB-JLG-019 | Unknown | 2526203249 | 1 | W2 | ✓ On-Time | 0
W2 | 2025-12-04 | 2025-11-29 | MCB-JLG-019 | Unknown | 2526203250 | 1 | W2 | ✓ On-Time | 0
W2 | 2025-12-05 | 2025-11-29 | MCB-JLG-020 | Unknown | 2526203142 | 4 | W2 | ✓ On-Time | 0
W2 | 2025-11-29 | 2025-11-29 | MCB-JLG-047 | Unknown | 2526203140 | 11 | W2 | ✓ On-Time | 0
W2 | 2025-12-01 | 2025-12-06 | TAS-GN-009 | Unknown | 2526203459 | 20 | W3 | ✓ On-Time | -1
W2 | 2025-12-02 | 2025-12-06 | TAS-GN-012 | Unknown | 2526203456 | 2 | W3 | ✓ On-Time | -1
W2 | 2025-12-03 | 2025-11-29 | UBC-014 | Unknown | 2526203078 | 20 | W2 | ✓ On-Time | 0
W2 | 2025-12-04 | 2025-11-29 | UBC-020 | Unknown | 2526203076 | 8 | W2 | ✓ On-Time | 0
W2 | 2025-12-05 | 2025-11-29 | UBC-022 | Unknown | 2526203076 | 4 | W2 | ✓ On-Time | 0
W2 | 2025-11-29 | 2025-11-29 | UBC-050 | Unknown | 2526203076 | 4 | W2 | ✓ On-Time | 0
W3 | 2025-12-06 | 2025-12-06 | ARM-007 | Unknown | 2526100568 | 4 | W3 | ✓ On-Time | 0
W3 | 2025-12-08 | 2025-12-13 | ATT-001 | Unknown | 2526202954 | 3 | W4 | ✓ On-Time | -1
W3 | 2025-12-09 | 2025-12-13 | ATT-001 | Unknown | 2526202955 | 2 | W4 | ✓ On-Time | -1
W3 | 2025-12-10 | 2025-12-13 | ATT-002 | Unknown | 2526202954 | 2 | W4 | ✓ On-Time | -1
W3 | 2025-12-11 | 2025-12-13 | ATT-002 | Unknown | 2526202955 | 2 | W4 | ✓ On-Time | -1
W3 | 2025-12-12 | 2025-12-13 | DGC-001 | Unknown | 2526203274 | 56 | W4 | ✓ On-Time | -1
W3 | 2025-12-06 | 2025-11-29 | DGC-006 | Unknown | 2526203332 | 6 | W2 | ⚠ 1w Late | 1 | Minor delay
W3 | 2025-12-08 | 2025-11-29 | DGC-009 | Unknown | 2526203332 | 14 | W2 | ⚠ 1w Late | 1 | Minor delay
W3 | 2025-12-09 | 2025-11-29 | KBS-012 | Unknown | 2526500126 | 14 | W2 | ⚠ 1w Late | 1 | Minor delay
W3 | 2025-12-10 | 2025-11-29 | KBS-012 | Unknown | 2526500127 | 13 | W2 | ⚠ 1w Late | 1 | Minor delay
W3 | 2025-12-11 | 2025-12-06 | KBS-014 | Unknown | 2526500131 | 24 | W3 | ✓ On-Time | 0
W3 | 2025-12-12 | 2025-12-06 | KBS-016 | Unknown | 2526500110 | 24 | W3 | ✓ On-Time | 0
W3 | 2025-12-06 | 2025-12-06 | KBS-017 | Unknown | 2526500099 | 22 | W3 | ✓ On-Time | 0
W3 | 2025-12-08 | 2025-12-06 | LKK-01 | Unknown | 2526202965 | 8 | W3 | ✓ On-Time | 0
W3 | 2025-12-09 | 2025-12-06 | LKK-030 | Unknown | 2526203464 | 3 | W3 | ✓ On-Time | 0
W3 | 2025-12-10 | 2025-12-06 | LKK-032 | Unknown | 2526203464 | 3 | W3 | ✓ On-Time | 0
W3 | 2025-12-11 | 2025-12-06 | LKK-033 | Unknown | 2526203464 | 4 | W3 | ✓ On-Time | 0
W3 | 2025-12-12 | 2025-12-06 | LKK-034 | Unknown | 2526203464 | 2 | W3 | ✓ On-Time | 0
W3 | 2025-12-06 | 2025-12-13 | LKK-10 | Unknown | 2526203095 | 6 | W4 | ✓ On-Time | -1
W3 | 2025-12-08 | 2025-12-13 | LKK-11 | Unknown | 2526203095 | 10 | W4 | ✓ On-Time | -1
W3 | 2025-12-09 | 2025-12-13 | LKK-12 | Unknown | 2526203095 | 1 | W4 | ✓ On-Time | -1
W3 | 2025-12-10 | 2025-11-29 | MCB-010 | Unknown | 2526203171 | 2 | W2 | ⚠ 1w Late | 1 | Minor delay
W3 | 2025-12-11 | 2025-11-29 | MCB-010 | Unknown | 2526203172 | 2 | W2 | ⚠ 1w Late | 1 | Minor delay
W3 | 2025-12-12 | 2025-11-29 | MCB-010 | Unknown | 2526203173 | 1 | W2 | ⚠ 1w Late | 1 | Minor delay
W3 | 2025-12-06 | 2025-11-29 | MCB-010 | Unknown | 2526203174 | 1 | W2 | ⚠ 1w Late | 1 | Minor delay
W3 | 2025-12-08 | 2025-11-29 | MCB-010 | Unknown | 2526203175 | 1 | W2 | ⚠ 1w Late | 1 | Minor delay
W3 | 2025-12-09 | 2025-11-29 | MCB-010 | Unknown | 2526203176 | 1 | W2 | ⚠ 1w Late | 1 | Minor delay
W3 | 2025-12-10 | 2025-11-29 | MCB-010 | Unknown | 2526203177 | 1 | W2 | ⚠ 1w Late | 1 | Minor delay
W3 | 2025-12-11 | 2025-12-06 | MCB-010 | Unknown | 2526203260 | 7 | W3 | ✓ On-Time | 0
W3 | 2025-12-12 | 2025-12-06 | MCB-010 | Unknown | 2526203396 | 7 | W3 | ✓ On-Time | 0
W3 | 2025-12-06 | 2025-12-06 | MCB-010 | Unknown | 2526203397 | 7 | W3 | ✓ On-Time | 0
W3 | 2025-12-08 | 2025-12-06 | MCB-HYG-015 | Unknown | 2526203253 | 8 | W3 | ✓ On-Time | 0
W3 | 2025-12-09 | 2025-12-06 | MCB-HYG-023 | Unknown | 2526203252 | 6 | W3 | ✓ On-Time | 0
W3 | 2025-12-10 | 2025-12-13 | MCB-HYG-023 | Unknown | 2526203398 | 6 | W4 | ✓ On-Time | -1
W3 | 2025-12-11 | 2025-12-06 | MCB-JLG-014 | Unknown | 2526203261 | 6 | W3 | ✓ On-Time | 0
W3 | 2025-12-12 | 2025-12-06 | MCB-JLG-014 | Unknown | 2526203262 | 6 | W3 | ✓ On-Time | 0
W3 | 2025-12-06 | 2025-11-29 | MCB-JLG-019 | Unknown | 2526203249 | 15 | W2 | ⚠ 1w Late | 1 | Minor delay
W3 | 2025-12-08 | 2025-11-29 | MCB-JLG-019 | Unknown | 2526203250 | 14 | W2 | ⚠ 1w Late | 1 | Minor delay
W3 | 2025-12-09 | 2025-11-29 | MCB-JLG-019 | Unknown | 2526203251 | 14 | W2 | ⚠ 1w Late | 1 | Minor delay
W3 | 2025-12-10 | 2025-11-29 | MCB-JLG-032 | Unknown | 2526203388 | 4 | W2 | ⚠ 1w Late | 1 | Minor delay
W3 | 2025-12-11 | 2025-12-06 | MCB-JLG-033 | Unknown | 2526203258 | 3 | W3 | ✓ On-Time | 0
W3 | 2025-12-12 | 2025-12-13 | TAS-GN-004 | Unknown | 2526203460 | 2 | W4 | ✓ On-Time | -1
W3 | 2025-12-06 | 2025-11-29 | TAS-GN-006 | Unknown | 2526201561 | 3 | W2 | ⚠ 1w Late | 1 | Minor delay
W3 | 2025-12-08 | 2025-12-06 | TAS-GN-006 | Unknown | 2526203459 | 9 | W3 | ✓ On-Time | 0
W3 | 2025-12-09 | 2025-12-06 | TAS-GN-007 | Unknown | 2526203459 | 20 | W3 | ✓ On-Time | 0
W3 | 2025-12-10 | 2025-12-06 | TAS-GN-008 | Unknown | 2526203456 | 1 | W3 | ✓ On-Time | 0
W3 | 2025-12-11 | 2025-12-06 | TAS-GN-012 | Unknown | 2526203456 | 5 | W3 | ✓ On-Time | 0
W3 | 2025-12-12 | 2025-12-06 | TAS-GN-014 | Unknown | 2526203459 | 10 | W3 | ✓ On-Time | 0
W3 | 2025-12-06 | 2025-12-06 | TAS-GN-021 | Unknown | 2526203454 | 12 | W3 | ✓ On-Time | 0
W3 | 2025-12-08 | 2025-12-13 | TAS-GN-021 | Unknown | 2526203455 | 14 | W4 | ✓ On-Time | -1
W3 | 2025-12-09 | 2025-12-06 | TAS-GN-029 | Unknown | 2526203454 | 6 | W3 | ✓ On-Time | 0
W3 | 2025-12-10 | 2025-12-06 | TAS-GN-029 | Unknown | 2526203454 | 12 | W3 | ✓ On-Time | 0
W3 | 2025-12-11 | 2025-12-06 | TAS-GN-029 | Unknown | 2526203454 | 12 | W3 | ✓ On-Time | 0
W3 | 2025-12-12 | 2025-12-13 | TAS-GN-029 | Unknown | 2526203455 | 3 | W4 | ✓ On-Time | -1
W3 | 2025-12-06 | 2025-12-13 | UBC-018 | Unknown | 2526203312 | 12 | W4 | ✓ On-Time | -1
W3 | 2025-12-08 | 2025-12-13 | UBC-051 | Unknown | 2526203310 | 4 | W4 | ✓ On-Time | -1
W4 | 2025-12-13 | 2025-12-13 | ATT-001 | Unknown | 2526202954 | 6 | W4 | ✓ On-Time | 0
W4 | 2025-12-15 | 2025-12-13 | ATT-001 | Unknown | 2526202955 | 5 | W4 | ✓ On-Time | 0
W4 | 2025-12-16 | 2025-12-13 | ATT-002 | Unknown | 2526202954 | 6 | W4 | ✓ On-Time | 0
W4 | 2025-12-17 | 2025-12-13 | ATT-002 | Unknown | 2526202955 | 6 | W4 | ✓ On-Time | 0
W4 | 2025-12-18 | 2025-12-20 | DGC-001 | Unknown | 2526203276 | 34 | W5 | ✓ On-Time | -1
W4 | 2025-12-19 | 2025-12-20 | DGC-001 | Unknown | 2526203277 | 56 | W5 | ✓ On-Time | -1
W4 | 2025-12-13 | 2025-12-20 | KBS-011 | Unknown | 2526500119 | 1 | W5 | ✓ On-Time | -1
W4 | 2025-12-15 | 2025-12-20 | KBS-011 | Unknown | 2526500123 | 1 | W5 | ✓ On-Time | -1
W4 | 2025-12-16 | 2025-12-13 | KBS-017 | Unknown | 2526500111 | 20 | W4 | ✓ On-Time | 0
W4 | 2025-12-17 | 2025-12-13 | KBS-017 | Unknown | 2526500112 | 20 | W4 | ✓ On-Time | 0
W4 | 2025-12-18 | 2025-12-13 | LKK-035 | Unknown | 2526203465 | 9 | W4 | ✓ On-Time | 0
W4 | 2025-12-19 | 2025-12-13 | LKK-10 | Unknown | 2526203095 | 4 | W4 | ✓ On-Time | 0
W4 | 2025-12-13 | 2025-12-20 | LKK-10 | Unknown | 2526203096 | 10 | W5 | ✓ On-Time | -1
W4 | 2025-12-15 | 2025-12-20 | LKK-10 | Unknown | 2526203097 | 10 | W5 | ✓ On-Time | -1
W4 | 2025-12-16 | 2025-12-13 | LKK-12 | Unknown | 2526203095 | 8 | W4 | ✓ On-Time | 0
W4 | 2025-12-17 | 2025-12-13 | MCB-007 | Unknown | 2526203375 | 4 | W4 | ✓ On-Time | 0
W4 | 2025-12-18 | 2025-12-13 | MCB-007 | Unknown | 2526203376 | 4 | W4 | ✓ On-Time | 0
W4 | 2025-12-19 | 2025-12-13 | MCB-007 | Unknown | 2526203377 | 4 | W4 | ✓ On-Time | 0
W4 | 2025-12-13 | 2025-12-13 | MCB-007 | Unknown | 2526203378 | 4 | W4 | ✓ On-Time | 0
W4 | 2025-12-15 | 2025-12-13 | MCB-007 | Unknown | 2526203379 | 4 | W4 | ✓ On-Time | 0
W4 | 2025-12-16 | 2025-12-13 | MCB-007 | Unknown | 2526203380 | 4 | W4 | ✓ On-Time | 0
W4 | 2025-12-17 | 2025-12-13 | MCB-007 | Unknown | 2526203381 | 4 | W4 | ✓ On-Time | 0
W4 | 2025-12-18 | 2025-12-13 | MCB-007 | Unknown | 2526203382 | 4 | W4 | ✓ On-Time | 0
W4 | 2025-12-19 | 2025-12-13 | MCB-007 | Unknown | 2526203383 | 4 | W4 | ✓ On-Time | 0
W4 | 2025-12-13 | 2025-12-13 | MCB-007 | Unknown | 2526203384 | 4 | W4 | ✓ On-Time | 0
W4 | 2025-12-15 | 2025-12-13 | MCB-007 | Unknown | 2526203385 | 4 | W4 | ✓ On-Time | 0
W4 | 2025-12-16 | 2025-12-13 | MCB-008 | Unknown | 2526203394 | 6 | W4 | ✓ On-Time | 0
W4 | 2025-12-17 | 2025-12-13 | MCB-JLG-019 | Unknown | 2526203373 | 15 | W4 | ✓ On-Time | 0
W4 | 2025-12-18 | 2025-12-13 | MCB-JLG-020 | Unknown | 2526203374 | 4 | W4 | ✓ On-Time | 0
W4 | 2025-12-19 | 2025-12-13 | MCB-JLG-047 | Unknown | 2526203370 | 11 | W4 | ✓ On-Time | 0
W4 | 2025-12-13 | 2025-12-13 | MCB-JLG-047 | Unknown | 2526203389 | 11 | W4 | ✓ On-Time | 0
W4 | 2025-12-15 | 2025-12-13 | TAS-GN-004 | Unknown | 2526203460 | 7 | W4 | ✓ On-Time | 0
W4 | 2025-12-16 | 2025-12-13 | TAS-GN-010 | Unknown | 2526203455 | 2 | W4 | ✓ On-Time | 0
W4 | 2025-12-17 | 2025-12-13 | TAS-GN-011 | Unknown | 2526203455 | 2 | W4 | ✓ On-Time | 0
W4 | 2025-12-18 | 2025-12-13 | TAS-GN-012 | Unknown | 2526203457 | 10 | W4 | ✓ On-Time | 0
W4 | 2025-12-19 | 2025-12-20 | TAS-GN-012 | Unknown | 2526203458 | 10 | W5 | ✓ On-Time | -1
W4 | 2025-12-13 | 2025-12-13 | UBC-018 | Unknown | 2526203312 | 24 | W4 | ✓ On-Time | 0
W4 | 2025-12-15 | 2025-12-13 | UBC-019 | Unknown | 2526203311 | 14 | W4 | ✓ On-Time | 0
W4 | 2025-12-16 | 2025-12-13 | UBC-019 | Unknown | 2526203312 | 1 | W4 | ✓ On-Time | 0
W4 | 2025-12-17 | 2025-12-13 | UBC-019 | Unknown | 2526203312 | 1 | W4 | ✓ On-Time | 0
W4 | 2025-12-18 | 2025-12-13 | UBC-021 | Unknown | 2526203310 | 1 | W4 | ✓ On-Time | 0
W4 | 2025-12-19 | 2025-12-13 | UBC-022 | Unknown | 2526203310 | 8 | W4 | ✓ On-Time | 0
W4 | 2025-12-13 | 2025-12-13 | UBC-050 | Unknown | 2526203310 | 4 | W4 | ✓ On-Time | 0
W4 | 2025-12-15 | 2025-12-20 | UBC-050 | Unknown | 2526203331 | 4 | W5 | ✓ On-Time | -1
W5 | 2025-12-20 | 2025-12-20 | ATT-002 | Unknown | 2526203236 | 28 | W5 | ✓ On-Time | 0
W5 | 2025-12-22 | 2025-12-20 | DGC-011 | Unknown | 2526203276 | 4 | W5 | ✓ On-Time | 0
W5 | 2025-12-23 | 2025-12-20 | KBS-009 | Unknown | 2526500117 | 2 | W5 | ✓ On-Time | 0
W5 | 2025-12-24 | 2025-12-20 | KBS-009 | Unknown | 2526500121 | 2 | W5 | ✓ On-Time | 0
W5 | 2025-12-26 | 2025-12-20 | KBS-010 | Unknown | 2526500118 | 4 | W5 | ✓ On-Time | 0
W5 | 2025-12-20 | 2025-12-20 | KBS-017 | Unknown | 2526500113 | 20 | W5 | ✓ On-Time | 0
W5 | 2025-12-22 | 2025-12-27 | LKK-10 | Unknown | 2526203098 | 10 | W6 | ✓ On-Time | -1
W5 | 2025-12-23 | 2025-12-20 | LKK-11 | Unknown | 2526203096 | 10 | W5 | ✓ On-Time | 0
W5 | 2025-12-24 | 2025-12-20 | LKK-11 | Unknown | 2526203097 | 10 | W5 | ✓ On-Time | 0
W5 | 2025-12-26 | 2025-12-20 | LKK-12 | Unknown | 2526203096 | 10 | W5 | ✓ On-Time | 0
W5 | 2025-12-20 | 2025-12-20 | LKK-12 | Unknown | 2526203097 | 10 | W5 | ✓ On-Time | 0
W5 | 2025-12-22 | 2025-12-27 | MCB-009 | Unknown | 2526203259 | 12 | W6 | ✓ On-Time | -1
W5 | 2025-12-23 | 2025-12-27 | MCB-009 | Unknown | 2526203390 | 12 | W6 | ✓ On-Time | -1
W5 | 2025-12-24 | 2025-12-20 | TAS-GN-004 | Unknown | 2526203461 | 6 | W5 | ✓ On-Time | 0
W5 | 2025-12-26 | 2025-12-20 | TAS-GN-008 | Unknown | 2526203461 | 3 | W5 | ✓ On-Time | 0
W5 | 2025-12-20 | 2025-12-20 | TAS-GN-008 | Unknown | 2526203462 | 3 | W5 | ✓ On-Time | 0
W5 | 2025-12-22 | 2025-12-20 | TAS-GN-008 | Unknown | 2526203462 | 6 | W5 | ✓ On-Time | 0
W5 | 2025-12-23 | 2025-12-20 | UBC-021 | Unknown | 2526203331 | 2 | W5 | ✓ On-Time | 0
W5 | 2025-12-24 | 2025-12-27 | UBC-021 | Unknown | 2526203427 | 2 | W6 | ✓ On-Time | -1
W5 | 2025-12-26 | 2025-12-20 | UBC-022 | Unknown | 2526203331 | 8 | W5 | ✓ On-Time | 0
W5 | 2025-12-20 | 2025-12-27 | UBC-050 | Unknown | 2526203427 | 4 | W6 | ✓ On-Time | -1
W5 | 2025-12-22 | 2025-12-20 | UBC-051 | Unknown | 2526203331 | 4 | W5 | ✓ On-Time | 0
W6 | 2025-12-27 | 2025-12-27 | DGC-001 | Unknown | 2526203280 | 56 | W6 | ✓ On-Time | 0
W6 | 2025-12-29 | 2026-01-03 | DGC-012 | Unknown | 2526203554 | 40 | W7 | ✓ On-Time | -1
W6 | 2025-12-30 | 2026-01-03 | LKK-03 | Unknown | 2526203099 | 4 | W7 | ✓ On-Time | -1
W6 | 2025-12-31 | 2026-01-03 | LKK-10 | Unknown | 2526203099 | 4 | W7 | ✓ On-Time | -1
W6 | 2026-01-01 | 2025-12-27 | LKK-11 | Unknown | 2526203098 | 10 | W6 | ✓ On-Time | 0
W6 | 2026-01-02 | 2025-12-27 | LKK-12 | Unknown | 2526203098 | 10 | W6 | ✓ On-Time | 0
W6 | 2025-12-27 | 2025-12-27 | NMS-V-004 | Unknown | 2526203103 | 5 | W6 | ✓ On-Time | 0
W6 | 2025-12-29 | 2025-12-27 | NMS-V-004 | Unknown | 2526203148 | 5 | W6 | ✓ On-Time | 0
W6 | 2025-12-30 | 2026-01-03 | UBC-014 | Unknown | 2526203484 | 50 | W7 | ✓ On-Time | -1
W6 | 2025-12-31 | 2025-12-27 | UBC-022 | Unknown | 2526203427 | 8 | W6 | ✓ On-Time | 0
W6 | 2026-01-01 | 2025-12-27 | UBC-051 | Unknown | 2526203427 | 4 | W6 | ✓ On-Time | 0
W7 | 2026-01-03 | 2026-01-03 | DGC-001 | Unknown | 2526203549 | 56 | W7 | ✓ On-Time | 0
W7 | 2026-01-05 | 2026-01-10 | DGC-001 | Unknown | 2526203550 | 56 | W8 | ✓ On-Time | -1
W7 | 2026-01-06 | 2026-01-10 | DGC-001 | Unknown | 2526203551 | 56 | W8 | ✓ On-Time | -1
W7 | 2026-01-07 | 2026-01-03 | DGC-011 | Unknown | 2526203554 | 6 | W7 | ✓ On-Time | 0
W7 | 2026-01-08 | 2026-01-10 | DGC-011 | Unknown | 2526203555 | 6 | W8 | ✓ On-Time | -1
W7 | 2026-01-09 | 2026-01-10 | DGC-012 | Unknown | 2526203555 | 40 | W8 | ✓ On-Time | -1
W7 | 2026-01-03 | 2026-01-03 | LKK-01 | Unknown | 2526203099 | 4 | W7 | ✓ On-Time | 0
W7 | 2026-01-05 | 2026-01-03 | LKK-02 | Unknown | 2526203099 | 4 | W7 | ✓ On-Time | 0
W7 | 2026-01-06 | 2026-01-03 | LKK-11 | Unknown | 2526203099 | 4 | W7 | ✓ On-Time | 0
W7 | 2026-01-07 | 2026-01-03 | LKK-12 | Unknown | 2526203099 | 4 | W7 | ✓ On-Time | 0
W7 | 2026-01-08 | 2026-01-03 | UBC-021 | Unknown | 2526203482 | 2 | W7 | ✓ On-Time | 0
W7 | 2026-01-09 | 2026-01-03 | UBC-022 | Unknown | 2526203482 | 8 | W7 | ✓ On-Time | 0
W7 | 2026-01-03 | 2026-01-03 | UBC-050 | Unknown | 2526203482 | 4 | W7 | ✓ On-Time | 0
W7 | 2026-01-05 | 2026-01-10 | UBC-050 | Unknown | 2526203547 | 12 | W8 | ✓ On-Time | -1
W7 | 2026-01-06 | 2026-01-03 | UBC-051 | Unknown | 2526203482 | 4 | W7 | ✓ On-Time | 0
W7 | 2026-01-07 | 2026-01-10 | UBC-051 | Unknown | 2526203547 | 12 | W8 | ✓ On-Time | -1
W8 | 2026-01-10 | 2026-01-10 | ATT-001 | Unknown | 2526202956 | 8 | W8 | ✓ On-Time | 0
W8 | 2026-01-12 | 2026-01-10 | ATT-001 | Unknown | 2526202957 | 8 | W8 | ✓ On-Time | 0
W8 | 2026-01-13 | 2026-01-10 | ATT-002 | Unknown | 2526202956 | 8 | W8 | ✓ On-Time | 0
W8 | 2026-01-14 | 2026-01-10 | ATT-002 | Unknown | 2526202957 | 8 | W8 | ✓ On-Time | 0
W8 | 2026-01-15 | 2026-01-17 | DGC-011 | Unknown | 2526203556 | 5 | W9 | ✓ On-Time | -1
W8 | 2026-01-16 | 2026-01-17 | DGC-012 | Unknown | 2526203556 | 34 | W9 | ✓ On-Time | -1
W8 | 2026-01-10 | 2026-01-10 | UBC-020 | Unknown | 2526203547 | 4 | W8 | ✓ On-Time | 0
W8 | 2026-01-12 | 2026-01-10 | UBC-021 | Unknown | 2526203547 | 2 | W8 | ✓ On-Time | 0
W9 | 2026-01-17 | 2026-01-17 | DGC-001 | Unknown | 2526203552 | 56 | W9 | ✓ On-Time | 0
W9 | 2026-01-19 | 2026-01-17 | DGC-001 | Unknown | 2526203556 | 12 | W9 | ✓ On-Time | 0
W10 | 2026-01-24 | 2026-01-24 | DGC-001 | Unknown | 2526203553 | 56 | W10 | ✓ On-Time | 0
W12 | 2026-02-07 | 2026-02-14 | ATT-001 | Unknown | 2526202958 | 8 | W13 | ✓ On-Time | -1
W12 | 2026-02-09 | 2026-02-14 | ATT-001 | Unknown | 2526202959 | 8 | W13 | ✓ On-Time | -1
W13 | 2026-02-14 | 2026-02-14 | ATT-002 | Unknown | 2526202958 | 8 | W13 | ✓ On-Time | 0
W13 | 2026-02-16 | 2026-02-14 | ATT-002 | Unknown | 2526202959 | 8 | W13 | ✓ On-Time | 0
W16 | 2026-03-07 | 2026-03-14 | ATT-001 | Unknown | 2526202960 | 8 | W17 | ✓ On-Time | -1
W16 | 2026-03-09 | 2026-03-14 | ATT-001 | Unknown | 2526202961 | 8 | W17 | ✓ On-Time | -1
W16 | 2026-03-10 | 2026-03-14 | ATT-002 | Unknown | 2526202960 | 8 | W17 | ✓ On-Time | -1
W16 | 2026-03-11 | 2026-03-14 | ATT-002 | Unknown | 2526202961 | 8 | W17 | ✓ On-Time | -1

## 3_DELIVERY_TRACKER
CUSTOMER DELIVERY TRACKER - WITH WIP BREAKDOWN
Track shipments, fulfillment status, and source of delivered units ¦ Planning Period: 19 weeks
FULFILLMENT SUMMARY
Metric | Value | Percentage
Total Orders | 303
Fulfilled Orders | 287 | 94.7%
Total Ordered Quantity | 3,307
Total Delivered Quantity | 3,286 | 99.4%
WEEKLY DELIVERY SUMMARY
Overview of deliveries scheduled per week ¦ Some weeks may show zero deliveries due to early fulfillment from WIP
Week | Deliveries | Status
W1 | 114 | ✓ Peak week
W2 | 49 | ✓ High volume
W3 | 56 | ✓ Peak week
W4 | 44 | ✓ High volume
W5 | 22 | ✓ Active
W6 | 11 | ✓ Active
W7 | 16 | ✓ Active
W8 | 8 | ✓ Low volume
W9 | 2 | ✓ Low volume
W10 | 1 | ⚠ Late delivery
W11 | 0 | - No shipments
W12 | 2 | ✓ Low volume
W13 | 2 | ✓ Low volume
W14 | 0 | - No shipments
W15 | 0 | - No shipments
W16 | 4 | ✓ Low volume
W17 | 0 | - No shipments
W18 | 0 | - No shipments
W19 | 0 | - No shipments
NOTE: Weeks 2-4 show no deliveries because orders committed for these weeks were fulfilled early using WIP inventory in Week 1
WEEKLY SHIPMENT SCHEDULE WITH WIP BREAKDOWN
Detailed list of all shipments with WIP vs New Production breakdown
Week | Material | Quantity | From WIP | New Production | Customer | Sales Order | Committed Week | Committed Date | Delivery Date | Status | Notes
W1 | ARM-004-N | 4 | 4 | 0 | Unknown | 2526100558 | W1 | 2025-11-22 | 2025-11-22 | ✓ On-Time
W1 | ARM-004-N | 1 | 1 | 0 | Unknown | 2526100561 | W1 | 2025-11-22 | 2025-11-22 | ✓ On-Time
W1 | ARM-004-N | 5 | 5 | 0 | Unknown | 2526100562 | W1 | 2025-11-22 | 2025-11-22 | ✓ On-Time
W1 | ARM-004-N | 7 | 7 | 0 | Unknown | 2526100563 | W1 | 2025-11-22 | 2025-11-22 | ✓ On-Time
W1 | ARM-007 | 1 | 1 | 0 | Unknown | 2526100559 | W1 | 2025-11-22 | 2025-11-22 | ✓ On-Time
W1 | ARM-007 | 2 | 2 | 0 | Unknown | 2526100560 | W1 | 2025-11-22 | 2025-11-22 | ✓ On-Time
W1 | ARM-007 | 2 | 2 | 0 | Unknown | 2526100564 | W1 | 2025-11-22 | 2025-11-22 | ✓ On-Time
W1 | ARM-007 | 4 | 4 | 0 | Unknown | 2526100565 | W1 | 2025-11-22 | 2025-11-22 | ✓ On-Time
W1 | ARM-007 | 4 | 4 | 0 | Unknown | 2526100566 | W1 | 2025-11-22 | 2025-11-22 | ✓ On-Time
W1 | ARM-007 | 1 | 1 | 0 | Unknown | 2526100569 | W1 | 2025-11-22 | 2025-11-22 | ✓ On-Time
W1 | ATT-001 | 3 | 3 | 0 | Unknown | 2526201015 | W1 | 2025-11-22 | 2025-11-22 | ✓ On-Time
W1 | ATT-001 | 3 | 3 | 0 | Unknown | 2526202952 | W1 | 2025-11-22 | 2025-11-22 | ✓ On-Time
W1 | ATT-001 | 3 | 3 | 0 | Unknown | 2526202953 | W1 | 2025-11-22 | 2025-11-22 | ✓ On-Time
W1 | ATT-002 | 5 | 5 | 0 | Unknown | 2526201015 | W1 | 2025-11-22 | 2025-11-22 | ✓ On-Time
W1 | ATT-002 | 4 | 4 | 0 | Unknown | 2526202952 | W1 | 2025-11-22 | 2025-11-22 | ✓ On-Time
W1 | ATT-002 | 4 | 4 | 0 | Unknown | 2526202953 | W1 | 2025-11-22 | 2025-11-22 | ✓ On-Time
W1 | DGC-001 | 12 | 12 | 0 | Unknown | 2526202970 | W1 | 2025-11-22 | 2025-11-22 | ✓ On-Time
W1 | DGC-001 | 12 | 12 | 0 | Unknown | 2526202971 | W1 | 2025-11-22 | 2025-11-22 | ✓ On-Time
W1 | DGC-001 | 11 | 11 | 0 | Unknown | 2526203269 | W1 | 2025-11-22 | 2025-11-22 | ✓ On-Time
W1 | DGC-001 | 7 | 7 | 0 | Unknown | 2526203270 | W1 | 2025-11-22 | 2025-11-22 | ✓ On-Time
W1 | DGC-006 | 4 | 4 | 0 | Unknown | 2526203332 | W2 | 2025-11-29 | 2025-11-22 | ✓ On-Time | 1 weeks early
W1 | DGC-012 | 14 | 14 | 0 | Unknown | 2526203271 | W2 | 2025-11-29 | 2025-11-22 | ✓ On-Time | 1 weeks early
W1 | KBS-008 | 20 | 20 | 0 | Unknown | 2526500109 | W1 | 2025-11-22 | 2025-11-22 | ✓ On-Time
W1 | KBS-009 | 18 | 18 | 0 | Unknown | 2526500114 | W1 | 2025-11-22 | 2025-11-22 | ✓ On-Time
W1 | KBS-009 | 18 | 18 | 0 | Unknown | 2526500124 | W1 | 2025-11-22 | 2025-11-22 | ✓ On-Time
W1 | KBS-010 | 8 | 8 | 0 | Unknown | 2526500115 | W1 | 2025-11-22 | 2025-11-22 | ✓ On-Time
W1 | KBS-011 | 13 | 13 | 0 | Unknown | 2526500116 | W1 | 2025-11-22 | 2025-11-22 | ✓ On-Time
W1 | KBS-012 | 1 | 1 | 0 | Unknown | 2526500083 | W1 | 2025-11-22 | 2025-11-22 | ✓ On-Time
W1 | KBS-012 | 11 | 11 | 0 | Unknown | 2526500126 | W2 | 2025-11-29 | 2025-11-22 | ✓ On-Time | 1 weeks early
W1 | KBS-012 | 10 | 9 | 1 | Unknown | 2526500127 | W2 | 2025-11-29 | 2025-11-22 | ✓ On-Time | 1 weeks early
W1 | KBS-014 | 24 | 24 | 0 | Unknown | 2526500107 | W1 | 2025-11-22 | 2025-11-22 | ✓ On-Time
W1 | KBS-014 | 24 | 0 | 24 | Unknown | 2526500130 | W2 | 2025-11-29 | 2025-11-22 | ✓ On-Time | 1 weeks early
W1 | KBS-016 | 19 | 19 | 0 | Unknown | 2526500086 | W1 | 2025-11-22 | 2025-11-22 | ✓ On-Time
W1 | KBS-016 | 19 | 19 | 0 | Unknown | 2526500104 | W1 | 2025-11-22 | 2025-11-22 | ✓ On-Time
W1 | KBS-016 | 19 | 19 | 0 | Unknown | 2526500105 | W1 | 2025-11-22 | 2025-11-22 | ✓ On-Time
W1 | KBS-017 | 5 | 5 | 0 | Unknown | 2526500087 | W1 | 2025-11-22 | 2025-11-22 | ✓ On-Time
W1 | KBS-017 | 1 | 1 | 0 | Unknown | 2526500092 | W1 | 2025-11-22 | 2025-11-22 | ✓ On-Time
W1 | KBS-017 | 15 | 15 | 0 | Unknown | 2526500094 | W1 | 2025-11-22 | 2025-11-22 | ✓ On-Time
W1 | KBS-017 | 17 | 17 | 0 | Unknown | 2526500095 | W1 | 2025-11-22 | 2025-11-22 | ✓ On-Time
W1 | KBS-017 | 14 | 14 | 0 | Unknown | 2526500096 | W1 | 2025-11-22 | 2025-11-22 | ✓ On-Time
W1 | KBS-017 | 3 | 3 | 0 | Unknown | 2526500097 | W1 | 2025-11-22 | 2025-11-22 | ✓ On-Time
W1 | KBS-018 | 8 | 8 | 0 | Unknown | 2526500091 | W1 | 2025-11-22 | 2025-11-22 | ✓ On-Time
W1 | KBS-018 | 16 | 16 | 0 | Unknown | 2526500093 | W1 | 2025-11-22 | 2025-11-22 | ✓ On-Time
W1 | LKK-01 | 2 | 2 | 0 | Unknown | 2526202458 | W1 | 2025-11-22 | 2025-11-22 | ✓ On-Time
W1 | LKK-02 | 4 | 4 | 0 | Unknown | 2526202458 | W1 | 2025-11-22 | 2025-11-22 | ✓ On-Time
W1 | LKK-03 | 3 | 3 | 0 | Unknown | 2526202458 | W1 | 2025-11-22 | 2025-11-22 | ✓ On-Time
W1 | LKK-04 | 3 | 3 | 0 | Unknown | 2526202458 | W1 | 2025-11-22 | 2025-11-22 | ✓ On-Time
W1 | LKK-05 | 4 | 4 | 0 | Unknown | 2526202458 | W1 | 2025-11-22 | 2025-11-22 | ✓ On-Time
W1 | LKK-06 | 4 | 4 | 0 | Unknown | 2526202458 | W1 | 2025-11-22 | 2025-11-22 | ✓ On-Time
W1 | LKK-10 | 2 | 2 | 0 | Unknown | 2526202459 | W1 | 2025-11-22 | 2025-11-22 | ✓ On-Time
W1 | LKK-11 | 1 | 1 | 0 | Unknown | 2526202459 | W1 | 2025-11-22 | 2025-11-22 | ✓ On-Time
W1 | LKK-12 | 10 | 10 | 0 | Unknown | 2526202459 | W1 | 2025-11-22 | 2025-11-22 | ✓ On-Time
W1 | LKK-17 | 5 | 5 | 0 | Unknown | 2526203463 | W2 | 2025-11-29 | 2025-11-22 | ✓ On-Time | 1 weeks early
W1 | MCB-007 | 1 | 1 | 0 | Unknown | 2526203284 | W1 | 2025-11-22 | 2025-11-22 | ✓ On-Time
W1 | MCB-007 | 1 | 1 | 0 | Unknown | 2526203285 | W1 | 2025-11-22 | 2025-11-22 | ✓ On-Time
W1 | MCB-008 | 3 | 3 | 0 | Unknown | 2526203153 | W2 | 2025-11-29 | 2025-11-22 | ✓ On-Time | 1 weeks early
W1 | MCB-008 | 3 | 3 | 0 | Unknown | 2526203154 | W2 | 2025-11-29 | 2025-11-22 | ✓ On-Time | 1 weeks early
W1 | MCB-008 | 2 | 2 | 0 | Unknown | 2526203164 | W2 | 2025-11-29 | 2025-11-22 | ✓ On-Time | 1 weeks early
W1 | MCB-009 | 7 | 7 | 0 | Unknown | 2526203038 | W1 | 2025-11-22 | 2025-11-22 | ✓ On-Time
W1 | MCB-009 | 6 | 6 | 0 | Unknown | 2526203139 | W1 | 2025-11-22 | 2025-11-22 | ✓ On-Time
W1 | MCB-010 | 2 | 2 | 0 | Unknown | 2526203171 | W2 | 2025-11-29 | 2025-11-22 | ✓ On-Time | 1 weeks early
W1 | MCB-010 | 2 | 2 | 0 | Unknown | 2526203172 | W2 | 2025-11-29 | 2025-11-22 | ✓ On-Time | 1 weeks early
W1 | MCB-010 | 2 | 2 | 0 | Unknown | 2526203173 | W2 | 2025-11-29 | 2025-11-22 | ✓ On-Time | 1 weeks early
W1 | MCB-010 | 2 | 2 | 0 | Unknown | 2526203174 | W2 | 2025-11-29 | 2025-11-22 | ✓ On-Time | 1 weeks early
W1 | MCB-010 | 2 | 2 | 0 | Unknown | 2526203175 | W2 | 2025-11-29 | 2025-11-22 | ✓ On-Time | 1 weeks early
W1 | MCB-010 | 1 | 1 | 0 | Unknown | 2526203176 | W2 | 2025-11-29 | 2025-11-22 | ✓ On-Time | 1 weeks early
W1 | MCB-010 | 1 | 1 | 0 | Unknown | 2526203177 | W2 | 2025-11-29 | 2025-11-22 | ✓ On-Time | 1 weeks early
W1 | MCB-HYG-016 | 4 | 4 | 0 | Unknown | 2526202705 | W1 | 2025-11-22 | 2025-11-22 | ✓ On-Time
W1 | MCB-HYG-016 | 4 | 4 | 0 | Unknown | 2526202706 | W1 | 2025-11-22 | 2025-11-22 | ✓ On-Time
W1 | MCB-HYG-016 | 4 | 4 | 0 | Unknown | 2526202707 | W1 | 2025-11-22 | 2025-11-22 | ✓ On-Time
W1 | MCB-HYG-016 | 4 | 4 | 0 | Unknown | 2526202708 | W1 | 2025-11-22 | 2025-11-22 | ✓ On-Time
W1 | MCB-HYG-023 | 6 | 6 | 0 | Unknown | 2526202788 | W1 | 2025-11-22 | 2025-11-22 | ✓ On-Time
W1 | MCB-HYG-023 | 5 | 5 | 0 | Unknown | 2526202818 | W1 | 2025-11-22 | 2025-11-22 | ✓ On-Time
W1 | MCB-HYG-026 | 5 | 5 | 0 | Unknown | 2526202474 | W1 | 2025-11-22 | 2025-11-22 | ✓ On-Time
W1 | MCB-HYG-026 | 4 | 4 | 0 | Unknown | 2526202709 | W1 | 2025-11-22 | 2025-11-22 | ✓ On-Time
W1 | MCB-JLG-014 | 6 | 6 | 0 | Unknown | 2526203279 | W1 | 2025-11-22 | 2025-11-22 | ✓ On-Time
W1 | MCB-JLG-020 | 4 | 4 | 0 | Unknown | 2526203039 | W1 | 2025-11-22 | 2025-11-22 | ✓ On-Time
W1 | MCB-JLG-020 | 4 | 4 | 0 | Unknown | 2526203143 | W1 | 2025-11-22 | 2025-11-22 | ✓ On-Time
W1 | MCB-JLG-031 | 1 | 1 | 0 | Unknown | 2526201341 | W2 | 2025-11-29 | 2025-11-22 | ✓ On-Time | 1 weeks early
W1 | MCB-JLG-046 | 3 | 3 | 0 | Unknown | 2526202810 | W1 | 2025-11-22 | 2025-11-22 | ✓ On-Time
W1 | MCB-JLG-046 | 1 | 1 | 0 | Unknown | 2526202810 | W1 | 2025-11-22 | 2025-11-22 | ✓ On-Time
W1 | MCB-JLG-047 | 9 | 9 | 0 | Unknown | 2526203057 | W1 | 2025-11-22 | 2025-11-22 | ✓ On-Time
W1 | MCB-JLG-047 | 9 | 9 | 0 | Unknown | 2526203141 | W1 | 2025-11-22 | 2025-11-22 | ✓ On-Time
W1 | NMS-H-001 | 13 | 13 | 0 | Unknown | 2526203092 | W1 | 2025-11-22 | 2025-11-22 | ✓ On-Time
W1 | NMS-H-001 | 13 | 13 | 0 | Unknown | 2526203093 | W1 | 2025-11-22 | 2025-11-22 | ✓ On-Time
W1 | NMS-V-003 | 10 | 10 | 0 | Unknown | 2526203094 | W1 | 2025-11-22 | 2025-11-22 | ✓ On-Time
W1 | NMS-V-004 | 5 | 5 | 0 | Unknown | 2526202939 | W1 | 2025-11-22 | 2025-11-22 | ✓ On-Time
W1 | NMS-V-004 | 4 | 4 | 0 | Unknown | 2526203090 | W1 | 2025-11-22 | 2025-11-22 | ✓ On-Time
W1 | NMS-V-004 | 4 | 4 | 0 | Unknown | 2526203091 | W1 | 2025-11-22 | 2025-11-22 | ✓ On-Time
W1 | TAS-GN-004 | 2 | 2 | 0 | Unknown | 2526202713 | W1 | 2025-11-22 | 2025-11-22 | ✓ On-Time
W1 | TAS-GN-006 | 3 | 3 | 0 | Unknown | 2526201561 | W2 | 2025-11-29 | 2025-11-22 | ✓ On-Time | 1 weeks early
W1 | TAS-GN-008 | 3 | 3 | 0 | Unknown | 2526201611 | W1 | 2025-11-22 | 2025-11-22 | ✓ On-Time
W1 | TAS-GN-008 | 2 | 2 | 0 | Unknown | 2526201804 | W1 | 2025-11-22 | 2025-11-22 | ✓ On-Time
W1 | TAS-GN-008 | 1 | 1 | 0 | Unknown | 2526202929 | W1 | 2025-11-22 | 2025-11-22 | ✓ On-Time
W1 | UBC-018 | 18 | 18 | 0 | Unknown | 2526203023 | W1 | 2025-11-22 | 2025-11-22 | ✓ On-Time
W1 | UBC-020 | 1 | 1 | 0 | Unknown | 2526202941 | W1 | 2025-11-22 | 2025-11-22 | ✓ On-Time
W1 | UBC-020 | 3 | 3 | 0 | Unknown | 2526202947 | W1 | 2025-11-22 | 2025-11-22 | ✓ On-Time
W1 | UBC-020 | 6 | 6 | 0 | Unknown | 2526203022 | W1 | 2025-11-22 | 2025-11-22 | ✓ On-Time
W1 | UBC-020 | 6 | 6 | 0 | Unknown | 2526203022 | W1 | 2025-11-22 | 2025-11-22 | ✓ On-Time
W1 | UBC-022 | 3 | 3 | 0 | Unknown | 2526202943 | W1 | 2025-11-22 | 2025-11-22 | ✓ On-Time
W1 | UBC-022 | 3 | 3 | 0 | Unknown | 2526202943 | W1 | 2025-11-22 | 2025-11-22 | ✓ On-Time
W1 | UBC-022 | 2 | 2 | 0 | Unknown | 2526203022 | W1 | 2025-11-22 | 2025-11-22 | ✓ On-Time
W1 | UBC-022 | 2 | 2 | 0 | Unknown | 2526203022 | W1 | 2025-11-22 | 2025-11-22 | ✓ On-Time
W1 | UBC-035 | 46 | 46 | 0 | Unknown | 2526100367 | W1 | 2025-11-22 | 2025-11-22 | ✓ On-Time
W1 | UBC-046 | 7 | 7 | 0 | Unknown | 2526201681 | W1 | 2025-11-22 | 2025-11-22 | ✓ On-Time
W1 | UBC-050 | 5 | 5 | 0 | Unknown | 2526202947 | W1 | 2025-11-22 | 2025-11-22 | ✓ On-Time
W1 | UBC-050 | 3 | 3 | 0 | Unknown | 2526203022 | W1 | 2025-11-22 | 2025-11-22 | ✓ On-Time
W1 | UBC-051 | 5 | 5 | 0 | Unknown | 2526202947 | W1 | 2025-11-22 | 2025-11-22 | ✓ On-Time
W1 | UBC-051 | 3 | 3 | 0 | Unknown | 2526203022 | W1 | 2025-11-22 | 2025-11-22 | ✓ On-Time
W1 | UBC-051 | 4 | 4 | 0 | Unknown | 2526203076 | W2 | 2025-11-29 | 2025-11-22 | ✓ On-Time | 1 weeks early
W1 | UBC-062 | 2 | 2 | 0 | Unknown | 2526200576 | W1 | 2025-11-22 | 2025-11-22 | ✓ On-Time
W1 | UBC-063 | 2 | 2 | 0 | Unknown | 2526200576 | W1 | 2025-11-22 | 2025-11-22 | ✓ On-Time
W1 | UBC-064 | 2 | 2 | 0 | Unknown | 2526200576 | W1 | 2025-11-22 | 2025-11-22 | ✓ On-Time
W1 | UBC-064 | 1 | 1 | 0 | Unknown | 2526203434 | W1 | 2025-11-22 | 2025-11-22 | ✓ On-Time
W2 | ARM-007 | 4 | 4 | 0 | Unknown | 2526100567 | W2 | 2025-11-29 | 2025-11-29 | ✓ On-Time
W2 | ATT-001 | 1 | 1 | 0 | Unknown | 2526201561 | W2 | 2025-11-29 | 2025-11-29 | ✓ On-Time
W2 | DGC-001 | 38 | 38 | 0 | Unknown | 2526203271 | W2 | 2025-11-29 | 2025-11-29 | ✓ On-Time
W2 | KBS-009 | 20 | 20 | 0 | Unknown | 2526500120 | W2 | 2025-11-29 | 2025-11-29 | ✓ On-Time
W2 | KBS-011 | 15 | 15 | 0 | Unknown | 2526500122 | W2 | 2025-11-29 | 2025-11-29 | ✓ On-Time
W2 | KBS-011 | 15 | 12 | 3 | Unknown | 2526500125 | W2 | 2025-11-29 | 2025-11-29 | ✓ On-Time
W2 | KBS-017 | 22 | 22 | 0 | Unknown | 2526500098 | W2 | 2025-11-29 | 2025-11-29 | ✓ On-Time
W2 | KBS-017 | 12 | 10 | 2 | Unknown | 2526500106 | W2 | 2025-11-29 | 2025-11-29 | ✓ On-Time
W2 | LKK-01 | 2 | 2 | 0 | Unknown | 2526201561 | W2 | 2025-11-29 | 2025-11-29 | ✓ On-Time
W2 | LKK-01 | 8 | 8 | 0 | Unknown | 2526202964 | W2 | 2025-11-29 | 2025-11-29 | ✓ On-Time
W2 | LKK-02 | 8 | 8 | 0 | Unknown | 2526202964 | W2 | 2025-11-29 | 2025-11-29 | ✓ On-Time
W2 | LKK-02 | 8 | 8 | 0 | Unknown | 2526202965 | W3 | 2025-12-06 | 2025-11-29 | ✓ On-Time | 1 weeks early
W2 | LKK-03 | 8 | 8 | 0 | Unknown | 2526202964 | W2 | 2025-11-29 | 2025-11-29 | ✓ On-Time
W2 | LKK-03 | 8 | 0 | 8 | Unknown | 2526202965 | W3 | 2025-12-06 | 2025-11-29 | ✓ On-Time | 1 weeks early
W2 | LKK-031 | 3 | 3 | 0 | Unknown | 2526203464 | W3 | 2025-12-06 | 2025-11-29 | ✓ On-Time | 1 weeks early
W2 | LKK-033 | 2 | 2 | 0 | Unknown | 2526203464 | W3 | 2025-12-06 | 2025-11-29 | ✓ On-Time | 1 weeks early
W2 | LKK-034 | 1 | 1 | 0 | Unknown | 2526203464 | W3 | 2025-12-06 | 2025-11-29 | ✓ On-Time | 1 weeks early
W2 | LKK-04 | 4 | 4 | 0 | Unknown | 2526203463 | W2 | 2025-11-29 | 2025-11-29 | ✓ On-Time
W2 | LKK-05 | 4 | 2 | 2 | Unknown | 2526203463 | W2 | 2025-11-29 | 2025-11-29 | ✓ On-Time
W2 | LKK-06 | 4 | 4 | 0 | Unknown | 2526203463 | W2 | 2025-11-29 | 2025-11-29 | ✓ On-Time
W2 | LKK-16 | 12 | 12 | 0 | Unknown | 2526203463 | W2 | 2025-11-29 | 2025-11-29 | ✓ On-Time
W2 | LKK-17 | 7 | 7 | 0 | Unknown | 2526203463 | W2 | 2025-11-29 | 2025-11-29 | ✓ On-Time
W2 | MCB-007 | 4 | 4 | 0 | Unknown | 2526203256 | W3 | 2025-12-06 | 2025-11-29 | ✓ On-Time | 1 weeks early
W2 | MCB-007 | 4 | 4 | 0 | Unknown | 2526203386 | W3 | 2025-12-06 | 2025-11-29 | ✓ On-Time | 1 weeks early
W2 | MCB-007 | 4 | 4 | 0 | Unknown | 2526203387 | W3 | 2025-12-06 | 2025-11-29 | ✓ On-Time | 1 weeks early
W2 | MCB-008 | 6 | 6 | 0 | Unknown | 2526203255 | W3 | 2025-12-06 | 2025-11-29 | ✓ On-Time | 1 weeks early
W2 | MCB-009 | 7 | 7 | 0 | Unknown | 2526201341 | W2 | 2025-11-29 | 2025-11-29 | ✓ On-Time
W2 | MCB-009 | 12 | 12 | 0 | Unknown | 2526203138 | W2 | 2025-11-29 | 2025-11-29 | ✓ On-Time
W2 | MCB-010 | 3 | 3 | 0 | Unknown | 2526203171 | W2 | 2025-11-29 | 2025-11-29 | ✓ On-Time
W2 | MCB-010 | 3 | 3 | 0 | Unknown | 2526203172 | W2 | 2025-11-29 | 2025-11-29 | ✓ On-Time
W2 | MCB-010 | 3 | 3 | 0 | Unknown | 2526203173 | W2 | 2025-11-29 | 2025-11-29 | ✓ On-Time
W2 | MCB-010 | 2 | 2 | 0 | Unknown | 2526203174 | W2 | 2025-11-29 | 2025-11-29 | ✓ On-Time
W2 | MCB-010 | 2 | 2 | 0 | Unknown | 2526203175 | W2 | 2025-11-29 | 2025-11-29 | ✓ On-Time
W2 | MCB-010 | 2 | 2 | 0 | Unknown | 2526203176 | W2 | 2025-11-29 | 2025-11-29 | ✓ On-Time
W2 | MCB-010 | 2 | 2 | 0 | Unknown | 2526203177 | W2 | 2025-11-29 | 2025-11-29 | ✓ On-Time
W2 | MCB-HYG-016 | 5 | 5 | 0 | Unknown | 2526202819 | W2 | 2025-11-29 | 2025-11-29 | ✓ On-Time
W2 | MCB-HYG-016 | 5 | 2 | 3 | Unknown | 2526202820 | W2 | 2025-11-29 | 2025-11-29 | ✓ On-Time
W2 | MCB-HYG-034 | 9 | 9 | 0 | Unknown | 2526201160 | W2 | 2025-11-29 | 2025-11-29 | ✓ On-Time
W2 | MCB-JLG-014 | 1 | 1 | 0 | Unknown | 2526203131 | W2 | 2025-11-29 | 2025-11-29 | ✓ On-Time
W2 | MCB-JLG-019 | 1 | 1 | 0 | Unknown | 2526203249 | W2 | 2025-11-29 | 2025-11-29 | ✓ On-Time
W2 | MCB-JLG-019 | 1 | 1 | 0 | Unknown | 2526203250 | W2 | 2025-11-29 | 2025-11-29 | ✓ On-Time
W2 | MCB-JLG-020 | 4 | 1 | 3 | Unknown | 2526203142 | W2 | 2025-11-29 | 2025-11-29 | ✓ On-Time
W2 | MCB-JLG-047 | 11 | 11 | 0 | Unknown | 2526203140 | W2 | 2025-11-29 | 2025-11-29 | ✓ On-Time
W2 | TAS-GN-009 | 20 | 20 | 0 | Unknown | 2526203459 | W3 | 2025-12-06 | 2025-11-29 | ✓ On-Time | 1 weeks early
W2 | TAS-GN-012 | 2 | 2 | 0 | Unknown | 2526203456 | W3 | 2025-12-06 | 2025-11-29 | ✓ On-Time | 1 weeks early
W2 | UBC-014 | 20 | 20 | 0 | Unknown | 2526203078 | W2 | 2025-11-29 | 2025-11-29 | ✓ On-Time
W2 | UBC-020 | 8 | 8 | 0 | Unknown | 2526203076 | W2 | 2025-11-29 | 2025-11-29 | ✓ On-Time
W2 | UBC-022 | 4 | 4 | 0 | Unknown | 2526203076 | W2 | 2025-11-29 | 2025-11-29 | ✓ On-Time
W2 | UBC-050 | 4 | 4 | 0 | Unknown | 2526203076 | W2 | 2025-11-29 | 2025-11-29 | ✓ On-Time
W3 | ARM-007 | 4 | 1 | 3 | Unknown | 2526100568 | W3 | 2025-12-06 | 2025-12-06 | ✓ On-Time
W3 | ATT-001 | 3 | 3 | 0 | Unknown | 2526202954 | W4 | 2025-12-13 | 2025-12-06 | ✓ On-Time | 1 weeks early
W3 | ATT-001 | 2 | 2 | 0 | Unknown | 2526202955 | W4 | 2025-12-13 | 2025-12-06 | ✓ On-Time | 1 weeks early
W3 | ATT-002 | 2 | 2 | 0 | Unknown | 2526202954 | W4 | 2025-12-13 | 2025-12-06 | ✓ On-Time | 1 weeks early
W3 | ATT-002 | 2 | 2 | 0 | Unknown | 2526202955 | W4 | 2025-12-13 | 2025-12-06 | ✓ On-Time | 1 weeks early
W3 | DGC-001 | 56 | 56 | 0 | Unknown | 2526203274 | W4 | 2025-12-13 | 2025-12-06 | ✓ On-Time | 1 weeks early
W3 | DGC-006 | 6 | 0 | 6 | Unknown | 2526203332 | W2 | 2025-11-29 | 2025-12-06 | ⚠ Late | 1 weeks late
W3 | DGC-009 | 14 | 0 | 14 | Unknown | 2526203332 | W2 | 2025-11-29 | 2025-12-06 | ⚠ Late | 1 weeks late
W3 | KBS-012 | 14 | 0 | 14 | Unknown | 2526500126 | W2 | 2025-11-29 | 2025-12-06 | ⚠ Late | 1 weeks late
W3 | KBS-012 | 13 | 0 | 13 | Unknown | 2526500127 | W2 | 2025-11-29 | 2025-12-06 | ⚠ Late | 1 weeks late
W3 | KBS-014 | 24 | 0 | 24 | Unknown | 2526500131 | W3 | 2025-12-06 | 2025-12-06 | ✓ On-Time
W3 | KBS-016 | 24 | 24 | 0 | Unknown | 2526500110 | W3 | 2025-12-06 | 2025-12-06 | ✓ On-Time
W3 | KBS-017 | 22 | 0 | 22 | Unknown | 2526500099 | W3 | 2025-12-06 | 2025-12-06 | ✓ On-Time
W3 | LKK-01 | 8 | 8 | 0 | Unknown | 2526202965 | W3 | 2025-12-06 | 2025-12-06 | ✓ On-Time
W3 | LKK-030 | 3 | 0 | 3 | Unknown | 2526203464 | W3 | 2025-12-06 | 2025-12-06 | ✓ On-Time
W3 | LKK-032 | 3 | 1 | 2 | Unknown | 2526203464 | W3 | 2025-12-06 | 2025-12-06 | ✓ On-Time
W3 | LKK-033 | 4 | 0 | 4 | Unknown | 2526203464 | W3 | 2025-12-06 | 2025-12-06 | ✓ On-Time
W3 | LKK-034 | 2 | 0 | 2 | Unknown | 2526203464 | W3 | 2025-12-06 | 2025-12-06 | ✓ On-Time
W3 | LKK-10 | 6 | 6 | 0 | Unknown | 2526203095 | W4 | 2025-12-13 | 2025-12-06 | ✓ On-Time | 1 weeks early
W3 | LKK-11 | 10 | 10 | 0 | Unknown | 2526203095 | W4 | 2025-12-13 | 2025-12-06 | ✓ On-Time | 1 weeks early
W3 | LKK-12 | 1 | 1 | 0 | Unknown | 2526203095 | W4 | 2025-12-13 | 2025-12-06 | ✓ On-Time | 1 weeks early
W3 | MCB-010 | 2 | 0 | 2 | Unknown | 2526203171 | W2 | 2025-11-29 | 2025-12-06 | ⚠ Late | 1 weeks late
W3 | MCB-010 | 2 | 0 | 2 | Unknown | 2526203172 | W2 | 2025-11-29 | 2025-12-06 | ⚠ Late | 1 weeks late
W3 | MCB-010 | 1 | 0 | 1 | Unknown | 2526203173 | W2 | 2025-11-29 | 2025-12-06 | ⚠ Late | 1 weeks late
W3 | MCB-010 | 1 | 0 | 1 | Unknown | 2526203174 | W2 | 2025-11-29 | 2025-12-06 | ⚠ Late | 1 weeks late
W3 | MCB-010 | 1 | 0 | 1 | Unknown | 2526203175 | W2 | 2025-11-29 | 2025-12-06 | ⚠ Late | 1 weeks late
W3 | MCB-010 | 1 | 0 | 1 | Unknown | 2526203176 | W2 | 2025-11-29 | 2025-12-06 | ⚠ Late | 1 weeks late
W3 | MCB-010 | 1 | 0 | 1 | Unknown | 2526203177 | W2 | 2025-11-29 | 2025-12-06 | ⚠ Late | 1 weeks late
W3 | MCB-010 | 7 | 0 | 7 | Unknown | 2526203260 | W3 | 2025-12-06 | 2025-12-06 | ✓ On-Time
W3 | MCB-010 | 7 | 0 | 7 | Unknown | 2526203396 | W3 | 2025-12-06 | 2025-12-06 | ✓ On-Time
W3 | MCB-010 | 7 | 0 | 7 | Unknown | 2526203397 | W3 | 2025-12-06 | 2025-12-06 | ✓ On-Time
W3 | MCB-HYG-015 | 8 | 8 | 0 | Unknown | 2526203253 | W3 | 2025-12-06 | 2025-12-06 | ✓ On-Time
W3 | MCB-HYG-023 | 6 | 6 | 0 | Unknown | 2526203252 | W3 | 2025-12-06 | 2025-12-06 | ✓ On-Time
W3 | MCB-HYG-023 | 6 | 6 | 0 | Unknown | 2526203398 | W4 | 2025-12-13 | 2025-12-06 | ✓ On-Time | 1 weeks early
W3 | MCB-JLG-014 | 6 | 6 | 0 | Unknown | 2526203261 | W3 | 2025-12-06 | 2025-12-06 | ✓ On-Time
W3 | MCB-JLG-014 | 6 | 6 | 0 | Unknown | 2526203262 | W3 | 2025-12-06 | 2025-12-06 | ✓ On-Time
W3 | MCB-JLG-019 | 15 | 0 | 15 | Unknown | 2526203249 | W2 | 2025-11-29 | 2025-12-06 | ⚠ Late | 1 weeks late
W3 | MCB-JLG-019 | 14 | 0 | 14 | Unknown | 2526203250 | W2 | 2025-11-29 | 2025-12-06 | ⚠ Late | 1 weeks late
W3 | MCB-JLG-019 | 14 | 0 | 14 | Unknown | 2526203251 | W2 | 2025-11-29 | 2025-12-06 | ⚠ Late | 1 weeks late
W3 | MCB-JLG-032 | 4 | 0 | 4 | Unknown | 2526203388 | W2 | 2025-11-29 | 2025-12-06 | ⚠ Late | 1 weeks late
W3 | MCB-JLG-033 | 3 | 1 | 2 | Unknown | 2526203258 | W3 | 2025-12-06 | 2025-12-06 | ✓ On-Time
W3 | TAS-GN-004 | 2 | 2 | 0 | Unknown | 2526203460 | W4 | 2025-12-13 | 2025-12-06 | ✓ On-Time | 1 weeks early
W3 | TAS-GN-006 | 3 | 0 | 3 | Unknown | 2526201561 | W2 | 2025-11-29 | 2025-12-06 | ⚠ Late | 1 weeks late
W3 | TAS-GN-006 | 9 | 0 | 9 | Unknown | 2526203459 | W3 | 2025-12-06 | 2025-12-06 | ✓ On-Time
W3 | TAS-GN-007 | 20 | 4 | 16 | Unknown | 2526203459 | W3 | 2025-12-06 | 2025-12-06 | ✓ On-Time
W3 | TAS-GN-008 | 1 | 1 | 0 | Unknown | 2526203456 | W3 | 2025-12-06 | 2025-12-06 | ✓ On-Time
W3 | TAS-GN-012 | 5 | 5 | 0 | Unknown | 2526203456 | W3 | 2025-12-06 | 2025-12-06 | ✓ On-Time
W3 | TAS-GN-014 | 10 | 10 | 0 | Unknown | 2526203459 | W3 | 2025-12-06 | 2025-12-06 | ✓ On-Time
W3 | TAS-GN-021 | 12 | 2 | 10 | Unknown | 2526203454 | W3 | 2025-12-06 | 2025-12-06 | ✓ On-Time
W3 | TAS-GN-021 | 14 | 0 | 14 | Unknown | 2526203455 | W4 | 2025-12-13 | 2025-12-06 | ✓ On-Time | 1 weeks early
W3 | TAS-GN-029 | 6 | 3 | 3 | Unknown | 2526203454 | W3 | 2025-12-06 | 2025-12-06 | ✓ On-Time
W3 | TAS-GN-029 | 12 | 0 | 12 | Unknown | 2526203454 | W3 | 2025-12-06 | 2025-12-06 | ✓ On-Time
W3 | TAS-GN-029 | 12 | 0 | 12 | Unknown | 2526203454 | W3 | 2025-12-06 | 2025-12-06 | ✓ On-Time
W3 | TAS-GN-029 | 3 | 0 | 3 | Unknown | 2526203455 | W4 | 2025-12-13 | 2025-12-06 | ✓ On-Time | 1 weeks early
W3 | UBC-018 | 12 | 12 | 0 | Unknown | 2526203312 | W4 | 2025-12-13 | 2025-12-06 | ✓ On-Time | 1 weeks early
W3 | UBC-051 | 4 | 4 | 0 | Unknown | 2526203310 | W4 | 2025-12-13 | 2025-12-06 | ✓ On-Time | 1 weeks early
W4 | ATT-001 | 6 | 6 | 0 | Unknown | 2526202954 | W4 | 2025-12-13 | 2025-12-13 | ✓ On-Time
W4 | ATT-001 | 5 | 5 | 0 | Unknown | 2526202955 | W4 | 2025-12-13 | 2025-12-13 | ✓ On-Time
W4 | ATT-002 | 6 | 3 | 3 | Unknown | 2526202954 | W4 | 2025-12-13 | 2025-12-13 | ✓ On-Time
W4 | ATT-002 | 6 | 0 | 6 | Unknown | 2526202955 | W4 | 2025-12-13 | 2025-12-13 | ✓ On-Time
W4 | DGC-001 | 34 | 34 | 0 | Unknown | 2526203276 | W5 | 2025-12-20 | 2025-12-13 | ✓ On-Time | 1 weeks early
W4 | DGC-001 | 56 | 56 | 0 | Unknown | 2526203277 | W5 | 2025-12-20 | 2025-12-13 | ✓ On-Time | 1 weeks early
W4 | KBS-011 | 1 | 0 | 1 | Unknown | 2526500119 | W5 | 2025-12-20 | 2025-12-13 | ✓ On-Time | 1 weeks early
W4 | KBS-011 | 1 | 0 | 1 | Unknown | 2526500123 | W5 | 2025-12-20 | 2025-12-13 | ✓ On-Time | 1 weeks early
W4 | KBS-017 | 20 | 0 | 20 | Unknown | 2526500111 | W4 | 2025-12-13 | 2025-12-13 | ✓ On-Time
W4 | KBS-017 | 20 | 0 | 20 | Unknown | 2526500112 | W4 | 2025-12-13 | 2025-12-13 | ✓ On-Time
W4 | LKK-035 | 9 | 0 | 9 | Unknown | 2526203465 | W4 | 2025-12-13 | 2025-12-13 | ✓ On-Time
W4 | LKK-10 | 4 | 2 | 2 | Unknown | 2526203095 | W4 | 2025-12-13 | 2025-12-13 | ✓ On-Time
W4 | LKK-10 | 10 | 0 | 10 | Unknown | 2526203096 | W5 | 2025-12-20 | 2025-12-13 | ✓ On-Time | 1 weeks early
W4 | LKK-10 | 10 | 0 | 10 | Unknown | 2526203097 | W5 | 2025-12-20 | 2025-12-13 | ✓ On-Time | 1 weeks early
W4 | LKK-12 | 8 | 1 | 7 | Unknown | 2526203095 | W4 | 2025-12-13 | 2025-12-13 | ✓ On-Time
W4 | MCB-007 | 4 | 4 | 0 | Unknown | 2526203375 | W4 | 2025-12-13 | 2025-12-13 | ✓ On-Time
W4 | MCB-007 | 4 | 0 | 4 | Unknown | 2526203376 | W4 | 2025-12-13 | 2025-12-13 | ✓ On-Time
W4 | MCB-007 | 4 | 0 | 4 | Unknown | 2526203377 | W4 | 2025-12-13 | 2025-12-13 | ✓ On-Time
W4 | MCB-007 | 4 | 0 | 4 | Unknown | 2526203378 | W4 | 2025-12-13 | 2025-12-13 | ✓ On-Time
W4 | MCB-007 | 4 | 0 | 4 | Unknown | 2526203379 | W4 | 2025-12-13 | 2025-12-13 | ✓ On-Time
W4 | MCB-007 | 4 | 0 | 4 | Unknown | 2526203380 | W4 | 2025-12-13 | 2025-12-13 | ✓ On-Time
W4 | MCB-007 | 4 | 0 | 4 | Unknown | 2526203381 | W4 | 2025-12-13 | 2025-12-13 | ✓ On-Time
W4 | MCB-007 | 4 | 0 | 4 | Unknown | 2526203382 | W4 | 2025-12-13 | 2025-12-13 | ✓ On-Time
W4 | MCB-007 | 4 | 0 | 4 | Unknown | 2526203383 | W4 | 2025-12-13 | 2025-12-13 | ✓ On-Time
W4 | MCB-007 | 4 | 0 | 4 | Unknown | 2526203384 | W4 | 2025-12-13 | 2025-12-13 | ✓ On-Time
W4 | MCB-007 | 4 | 0 | 4 | Unknown | 2526203385 | W4 | 2025-12-13 | 2025-12-13 | ✓ On-Time
W4 | MCB-008 | 6 | 6 | 0 | Unknown | 2526203394 | W4 | 2025-12-13 | 2025-12-13 | ✓ On-Time
W4 | MCB-JLG-019 | 15 | 0 | 15 | Unknown | 2526203373 | W4 | 2025-12-13 | 2025-12-13 | ✓ On-Time
W4 | MCB-JLG-020 | 4 | 0 | 4 | Unknown | 2526203374 | W4 | 2025-12-13 | 2025-12-13 | ✓ On-Time
W4 | MCB-JLG-047 | 11 | 11 | 0 | Unknown | 2526203370 | W4 | 2025-12-13 | 2025-12-13 | ✓ On-Time
W4 | MCB-JLG-047 | 11 | 4 | 7 | Unknown | 2526203389 | W4 | 2025-12-13 | 2025-12-13 | ✓ On-Time
W4 | TAS-GN-004 | 7 | 0 | 7 | Unknown | 2526203460 | W4 | 2025-12-13 | 2025-12-13 | ✓ On-Time
W4 | TAS-GN-010 | 2 | 0 | 2 | Unknown | 2526203455 | W4 | 2025-12-13 | 2025-12-13 | ✓ On-Time
W4 | TAS-GN-011 | 2 | 0 | 2 | Unknown | 2526203455 | W4 | 2025-12-13 | 2025-12-13 | ✓ On-Time
W4 | TAS-GN-012 | 10 | 0 | 10 | Unknown | 2526203457 | W4 | 2025-12-13 | 2025-12-13 | ✓ On-Time
W4 | TAS-GN-012 | 10 | 0 | 10 | Unknown | 2526203458 | W5 | 2025-12-20 | 2025-12-13 | ✓ On-Time | 1 weeks early
W4 | UBC-018 | 24 | 24 | 0 | Unknown | 2526203312 | W4 | 2025-12-13 | 2025-12-13 | ✓ On-Time
W4 | UBC-019 | 14 | 3 | 11 | Unknown | 2526203311 | W4 | 2025-12-13 | 2025-12-13 | ✓ On-Time
W4 | UBC-019 | 1 | 0 | 1 | Unknown | 2526203312 | W4 | 2025-12-13 | 2025-12-13 | ✓ On-Time
W4 | UBC-019 | 1 | 0 | 1 | Unknown | 2526203312 | W4 | 2025-12-13 | 2025-12-13 | ✓ On-Time
W4 | UBC-021 | 1 | 1 | 0 | Unknown | 2526203310 | W4 | 2025-12-13 | 2025-12-13 | ✓ On-Time
W4 | UBC-022 | 8 | 8 | 0 | Unknown | 2526203310 | W4 | 2025-12-13 | 2025-12-13 | ✓ On-Time
W4 | UBC-050 | 4 | 4 | 0 | Unknown | 2526203310 | W4 | 2025-12-13 | 2025-12-13 | ✓ On-Time
W4 | UBC-050 | 4 | 4 | 0 | Unknown | 2526203331 | W5 | 2025-12-20 | 2025-12-13 | ✓ On-Time | 1 weeks early
W5 | ATT-002 | 28 | 0 | 28 | Unknown | 2526203236 | W5 | 2025-12-20 | 2025-12-20 | ✓ On-Time
W5 | DGC-011 | 4 | 0 | 4 | Unknown | 2526203276 | W5 | 2025-12-20 | 2025-12-20 | ✓ On-Time
W5 | KBS-009 | 2 | 2 | 0 | Unknown | 2526500117 | W5 | 2025-12-20 | 2025-12-20 | ✓ On-Time
W5 | KBS-009 | 2 | 2 | 0 | Unknown | 2526500121 | W5 | 2025-12-20 | 2025-12-20 | ✓ On-Time
W5 | KBS-010 | 4 | 0 | 4 | Unknown | 2526500118 | W5 | 2025-12-20 | 2025-12-20 | ✓ On-Time
W5 | KBS-017 | 20 | 0 | 20 | Unknown | 2526500113 | W5 | 2025-12-20 | 2025-12-20 | ✓ On-Time
W5 | LKK-10 | 10 | 0 | 10 | Unknown | 2526203098 | W6 | 2025-12-27 | 2025-12-20 | ✓ On-Time | 1 weeks early
W5 | LKK-11 | 10 | 5 | 5 | Unknown | 2526203096 | W5 | 2025-12-20 | 2025-12-20 | ✓ On-Time
W5 | LKK-11 | 10 | 0 | 10 | Unknown | 2526203097 | W5 | 2025-12-20 | 2025-12-20 | ✓ On-Time
W5 | LKK-12 | 10 | 0 | 10 | Unknown | 2526203096 | W5 | 2025-12-20 | 2025-12-20 | ✓ On-Time
W5 | LKK-12 | 10 | 0 | 10 | Unknown | 2526203097 | W5 | 2025-12-20 | 2025-12-20 | ✓ On-Time
W5 | MCB-009 | 12 | 12 | 0 | Unknown | 2526203259 | W6 | 2025-12-27 | 2025-12-20 | ✓ On-Time | 1 weeks early
W5 | MCB-009 | 12 | 3 | 9 | Unknown | 2526203390 | W6 | 2025-12-27 | 2025-12-20 | ✓ On-Time | 1 weeks early
W5 | TAS-GN-004 | 6 | 0 | 6 | Unknown | 2526203461 | W5 | 2025-12-20 | 2025-12-20 | ✓ On-Time
W5 | TAS-GN-008 | 3 | 1 | 2 | Unknown | 2526203461 | W5 | 2025-12-20 | 2025-12-20 | ✓ On-Time
W5 | TAS-GN-008 | 3 | 0 | 3 | Unknown | 2526203462 | W5 | 2025-12-20 | 2025-12-20 | ✓ On-Time
W5 | TAS-GN-008 | 6 | 0 | 6 | Unknown | 2526203462 | W5 | 2025-12-20 | 2025-12-20 | ✓ On-Time
W5 | UBC-021 | 2 | 0 | 2 | Unknown | 2526203331 | W5 | 2025-12-20 | 2025-12-20 | ✓ On-Time
W5 | UBC-021 | 2 | 0 | 2 | Unknown | 2526203427 | W6 | 2025-12-27 | 2025-12-20 | ✓ On-Time | 1 weeks early
W5 | UBC-022 | 8 | 1 | 7 | Unknown | 2526203331 | W5 | 2025-12-20 | 2025-12-20 | ✓ On-Time
W5 | UBC-050 | 4 | 4 | 0 | Unknown | 2526203427 | W6 | 2025-12-27 | 2025-12-20 | ✓ On-Time | 1 weeks early
W5 | UBC-051 | 4 | 4 | 0 | Unknown | 2526203331 | W5 | 2025-12-20 | 2025-12-20 | ✓ On-Time
W6 | DGC-001 | 56 | 56 | 0 | Unknown | 2526203280 | W6 | 2025-12-27 | 2025-12-27 | ✓ On-Time
W6 | DGC-012 | 40 | 26 | 14 | Unknown | 2526203554 | W7 | 2026-01-03 | 2025-12-27 | ✓ On-Time | 1 weeks early
W6 | LKK-03 | 4 | 0 | 4 | Unknown | 2526203099 | W7 | 2026-01-03 | 2025-12-27 | ✓ On-Time | 1 weeks early
W6 | LKK-10 | 4 | 0 | 4 | Unknown | 2526203099 | W7 | 2026-01-03 | 2025-12-27 | ✓ On-Time | 1 weeks early
W6 | LKK-11 | 10 | 0 | 10 | Unknown | 2526203098 | W6 | 2025-12-27 | 2025-12-27 | ✓ On-Time
W6 | LKK-12 | 10 | 0 | 10 | Unknown | 2526203098 | W6 | 2025-12-27 | 2025-12-27 | ✓ On-Time
W6 | NMS-V-004 | 5 | 0 | 5 | Unknown | 2526203103 | W6 | 2025-12-27 | 2025-12-27 | ✓ On-Time
W6 | NMS-V-004 | 5 | 0 | 5 | Unknown | 2526203148 | W6 | 2025-12-27 | 2025-12-27 | ✓ On-Time
W6 | UBC-014 | 50 | 44 | 6 | Unknown | 2526203484 | W7 | 2026-01-03 | 2025-12-27 | ✓ On-Time | 1 weeks early
W6 | UBC-022 | 8 | 0 | 8 | Unknown | 2526203427 | W6 | 2025-12-27 | 2025-12-27 | ✓ On-Time
W6 | UBC-051 | 4 | 4 | 0 | Unknown | 2526203427 | W6 | 2025-12-27 | 2025-12-27 | ✓ On-Time
W7 | DGC-001 | 56 | 56 | 0 | Unknown | 2526203549 | W7 | 2026-01-03 | 2026-01-03 | ✓ On-Time
W7 | DGC-001 | 56 | 13 | 43 | Unknown | 2526203550 | W8 | 2026-01-10 | 2026-01-03 | ✓ On-Time | 1 weeks early
W7 | DGC-001 | 56 | 0 | 56 | Unknown | 2526203551 | W8 | 2026-01-10 | 2026-01-03 | ✓ On-Time | 1 weeks early
W7 | DGC-011 | 6 | 0 | 6 | Unknown | 2526203554 | W7 | 2026-01-03 | 2026-01-03 | ✓ On-Time
W7 | DGC-011 | 6 | 0 | 6 | Unknown | 2526203555 | W8 | 2026-01-10 | 2026-01-03 | ✓ On-Time | 1 weeks early
W7 | DGC-012 | 40 | 0 | 40 | Unknown | 2526203555 | W8 | 2026-01-10 | 2026-01-03 | ✓ On-Time | 1 weeks early
W7 | LKK-01 | 4 | 2 | 2 | Unknown | 2526203099 | W7 | 2026-01-03 | 2026-01-03 | ✓ On-Time
W7 | LKK-02 | 4 | 1 | 3 | Unknown | 2526203099 | W7 | 2026-01-03 | 2026-01-03 | ✓ On-Time
W7 | LKK-11 | 4 | 0 | 4 | Unknown | 2526203099 | W7 | 2026-01-03 | 2026-01-03 | ✓ On-Time
W7 | LKK-12 | 4 | 0 | 4 | Unknown | 2526203099 | W7 | 2026-01-03 | 2026-01-03 | ✓ On-Time
W7 | UBC-021 | 2 | 0 | 2 | Unknown | 2526203482 | W7 | 2026-01-03 | 2026-01-03 | ✓ On-Time
W7 | UBC-022 | 8 | 0 | 8 | Unknown | 2526203482 | W7 | 2026-01-03 | 2026-01-03 | ✓ On-Time
W7 | UBC-050 | 4 | 4 | 0 | Unknown | 2526203482 | W7 | 2026-01-03 | 2026-01-03 | ✓ On-Time
W7 | UBC-050 | 12 | 12 | 0 | Unknown | 2526203547 | W8 | 2026-01-10 | 2026-01-03 | ✓ On-Time | 1 weeks early
W7 | UBC-051 | 4 | 4 | 0 | Unknown | 2526203482 | W7 | 2026-01-03 | 2026-01-03 | ✓ On-Time
W7 | UBC-051 | 12 | 12 | 0 | Unknown | 2526203547 | W8 | 2026-01-10 | 2026-01-03 | ✓ On-Time | 1 weeks early
W8 | ATT-001 | 8 | 3 | 5 | Unknown | 2526202956 | W8 | 2026-01-10 | 2026-01-10 | ✓ On-Time
W8 | ATT-001 | 8 | 0 | 8 | Unknown | 2526202957 | W8 | 2026-01-10 | 2026-01-10 | ✓ On-Time
W8 | ATT-002 | 8 | 0 | 8 | Unknown | 2526202956 | W8 | 2026-01-10 | 2026-01-10 | ✓ On-Time
W8 | ATT-002 | 8 | 0 | 8 | Unknown | 2526202957 | W8 | 2026-01-10 | 2026-01-10 | ✓ On-Time
W8 | DGC-011 | 5 | 0 | 5 | Unknown | 2526203556 | W9 | 2026-01-17 | 2026-01-10 | ✓ On-Time | 1 weeks early
W8 | DGC-012 | 34 | 0 | 34 | Unknown | 2526203556 | W9 | 2026-01-17 | 2026-01-10 | ✓ On-Time | 1 weeks early
W8 | UBC-020 | 4 | 4 | 0 | Unknown | 2526203547 | W8 | 2026-01-10 | 2026-01-10 | ✓ On-Time
W8 | UBC-021 | 2 | 0 | 2 | Unknown | 2526203547 | W8 | 2026-01-10 | 2026-01-10 | ✓ On-Time
W9 | DGC-001 | 56 | 0 | 56 | Unknown | 2526203552 | W9 | 2026-01-17 | 2026-01-17 | ✓ On-Time
W9 | DGC-001 | 12 | 0 | 12 | Unknown | 2526203556 | W9 | 2026-01-17 | 2026-01-17 | ✓ On-Time
W10 | DGC-001 | 56 | 0 | 56 | Unknown | 2526203553 | W10 | 2026-01-24 | 2026-01-24 | ✓ On-Time
W12 | ATT-001 | 8 | 0 | 8 | Unknown | 2526202958 | W13 | 2026-02-14 | 2026-02-07 | ✓ On-Time | 1 weeks early
W12 | ATT-001 | 8 | 0 | 8 | Unknown | 2526202959 | W13 | 2026-02-14 | 2026-02-07 | ✓ On-Time | 1 weeks early
W13 | ATT-002 | 8 | 0 | 8 | Unknown | 2526202958 | W13 | 2026-02-14 | 2026-02-14 | ✓ On-Time
W13 | ATT-002 | 8 | 0 | 8 | Unknown | 2526202959 | W13 | 2026-02-14 | 2026-02-14 | ✓ On-Time
W16 | ATT-001 | 8 | 0 | 8 | Unknown | 2526202960 | W17 | 2026-03-14 | 2026-03-07 | ✓ On-Time | 1 weeks early
W16 | ATT-001 | 8 | 0 | 8 | Unknown | 2526202961 | W17 | 2026-03-14 | 2026-03-07 | ✓ On-Time | 1 weeks early
W16 | ATT-002 | 8 | 0 | 8 | Unknown | 2526202960 | W17 | 2026-03-14 | 2026-03-07 | ✓ On-Time | 1 weeks early
W16 | ATT-002 | 8 | 0 | 8 | Unknown | 2526202961 | W17 | 2026-03-14 | 2026-03-07 | ✓ On-Time | 1 weeks early
CUSTOMER SUMMARY WITH WIP ANALYSIS
Customer | Orders | Ordered Qty | Delivered Qty | Fulfillment % | On-Time | Status
Unknown | 303 | 3,307 | 3,286 | 99.4% | 271 | ✓ Good
PART-LEVEL WIP vs NEW PRODUCTION SUMMARY
Part | Initial WIP | New Production | Total Delivered | WIP Used %
ARM-004-N | 18 | 0 | 17 | 100.0%
ARM-007 | 19 | 6 | 22 | 86.4%
ATT-001 | 29 | 45 | 74 | 39.2%
ATT-002 | 20 | 105 | 105 | 19.0%
DGC-001 | 351 | 223 | 574 | 61.1%
DGC-006 | 4 | 6 | 10 | 40.0%
DGC-009 | 0 | 14 | 14 | 0.0%
DGC-011 | 0 | 125 | 21 | 0.0%
DGC-012 | 40 | 110 | 128 | 31.2%
KBS-008 | 20 | 0 | 20 | 100.0%
KBS-009 | 66 | 0 | 60 | 100.0%
KBS-010 | 8 | 18 | 12 | 66.7%
KBS-011 | 40 | 7 | 45 | 88.9%
KBS-012 | 21 | 30 | 49 | 42.9%
KBS-014 | 24 | 48 | 72 | 33.3%
KBS-016 | 85 | 0 | 81 | 100.0%
KBS-017 | 87 | 94 | 171 | 50.9%
KBS-018 | 33 | 0 | 24 | 100.0%
DELIVERY RECOMMENDATIONS & ACTION PLAN
Actionable solutions for late and at-risk orders (model explains WHY, not just schedule earlier)
Found 30 recommendations: 15 critical actions, 15 alternatives
Priority | Order / Part | Root Cause | Recommended Action | Impact | Timeline
🔴 CRITICAL | 2526100367 / UBC-035 | Impossible timeline - need 4 weeks, only 0 available | RENEGOTIATE: Request customer accept Week 1 (earliest possible) | Avoid Rs 0 late penalty | Immediate
🟡 OPTION 2 | 2526100367 / UBC-035 | 46 units available in WIP | PARTIAL DELIVERY: Ship 46 units Week 1, 14 Week 1 | 76% on-time fulfillment | Week 1
🔴 CRITICAL | 2526100558 / ARM-004-N | Impossible timeline - need 4 weeks, only 0 available | RENEGOTIATE: Request customer accept Week 1 (earliest possible) | Avoid Rs 0 late penalty | Immediate
🟡 OPTION 2 | 2526100558 / ARM-004-N | 18 units available in WIP | PARTIAL DELIVERY: Ship 18 units Week 1, -14 Week 1 | 100% on-time fulfillment | Week 1
🔴 CRITICAL | 2526100559 / ARM-007 | Impossible timeline - need 4 weeks, only 0 available | RENEGOTIATE: Request customer accept Week 1 (earliest possible) | Avoid Rs 0 late penalty | Immediate
🟡 OPTION 2 | 2526100559 / ARM-007 | 19 units available in WIP | PARTIAL DELIVERY: Ship 19 units Week 1, -18 Week 1 | 100% on-time fulfillment | Week 1
🔴 CRITICAL | 2526100560 / ARM-007 | Impossible timeline - need 4 weeks, only 0 available | RENEGOTIATE: Request customer accept Week 1 (earliest possible) | Avoid Rs 0 late penalty | Immediate
🟡 OPTION 2 | 2526100560 / ARM-007 | 19 units available in WIP | PARTIAL DELIVERY: Ship 19 units Week 1, -17 Week 1 | 100% on-time fulfillment | Week 1
🔴 CRITICAL | 2526100561 / ARM-004-N | Impossible timeline - need 4 weeks, only 0 available | RENEGOTIATE: Request customer accept Week 1 (earliest possible) | Avoid Rs 0 late penalty | Immediate
🟡 OPTION 2 | 2526100561 / ARM-004-N | 18 units available in WIP | PARTIAL DELIVERY: Ship 18 units Week 1, -17 Week 1 | 100% on-time fulfillment | Week 1
🔴 CRITICAL | 2526100562 / ARM-004-N | Impossible timeline - need 4 weeks, only 0 available | RENEGOTIATE: Request customer accept Week 1 (earliest possible) | Avoid Rs 0 late penalty | Immediate
🟡 OPTION 2 | 2526100562 / ARM-004-N | 18 units available in WIP | PARTIAL DELIVERY: Ship 18 units Week 1, -13 Week 1 | 100% on-time fulfillment | Week 1
🔴 CRITICAL | 2526100564 / ARM-007 | Impossible timeline - need 4 weeks, only 0 available | RENEGOTIATE: Request customer accept Week 1 (earliest possible) | Avoid Rs 0 late penalty | Immediate
🟡 OPTION 2 | 2526100564 / ARM-007 | 19 units available in WIP | PARTIAL DELIVERY: Ship 19 units Week 1, -17 Week 1 | 100% on-time fulfillment | Week 1
🔴 CRITICAL | 2526100565 / ARM-007 | Impossible timeline - need 4 weeks, only 0 available | RENEGOTIATE: Request customer accept Week 1 (earliest possible) | Avoid Rs 0 late penalty | Immediate
🟡 OPTION 2 | 2526100565 / ARM-007 | 19 units available in WIP | PARTIAL DELIVERY: Ship 19 units Week 1, -15 Week 1 | 100% on-time fulfillment | Week 1
🔴 CRITICAL | 2526100569 / ARM-007 | Impossible timeline - need 4 weeks, only 0 available | RENEGOTIATE: Request customer accept Week 1 (earliest possible) | Avoid Rs 0 late penalty | Immediate
🟡 OPTION 2 | 2526100569 / ARM-007 | 19 units available in WIP | PARTIAL DELIVERY: Ship 19 units Week 1, -18 Week 1 | 100% on-time fulfillment | Week 1
🔴 CRITICAL | 2526200576 / UBC-062 | Impossible timeline - need 4 weeks, only 0 available | RENEGOTIATE: Request customer accept Week 1 (earliest possible) | Avoid Rs 0 late penalty | Immediate
🟡 OPTION 2 | 2526200576 / UBC-062 | 2 units available in WIP | PARTIAL DELIVERY: Ship 2 units Week 1, 0 Week 1 | 100% on-time fulfillment | Week 1
WHY THESE RECOMMENDATIONS?
The optimization model ALREADY tried to schedule optimally. If orders are late, it means:
1. IMPOSSIBLE TIMELINE - Need 4 weeks, but committed date is sooner (physics constraint)
2. CAPACITY BOTTLENECK - A stage (grinding, machining, etc.) is overloaded >95%
3. OPTIMIZATION TRADEOFF - Model chose to delay this order to fulfill higher-value orders
4. WIP INSUFFICIENT - Partial inventory exists but not enough for full order
Recommendations provide OPTIONS OUTSIDE the model scope (renegotiate, add capacity, outsource, re-run with different penalties)

## 4_BOTTLENECK_ALERTS
BOTTLENECK ALERTS & ACTION ITEMS - ALL 8 STAGES
Issues ranked by priority - Address from top to bottom
Priority | Resource/Issue | Impact | Action Required | Timeline
🔴 CRITICAL | Unmet Customer Demand | 22 units cannot be fulfilled | Increase capacity or reschedule | Immediate
🟡 WARNING | Casting Approaching Limit | 1 weeks at 85-95% utilization | Monitor and plan capacity increase | Next 2 Weeks
🟡 WARNING | Grinding Approaching Limit | 1 weeks at 85-95% utilization | Monitor and plan capacity increase | Next 2 Weeks
🟡 WARNING | Machining Stage 1 (MC1) Approaching Limit | 1 weeks at 85-95% utilization | Monitor and plan capacity increase | Next 2 Weeks
🟡 WARNING | Painting Stage 1 (SP1) Approaching Limit | 3 weeks at 85-95% utilization | Monitor and plan capacity increase | Next 2 Weeks
🟡 WARNING | Painting Stage 2 (SP2) Approaching Limit | 1 weeks at 85-95% utilization | Monitor and plan capacity increase | Next 2 Weeks
🟡 WARNING | Painting Stage 3 (SP3) Approaching Limit | 1 weeks at 85-95% utilization | Monitor and plan capacity increase | Next 2 Weeks
🟡 WARNING | Big Line Moulding Approaching Limit | 3 weeks at 85-95% utilization | Monitor and plan capacity increase | Next 2 Weeks
🟡 WARNING | Small Line Moulding Approaching Limit | 1 weeks at 85-95% utilization | Monitor and plan capacity increase | Next 2 Weeks
🟡 WARNING | Excessive Pattern Changeovers | 3 weeks with >5 changeovers (15.0 hours lost) | Consolidate parts or extend batches | Ongoing

## 5_CAPACITY_OVERVIEW
CAPACITY UTILIZATION OVERVIEW - ALL 8 STAGES
Complete resource capacity analysis across all production stages
COMPLETE STAGE CAPACITY SUMMARY
Stage | Avg Util % | Max Util % | Critical Weeks | Status | Recommendation
Casting | 11.5% | 91.0% | - | 🟡 Warning | Plan additional resources
Grinding | 17.6% | 86.8% | - | 🟡 Warning | Plan additional resources
Machining Stage 1 (MC1) | 18.1% | 87.9% | - | 🟡 Warning | Plan additional resources
Machining Stage 2 (MC2) | 14.6% | 64.5% | - | 🟢 Healthy | Continue monitoring
Machining Stage 3 (MC3) | 3.7% | 25.0% | - | 🟢 Healthy | Continue monitoring
Painting Stage 1 - Primer (SP1) | 19.3% | 91.0% | - | 🟡 Warning | Plan additional resources
Painting Stage 2 - Intermediate (SP2) | 17.3% | 91.0% | - | 🟡 Warning | Plan additional resources
Painting Stage 3 - Top Coat (SP3) | 12.3% | 91.0% | - | 🟡 Warning | Plan additional resources
Big Line Moulding | 16.2% | 94.0% | - | 🟡 Warning | Plan additional resources
Small Line Moulding | 15.2% | 88.6% | - | 🟡 Warning | Plan additional resources
VACUUM LINE CAPACITY
Line | Avg Util % | Max Util % | Overload Weeks | Status | Action Required
Big Line | 61.7% | 94.0% | - | 🟡 Warning | Monitor
Small Line | 57.7% | 88.6% | - | 🟡 Warning | Monitor
SETUP TIME IMPACT
Metric | Value | Weekly Average | Impact
Total Changeovers | 50 | 2.6/week | 15.0 hours lost
Big Line Changes | 23 | 1.2/week | 6.9 hours
Small Line Changes | 27 | 1.4/week | 8.1 hours
WEEKLY CAPACITY DETAILS - ALL 8 STAGES
Week | Cast% | Grind% | MC1% | MC2% | MC3% | SP1% | SP2% | SP3% | Big Line% | Small Line% | Status
W1 | 91.0% | 69.3% | 87.9% | 61.1% | 25.0% | 91.0% | 64.4% | 55.7% | 90.0% | 88.6% | 🟡 Warning
W2 | 53.6% | 69.9% | 76.0% | 45.5% | 8.5% | 45.8% | 42.5% | 19.3% | 94.0% | 70.6% | 🟡 Warning
W3 | 46.7% | 48.4% | 62.1% | 46.9% | 18.2% | 54.0% | 55.7% | 44.6% | 87.4% | 63.6% | 🟡 Warning
W4 | 10.4% | 60.8% | 49.0% | 59.0% | 16.0% | 90.4% | 75.0% | 22.7% | 14.1% | 28.4% | 🟡 Warning
W5 | 17.2% | 86.8% | 69.8% | 64.5% | 2.5% | 86.3% | 91.0% | 91.0% | 23.1% | 37.4% | 🟡 Warning
W6 | 0.0% | 0.0% | 0.0% | 0.0% | 0.0% | 0.0% | 0.0% | 0.0% | 0.0% | 0.0% | 🟢 Healthy
W7 | 0.0% | 0.0% | 0.0% | 0.0% | 0.0% | 0.0% | 0.0% | 0.0% | 0.0% | 0.0% | 🟢 Healthy
W8 | 0.0% | 0.0% | 0.0% | 0.0% | 0.0% | 0.0% | 0.0% | 0.0% | 0.0% | 0.0% | 🟢 Healthy
W9 | 0.0% | 0.0% | 0.0% | 0.0% | 0.0% | 0.0% | 0.0% | 0.0% | 0.0% | 0.0% | 🟢 Healthy
W10 | 0.0% | 0.0% | 0.0% | 0.0% | 0.0% | 0.0% | 0.0% | 0.0% | 0.0% | 0.0% | 🟢 Healthy
W11 | 0.0% | 0.0% | 0.0% | 0.0% | 0.0% | 0.0% | 0.0% | 0.0% | 0.0% | 0.0% | 🟢 Healthy
W12 | 0.0% | 0.0% | 0.0% | 0.0% | 0.0% | 0.0% | 0.0% | 0.0% | 0.0% | 0.0% | 🟢 Healthy
W13 | 0.0% | 0.0% | 0.0% | 0.0% | 0.0% | 0.0% | 0.0% | 0.0% | 0.0% | 0.0% | 🟢 Healthy
W14 | 0.0% | 0.0% | 0.0% | 0.0% | 0.0% | 0.0% | 0.0% | 0.0% | 0.0% | 0.0% | 🟢 Healthy
W15 | 0.0% | 0.0% | 0.0% | 0.0% | 0.0% | 0.0% | 0.0% | 0.0% | 0.0% | 0.0% | 🟢 Healthy
W16 | 0.0% | 0.0% | 0.0% | 0.0% | 0.0% | 0.0% | 0.0% | 0.0% | 0.0% | 0.0% | 🟢 Healthy
W17 | 0.0% | 0.0% | 0.0% | 0.0% | 0.0% | 0.0% | 0.0% | 0.0% | 0.0% | 0.0% | 🟢 Healthy
W18 | 0.0% | 0.0% | 0.0% | 0.0% | 0.0% | 0.0% | 0.0% | 0.0% | 0.0% | 0.0% | 🟢 Healthy
W19 | 0.0% | 0.0% | 0.0% | 0.0% | 0.0% | 0.0% | 0.0% | 0.0% | 0.0% | 0.0% | 🟢 Healthy

## 6_MATERIAL_FLOW
MATERIAL FLOW TRACKER - COMPLETE 8-STAGE VIEW
Track material through: Casting → Grinding → MC1 → MC2 → MC3 → SP1 → SP2 → SP3 → Delivery
Week | Casting | Grinding | MC1 | MC2 | MC3 | SP1 | SP2 | SP3 | Delivery | Big Line Util % | Small Line Util % | Notes
W1 | 743 | 347 | 352 | 245 | 100 | 586 | 450 | 317 | 726 | 90.0% | 88.6% | MC3 bottleneck
W2 | 438 | 349 | 304 | 182 | 34 | 295 | 297 | 110 | 355 | 94.0% | 70.6% | MC3 bottleneck, SP3 bottleneck
W3 | 381 | 242 | 248 | 187 | 73 | 348 | 389 | 254 | 460 | 87.4% | 63.6% | MC3 bottleneck
W4 | 85 | 304 | 196 | 236 | 64 | 582 | 524 | 129 | 375 | 14.1% | 28.4% | MC3 bottleneck, SP3 bottleneck
W5 | 141 | 434 | 279 | 258 | 10 | 556 | 636 | 518 | 172 | 23.1% | 37.4% | MC3 bottleneck
W6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 196 | 0.0% | 0.0%
W7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 278 | 0.0% | 0.0%
W8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77 | 0.0% | 0.0%
W9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68 | 0.0% | 0.0%
W10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56 | 0.0% | 0.0%
W11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0% | 0.0%
W12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0.0% | 0.0%
W13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0.0% | 0.0%
W14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0% | 0.0%
W15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0% | 0.0%
W16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0.0% | 0.0%
W17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0% | 0.0%
W18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0% | 0.0%
W19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0% | 0.0%
TOTAL | 1788 | 1676 | 1379 | 1108 | 281 | 2367 | 2296 | 1328 | 2827 | 16.2% | 15.2%
AVERAGE | 94 | 88 | 73 | 58 | 15 | 125 | 121 | 70 | 149 | 16.2% | 15.2%
COMPLETE STAGE FLOW ANALYSIS
From Stage | To Stage | Total Flow | Avg Weekly | Balance Status | Avg Util % | Peak Util %
Casting | Grinding | 1676 | 88 | ?o" Balanced | 11.5% | 91.0%
Grinding | MC1 | 1379 | 73 | ?o" Balanced | 17.6% | 86.8%
MC1 | MC2 | 1108 | 58 | ?o" Balanced | 18.1% | 87.9%
MC2 | MC3 | 281 | 15 | ?o" Balanced | 14.6% | 64.5%
MC3 | SP1 | 2367 | 125 | ?o" Balanced | 3.7% | 25.0%
SP1 | SP2 | 2296 | 121 | ?o" Balanced | 19.3% | 91.0%
SP2 | SP3 | 1328 | 70 | ?o" Balanced | 17.3% | 91.0%
SP3 | Delivery | 2827 | 149 | ?o" Balanced | 12.3% | 91.0%
Big Line | Capacity | 400 | 21 | ?o" Balanced | 16.2% | 94.0%
Small Line | Capacity | 374 | 20 | ?o" Balanced | 15.2% | 88.6%

## 7_DAILY_SCHEDULE
DAILY PRODUCTION SCHEDULE WITH CALENDAR DATES
Day-by-day production plan ¦ Excludes Sundays & India National Holidays ¦ Planning Period: 19 weeks
CALENDAR SUMMARY
Metric | Count | Percentage
Total Days in Schedule | 133 | 100%
Working Days (Mon-Sat) | 109 | 82.0%
Sundays (Weekly Off) | 19 | 14.3%
National Holidays | 5 | 3.8%
Total Holidays | 24 | 18.0%
DAILY PRODUCTION SCHEDULE
Week | Date | Day | Status | Holiday/Event | Casting | Grinding | MC1 | MC2 | MC3 | SP1 | SP2 | SP3 | Big Line (hrs) | Small Line (hrs) | Big Line Util % | Small Line Util %
W1 | 2025-11-22 | Saturday | 🟡 Saturday | - | 123.9 | 58 | 59 | 41 | 17 | 98 | 75 | 53 | 19.4 | 19.1 | 90.0% | 88.6%
W1 | 2025-11-23 | Sunday | 🔴 HOLIDAY | Sunday - Weekly Off | - | - | [6 empty] | - | - | 90.0% | 88.6% | bar: MC1 to SP3
W1 | 2025-11-24 | Monday | 🟢 Working | - | 123.9 | 58 | 59 | 41 | 17 | 98 | 75 | 53 | 19.4 | 19.1 | 90.0% | 88.6%
W1 | 2025-11-25 | Tuesday | 🟢 Working | - | 123.9 | 58 | 59 | 41 | 17 | 98 | 75 | 53 | 19.4 | 19.1 | 90.0% | 88.6%
W1 | 2025-11-26 | Wednesday | 🟢 Working | - | 123.9 | 58 | 59 | 41 | 17 | 98 | 75 | 53 | 19.4 | 19.1 | 90.0% | 88.6%
W1 | 2025-11-27 | Thursday | 🟢 Working | - | 123.9 | 58 | 59 | 41 | 17 | 98 | 75 | 53 | 19.4 | 19.1 | 90.0% | 88.6%
W1 | 2025-11-28 | Friday | 🟢 Working | - | 123.9 | 58 | 59 | 41 | 17 | 98 | 75 | 53 | 19.4 | 19.1 | 90.0% | 88.6%
W2 | 2025-11-29 | Saturday | 🟡 Saturday | - | 72.9 | 58 | 51 | 30 | 6 | 49 | 50 | 18 | 20.3 | 15.2 | 94.0% | 70.6%
W2 | 2025-11-30 | Sunday | 🔴 HOLIDAY | Sunday - Weekly Off | - | - | [6 empty] | - | - | 94.0% | 70.6% | bar: MC1 to SP3
W2 | 2025-12-01 | Monday | 🟢 Working | - | 72.9 | 58 | 51 | 30 | 6 | 49 | 50 | 18 | 20.3 | 15.2 | 94.0% | 70.6%
W2 | 2025-12-02 | Tuesday | 🟢 Working | - | 72.9 | 58 | 51 | 30 | 6 | 49 | 50 | 18 | 20.3 | 15.2 | 94.0% | 70.6%
W2 | 2025-12-03 | Wednesday | 🟢 Working | - | 72.9 | 58 | 51 | 30 | 6 | 49 | 50 | 18 | 20.3 | 15.2 | 94.0% | 70.6%
W2 | 2025-12-04 | Thursday | 🟢 Working | - | 72.9 | 58 | 51 | 30 | 6 | 49 | 50 | 18 | 20.3 | 15.2 | 94.0% | 70.6%
W2 | 2025-12-05 | Friday | 🟢 Working | - | 72.9 | 58 | 51 | 30 | 6 | 49 | 50 | 18 | 20.3 | 15.2 | 94.0% | 70.6%
W3 | 2025-12-06 | Saturday | 🟡 Saturday | - | 63.6 | 40 | 41 | 31 | 12 | 58 | 65 | 42 | 18.9 | 13.7 | 87.4% | 63.6%
W3 | 2025-12-07 | Sunday | 🔴 HOLIDAY | Sunday - Weekly Off | - | - | [6 empty] | - | - | 87.4% | 63.6% | bar: MC1 to SP3
W3 | 2025-12-08 | Monday | 🟢 Working | - | 63.6 | 40 | 41 | 31 | 12 | 58 | 65 | 42 | 18.9 | 13.7 | 87.4% | 63.6%
W3 | 2025-12-09 | Tuesday | 🟢 Working | - | 63.6 | 40 | 41 | 31 | 12 | 58 | 65 | 42 | 18.9 | 13.7 | 87.4% | 63.6%
W3 | 2025-12-10 | Wednesday | 🟢 Working | - | 63.6 | 40 | 41 | 31 | 12 | 58 | 65 | 42 | 18.9 | 13.7 | 87.4% | 63.6%
W3 | 2025-12-11 | Thursday | 🟢 Working | - | 63.6 | 40 | 41 | 31 | 12 | 58 | 65 | 42 | 18.9 | 13.7 | 87.4% | 63.6%
W3 | 2025-12-12 | Friday | 🟢 Working | - | 63.6 | 40 | 41 | 31 | 12 | 58 | 65 | 42 | 18.9 | 13.7 | 87.4% | 63.6%
W4 | 2025-12-13 | Saturday | 🟡 Saturday | - | 14.1 | 51 | 33 | 39 | 11 | 97 | 87 | 22 | 3.1 | 6.1 | 14.1% | 28.4%
W4 | 2025-12-14 | Sunday | 🔴 HOLIDAY | Sunday - Weekly Off | - | - | [6 empty] | - | - | 14.1% | 28.4% | bar: MC1 to SP3
W4 | 2025-12-15 | Monday | 🟢 Working | - | 14.1 | 51 | 33 | 39 | 11 | 97 | 87 | 22 | 3.1 | 6.1 | 14.1% | 28.4%
W4 | 2025-12-16 | Tuesday | 🟢 Working | - | 14.1 | 51 | 33 | 39 | 11 | 97 | 87 | 22 | 3.1 | 6.1 | 14.1% | 28.4%
W4 | 2025-12-17 | Wednesday | 🟢 Working | - | 14.1 | 51 | 33 | 39 | 11 | 97 | 87 | 22 | 3.1 | 6.1 | 14.1% | 28.4%
W4 | 2025-12-18 | Thursday | 🟢 Working | - | 14.1 | 51 | 33 | 39 | 11 | 97 | 87 | 22 | 3.1 | 6.1 | 14.1% | 28.4%
W4 | 2025-12-19 | Friday | 🟢 Working | - | 14.1 | 51 | 33 | 39 | 11 | 97 | 87 | 22 | 3.1 | 6.1 | 14.1% | 28.4%
W5 | 2025-12-20 | Saturday | 🟡 Saturday | - | 28.1 | 87 | 56 | 52 | 2 | 111 | 127 | 104 | 6.0 | 9.7 | 23.1% | 37.4%
W5 | 2025-12-21 | Sunday | 🔴 HOLIDAY | Sunday - Weekly Off | - | - | [6 empty] | - | - | 23.1% | 37.4% | bar: MC1 to SP3
W5 | 2025-12-22 | Monday | 🟢 Working | - | 28.1 | 87 | 56 | 52 | 2 | 111 | 127 | 104 | 6.0 | 9.7 | 23.1% | 37.4%
W5 | 2025-12-23 | Tuesday | 🟢 Working | - | 28.1 | 87 | 56 | 52 | 2 | 111 | 127 | 104 | 6.0 | 9.7 | 23.1% | 37.4%
W5 | 2025-12-24 | Wednesday | 🟢 Working | - | 28.1 | 87 | 56 | 52 | 2 | 111 | 127 | 104 | 6.0 | 9.7 | 23.1% | 37.4%
W5 | 2025-12-25 | Thursday | 🔴 HOLIDAY | Christmas | - | - | [6 empty] | - | - | 23.1% | 37.4% | bar: MC1 to SP3
W5 | 2025-12-26 | Friday | 🟢 Working | - | 28.1 | 87 | 56 | 52 | 2 | 111 | 127 | 104 | 6.0 | 9.7 | 23.1% | 37.4%
W6 | 2025-12-27 | Saturday | 🟡 Saturday | - | - | - | [6 empty] | - | - | - | - | bar: MC1 to SP3
W6 | 2025-12-28 | Sunday | 🔴 HOLIDAY | Sunday - Weekly Off | - | - | [6 empty] | - | - | - | - | bar: MC1 to SP3
W6 | 2025-12-29 | Monday | 🟢 Working | - | - | - | [6 empty] | - | - | - | - | bar: MC1 to SP3
W6 | 2025-12-30 | Tuesday | 🟢 Working | - | - | - | [6 empty] | - | - | - | - | bar: MC1 to SP3
W6 | 2025-12-31 | Wednesday | 🟢 Working | - | - | - | [6 empty] | - | - | - | - | bar: MC1 to SP3
W6 | 2026-01-01 | Thursday | 🟢 Working | - | - | - | [6 empty] | - | - | - | - | bar: MC1 to SP3
W6 | 2026-01-02 | Friday | 🟢 Working | - | - | - | [6 empty] | - | - | - | - | bar: MC1 to SP3
W7 | 2026-01-03 | Saturday | 🟡 Saturday | - | - | - | [6 empty] | - | - | - | - | bar: MC1 to SP3
W7 | 2026-01-04 | Sunday | 🔴 HOLIDAY | Sunday - Weekly Off | - | - | [6 empty] | - | - | - | - | bar: MC1 to SP3
W7 | 2026-01-05 | Monday | 🟢 Working | - | - | - | [6 empty] | - | - | - | - | bar: MC1 to SP3
W7 | 2026-01-06 | Tuesday | 🟢 Working | - | - | - | [6 empty] | - | - | - | - | bar: MC1 to SP3
W7 | 2026-01-07 | Wednesday | 🟢 Working | - | - | - | [6 empty] | - | - | - | - | bar: MC1 to SP3
W7 | 2026-01-08 | Thursday | 🟢 Working | - | - | - | [6 empty] | - | - | - | - | bar: MC1 to SP3
W7 | 2026-01-09 | Friday | 🟢 Working | - | - | - | [6 empty] | - | - | - | - | bar: MC1 to SP3
W8 | 2026-01-10 | Saturday | 🟡 Saturday | - | - | - | [6 empty] | - | - | - | - | bar: MC1 to SP3
W8 | 2026-01-11 | Sunday | 🔴 HOLIDAY | Sunday - Weekly Off | - | - | [6 empty] | - | - | - | - | bar: MC1 to SP3
W8 | 2026-01-12 | Monday | 🟢 Working | - | - | - | [6 empty] | - | - | - | - | bar: MC1 to SP3
W8 | 2026-01-13 | Tuesday | 🟢 Working | - | - | - | [6 empty] | - | - | - | - | bar: MC1 to SP3
W8 | 2026-01-14 | Wednesday | 🟢 Working | - | - | - | [6 empty] | - | - | - | - | bar: MC1 to SP3
W8 | 2026-01-15 | Thursday | 🟢 Working | - | - | - | [6 empty] | - | - | - | - | bar: MC1 to SP3
W8 | 2026-01-16 | Friday | 🟢 Working | - | - | - | [6 empty] | - | - | - | - | bar: MC1 to SP3
W9 | 2026-01-17 | Saturday | 🟡 Saturday | - | - | - | [6 empty] | - | - | - | - | bar: MC1 to SP3
W9 | 2026-01-18 | Sunday | 🔴 HOLIDAY | Sunday - Weekly Off | - | - | [6 empty] | - | - | - | - | bar: MC1 to SP3
W9 | 2026-01-19 | Monday | 🟢 Working | - | - | - | [6 empty] | - | - | - | - | bar: MC1 to SP3
W9 | 2026-01-20 | Tuesday | 🟢 Working | - | - | - | [6 empty] | - | - | - | - | bar: MC1 to SP3
W9 | 2026-01-21 | Wednesday | 🟢 Working | - | - | - | [6 empty] | - | - | - | - | bar: MC1 to SP3
W9 | 2026-01-22 | Thursday | 🟢 Working | - | - | - | [6 empty] | - | - | - | - | bar: MC1 to SP3
W9 | 2026-01-23 | Friday | 🟢 Working | - | - | - | [6 empty] | - | - | - | - | bar: MC1 to SP3
W10 | 2026-01-24 | Saturday | 🟡 Saturday | - | - | - | [6 empty] | - | - | - | - | bar: MC1 to SP3
W10 | 2026-01-25 | Sunday | 🔴 HOLIDAY | Sunday - Weekly Off | - | - | [6 empty] | - | - | - | - | bar: MC1 to SP3
W10 | 2026-01-26 | Monday | 🔴 HOLIDAY | Republic Day | - | - | [6 empty] | - | - | - | - | bar: MC1 to SP3
W10 | 2026-01-27 | Tuesday | 🟢 Working | - | - | - | [6 empty] | - | - | - | - | bar: MC1 to SP3
W10 | 2026-01-28 | Wednesday | 🟢 Working | - | - | - | [6 empty] | - | - | - | - | bar: MC1 to SP3
W10 | 2026-01-29 | Thursday | 🟢 Working | - | - | - | [6 empty] | - | - | - | - | bar: MC1 to SP3
W10 | 2026-01-30 | Friday | 🟢 Working | - | - | - | [6 empty] | - | - | - | - | bar: MC1 to SP3
W11 | 2026-01-31 | Saturday | 🟡 Saturday | - | - | - | [6 empty] | - | - | - | - | bar: MC1 to SP3
W11 | 2026-02-01 | Sunday | 🔴 HOLIDAY | Sunday - Weekly Off | - | - | [6 empty] | - | - | - | - | bar: MC1 to SP3
W11 | 2026-02-02 | Monday | 🟢 Working | - | - | - | [6 empty] | - | - | - | - | bar: MC1 to SP3
W11 | 2026-02-03 | Tuesday | 🟢 Working | - | - | - | [6 empty] | - | - | - | - | bar: MC1 to SP3
W11 | 2026-02-04 | Wednesday | 🟢 Working | - | - | - | [6 empty] | - | - | - | - | bar: MC1 to SP3
W11 | 2026-02-05 | Thursday | 🟢 Working | - | - | - | [6 empty] | - | - | - | - | bar: MC1 to SP3
W11 | 2026-02-06 | Friday | 🟢 Working | - | - | - | [6 empty] | - | - | - | - | bar: MC1 to SP3
W12 | 2026-02-07 | Saturday | 🟡 Saturday | - | - | - | [6 empty] | - | - | - | - | bar: MC1 to SP3
W12 | 2026-02-08 | Sunday | 🔴 HOLIDAY | Sunday - Weekly Off | - | - | [6 empty] | - | - | - | - | bar: MC1 to SP3
W12 | 2026-02-09 | Monday | 🟢 Working | - | - | - | [6 empty] | - | - | - | - | bar: MC1 to SP3
W12 | 2026-02-10 | Tuesday | 🟢 Working | - | - | - | [6 empty] | - | - | - | - | bar: MC1 to SP3
W12 | 2026-02-11 | Wednesday | 🟢 Working | - | - | - | [6 empty] | - | - | - | - | bar: MC1 to SP3
W12 | 2026-02-12 | Thursday | 🟢 Working | - | - | - | [6 empty] | - | - | - | - | bar: MC1 to SP3
W12 | 2026-02-13 | Friday | 🟢 Working | - | - | - | [6 empty] | - | - | - | - | bar: MC1 to SP3
W13 | 2026-02-14 | Saturday | 🟡 Saturday | - | - | - | [6 empty] | - | - | - | - | bar: MC1 to SP3
W13 | 2026-02-15 | Sunday | 🔴 HOLIDAY | Sunday - Weekly Off | - | - | [6 empty] | - | - | - | - | bar: MC1 to SP3
W13 | 2026-02-16 | Monday | 🟢 Working | - | - | - | [6 empty] | - | - | - | - | bar: MC1 to SP3
W13 | 2026-02-17 | Tuesday | 🟢 Working | - | - | - | [6 empty] | - | - | - | - | bar: MC1 to SP3
W13 | 2026-02-18 | Wednesday | 🟢 Working | - | - | - | [6 empty] | - | - | - | - | bar: MC1 to SP3
W13 | 2026-02-19 | Thursday | 🟢 Working | - | - | - | [6 empty] | - | - | - | - | bar: MC1 to SP3
W13 | 2026-02-20 | Friday | 🟢 Working | - | - | - | [6 empty] | - | - | - | - | bar: MC1 to SP3
W14 | 2026-02-21 | Saturday | 🟡 Saturday | - | - | - | [6 empty] | - | - | - | - | bar: MC1 to SP3
W14 | 2026-02-22 | Sunday | 🔴 HOLIDAY | Sunday - Weekly Off | - | - | [6 empty] | - | - | - | - | bar: MC1 to SP3
W14 | 2026-02-23 | Monday | 🟢 Working | - | - | - | [6 empty] | - | - | - | - | bar: MC1 to SP3
W14 | 2026-02-24 | Tuesday | 🟢 Working | - | - | - | [6 empty] | - | - | - | - | bar: MC1 to SP3
W14 | 2026-02-25 | Wednesday | 🟢 Working | - | - | - | [6 empty] | - | - | - | - | bar: MC1 to SP3
W14 | 2026-02-26 | Thursday | 🟢 Working | - | - | - | [6 empty] | - | - | - | - | bar: MC1 to SP3
W14 | 2026-02-27 | Friday | 🟢 Working | - | - | - | [6 empty] | - | - | - | - | bar: MC1 to SP3
W15 | 2026-02-28 | Saturday | 🟡 Saturday | - | - | - | [6 empty] | - | - | - | - | bar: MC1 to SP3
W15 | 2026-03-01 | Sunday | 🔴 HOLIDAY | Sunday - Weekly Off | - | - | [6 empty] | - | - | - | - | bar: MC1 to SP3
W15 | 2026-03-02 | Monday | 🟢 Working | - | - | - | [6 empty] | - | - | - | - | bar: MC1 to SP3
W15 | 2026-03-03 | Tuesday | 🟢 Working | - | - | - | [6 empty] | - | - | - | - | bar: MC1 to SP3
W15 | 2026-03-04 | Wednesday | 🟢 Working | - | - | - | [6 empty] | - | - | - | - | bar: MC1 to SP3
W15 | 2026-03-05 | Thursday | 🟢 Working | - | - | - | [6 empty] | - | - | - | - | bar: MC1 to SP3
W15 | 2026-03-06 | Friday | 🟢 Working | - | - | - | [6 empty] | - | - | - | - | bar: MC1 to SP3
W16 | 2026-03-07 | Saturday | 🟡 Saturday | - | - | - | [6 empty] | - | - | - | - | bar: MC1 to SP3
W16 | 2026-03-08 | Sunday | 🔴 HOLIDAY | Sunday - Weekly Off | - | - | [6 empty] | - | - | - | - | bar: MC1 to SP3
W16 | 2026-03-09 | Monday | 🟢 Working | - | - | - | [6 empty] | - | - | - | - | bar: MC1 to SP3
W16 | 2026-03-10 | Tuesday | 🟢 Working | - | - | - | [6 empty] | - | - | - | - | bar: MC1 to SP3
W16 | 2026-03-11 | Wednesday | 🟢 Working | - | - | - | [6 empty] | - | - | - | - | bar: MC1 to SP3
W16 | 2026-03-12 | Thursday | 🟢 Working | - | - | - | [6 empty] | - | - | - | - | bar: MC1 to SP3
W16 | 2026-03-13 | Friday | 🟢 Working | - | - | - | [6 empty] | - | - | - | - | bar: MC1 to SP3
W17 | 2026-03-14 | Saturday | 🟡 Saturday | - | - | - | [6 empty] | - | - | - | - | bar: MC1 to SP3
W17 | 2026-03-15 | Sunday | 🔴 HOLIDAY | Sunday - Weekly Off | - | - | [6 empty] | - | - | - | - | bar: MC1 to SP3
W17 | 2026-03-16 | Monday | 🟢 Working | - | - | - | [6 empty] | - | - | - | - | bar: MC1 to SP3
W17 | 2026-03-17 | Tuesday | 🟢 Working | - | - | - | [6 empty] | - | - | - | - | bar: MC1 to SP3
W17 | 2026-03-18 | Wednesday | 🟢 Working | - | - | - | [6 empty] | - | - | - | - | bar: MC1 to SP3
W17 | 2026-03-19 | Thursday | 🟢 Working | - | - | - | [6 empty] | - | - | - | - | bar: MC1 to SP3
W17 | 2026-03-20 | Friday | 🟢 Working | - | - | - | [6 empty] | - | - | - | - | bar: MC1 to SP3
W18 | 2026-03-21 | Saturday | 🔴 HOLIDAY | Id-ul-Fitr (estimated) | - | - | [6 empty] | - | - | - | - | bar: MC1 to SP3
W18 | 2026-03-22 | Sunday | 🔴 HOLIDAY | Sunday - Weekly Off | - | - | [6 empty] | - | - | - | - | bar: MC1 to SP3
W18 | 2026-03-23 | Monday | 🟢 Working | - | - | - | [6 empty] | - | - | - | - | bar: MC1 to SP3
W18 | 2026-03-24 | Tuesday | 🟢 Working | - | - | - | [6 empty] | - | - | - | - | bar: MC1 to SP3
W18 | 2026-03-25 | Wednesday | 🟢 Working | - | - | - | [6 empty] | - | - | - | - | bar: MC1 to SP3
W18 | 2026-03-26 | Thursday | 🟢 Working | - | - | - | [6 empty] | - | - | - | - | bar: MC1 to SP3
W18 | 2026-03-27 | Friday | 🟢 Working | - | - | - | [6 empty] | - | - | - | - | bar: MC1 to SP3
W19 | 2026-03-28 | Saturday | 🟡 Saturday | - | - | - | [6 empty] | - | - | - | - | bar: MC1 to SP3
W19 | 2026-03-29 | Sunday | 🔴 HOLIDAY | Sunday - Weekly Off | - | - | [6 empty] | - | - | - | - | bar: MC1 to SP3
W19 | 2026-03-30 | Monday | 🟢 Working | - | - | - | [6 empty] | - | - | - | - | bar: MC1 to SP3
W19 | 2026-03-31 | Tuesday | 🔴 HOLIDAY | Mahavir Jayanti | - | - | [6 empty] | - | - | - | - | bar: MC1 to SP3
W19 | 2026-04-01 | Wednesday | 🟢 Working | - | - | - | [6 empty] | - | - | - | - | bar: MC1 to SP3
W19 | 2026-04-02 | Thursday | 🟢 Working | - | - | - | [6 empty] | - | - | - | - | bar: MC1 to SP3
W19 | 2026-04-03 | Friday | 🔴 HOLIDAY | Good Friday | - | - | [6 empty] | - | - | - | - | bar: MC1 to SP3
WEEKLY TOTALS SUMMARY (All Weeks)
Week | Working Days | Holidays | Casting Tons | Grinding Units | MC1 Units | MC2 Units | MC3 Units | SP1 Units | SP2 Units | SP3 Units | Big Line (hrs) | Small Line (hrs) | Big Line Util % | Small Line Util %
W1 | 6 | 1 | 743.3 | 347 | 352 | 245 | 100 | 586 | 450 | 317 | 116.6 | 114.9 | 90.0% | 88.6%
W2 | 6 | 1 | 437.5 | 349 | 304 | 182 | 34 | 295 | 297 | 110 | 121.8 | 91.5 | 94.0% | 70.6%
W3 | 6 | 1 | 381.4 | 242 | 248 | 187 | 73 | 348 | 389 | 254 | 113.3 | 82.4 | 87.4% | 63.6%
W4 | 6 | 1 | 84.8 | 304 | 196 | 236 | 64 | 582 | 524 | 129 | 18.3 | 36.8 | 14.1% | 28.4%
W5 | 5 | 2 | 140.7 | 434 | 279 | 258 | 10 | 556 | 636 | 518 | 30.0 | 48.4 | 23.1% | 37.4%
W6 | 6 | 1 | 0.0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | 0.0 | 0.0% | 0.0%
W7 | 6 | 1 | 0.0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | 0.0 | 0.0% | 0.0%
W8 | 6 | 1 | 0.0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | 0.0 | 0.0% | 0.0%
W9 | 6 | 1 | 0.0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | 0.0 | 0.0% | 0.0%
W10 | 5 | 2 | 0.0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | 0.0 | 0.0% | 0.0%
W11 | 6 | 1 | 0.0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | 0.0 | 0.0% | 0.0%
W12 | 6 | 1 | 0.0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | 0.0 | 0.0% | 0.0%
W13 | 6 | 1 | 0.0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | 0.0 | 0.0% | 0.0%
W14 | 6 | 1 | 0.0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | 0.0 | 0.0% | 0.0%
W15 | 6 | 1 | 0.0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | 0.0 | 0.0% | 0.0%
W16 | 6 | 1 | 0.0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | 0.0 | 0.0% | 0.0%
W17 | 6 | 1 | 0.0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | 0.0 | 0.0% | 0.0%
W18 | 5 | 2 | 0.0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | 0.0 | 0.0% | 0.0%
W19 | 4 | 3 | 0.0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 | 0.0 | 0.0% | 0.0%
NOTES:
🔴 HOLIDAY = No production (Sunday or National Holiday)
🟡 Saturday = Working day but may have reduced shifts
🟢 Working = Full production day (Monday-Friday)
Production quantities are distributed evenly across working days in each week
MOULDING LINE UTILIZATION BY WEEK
Week | Big Line Util % | Small Line Util % | Big Line Hours | Small Line Hours
W1 | 90.0% | 88.6% | 116.6 | 114.9
W2 | 94.0% | 70.6% | 121.8 | 91.5
W3 | 87.4% | 63.6% | 113.3 | 82.4
W4 | 14.1% | 28.4% | 18.3 | 36.8
W5 | 23.1% | 37.4% | 30.0 | 48.4
W6 | 0.0% | 0.0% | 0.0 | 0.0
W7 | 0.0% | 0.0% | 0.0 | 0.0
W8 | 0.0% | 0.0% | 0.0 | 0.0
W9 | 0.0% | 0.0% | 0.0 | 0.0
W10 | 0.0% | 0.0% | 0.0 | 0.0
W11 | 0.0% | 0.0% | 0.0 | 0.0
W12 | 0.0% | 0.0% | 0.0 | 0.0
W13 | 0.0% | 0.0% | 0.0 | 0.0
W14 | 0.0% | 0.0% | 0.0 | 0.0
W15 | 0.0% | 0.0% | 0.0 | 0.0
W16 | 0.0% | 0.0% | 0.0 | 0.0
W17 | 0.0% | 0.0% | 0.0 | 0.0
W18 | 0.0% | 0.0% | 0.0 | 0.0
W19 | 0.0% | 0.0% | 0.0 | 0.0

## 8_PART_DAILY_SCHEDULE
PART-LEVEL DAILY PRODUCTION SCHEDULE - ALL 8 STAGES
Complete production flow: Casting → Grinding → MC1 → MC2 → MC3 → SP1 → SP2 → SP3 → Delivery ¦ Planning Period: 19 weeks
This schedule shows the ACTUAL daily production flow to determine REAL delivery dates
SCHEDULE OVERVIEW
Metric | Value
Total Schedule Entries | 2,647
Unique Sales Orders | 191
Unique Parts | 76
Total Production Units | 8,456
Operations Tracked | 8 Stages (Casting, Grinding, MC1-3, SP1-3)
STAGE BREAKDOWN:
Casting Entries | 323
Grinding Entries | 459
MC1 Entries | 406
MC2 Entries | 39
MC3 Entries | 39
SP1 (Primer) Entries | 534
SP2 (Intermediate) Entries | 222
SP3 (Top Coat) Entries | 222
MOULDING LINE CAPACITY UTILIZATION
Line | Avg Util % | Max Util % | Total Hours | Capacity Hours
Big Line | 16.2% | 94.0% | 400.0 | 2462.4
Small Line | 15.2% | 88.6% | 374.0 | 2462.4
PART-LEVEL DAILY PRODUCTION SCHEDULE - CLEAN DATA VIEW
All production data without separator rows for easy Excel filtering/sorting ¦ Total: 2647 entries
Use "Freeze Panes" on Row 4 and Filter on "Sales Order" column to navigate by order
Date | Moulding Date | Day | Week | Part | Sales Order | Customer | Committed Week | Order Qty | Batch No | Cumulative Qty | Progress | Units | Operation | Machine/Resource | Unit Wt (kg) | Total Wt (ton) | Cycle Time | Batch Size | Prod Time | Notes
2025-11-22 | 2025-11-22 | Saturday | W1 | UBC-035 | 2526100367 | Unknown | W1 | 46 | 1 | 46 | 46/46 COMPLETE ✓ | 46 | MC1 | BVCAD30MC001 | 236.00 | 10.856 | 90 min | 0 | - | Order Total: 46 units
2025-11-22 | 2025-11-22 | Saturday | W1 | UBC-035 | 2526100367 | Unknown | W1 | 46 | 1 | 46 | 46/46 COMPLETE ✓ | 46 | SP1 | KVCALPPSP001 | 236.00 | 10.856 | 12 min | 1 | 552 min | Order Total: 46 units
2025-11-22 | 2025-11-22 | Saturday | W1 | UBC-035 | 2526100367 | Unknown | W1 | 46 | 1 | 46 | 46/46 COMPLETE ✓ | 46 | SP2 | KVCALPPSP002 | 236.00 | 10.856 | 12 min | 1 | 552 min | Order Total: 46 units
2025-11-22 | 2025-11-22 | Saturday | W1 | UBC-035 | 2526100367 | Unknown | W1 | 46 | 1 | 46 | 46/46 COMPLETE ✓ | 46 | SP3 | KVCALFPSP001 | 236.00 | 10.856 | 7 min | 1 | 322 min | Order Total: 46 units
2025-11-22 | 2025-11-22 | Saturday | W1 | ARM-004-N | 2526100558 | Unknown | W1 | 4 | 1 | 2 | 2/4 (50%) | 2 | Grinding | KVCALHMGR001 | 2835.75 | 5.671 | 300 min | 1 | 600 min | Order Total: 4 units
2025-11-22 | 2025-11-22 | Saturday | W1 | ARM-004-N | 2526100558 | Unknown | W1 | 4 | 1 | 2 | 2/4 (50%) | 2 | MC1 | KVCAD30MC001 | 2835.75 | 5.671 | 240 min | 0 | - | Order Total: 4 units
2025-11-22 | 2025-11-22 | Saturday | W1 | ARM-004-N | 2526100558 | Unknown | W1 | 4 | 1 | 2 | 2/4 (50%) | 2 | SP1 | KVCALPPSP001 | 2835.75 | 5.671 | 12 min | 1 | 24 min | Order Total: 4 units
2025-11-22 | 2025-11-22 | Saturday | W1 | ARM-004-N | 2526100558 | Unknown | W1 | 4 | 1 | 2 | 2/4 (50%) | 2 | SP2 | KVCALPPSP002 | 2835.75 | 5.671 | 12 min | 1 | 24 min | Order Total: 4 units
2025-11-22 | 2025-11-22 | Saturday | W1 | ARM-004-N | 2526100558 | Unknown | W1 | 4 | 1 | 2 | 2/4 (50%) | 2 | SP3 | KVCALFPSP001 | 2835.75 | 5.671 | 12 min | 1 | 24 min | Order Total: 4 units
2025-11-24 | 2025-11-24 | Monday | W1 | ARM-004-N | 2526100558 | Unknown | W1 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | Grinding | KVCALHMGR001 | 2835.75 | 5.671 | 300 min | 1 | 600 min | Order Total: 4 units
2025-11-24 | 2025-11-24 | Monday | W1 | ARM-004-N | 2526100558 | Unknown | W1 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | MC1 | KVCAD30MC001 | 2835.75 | 5.671 | 240 min | 0 | - | Order Total: 4 units
2025-11-24 | 2025-11-24 | Monday | W1 | ARM-004-N | 2526100558 | Unknown | W1 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | SP1 | KVCALPPSP001 | 2835.75 | 5.671 | 12 min | 1 | 24 min | Order Total: 4 units
2025-11-24 | 2025-11-24 | Monday | W1 | ARM-004-N | 2526100558 | Unknown | W1 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | SP2 | KVCALPPSP002 | 2835.75 | 5.671 | 12 min | 1 | 24 min | Order Total: 4 units
2025-11-24 | 2025-11-24 | Monday | W1 | ARM-004-N | 2526100558 | Unknown | W1 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | SP3 | KVCALFPSP001 | 2835.75 | 5.671 | 12 min | 1 | 24 min | Order Total: 4 units
2025-11-22 | 2025-11-29 | Saturday | W1 | ARM-007 | 2526100559 | Unknown | W1 | 1 | 1 | 1 | 1/1 COMPLETE ✓ | 1 | Grinding | GR1ARM-007 | 4536.00 | 4.536 | 240 min | 1 | 240 min | Order Total: 1 units
2025-11-22 | 2025-11-29 | Saturday | W1 | ARM-007 | 2526100559 | Unknown | W1 | 1 | 1 | 1 | 1/1 COMPLETE ✓ | 1 | MC1 | MC1ARM-007 | 4536.00 | 4.536 | 240 min | 1 | 240 min | Order Total: 1 units
2025-11-22 | 2025-11-29 | Saturday | W1 | ARM-007 | 2526100559 | Unknown | W1 | 1 | 1 | 1 | 1/1 COMPLETE ✓ | 1 | SP1 | SP1ARM-007 | 4536.00 | 4.536 | - | 1 | - | Order Total: 1 units
2025-11-22 | 2025-11-29 | Saturday | W1 | ARM-007 | 2526100559 | Unknown | W1 | 1 | 1 | 1 | 1/1 COMPLETE ✓ | 1 | SP2 | KVCALPPSP002 | 4536.00 | 4.536 | - | 1 | - | Order Total: 1 units
2025-11-22 | 2025-11-29 | Saturday | W1 | ARM-007 | 2526100559 | Unknown | W1 | 1 | 1 | 1 | 1/1 COMPLETE ✓ | 1 | SP3 | KVCALFPSP001 | 4536.00 | 4.536 | - | 1 | - | Order Total: 1 units
2025-11-29 | 2025-11-29 | Saturday | W2 | ARM-007 | 2526100559 | Unknown | W1 | 1 | 1 | 1 | 1/1 COMPLETE ✓ | 1 | Casting | CS1ARM-007 | 4536.00 | 4.536 | 24 min | 1 | 24 min | Order Total: 1 units
2025-11-30 | 2025-11-29 | Sunday | W2 | ARM-007 | 2526100559 | Unknown | W1 | 1 | 1 | 1 | 1/1 COMPLETE ✓ | 1 | Cooling/Shakeout | N/A | 4536.00 | 4.536 | - | 1 | - | Order Total: 1 units
2025-11-22 | 2025-11-29 | Saturday | W1 | ARM-007 | 2526100560 | Unknown | W1 | 2 | 1 | 1 | 1/2 (50%) | 1 | Grinding | GR1ARM-007 | 4536.00 | 4.536 | 240 min | 1 | 240 min | Order Total: 2 units
2025-11-22 | 2025-11-29 | Saturday | W1 | ARM-007 | 2526100560 | Unknown | W1 | 2 | 1 | 1 | 1/2 (50%) | 1 | MC1 | MC1ARM-007 | 4536.00 | 4.536 | 240 min | 1 | 240 min | Order Total: 2 units
2025-11-22 | 2025-11-29 | Saturday | W1 | ARM-007 | 2526100560 | Unknown | W1 | 2 | 1 | 1 | 1/2 (50%) | 1 | SP1 | SP1ARM-007 | 4536.00 | 4.536 | - | 1 | - | Order Total: 2 units
2025-11-22 | 2025-11-29 | Saturday | W1 | ARM-007 | 2526100560 | Unknown | W1 | 2 | 1 | 1 | 1/2 (50%) | 1 | SP2 | KVCALPPSP002 | 4536.00 | 4.536 | - | 1 | - | Order Total: 2 units
2025-11-22 | 2025-11-29 | Saturday | W1 | ARM-007 | 2526100560 | Unknown | W1 | 2 | 1 | 1 | 1/2 (50%) | 1 | SP3 | KVCALFPSP001 | 4536.00 | 4.536 | - | 1 | - | Order Total: 2 units
2025-11-24 | 2025-12-01 | Monday | W1 | ARM-007 | 2526100560 | Unknown | W1 | 2 | 2 | 2 | 2/2 COMPLETE ✓ | 1 | Grinding | GR1ARM-007 | 4536.00 | 4.536 | 240 min | 1 | 240 min | Order Total: 2 units
2025-11-24 | 2025-12-01 | Monday | W1 | ARM-007 | 2526100560 | Unknown | W1 | 2 | 2 | 2 | 2/2 COMPLETE ✓ | 1 | MC1 | MC1ARM-007 | 4536.00 | 4.536 | 240 min | 1 | 240 min | Order Total: 2 units
2025-11-24 | 2025-12-01 | Monday | W1 | ARM-007 | 2526100560 | Unknown | W1 | 2 | 2 | 2 | 2/2 COMPLETE ✓ | 1 | SP1 | SP1ARM-007 | 4536.00 | 4.536 | - | 1 | - | Order Total: 2 units
2025-11-24 | 2025-12-01 | Monday | W1 | ARM-007 | 2526100560 | Unknown | W1 | 2 | 2 | 2 | 2/2 COMPLETE ✓ | 1 | SP2 | KVCALPPSP002 | 4536.00 | 4.536 | - | 1 | - | Order Total: 2 units
2025-11-24 | 2025-12-01 | Monday | W1 | ARM-007 | 2526100560 | Unknown | W1 | 2 | 2 | 2 | 2/2 COMPLETE ✓ | 1 | SP3 | KVCALFPSP001 | 4536.00 | 4.536 | - | 1 | - | Order Total: 2 units
2025-11-29 | 2025-11-29 | Saturday | W2 | ARM-007 | 2526100560 | Unknown | W1 | 2 | 1 | 1 | 1/2 (50%) | 1 | Casting | CS1ARM-007 | 4536.00 | 4.536 | 24 min | 1 | 24 min | Order Total: 2 units
2025-11-30 | 2025-11-29 | Sunday | W2 | ARM-007 | 2526100560 | Unknown | W1 | 2 | 1 | 1 | 1/2 (50%) | 1 | Cooling/Shakeout | N/A | 4536.00 | 4.536 | - | 1 | - | Order Total: 2 units
2025-12-01 | 2025-12-01 | Monday | W2 | ARM-007 | 2526100560 | Unknown | W1 | 2 | 2 | 2 | 2/2 COMPLETE ✓ | 1 | Casting | CS1ARM-007 | 4536.00 | 4.536 | 24 min | 1 | 24 min | Order Total: 2 units
2025-12-02 | 2025-12-01 | Tuesday | W2 | ARM-007 | 2526100560 | Unknown | W1 | 2 | 2 | 2 | 2/2 COMPLETE ✓ | 1 | Cooling/Shakeout | N/A | 4536.00 | 4.536 | - | 1 | - | Order Total: 2 units
2025-11-22 | 2025-11-22 | Saturday | W1 | ARM-004-N | 2526100561 | Unknown | W1 | 1 | 1 | 1 | 1/1 COMPLETE ✓ | 1 | Grinding | KVCALHMGR001 | 2835.75 | 2.836 | 300 min | 1 | 300 min | Order Total: 1 units
2025-11-22 | 2025-11-22 | Saturday | W1 | ARM-004-N | 2526100561 | Unknown | W1 | 1 | 1 | 1 | 1/1 COMPLETE ✓ | 1 | MC1 | KVCAD30MC001 | 2835.75 | 2.836 | 240 min | 0 | - | Order Total: 1 units
2025-11-22 | 2025-11-22 | Saturday | W1 | ARM-004-N | 2526100561 | Unknown | W1 | 1 | 1 | 1 | 1/1 COMPLETE ✓ | 1 | SP1 | KVCALPPSP001 | 2835.75 | 2.836 | 12 min | 1 | 12 min | Order Total: 1 units
2025-11-22 | 2025-11-22 | Saturday | W1 | ARM-004-N | 2526100561 | Unknown | W1 | 1 | 1 | 1 | 1/1 COMPLETE ✓ | 1 | SP2 | KVCALPPSP002 | 2835.75 | 2.836 | 12 min | 1 | 12 min | Order Total: 1 units
2025-11-22 | 2025-11-22 | Saturday | W1 | ARM-004-N | 2526100561 | Unknown | W1 | 1 | 1 | 1 | 1/1 COMPLETE ✓ | 1 | SP3 | KVCALFPSP001 | 2835.75 | 2.836 | 12 min | 1 | 12 min | Order Total: 1 units
2025-11-22 | 2025-11-22 | Saturday | W1 | ARM-004-N | 2526100562 | Unknown | W1 | 5 | 1 | 2 | 2/5 (40%) | 2 | Grinding | KVCALHMGR001 | 2835.75 | 5.671 | 300 min | 1 | 600 min | Order Total: 5 units
2025-11-22 | 2025-11-22 | Saturday | W1 | ARM-004-N | 2526100562 | Unknown | W1 | 5 | 1 | 2 | 2/5 (40%) | 2 | MC1 | KVCAD30MC001 | 2835.75 | 5.671 | 240 min | 0 | - | Order Total: 5 units
2025-11-22 | 2025-11-22 | Saturday | W1 | ARM-004-N | 2526100562 | Unknown | W1 | 5 | 1 | 2 | 2/5 (40%) | 2 | SP1 | KVCALPPSP001 | 2835.75 | 5.671 | 12 min | 1 | 24 min | Order Total: 5 units
2025-11-22 | 2025-11-22 | Saturday | W1 | ARM-004-N | 2526100562 | Unknown | W1 | 5 | 1 | 2 | 2/5 (40%) | 2 | SP2 | KVCALPPSP002 | 2835.75 | 5.671 | 12 min | 1 | 24 min | Order Total: 5 units
2025-11-22 | 2025-11-22 | Saturday | W1 | ARM-004-N | 2526100562 | Unknown | W1 | 5 | 1 | 2 | 2/5 (40%) | 2 | SP3 | KVCALFPSP001 | 2835.75 | 5.671 | 12 min | 1 | 24 min | Order Total: 5 units
2025-11-24 | 2025-11-24 | Monday | W1 | ARM-004-N | 2526100562 | Unknown | W1 | 5 | 2 | 5 | 5/5 COMPLETE ✓ | 3 | Grinding | KVCALHMGR001 | 2835.75 | 8.507 | 300 min | 1 | 900 min | Order Total: 5 units
2025-11-24 | 2025-11-24 | Monday | W1 | ARM-004-N | 2526100562 | Unknown | W1 | 5 | 2 | 5 | 5/5 COMPLETE ✓ | 3 | MC1 | KVCAD30MC001 | 2835.75 | 8.507 | 240 min | 0 | - | Order Total: 5 units
2025-11-24 | 2025-11-24 | Monday | W1 | ARM-004-N | 2526100562 | Unknown | W1 | 5 | 2 | 5 | 5/5 COMPLETE ✓ | 3 | SP1 | KVCALPPSP001 | 2835.75 | 8.507 | 12 min | 1 | 36 min | Order Total: 5 units
2025-11-24 | 2025-11-24 | Monday | W1 | ARM-004-N | 2526100562 | Unknown | W1 | 5 | 2 | 5 | 5/5 COMPLETE ✓ | 3 | SP2 | KVCALPPSP002 | 2835.75 | 8.507 | 12 min | 1 | 36 min | Order Total: 5 units
2025-11-24 | 2025-11-24 | Monday | W1 | ARM-004-N | 2526100562 | Unknown | W1 | 5 | 2 | 5 | 5/5 COMPLETE ✓ | 3 | SP3 | KVCALFPSP001 | 2835.75 | 8.507 | 12 min | 1 | 36 min | Order Total: 5 units
2025-11-22 | 2025-11-22 | Saturday | W1 | ARM-004-N | 2526100563 | Unknown | W1 | 7 | 1 | 2 | 2/7 (28%) | 2 | Grinding | KVCALHMGR001 | 2835.75 | 5.671 | 300 min | 1 | 600 min | Order Total: 7 units
2025-11-22 | 2025-11-22 | Saturday | W1 | ARM-004-N | 2526100563 | Unknown | W1 | 7 | 1 | 2 | 2/7 (28%) | 2 | MC1 | KVCAD30MC001 | 2835.75 | 5.671 | 240 min | 0 | - | Order Total: 7 units
2025-11-22 | 2025-11-22 | Saturday | W1 | ARM-004-N | 2526100563 | Unknown | W1 | 7 | 1 | 2 | 2/7 (28%) | 2 | SP1 | KVCALPPSP001 | 2835.75 | 5.671 | 12 min | 1 | 24 min | Order Total: 7 units
2025-11-22 | 2025-11-22 | Saturday | W1 | ARM-004-N | 2526100563 | Unknown | W1 | 7 | 1 | 2 | 2/7 (28%) | 2 | SP2 | KVCALPPSP002 | 2835.75 | 5.671 | 12 min | 1 | 24 min | Order Total: 7 units
2025-11-22 | 2025-11-22 | Saturday | W1 | ARM-004-N | 2526100563 | Unknown | W1 | 7 | 1 | 2 | 2/7 (28%) | 2 | SP3 | KVCALFPSP001 | 2835.75 | 5.671 | 12 min | 1 | 24 min | Order Total: 7 units
2025-11-24 | 2025-11-24 | Monday | W1 | ARM-004-N | 2526100563 | Unknown | W1 | 7 | 2 | 4 | 4/7 (57%) | 2 | Grinding | KVCALHMGR001 | 2835.75 | 5.671 | 300 min | 1 | 600 min | Order Total: 7 units
2025-11-24 | 2025-11-24 | Monday | W1 | ARM-004-N | 2526100563 | Unknown | W1 | 7 | 2 | 4 | 4/7 (57%) | 2 | MC1 | KVCAD30MC001 | 2835.75 | 5.671 | 240 min | 0 | - | Order Total: 7 units
2025-11-24 | 2025-11-24 | Monday | W1 | ARM-004-N | 2526100563 | Unknown | W1 | 7 | 2 | 4 | 4/7 (57%) | 2 | SP1 | KVCALPPSP001 | 2835.75 | 5.671 | 12 min | 1 | 24 min | Order Total: 7 units
2025-11-24 | 2025-11-24 | Monday | W1 | ARM-004-N | 2526100563 | Unknown | W1 | 7 | 2 | 4 | 4/7 (57%) | 2 | SP2 | KVCALPPSP002 | 2835.75 | 5.671 | 12 min | 1 | 24 min | Order Total: 7 units
2025-11-24 | 2025-11-24 | Monday | W1 | ARM-004-N | 2526100563 | Unknown | W1 | 7 | 2 | 4 | 4/7 (57%) | 2 | SP3 | KVCALFPSP001 | 2835.75 | 5.671 | 12 min | 1 | 24 min | Order Total: 7 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | ARM-004-N | 2526100563 | Unknown | W1 | 7 | 3 | 7 | 7/7 COMPLETE ✓ | 3 | Grinding | KVCALHMGR001 | 2835.75 | 8.507 | 300 min | 1 | 900 min | Order Total: 7 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | ARM-004-N | 2526100563 | Unknown | W1 | 7 | 3 | 7 | 7/7 COMPLETE ✓ | 3 | MC1 | KVCAD30MC001 | 2835.75 | 8.507 | 240 min | 0 | - | Order Total: 7 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | ARM-004-N | 2526100563 | Unknown | W1 | 7 | 3 | 7 | 7/7 COMPLETE ✓ | 3 | SP1 | KVCALPPSP001 | 2835.75 | 8.507 | 12 min | 1 | 36 min | Order Total: 7 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | ARM-004-N | 2526100563 | Unknown | W1 | 7 | 3 | 7 | 7/7 COMPLETE ✓ | 3 | SP2 | KVCALPPSP002 | 2835.75 | 8.507 | 12 min | 1 | 36 min | Order Total: 7 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | ARM-004-N | 2526100563 | Unknown | W1 | 7 | 3 | 7 | 7/7 COMPLETE ✓ | 3 | SP3 | KVCALFPSP001 | 2835.75 | 8.507 | 12 min | 1 | 36 min | Order Total: 7 units
2025-11-22 | 2025-11-29 | Saturday | W1 | ARM-007 | 2526100564 | Unknown | W1 | 2 | 1 | 1 | 1/2 (50%) | 1 | Grinding | GR1ARM-007 | 4536.00 | 4.536 | 240 min | 1 | 240 min | Order Total: 2 units
2025-11-22 | 2025-11-29 | Saturday | W1 | ARM-007 | 2526100564 | Unknown | W1 | 2 | 1 | 1 | 1/2 (50%) | 1 | MC1 | MC1ARM-007 | 4536.00 | 4.536 | 240 min | 1 | 240 min | Order Total: 2 units
2025-11-22 | 2025-11-29 | Saturday | W1 | ARM-007 | 2526100564 | Unknown | W1 | 2 | 1 | 1 | 1/2 (50%) | 1 | SP1 | SP1ARM-007 | 4536.00 | 4.536 | - | 1 | - | Order Total: 2 units
2025-11-22 | 2025-11-29 | Saturday | W1 | ARM-007 | 2526100564 | Unknown | W1 | 2 | 1 | 1 | 1/2 (50%) | 1 | SP2 | KVCALPPSP002 | 4536.00 | 4.536 | - | 1 | - | Order Total: 2 units
2025-11-22 | 2025-11-29 | Saturday | W1 | ARM-007 | 2526100564 | Unknown | W1 | 2 | 1 | 1 | 1/2 (50%) | 1 | SP3 | KVCALFPSP001 | 4536.00 | 4.536 | - | 1 | - | Order Total: 2 units
2025-11-24 | 2025-12-01 | Monday | W1 | ARM-007 | 2526100564 | Unknown | W1 | 2 | 2 | 2 | 2/2 COMPLETE ✓ | 1 | Grinding | GR1ARM-007 | 4536.00 | 4.536 | 240 min | 1 | 240 min | Order Total: 2 units
2025-11-24 | 2025-12-01 | Monday | W1 | ARM-007 | 2526100564 | Unknown | W1 | 2 | 2 | 2 | 2/2 COMPLETE ✓ | 1 | MC1 | MC1ARM-007 | 4536.00 | 4.536 | 240 min | 1 | 240 min | Order Total: 2 units
2025-11-24 | 2025-12-01 | Monday | W1 | ARM-007 | 2526100564 | Unknown | W1 | 2 | 2 | 2 | 2/2 COMPLETE ✓ | 1 | SP1 | SP1ARM-007 | 4536.00 | 4.536 | - | 1 | - | Order Total: 2 units
2025-11-24 | 2025-12-01 | Monday | W1 | ARM-007 | 2526100564 | Unknown | W1 | 2 | 2 | 2 | 2/2 COMPLETE ✓ | 1 | SP2 | KVCALPPSP002 | 4536.00 | 4.536 | - | 1 | - | Order Total: 2 units
2025-11-24 | 2025-12-01 | Monday | W1 | ARM-007 | 2526100564 | Unknown | W1 | 2 | 2 | 2 | 2/2 COMPLETE ✓ | 1 | SP3 | KVCALFPSP001 | 4536.00 | 4.536 | - | 1 | - | Order Total: 2 units
2025-11-29 | 2025-11-29 | Saturday | W2 | ARM-007 | 2526100564 | Unknown | W1 | 2 | 1 | 1 | 1/2 (50%) | 1 | Casting | CS1ARM-007 | 4536.00 | 4.536 | 24 min | 1 | 24 min | Order Total: 2 units
2025-11-30 | 2025-11-29 | Sunday | W2 | ARM-007 | 2526100564 | Unknown | W1 | 2 | 1 | 1 | 1/2 (50%) | 1 | Cooling/Shakeout | N/A | 4536.00 | 4.536 | - | 1 | - | Order Total: 2 units
2025-12-01 | 2025-12-01 | Monday | W2 | ARM-007 | 2526100564 | Unknown | W1 | 2 | 2 | 2 | 2/2 COMPLETE ✓ | 1 | Casting | CS1ARM-007 | 4536.00 | 4.536 | 24 min | 1 | 24 min | Order Total: 2 units
2025-12-02 | 2025-12-01 | Tuesday | W2 | ARM-007 | 2526100564 | Unknown | W1 | 2 | 2 | 2 | 2/2 COMPLETE ✓ | 1 | Cooling/Shakeout | N/A | 4536.00 | 4.536 | - | 1 | - | Order Total: 2 units
2025-11-22 | 2025-11-29 | Saturday | W1 | ARM-007 | 2526100565 | Unknown | W1 | 4 | 1 | 2 | 2/4 (50%) | 2 | Grinding | GR1ARM-007 | 4536.00 | 9.072 | 240 min | 1 | 480 min | Order Total: 4 units
2025-11-22 | 2025-11-29 | Saturday | W1 | ARM-007 | 2526100565 | Unknown | W1 | 4 | 1 | 2 | 2/4 (50%) | 2 | MC1 | MC1ARM-007 | 4536.00 | 9.072 | 240 min | 1 | 480 min | Order Total: 4 units
2025-11-22 | 2025-11-29 | Saturday | W1 | ARM-007 | 2526100565 | Unknown | W1 | 4 | 1 | 2 | 2/4 (50%) | 2 | SP1 | SP1ARM-007 | 4536.00 | 9.072 | - | 1 | - | Order Total: 4 units
2025-11-22 | 2025-11-29 | Saturday | W1 | ARM-007 | 2526100565 | Unknown | W1 | 4 | 1 | 2 | 2/4 (50%) | 2 | SP2 | KVCALPPSP002 | 4536.00 | 9.072 | - | 1 | - | Order Total: 4 units
2025-11-22 | 2025-11-29 | Saturday | W1 | ARM-007 | 2526100565 | Unknown | W1 | 4 | 1 | 2 | 2/4 (50%) | 2 | SP3 | KVCALFPSP001 | 4536.00 | 9.072 | - | 1 | - | Order Total: 4 units
2025-11-24 | 2025-12-01 | Monday | W1 | ARM-007 | 2526100565 | Unknown | W1 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | Grinding | GR1ARM-007 | 4536.00 | 9.072 | 240 min | 1 | 480 min | Order Total: 4 units
2025-11-24 | 2025-12-01 | Monday | W1 | ARM-007 | 2526100565 | Unknown | W1 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | MC1 | MC1ARM-007 | 4536.00 | 9.072 | 240 min | 1 | 480 min | Order Total: 4 units
2025-11-24 | 2025-12-01 | Monday | W1 | ARM-007 | 2526100565 | Unknown | W1 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | SP1 | SP1ARM-007 | 4536.00 | 9.072 | - | 1 | - | Order Total: 4 units
2025-11-24 | 2025-12-01 | Monday | W1 | ARM-007 | 2526100565 | Unknown | W1 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | SP2 | KVCALPPSP002 | 4536.00 | 9.072 | - | 1 | - | Order Total: 4 units
2025-11-24 | 2025-12-01 | Monday | W1 | ARM-007 | 2526100565 | Unknown | W1 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | SP3 | KVCALFPSP001 | 4536.00 | 9.072 | - | 1 | - | Order Total: 4 units
2025-11-29 | 2025-11-29 | Saturday | W2 | ARM-007 | 2526100565 | Unknown | W1 | 4 | 1 | 2 | 2/4 (50%) | 2 | Casting | CS1ARM-007 | 4536.00 | 9.072 | 24 min | 1 | 48 min | Order Total: 4 units
2025-11-30 | 2025-11-29 | Sunday | W2 | ARM-007 | 2526100565 | Unknown | W1 | 4 | 1 | 2 | 2/4 (50%) | 2 | Cooling/Shakeout | N/A | 4536.00 | 9.072 | - | 1 | - | Order Total: 4 units
2025-12-01 | 2025-12-01 | Monday | W2 | ARM-007 | 2526100565 | Unknown | W1 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | Casting | CS1ARM-007 | 4536.00 | 9.072 | 24 min | 1 | 48 min | Order Total: 4 units
2025-12-02 | 2025-12-01 | Tuesday | W2 | ARM-007 | 2526100565 | Unknown | W1 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | Cooling/Shakeout | N/A | 4536.00 | 9.072 | - | 1 | - | Order Total: 4 units
2025-11-22 | 2025-11-29 | Saturday | W1 | ARM-007 | 2526100566 | Unknown | W1 | 4 | 1 | 2 | 2/4 (50%) | 2 | Grinding | GR1ARM-007 | 4536.00 | 9.072 | 240 min | 1 | 480 min | Order Total: 4 units
2025-11-22 | 2025-11-29 | Saturday | W1 | ARM-007 | 2526100566 | Unknown | W1 | 4 | 1 | 2 | 2/4 (50%) | 2 | MC1 | MC1ARM-007 | 4536.00 | 9.072 | 240 min | 1 | 480 min | Order Total: 4 units
2025-11-22 | 2025-11-29 | Saturday | W1 | ARM-007 | 2526100566 | Unknown | W1 | 4 | 1 | 2 | 2/4 (50%) | 2 | SP1 | SP1ARM-007 | 4536.00 | 9.072 | - | 1 | - | Order Total: 4 units
2025-11-22 | 2025-11-29 | Saturday | W1 | ARM-007 | 2526100566 | Unknown | W1 | 4 | 1 | 2 | 2/4 (50%) | 2 | SP2 | KVCALPPSP002 | 4536.00 | 9.072 | - | 1 | - | Order Total: 4 units
2025-11-22 | 2025-11-29 | Saturday | W1 | ARM-007 | 2526100566 | Unknown | W1 | 4 | 1 | 2 | 2/4 (50%) | 2 | SP3 | KVCALFPSP001 | 4536.00 | 9.072 | - | 1 | - | Order Total: 4 units
2025-11-24 | 2025-12-01 | Monday | W1 | ARM-007 | 2526100566 | Unknown | W1 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | Grinding | GR1ARM-007 | 4536.00 | 9.072 | 240 min | 1 | 480 min | Order Total: 4 units
2025-11-24 | 2025-12-01 | Monday | W1 | ARM-007 | 2526100566 | Unknown | W1 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | MC1 | MC1ARM-007 | 4536.00 | 9.072 | 240 min | 1 | 480 min | Order Total: 4 units
2025-11-24 | 2025-12-01 | Monday | W1 | ARM-007 | 2526100566 | Unknown | W1 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | SP1 | SP1ARM-007 | 4536.00 | 9.072 | - | 1 | - | Order Total: 4 units
2025-11-24 | 2025-12-01 | Monday | W1 | ARM-007 | 2526100566 | Unknown | W1 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | SP2 | KVCALPPSP002 | 4536.00 | 9.072 | - | 1 | - | Order Total: 4 units
2025-11-24 | 2025-12-01 | Monday | W1 | ARM-007 | 2526100566 | Unknown | W1 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | SP3 | KVCALFPSP001 | 4536.00 | 9.072 | - | 1 | - | Order Total: 4 units
2025-11-29 | 2025-11-29 | Saturday | W2 | ARM-007 | 2526100566 | Unknown | W1 | 4 | 1 | 2 | 2/4 (50%) | 2 | Casting | CS1ARM-007 | 4536.00 | 9.072 | 24 min | 1 | 48 min | Order Total: 4 units
2025-11-30 | 2025-11-29 | Sunday | W2 | ARM-007 | 2526100566 | Unknown | W1 | 4 | 1 | 2 | 2/4 (50%) | 2 | Cooling/Shakeout | N/A | 4536.00 | 9.072 | - | 1 | - | Order Total: 4 units
2025-12-01 | 2025-12-01 | Monday | W2 | ARM-007 | 2526100566 | Unknown | W1 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | Casting | CS1ARM-007 | 4536.00 | 9.072 | 24 min | 1 | 48 min | Order Total: 4 units
2025-12-02 | 2025-12-01 | Tuesday | W2 | ARM-007 | 2526100566 | Unknown | W1 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | Cooling/Shakeout | N/A | 4536.00 | 9.072 | - | 1 | - | Order Total: 4 units
2025-11-22 | 2025-11-29 | Saturday | W1 | ARM-007 | 2526100567 | Unknown | W2 | 4 | 1 | 2 | 2/4 (50%) | 2 | SP1 | SP1ARM-007 | 4536.00 | 9.072 | - | 1 | - | Order Total: 4 units
2025-11-22 | 2025-11-29 | Saturday | W1 | ARM-007 | 2526100567 | Unknown | W2 | 4 | 1 | 2 | 2/4 (50%) | 2 | SP2 | KVCALPPSP002 | 4536.00 | 9.072 | - | 1 | - | Order Total: 4 units
2025-11-22 | 2025-11-29 | Saturday | W1 | ARM-007 | 2526100567 | Unknown | W2 | 4 | 1 | 2 | 2/4 (50%) | 2 | SP3 | KVCALFPSP001 | 4536.00 | 9.072 | - | 1 | - | Order Total: 4 units
2025-11-24 | 2025-12-01 | Monday | W1 | ARM-007 | 2526100567 | Unknown | W2 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | SP1 | SP1ARM-007 | 4536.00 | 9.072 | - | 1 | - | Order Total: 4 units
2025-11-24 | 2025-12-01 | Monday | W1 | ARM-007 | 2526100567 | Unknown | W2 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | SP2 | KVCALPPSP002 | 4536.00 | 9.072 | - | 1 | - | Order Total: 4 units
2025-11-24 | 2025-12-01 | Monday | W1 | ARM-007 | 2526100567 | Unknown | W2 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | SP3 | KVCALFPSP001 | 4536.00 | 9.072 | - | 1 | - | Order Total: 4 units
2025-11-29 | 2025-11-29 | Saturday | W2 | ARM-007 | 2526100567 | Unknown | W2 | 4 | 1 | 2 | 2/4 (50%) | 2 | Casting | CS1ARM-007 | 4536.00 | 9.072 | 24 min | 1 | 48 min | Order Total: 4 units
2025-11-30 | 2025-11-29 | Sunday | W2 | ARM-007 | 2526100567 | Unknown | W2 | 4 | 1 | 2 | 2/4 (50%) | 2 | Cooling/Shakeout | N/A | 4536.00 | 9.072 | - | 1 | - | Order Total: 4 units
2025-12-01 | 2025-12-01 | Monday | W2 | ARM-007 | 2526100567 | Unknown | W2 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | Casting | CS1ARM-007 | 4536.00 | 9.072 | 24 min | 1 | 48 min | Order Total: 4 units
2025-12-02 | 2025-12-01 | Tuesday | W2 | ARM-007 | 2526100567 | Unknown | W2 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | Cooling/Shakeout | N/A | 4536.00 | 9.072 | - | 1 | - | Order Total: 4 units
2025-12-06 | 2025-11-29 | Saturday | W3 | ARM-007 | 2526100567 | Unknown | W2 | 4 | 1 | 2 | 2/4 (50%) | 2 | MC1 | MC1ARM-007 | 4536.00 | 9.072 | 240 min | 1 | 480 min | Order Total: 4 units
2025-12-08 | 2025-12-01 | Monday | W3 | ARM-007 | 2526100567 | Unknown | W2 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | MC1 | MC1ARM-007 | 4536.00 | 9.072 | 240 min | 1 | 480 min | Order Total: 4 units
2025-12-06 | 2025-12-06 | Saturday | W3 | ARM-007 | 2526100568 | Unknown | W3 | 4 | 1 | 2 | 2/4 (50%) | 2 | MC1 | MC1ARM-007 | 4536.00 | 9.072 | 240 min | 1 | 480 min | Order Total: 4 units
2025-12-06 | 2025-12-06 | Saturday | W3 | ARM-007 | 2526100568 | Unknown | W3 | 4 | 1 | 2 | 2/4 (50%) | 2 | SP1 | SP1ARM-007 | 4536.00 | 9.072 | - | 1 | - | Order Total: 4 units
2025-12-06 | 2025-12-06 | Saturday | W3 | ARM-007 | 2526100568 | Unknown | W3 | 4 | 1 | 2 | 2/4 (50%) | 2 | SP2 | KVCALPPSP002 | 4536.00 | 9.072 | - | 1 | - | Order Total: 4 units
2025-12-06 | 2025-12-06 | Saturday | W3 | ARM-007 | 2526100568 | Unknown | W3 | 4 | 1 | 2 | 2/4 (50%) | 2 | SP3 | KVCALFPSP001 | 4536.00 | 9.072 | - | 1 | - | Order Total: 4 units
2025-12-08 | 2025-12-08 | Monday | W3 | ARM-007 | 2526100568 | Unknown | W3 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | MC1 | MC1ARM-007 | 4536.00 | 9.072 | 240 min | 1 | 480 min | Order Total: 4 units
2025-12-08 | 2025-12-08 | Monday | W3 | ARM-007 | 2526100568 | Unknown | W3 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | SP1 | SP1ARM-007 | 4536.00 | 9.072 | - | 1 | - | Order Total: 4 units
2025-12-08 | 2025-12-08 | Monday | W3 | ARM-007 | 2526100568 | Unknown | W3 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | SP2 | KVCALPPSP002 | 4536.00 | 9.072 | - | 1 | - | Order Total: 4 units
2025-12-08 | 2025-12-08 | Monday | W3 | ARM-007 | 2526100568 | Unknown | W3 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | SP3 | KVCALFPSP001 | 4536.00 | 9.072 | - | 1 | - | Order Total: 4 units
2025-11-22 | 2025-11-29 | Saturday | W1 | ARM-007 | 2526100569 | Unknown | W1 | 1 | 1 | 1 | 1/1 COMPLETE ✓ | 1 | Grinding | GR1ARM-007 | 4536.00 | 4.536 | 240 min | 1 | 240 min | Order Total: 1 units
2025-11-22 | 2025-11-29 | Saturday | W1 | ARM-007 | 2526100569 | Unknown | W1 | 1 | 1 | 1 | 1/1 COMPLETE ✓ | 1 | MC1 | MC1ARM-007 | 4536.00 | 4.536 | 240 min | 1 | 240 min | Order Total: 1 units
2025-11-22 | 2025-11-29 | Saturday | W1 | ARM-007 | 2526100569 | Unknown | W1 | 1 | 1 | 1 | 1/1 COMPLETE ✓ | 1 | SP1 | SP1ARM-007 | 4536.00 | 4.536 | - | 1 | - | Order Total: 1 units
2025-11-22 | 2025-11-29 | Saturday | W1 | ARM-007 | 2526100569 | Unknown | W1 | 1 | 1 | 1 | 1/1 COMPLETE ✓ | 1 | SP2 | KVCALPPSP002 | 4536.00 | 4.536 | - | 1 | - | Order Total: 1 units
2025-11-22 | 2025-11-29 | Saturday | W1 | ARM-007 | 2526100569 | Unknown | W1 | 1 | 1 | 1 | 1/1 COMPLETE ✓ | 1 | SP3 | KVCALFPSP001 | 4536.00 | 4.536 | - | 1 | - | Order Total: 1 units
2025-11-29 | 2025-11-29 | Saturday | W2 | ARM-007 | 2526100569 | Unknown | W1 | 1 | 1 | 1 | 1/1 COMPLETE ✓ | 1 | Casting | CS1ARM-007 | 4536.00 | 4.536 | 24 min | 1 | 24 min | Order Total: 1 units
2025-11-30 | 2025-11-29 | Sunday | W2 | ARM-007 | 2526100569 | Unknown | W1 | 1 | 1 | 1 | 1/1 COMPLETE ✓ | 1 | Cooling/Shakeout | N/A | 4536.00 | 4.536 | - | 1 | - | Order Total: 1 units
2025-11-22 | 2025-11-22 | Saturday | W1 | UBC-062 | 2526200576 | Unknown | W1 | 2 | 1 | 1 | 1/2 (50%) | 1 | MC1 | KVCAD50MC001 | 1375.00 | 1.375 | 90 min | 1 | 90 min | Order Total: 2 units
2025-11-22 | 2025-11-22 | Saturday | W1 | UBC-064 | 2526200576 | Unknown | W1 | 2 | 1 | 1 | 1/2 (50%) | 1 | MC1 | KVCAD50MC001 | 650.00 | 0.650 | 90 min | 1 | 90 min | Order Total: 2 units
2025-11-22 | 2025-11-22 | Saturday | W1 | UBC-062 | 2526200576 | Unknown | W1 | 2 | 1 | 1 | 1/2 (50%) | 1 | SP1 | KVCALPPSP001 | 1375.00 | 1.375 | 12 min | 1 | 12 min | Order Total: 2 units
2025-11-22 | 2025-11-22 | Saturday | W1 | UBC-063 | 2526200576 | Unknown | W1 | 2 | 1 | 1 | 1/2 (50%) | 1 | SP1 | KVCALPPSP001 | 1900.00 | 1.900 | 12 min | 1 | 12 min | Order Total: 2 units
2025-11-22 | 2025-11-22 | Saturday | W1 | UBC-064 | 2526200576 | Unknown | W1 | 2 | 1 | 1 | 1/2 (50%) | 1 | SP1 | KVCALPPSP001 | 650.00 | 0.650 | 12 min | 1 | 12 min | Order Total: 2 units
2025-11-22 | 2025-11-22 | Saturday | W1 | UBC-062 | 2526200576 | Unknown | W1 | 2 | 1 | 1 | 1/2 (50%) | 1 | SP2 | KVCALPPSP002 | 1375.00 | 1.375 | 12 min | 1 | 12 min | Order Total: 2 units
2025-11-22 | 2025-11-22 | Saturday | W1 | UBC-063 | 2526200576 | Unknown | W1 | 2 | 1 | 1 | 1/2 (50%) | 1 | SP2 | KVCALPPSP002 | 1900.00 | 1.900 | 12 min | 1 | 12 min | Order Total: 2 units
2025-11-22 | 2025-11-22 | Saturday | W1 | UBC-064 | 2526200576 | Unknown | W1 | 2 | 1 | 1 | 1/2 (50%) | 1 | SP2 | KVCALPPSP002 | 650.00 | 0.650 | 12 min | 1 | 12 min | Order Total: 2 units
2025-11-22 | 2025-11-22 | Saturday | W1 | UBC-062 | 2526200576 | Unknown | W1 | 2 | 1 | 1 | 1/2 (50%) | 1 | SP3 | KVCALFPSP001 | 1375.00 | 1.375 | 7 min | 1 | 7 min | Order Total: 2 units
2025-11-22 | 2025-11-22 | Saturday | W1 | UBC-063 | 2526200576 | Unknown | W1 | 2 | 1 | 1 | 1/2 (50%) | 1 | SP3 | KVCALFPSP001 | 1900.00 | 1.900 | 7 min | 1 | 7 min | Order Total: 2 units
2025-11-22 | 2025-11-22 | Saturday | W1 | UBC-064 | 2526200576 | Unknown | W1 | 2 | 1 | 1 | 1/2 (50%) | 1 | SP3 | KVCALFPSP001 | 650.00 | 0.650 | 7 min | 1 | 7 min | Order Total: 2 units
2025-11-24 | 2025-11-24 | Monday | W1 | UBC-062 | 2526200576 | Unknown | W1 | 2 | 2 | 2 | 2/2 COMPLETE ✓ | 1 | MC1 | KVCAD50MC001 | 1375.00 | 1.375 | 90 min | 1 | 90 min | Order Total: 2 units
2025-11-24 | 2025-11-24 | Monday | W1 | UBC-064 | 2526200576 | Unknown | W1 | 2 | 2 | 2 | 2/2 COMPLETE ✓ | 1 | MC1 | KVCAD50MC001 | 650.00 | 0.650 | 90 min | 1 | 90 min | Order Total: 2 units
2025-11-24 | 2025-11-24 | Monday | W1 | UBC-062 | 2526200576 | Unknown | W1 | 2 | 2 | 2 | 2/2 COMPLETE ✓ | 1 | SP1 | KVCALPPSP001 | 1375.00 | 1.375 | 12 min | 1 | 12 min | Order Total: 2 units
2025-11-24 | 2025-11-24 | Monday | W1 | UBC-063 | 2526200576 | Unknown | W1 | 2 | 2 | 2 | 2/2 COMPLETE ✓ | 1 | SP1 | KVCALPPSP001 | 1900.00 | 1.900 | 12 min | 1 | 12 min | Order Total: 2 units
2025-11-24 | 2025-11-24 | Monday | W1 | UBC-064 | 2526200576 | Unknown | W1 | 2 | 2 | 2 | 2/2 COMPLETE ✓ | 1 | SP1 | KVCALPPSP001 | 650.00 | 0.650 | 12 min | 1 | 12 min | Order Total: 2 units
2025-11-24 | 2025-11-24 | Monday | W1 | UBC-062 | 2526200576 | Unknown | W1 | 2 | 2 | 2 | 2/2 COMPLETE ✓ | 1 | SP2 | KVCALPPSP002 | 1375.00 | 1.375 | 12 min | 1 | 12 min | Order Total: 2 units
2025-11-24 | 2025-11-24 | Monday | W1 | UBC-063 | 2526200576 | Unknown | W1 | 2 | 2 | 2 | 2/2 COMPLETE ✓ | 1 | SP2 | KVCALPPSP002 | 1900.00 | 1.900 | 12 min | 1 | 12 min | Order Total: 2 units
2025-11-24 | 2025-11-24 | Monday | W1 | UBC-064 | 2526200576 | Unknown | W1 | 2 | 2 | 2 | 2/2 COMPLETE ✓ | 1 | SP2 | KVCALPPSP002 | 650.00 | 0.650 | 12 min | 1 | 12 min | Order Total: 2 units
2025-11-24 | 2025-11-24 | Monday | W1 | UBC-062 | 2526200576 | Unknown | W1 | 2 | 2 | 2 | 2/2 COMPLETE ✓ | 1 | SP3 | KVCALFPSP001 | 1375.00 | 1.375 | 7 min | 1 | 7 min | Order Total: 2 units
2025-11-24 | 2025-11-24 | Monday | W1 | UBC-063 | 2526200576 | Unknown | W1 | 2 | 2 | 2 | 2/2 COMPLETE ✓ | 1 | SP3 | KVCALFPSP001 | 1900.00 | 1.900 | 7 min | 1 | 7 min | Order Total: 2 units
2025-11-24 | 2025-11-24 | Monday | W1 | UBC-064 | 2526200576 | Unknown | W1 | 2 | 2 | 2 | 2/2 COMPLETE ✓ | 1 | SP3 | KVCALFPSP001 | 650.00 | 0.650 | 7 min | 1 | 7 min | Order Total: 2 units
2025-12-20 | 2025-12-20 | Saturday | W5 | ATT-002 | 2526201015 | Unknown | W1 | 5 | 1 | 2 | 2/5 (40%) | 2 | Grinding | KVCALHMGR001 | 640.00 | 1.280 | 330 min | 1 | 660 min | Order Total: 5 units
2025-12-22 | 2025-12-22 | Monday | W5 | ATT-002 | 2526201015 | Unknown | W1 | 5 | 2 | 5 | 5/5 COMPLETE ✓ | 3 | Grinding | KVCALHMGR001 | 640.00 | 1.920 | 330 min | 1 | 990 min | Order Total: 5 units
2025-11-29 | 2025-11-29 | Saturday | W2 | MCB-009 | 2526201341 | Unknown | W2 | 7 | 1 | 2 | 2/7 (28%) | 2 | SP1 | KVCALPPSP001 | 1500.00 | 3.000 | 7 min | 1 | 14 min | Order Total: 7 units
2025-12-01 | 2025-12-01 | Monday | W2 | MCB-009 | 2526201341 | Unknown | W2 | 7 | 2 | 4 | 4/7 (57%) | 2 | SP1 | KVCALPPSP001 | 1500.00 | 3.000 | 7 min | 1 | 14 min | Order Total: 7 units
2025-12-02 | 2025-12-02 | Tuesday | W2 | MCB-009 | 2526201341 | Unknown | W2 | 7 | 3 | 7 | 7/7 COMPLETE ✓ | 3 | SP1 | KVCALPPSP001 | 1500.00 | 4.500 | 7 min | 1 | 21 min | Order Total: 7 units
2025-12-20 | 2025-12-20 | Saturday | W5 | MCB-009 | 2526201341 | Unknown | W2 | 7 | 1 | 2 | 2/7 (28%) | 2 | MC1 | KVCAD50MC001 | 1500.00 | 3.000 | 100 min | 0 | - | Order Total: 7 units
2025-12-22 | 2025-12-22 | Monday | W5 | MCB-009 | 2526201341 | Unknown | W2 | 7 | 2 | 4 | 4/7 (57%) | 2 | MC1 | KVCAD50MC001 | 1500.00 | 3.000 | 100 min | 0 | - | Order Total: 7 units
2025-12-23 | 2025-12-23 | Tuesday | W5 | MCB-009 | 2526201341 | Unknown | W2 | 7 | 3 | 7 | 7/7 COMPLETE ✓ | 3 | MC1 | KVCAD50MC001 | 1500.00 | 4.500 | 100 min | 0 | - | Order Total: 7 units
2025-11-22 | 2025-11-22 | Saturday | W1 | TAS-GN-006 | 2526201561 | Unknown | W2 | 3 | 1 | 1 | 1/3 (33%) | 1 | Casting | CS1-TAS-GN-006 | 318.18 | 0.318 | 25 min | 1 | 25 min | Order Total: 3 units
2025-11-22 | 2025-11-22 | Saturday | W1 | TAS-GN-006 | 2526201561 | Unknown | W2 | 3 | 2 | 2 | 2/3 (66%) | 1 | Casting | CS1-TAS-GN-006 | 318.18 | 0.318 | 25 min | 1 | 25 min | Order Total: 3 units
2025-11-22 | 2025-11-22 | Saturday | W1 | TAS-GN-006 | 2526201561 | Unknown | W2 | 3 | 1 | 1 | 1/3 (33%) | 1 | SP1 | KVCALPPSP001 | 318.18 | 0.318 | 7 min | 1 | 7 min | Order Total: 3 units
2025-11-22 | 2025-12-13 | Saturday | W1 | LKK-01 | 2526201561 | Unknown | W2 | 2 | 1 | 1 | 1/2 (50%) | 1 | SP1 | KVCALPPSP001 | 199.66 | 0.200 | 7 min | 1 | 7 min | Order Total: 2 units
2025-11-22 | 2025-11-22 | Saturday | W1 | TAS-GN-006 | 2526201561 | Unknown | W2 | 3 | 2 | 2 | 2/3 (66%) | 1 | SP1 | KVCALPPSP001 | 318.18 | 0.318 | 7 min | 1 | 7 min | Order Total: 3 units
2025-11-22 | 2025-11-22 | Saturday | W1 | TAS-GN-006 | 2526201561 | Unknown | W2 | 3 | 1 | 1 | 1/3 (33%) | 1 | SP2 | KVCALPPSP002 | 318.18 | 0.318 | 7 min | 1 | 7 min | Order Total: 3 units
2025-11-22 | 2025-11-22 | Saturday | W1 | TAS-GN-006 | 2526201561 | Unknown | W2 | 3 | 2 | 2 | 2/3 (66%) | 1 | SP2 | KVCALPPSP002 | 318.18 | 0.318 | 7 min | 1 | 7 min | Order Total: 3 units
2025-11-22 | 2025-11-22 | Saturday | W1 | TAS-GN-006 | 2526201561 | Unknown | W2 | 3 | 1 | 1 | 1/3 (33%) | 1 | SP3 | KVCALFPSP001 | 318.18 | 0.318 | 7 min | 1 | 7 min | Order Total: 3 units
2025-11-22 | 2025-11-22 | Saturday | W1 | TAS-GN-006 | 2526201561 | Unknown | W2 | 3 | 2 | 2 | 2/3 (66%) | 1 | SP3 | KVCALFPSP001 | 318.18 | 0.318 | 7 min | 1 | 7 min | Order Total: 3 units
2025-11-23 | 2025-11-22 | Sunday | W1 | TAS-GN-006 | 2526201561 | Unknown | W2 | 3 | 1 | 1 | 1/3 (33%) | 1 | Cooling/Shakeout | N/A | 318.18 | 0.318 | - | 1 | - | Order Total: 3 units
2025-11-23 | 2025-11-22 | Sunday | W1 | TAS-GN-006 | 2526201561 | Unknown | W2 | 3 | 2 | 2 | 2/3 (66%) | 1 | Cooling/Shakeout | N/A | 318.18 | 0.318 | - | 1 | - | Order Total: 3 units
2025-11-24 | 2025-11-24 | Monday | W1 | TAS-GN-006 | 2526201561 | Unknown | W2 | 3 | 3 | 3 | 3/3 COMPLETE ✓ | 1 | Casting | CS1-TAS-GN-006 | 318.18 | 0.318 | 25 min | 1 | 25 min | Order Total: 3 units
2025-11-24 | 2025-11-24 | Monday | W1 | TAS-GN-006 | 2526201561 | Unknown | W2 | 3 | 4 | 4 | 4/3 COMPLETE ✓ | 1 | Casting | CS1-TAS-GN-006 | 318.18 | 0.318 | 25 min | 1 | 25 min | Order Total: 3 units
2025-11-24 | 2025-11-24 | Monday | W1 | TAS-GN-006 | 2526201561 | Unknown | W2 | 3 | 3 | 3 | 3/3 COMPLETE ✓ | 1 | SP1 | KVCALPPSP001 | 318.18 | 0.318 | 7 min | 1 | 7 min | Order Total: 3 units
2025-11-24 | 2025-12-15 | Monday | W1 | LKK-01 | 2526201561 | Unknown | W2 | 2 | 2 | 2 | 2/2 COMPLETE ✓ | 1 | SP1 | KVCALPPSP001 | 199.66 | 0.200 | 7 min | 1 | 7 min | Order Total: 2 units
2025-11-24 | 2025-11-24 | Monday | W1 | TAS-GN-006 | 2526201561 | Unknown | W2 | 3 | 4 | 4 | 4/3 COMPLETE ✓ | 1 | SP1 | KVCALPPSP001 | 318.18 | 0.318 | 7 min | 1 | 7 min | Order Total: 3 units
2025-11-24 | 2025-11-24 | Monday | W1 | TAS-GN-006 | 2526201561 | Unknown | W2 | 3 | 3 | 3 | 3/3 COMPLETE ✓ | 1 | SP2 | KVCALPPSP002 | 318.18 | 0.318 | 7 min | 1 | 7 min | Order Total: 3 units
2025-11-24 | 2025-11-24 | Monday | W1 | TAS-GN-006 | 2526201561 | Unknown | W2 | 3 | 4 | 4 | 4/3 COMPLETE ✓ | 1 | SP2 | KVCALPPSP002 | 318.18 | 0.318 | 7 min | 1 | 7 min | Order Total: 3 units
2025-11-24 | 2025-11-24 | Monday | W1 | TAS-GN-006 | 2526201561 | Unknown | W2 | 3 | 3 | 3 | 3/3 COMPLETE ✓ | 1 | SP3 | KVCALFPSP001 | 318.18 | 0.318 | 7 min | 1 | 7 min | Order Total: 3 units
2025-11-24 | 2025-11-24 | Monday | W1 | TAS-GN-006 | 2526201561 | Unknown | W2 | 3 | 4 | 4 | 4/3 COMPLETE ✓ | 1 | SP3 | KVCALFPSP001 | 318.18 | 0.318 | 7 min | 1 | 7 min | Order Total: 3 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | TAS-GN-006 | 2526201561 | Unknown | W2 | 3 | 5 | 5 | 5/3 COMPLETE ✓ | 1 | Casting | CS1-TAS-GN-006 | 318.18 | 0.318 | 25 min | 1 | 25 min | Order Total: 3 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | TAS-GN-006 | 2526201561 | Unknown | W2 | 3 | 6 | 6 | 6/3 COMPLETE ✓ | 1 | Casting | CS1-TAS-GN-006 | 318.18 | 0.318 | 25 min | 1 | 25 min | Order Total: 3 units
2025-11-25 | 2025-11-24 | Tuesday | W1 | TAS-GN-006 | 2526201561 | Unknown | W2 | 3 | 3 | 3 | 3/3 COMPLETE ✓ | 1 | Cooling/Shakeout | N/A | 318.18 | 0.318 | - | 1 | - | Order Total: 3 units
2025-11-25 | 2025-11-24 | Tuesday | W1 | TAS-GN-006 | 2526201561 | Unknown | W2 | 3 | 4 | 4 | 4/3 COMPLETE ✓ | 1 | Cooling/Shakeout | N/A | 318.18 | 0.318 | - | 1 | - | Order Total: 3 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | TAS-GN-006 | 2526201561 | Unknown | W2 | 3 | 5 | 5 | 5/3 COMPLETE ✓ | 1 | SP1 | KVCALPPSP001 | 318.18 | 0.318 | 7 min | 1 | 7 min | Order Total: 3 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | TAS-GN-006 | 2526201561 | Unknown | W2 | 3 | 6 | 6 | 6/3 COMPLETE ✓ | 1 | SP1 | KVCALPPSP001 | 318.18 | 0.318 | 7 min | 1 | 7 min | Order Total: 3 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | TAS-GN-006 | 2526201561 | Unknown | W2 | 3 | 5 | 5 | 5/3 COMPLETE ✓ | 1 | SP2 | KVCALPPSP002 | 318.18 | 0.318 | 7 min | 1 | 7 min | Order Total: 3 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | TAS-GN-006 | 2526201561 | Unknown | W2 | 3 | 6 | 6 | 6/3 COMPLETE ✓ | 1 | SP2 | KVCALPPSP002 | 318.18 | 0.318 | 7 min | 1 | 7 min | Order Total: 3 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | TAS-GN-006 | 2526201561 | Unknown | W2 | 3 | 5 | 5 | 5/3 COMPLETE ✓ | 1 | SP3 | KVCALFPSP001 | 318.18 | 0.318 | 7 min | 1 | 7 min | Order Total: 3 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | TAS-GN-006 | 2526201561 | Unknown | W2 | 3 | 6 | 6 | 6/3 COMPLETE ✓ | 1 | SP3 | KVCALFPSP001 | 318.18 | 0.318 | 7 min | 1 | 7 min | Order Total: 3 units
2025-11-26 | 2025-11-25 | Wednesday | W1 | TAS-GN-006 | 2526201561 | Unknown | W2 | 3 | 5 | 5 | 5/3 COMPLETE ✓ | 1 | Cooling/Shakeout | N/A | 318.18 | 0.318 | - | 1 | - | Order Total: 3 units
2025-11-26 | 2025-11-25 | Wednesday | W1 | TAS-GN-006 | 2526201561 | Unknown | W2 | 3 | 6 | 6 | 6/3 COMPLETE ✓ | 1 | Cooling/Shakeout | N/A | 318.18 | 0.318 | - | 1 | - | Order Total: 3 units
2025-12-06 | 2025-11-22 | Saturday | W3 | TAS-GN-006 | 2526201561 | Unknown | W2 | 3 | 1 | 1 | 1/3 (33%) | 1 | Grinding | KVCALHMGR001 | 318.18 | 0.318 | 120 min | 1 | 120 min | Order Total: 3 units
2025-12-06 | 2025-11-22 | Saturday | W3 | TAS-GN-006 | 2526201561 | Unknown | W2 | 3 | 2 | 2 | 2/3 (66%) | 1 | Grinding | KVCALHMGR001 | 318.18 | 0.318 | 120 min | 1 | 120 min | Order Total: 3 units
2025-12-08 | 2025-11-24 | Monday | W3 | TAS-GN-006 | 2526201561 | Unknown | W2 | 3 | 3 | 3 | 3/3 COMPLETE ✓ | 1 | Grinding | KVCALHMGR001 | 318.18 | 0.318 | 120 min | 1 | 120 min | Order Total: 3 units
2025-12-08 | 2025-11-24 | Monday | W3 | TAS-GN-006 | 2526201561 | Unknown | W2 | 3 | 4 | 4 | 4/3 COMPLETE ✓ | 1 | Grinding | KVCALHMGR001 | 318.18 | 0.318 | 120 min | 1 | 120 min | Order Total: 3 units
2025-12-09 | 2025-11-25 | Tuesday | W3 | TAS-GN-006 | 2526201561 | Unknown | W2 | 3 | 5 | 5 | 5/3 COMPLETE ✓ | 1 | Grinding | KVCALHMGR001 | 318.18 | 0.318 | 120 min | 1 | 120 min | Order Total: 3 units
2025-12-09 | 2025-11-25 | Tuesday | W3 | TAS-GN-006 | 2526201561 | Unknown | W2 | 3 | 6 | 6 | 6/3 COMPLETE ✓ | 1 | Grinding | KVCALHMGR001 | 318.18 | 0.318 | 120 min | 1 | 120 min | Order Total: 3 units
2025-12-13 | 2025-12-13 | Saturday | W4 | LKK-01 | 2526201561 | Unknown | W2 | 2 | 1 | 1 | 1/2 (50%) | 1 | Casting | CS1-LKK-001 | 199.66 | 0.200 | 22 min | 1 | 22 min | Order Total: 2 units
2025-12-14 | 2025-12-13 | Sunday | W4 | LKK-01 | 2526201561 | Unknown | W2 | 2 | 1 | 1 | 1/2 (50%) | 1 | Cooling/Shakeout | N/A | 199.66 | 0.200 | - | 1 | - | Order Total: 2 units
2025-12-15 | 2025-12-15 | Monday | W4 | LKK-01 | 2526201561 | Unknown | W2 | 2 | 2 | 2 | 2/2 COMPLETE ✓ | 1 | Casting | CS1-LKK-001 | 199.66 | 0.200 | 22 min | 1 | 22 min | Order Total: 2 units
2025-12-16 | 2025-12-15 | Tuesday | W4 | LKK-01 | 2526201561 | Unknown | W2 | 2 | 2 | 2 | 2/2 COMPLETE ✓ | 1 | Cooling/Shakeout | N/A | 199.66 | 0.200 | - | 1 | - | Order Total: 2 units
2025-12-20 | 2025-12-20 | Saturday | W5 | ATT-001 | 2526201561 | Unknown | W2 | 1 | 1 | 1 | 1/1 COMPLETE ✓ | 1 | MC1 | KVCAD50MC001 | 1590.00 | 1.590 | 40 min | 0 | - | Order Total: 1 units
2025-12-20 | 2025-12-13 | Saturday | W5 | LKK-01 | 2526201561 | Unknown | W2 | 2 | 1 | 1 | 1/2 (50%) | 1 | MC1 | KVCAD50MC001 | 199.66 | 0.200 | 30 min | 0 | - | Order Total: 2 units
2025-12-20 | 2025-12-20 | Saturday | W5 | ATT-001 | 2526201561 | Unknown | W2 | 1 | 1 | 1 | 1/1 COMPLETE ✓ | 1 | SP1 | KVCALPPSP001 | 1590.00 | 1.590 | 12 min | 1 | 12 min | Order Total: 1 units
2025-12-22 | 2025-12-15 | Monday | W5 | LKK-01 | 2526201561 | Unknown | W2 | 2 | 2 | 2 | 2/2 COMPLETE ✓ | 1 | MC1 | KVCAD50MC001 | 199.66 | 0.200 | 30 min | 0 | - | Order Total: 2 units
2025-11-22 | 2025-11-22 | Saturday | W1 | TAS-GN-008 | 2526201611 | Unknown | W1 | 3 | 1 | 1 | 1/3 (33%) | 1 | MC1 | KVCAD50MC001 | 2693.18 | 2.693 | 40 min | 0 | - | Order Total: 3 units
2025-11-24 | 2025-11-24 | Monday | W1 | TAS-GN-008 | 2526201611 | Unknown | W1 | 3 | 2 | 2 | 2/3 (66%) | 1 | MC1 | KVCAD50MC001 | 2693.18 | 2.693 | 40 min | 0 | - | Order Total: 3 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | TAS-GN-008 | 2526201611 | Unknown | W1 | 3 | 3 | 3 | 3/3 COMPLETE ✓ | 1 | MC1 | KVCAD50MC001 | 2693.18 | 2.693 | 40 min | 0 | - | Order Total: 3 units
2025-11-29 | 2025-11-29 | Saturday | W2 | TAS-GN-008 | 2526201611 | Unknown | W1 | 3 | 1 | 1 | 1/3 (33%) | 1 | Grinding | KVCALHMGR001 | 2693.18 | 2.693 | 360 min | 1 | 360 min | Order Total: 3 units
2025-12-01 | 2025-12-01 | Monday | W2 | TAS-GN-008 | 2526201611 | Unknown | W1 | 3 | 2 | 2 | 2/3 (66%) | 1 | Grinding | KVCALHMGR001 | 2693.18 | 2.693 | 360 min | 1 | 360 min | Order Total: 3 units
2025-12-02 | 2025-12-02 | Tuesday | W2 | TAS-GN-008 | 2526201611 | Unknown | W1 | 3 | 3 | 3 | 3/3 COMPLETE ✓ | 1 | Grinding | KVCALHMGR001 | 2693.18 | 2.693 | 360 min | 1 | 360 min | Order Total: 3 units
2025-11-22 | 2025-11-22 | Saturday | W1 | UBC-046 | 2526201681 | Unknown | W1 | 7 | 1 | 2 | 2/7 (28%) | 2 | SP1 | SP1-UBC-046 | 974.00 | 1.948 | - | 1 | - | Order Total: 7 units
2025-11-24 | 2025-11-24 | Monday | W1 | UBC-046 | 2526201681 | Unknown | W1 | 7 | 2 | 4 | 4/7 (57%) | 2 | SP1 | SP1-UBC-046 | 974.00 | 1.948 | - | 1 | - | Order Total: 7 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | UBC-046 | 2526201681 | Unknown | W1 | 7 | 3 | 7 | 7/7 COMPLETE ✓ | 3 | SP1 | SP1-UBC-046 | 974.00 | 2.922 | - | 1 | - | Order Total: 7 units
2025-11-22 | 2025-11-22 | Saturday | W1 | TAS-GN-008 | 2526201804 | Unknown | W1 | 2 | 1 | 1 | 1/2 (50%) | 1 | MC1 | KVCAD50MC001 | 2693.18 | 2.693 | 40 min | 0 | - | Order Total: 2 units
2025-11-24 | 2025-11-24 | Monday | W1 | TAS-GN-008 | 2526201804 | Unknown | W1 | 2 | 2 | 2 | 2/2 COMPLETE ✓ | 1 | MC1 | KVCAD50MC001 | 2693.18 | 2.693 | 40 min | 0 | - | Order Total: 2 units
2025-11-29 | 2025-11-29 | Saturday | W2 | TAS-GN-008 | 2526201804 | Unknown | W1 | 2 | 1 | 1 | 1/2 (50%) | 1 | Grinding | KVCALHMGR001 | 2693.18 | 2.693 | 360 min | 1 | 360 min | Order Total: 2 units
2025-12-01 | 2025-12-01 | Monday | W2 | TAS-GN-008 | 2526201804 | Unknown | W1 | 2 | 2 | 2 | 2/2 COMPLETE ✓ | 1 | Grinding | KVCALHMGR001 | 2693.18 | 2.693 | 360 min | 1 | 360 min | Order Total: 2 units
2025-11-22 | 2025-11-22 | Saturday | W1 | LKK-03 | 2526202458 | Unknown | W1 | 3 | 1 | 1 | 1/3 (33%) | 1 | Casting | CS1-LKK-003 | 1618.80 | 1.619 | 22 min | 1 | 22 min | Order Total: 3 units
2025-11-22 | 2025-11-22 | Saturday | W1 | LKK-04 | 2526202458 | Unknown | W1 | 3 | 1 | 1 | 1/3 (33%) | 1 | MC1 | KVCAD50MC001 | 1457.00 | 1.457 | 30 min | 0 | - | Order Total: 3 units
2025-11-23 | 2025-11-22 | Sunday | W1 | LKK-03 | 2526202458 | Unknown | W1 | 3 | 1 | 1 | 1/3 (33%) | 1 | Cooling/Shakeout | N/A | 1618.80 | 1.619 | - | 1 | - | Order Total: 3 units
2025-11-24 | 2025-11-24 | Monday | W1 | LKK-03 | 2526202458 | Unknown | W1 | 3 | 2 | 2 | 2/3 (66%) | 1 | Casting | CS1-LKK-003 | 1618.80 | 1.619 | 22 min | 1 | 22 min | Order Total: 3 units
2025-11-24 | 2025-11-24 | Monday | W1 | LKK-04 | 2526202458 | Unknown | W1 | 3 | 2 | 2 | 2/3 (66%) | 1 | MC1 | KVCAD50MC001 | 1457.00 | 1.457 | 30 min | 0 | - | Order Total: 3 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | LKK-03 | 2526202458 | Unknown | W1 | 3 | 3 | 3 | 3/3 COMPLETE ✓ | 1 | Casting | CS1-LKK-003 | 1618.80 | 1.619 | 22 min | 1 | 22 min | Order Total: 3 units
2025-11-25 | 2025-11-24 | Tuesday | W1 | LKK-03 | 2526202458 | Unknown | W1 | 3 | 2 | 2 | 2/3 (66%) | 1 | Cooling/Shakeout | N/A | 1618.80 | 1.619 | - | 1 | - | Order Total: 3 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | LKK-04 | 2526202458 | Unknown | W1 | 3 | 3 | 3 | 3/3 COMPLETE ✓ | 1 | MC1 | KVCAD50MC001 | 1457.00 | 1.457 | 30 min | 0 | - | Order Total: 3 units
2025-11-26 | 2025-11-25 | Wednesday | W1 | LKK-03 | 2526202458 | Unknown | W1 | 3 | 3 | 3 | 3/3 COMPLETE ✓ | 1 | Cooling/Shakeout | N/A | 1618.80 | 1.619 | - | 1 | - | Order Total: 3 units
2025-11-29 | 2025-11-29 | Saturday | W2 | LKK-05 | 2526202458 | Unknown | W1 | 4 | 1 | 4 | 4/4 COMPLETE ✓ | 4 | Casting | CS1-LKK-005 | 250.00 | 1.000 | 22 min | 1 | 88 min | Order Total: 4 units
2025-11-29 | 2025-12-13 | Saturday | W2 | LKK-02 | 2526202458 | Unknown | W1 | 4 | 1 | 2 | 2/4 (50%) | 2 | Grinding | KVCALHMGR001 | 193.60 | 0.387 | 70 min | 1 | 140 min | Order Total: 4 units
2025-11-29 | 2025-11-29 | Saturday | W2 | LKK-05 | 2526202458 | Unknown | W1 | 4 | 1 | 2 | 2/4 (50%) | 2 | Grinding | KVCALHMGR001 | 250.00 | 0.500 | 70 min | 1 | 140 min | Order Total: 4 units
2025-11-29 | 2025-11-29 | Saturday | W2 | LKK-06 | 2526202458 | Unknown | W1 | 4 | 1 | 2 | 2/4 (50%) | 2 | Grinding | KVCALHMGR001 | 250.00 | 0.500 | 70 min | 1 | 140 min | Order Total: 4 units
2025-11-29 | 2025-11-29 | Saturday | W2 | LKK-05 | 2526202458 | Unknown | W1 | 4 | 1 | 2 | 2/4 (50%) | 2 | MC1 | KVCAD50MC001 | 250.00 | 0.500 | 25 min | 0 | - | Order Total: 4 units
2025-11-29 | 2025-11-29 | Saturday | W2 | LKK-06 | 2526202458 | Unknown | W1 | 4 | 1 | 2 | 2/4 (50%) | 2 | MC1 | KVCAD50MC001 | 250.00 | 0.500 | 25 min | 0 | - | Order Total: 4 units
2025-11-29 | 2025-12-13 | Saturday | W2 | LKK-01 | 2526202458 | Unknown | W1 | 2 | 1 | 1 | 1/2 (50%) | 1 | SP1 | KVCALPPSP001 | 199.66 | 0.200 | 7 min | 1 | 7 min | Order Total: 2 units
2025-11-29 | 2025-12-13 | Saturday | W2 | LKK-02 | 2526202458 | Unknown | W1 | 4 | 1 | 2 | 2/4 (50%) | 2 | SP1 | KVCALPPSP001 | 193.60 | 0.387 | 7 min | 1 | 14 min | Order Total: 4 units
2025-11-30 | 2025-11-29 | Sunday | W2 | LKK-05 | 2526202458 | Unknown | W1 | 4 | 1 | 2 | 2/4 (50%) | 2 | Cooling/Shakeout | N/A | 250.00 | 0.500 | - | 1 | - | Order Total: 4 units
2025-12-01 | 2025-12-13 | Monday | W2 | LKK-02 | 2526202458 | Unknown | W1 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | Grinding | KVCALHMGR001 | 193.60 | 0.387 | 70 min | 1 | 140 min | Order Total: 4 units
2025-12-01 | 2025-11-29 | Monday | W2 | LKK-05 | 2526202458 | Unknown | W1 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | Grinding | KVCALHMGR001 | 250.00 | 0.500 | 70 min | 1 | 140 min | Order Total: 4 units
2025-12-01 | 2025-12-01 | Monday | W2 | LKK-06 | 2526202458 | Unknown | W1 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | Grinding | KVCALHMGR001 | 250.00 | 0.500 | 70 min | 1 | 140 min | Order Total: 4 units
2025-12-01 | 2025-11-29 | Monday | W2 | LKK-05 | 2526202458 | Unknown | W1 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | MC1 | KVCAD50MC001 | 250.00 | 0.500 | 25 min | 0 | - | Order Total: 4 units
2025-12-01 | 2025-12-01 | Monday | W2 | LKK-06 | 2526202458 | Unknown | W1 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | MC1 | KVCAD50MC001 | 250.00 | 0.500 | 25 min | 0 | - | Order Total: 4 units
2025-12-01 | 2025-12-15 | Monday | W2 | LKK-01 | 2526202458 | Unknown | W1 | 2 | 2 | 2 | 2/2 COMPLETE ✓ | 1 | SP1 | KVCALPPSP001 | 199.66 | 0.200 | 7 min | 1 | 7 min | Order Total: 2 units
2025-12-01 | 2025-12-13 | Monday | W2 | LKK-02 | 2526202458 | Unknown | W1 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | SP1 | KVCALPPSP001 | 193.60 | 0.387 | 7 min | 1 | 14 min | Order Total: 4 units
2025-12-02 | 2025-11-29 | Tuesday | W2 | LKK-05 | 2526202458 | Unknown | W1 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | Cooling/Shakeout | N/A | 250.00 | 0.500 | - | 1 | - | Order Total: 4 units
2025-12-13 | 2025-12-13 | Saturday | W4 | LKK-01 | 2526202458 | Unknown | W1 | 2 | 1 | 1 | 1/2 (50%) | 1 | Casting | CS1-LKK-001 | 199.66 | 0.200 | 22 min | 1 | 22 min | Order Total: 2 units
2025-12-13 | 2025-12-13 | Saturday | W4 | LKK-02 | 2526202458 | Unknown | W1 | 4 | 1 | 4 | 4/4 COMPLETE ✓ | 4 | Casting | CS1-LKK-002 | 193.60 | 0.774 | 22 min | 1 | 88 min | Order Total: 4 units
2025-12-13 | 2025-12-13 | Saturday | W4 | LKK-01 | 2526202458 | Unknown | W1 | 2 | 1 | 1 | 1/2 (50%) | 1 | Grinding | KVCALHMGR001 | 199.66 | 0.200 | 70 min | 1 | 70 min | Order Total: 2 units
2025-12-14 | 2025-12-13 | Sunday | W4 | LKK-01 | 2526202458 | Unknown | W1 | 2 | 1 | 1 | 1/2 (50%) | 1 | Cooling/Shakeout | N/A | 199.66 | 0.200 | - | 1 | - | Order Total: 2 units
2025-12-14 | 2025-12-13 | Sunday | W4 | LKK-02 | 2526202458 | Unknown | W1 | 4 | 1 | 2 | 2/4 (50%) | 2 | Cooling/Shakeout | N/A | 193.60 | 0.387 | - | 1 | - | Order Total: 4 units
2025-12-15 | 2025-12-15 | Monday | W4 | LKK-01 | 2526202458 | Unknown | W1 | 2 | 2 | 2 | 2/2 COMPLETE ✓ | 1 | Casting | CS1-LKK-001 | 199.66 | 0.200 | 22 min | 1 | 22 min | Order Total: 2 units
2025-12-15 | 2025-12-15 | Monday | W4 | LKK-01 | 2526202458 | Unknown | W1 | 2 | 2 | 2 | 2/2 COMPLETE ✓ | 1 | Grinding | KVCALHMGR001 | 199.66 | 0.200 | 70 min | 1 | 70 min | Order Total: 2 units
2025-12-16 | 2025-12-15 | Tuesday | W4 | LKK-01 | 2526202458 | Unknown | W1 | 2 | 2 | 2 | 2/2 COMPLETE ✓ | 1 | Cooling/Shakeout | N/A | 199.66 | 0.200 | - | 1 | - | Order Total: 2 units
2025-12-16 | 2025-12-13 | Tuesday | W4 | LKK-02 | 2526202458 | Unknown | W1 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | Cooling/Shakeout | N/A | 193.60 | 0.387 | - | 1 | - | Order Total: 4 units
2025-11-22 | 2025-11-22 | Saturday | W1 | LKK-11 | 2526202459 | Unknown | W1 | 1 | 1 | 1 | 1/1 COMPLETE ✓ | 1 | SP1 | KVCALPPSP001 | 215.73 | 0.216 | 7 min | 1 | 7 min | Order Total: 1 units
2025-11-29 | 2025-11-29 | Saturday | W2 | LKK-10 | 2526202459 | Unknown | W1 | 2 | 1 | 1 | 1/2 (50%) | 1 | Casting | CS1-LKK-010 | 1208.55 | 1.209 | 22 min | 1 | 22 min | Order Total: 2 units
2025-11-29 | 2025-11-29 | Saturday | W2 | LKK-11 | 2526202459 | Unknown | W1 | 1 | 1 | 1 | 1/1 COMPLETE ✓ | 1 | MC1 | KVCAD50MC001 | 215.73 | 0.216 | 35 min | 3 | 35 min | Order Total: 1 units
2025-11-30 | 2025-11-29 | Sunday | W2 | LKK-10 | 2526202459 | Unknown | W1 | 2 | 1 | 1 | 1/2 (50%) | 1 | Cooling/Shakeout | N/A | 1208.55 | 1.209 | - | 1 | - | Order Total: 2 units
2025-12-01 | 2025-12-01 | Monday | W2 | LKK-10 | 2526202459 | Unknown | W1 | 2 | 2 | 2 | 2/2 COMPLETE ✓ | 1 | Casting | CS1-LKK-010 | 1208.55 | 1.209 | 22 min | 1 | 22 min | Order Total: 2 units
2025-12-02 | 2025-12-01 | Tuesday | W2 | LKK-10 | 2526202459 | Unknown | W1 | 2 | 2 | 2 | 2/2 COMPLETE ✓ | 1 | Cooling/Shakeout | N/A | 1208.55 | 1.209 | - | 1 | - | Order Total: 2 units
2025-12-06 | 2025-12-06 | Saturday | W3 | LKK-12 | 2526202459 | Unknown | W1 | 10 | 1 | 2 | 2/10 (20%) | 2 | Grinding | KVCALHMGR001 | 208.39 | 0.417 | 70 min | 1 | 140 min | Order Total: 10 units
2025-12-08 | 2025-12-08 | Monday | W3 | LKK-12 | 2526202459 | Unknown | W1 | 10 | 2 | 4 | 4/10 (40%) | 2 | Grinding | KVCALHMGR001 | 208.39 | 0.417 | 70 min | 1 | 140 min | Order Total: 10 units
2025-12-09 | 2025-12-09 | Tuesday | W3 | LKK-12 | 2526202459 | Unknown | W1 | 10 | 3 | 7 | 7/10 (70%) | 3 | Grinding | KVCALHMGR001 | 208.39 | 0.625 | 70 min | 1 | 210 min | Order Total: 10 units
2025-12-10 | 2025-12-10 | Wednesday | W3 | LKK-12 | 2526202459 | Unknown | W1 | 10 | 4 | 10 | 10/10 COMPLETE ✓ | 3 | Grinding | KVCALHMGR001 | 208.39 | 0.625 | 70 min | 1 | 210 min | Order Total: 10 units
2025-12-13 | 2025-11-29 | Saturday | W4 | LKK-10 | 2526202459 | Unknown | W1 | 2 | 1 | 1 | 1/2 (50%) | 1 | MC1 | KVCAD50MC001 | 1208.55 | 1.209 | 20 min | 0 | - | Order Total: 2 units
2025-12-15 | 2025-12-01 | Monday | W4 | LKK-10 | 2526202459 | Unknown | W1 | 2 | 2 | 2 | 2/2 COMPLETE ✓ | 1 | MC1 | KVCAD50MC001 | 1208.55 | 1.209 | 20 min | 0 | - | Order Total: 2 units
2025-11-22 | 2025-11-22 | Saturday | W1 | MCB-HYG-026 | 2526202474 | Unknown | W1 | 5 | 1 | 2 | 2/5 (40%) | 2 | Grinding | KVCALHMGR001 | 3099.00 | 6.198 | 360 min | 1 | 720 min | Order Total: 5 units
2025-11-22 | 2025-11-22 | Saturday | W1 | MCB-HYG-026 | 2526202474 | Unknown | W1 | 5 | 1 | 2 | 2/5 (40%) | 2 | MC1 | KVCAD50MC001 | 3099.00 | 6.198 | 40 min | 1 | 80 min | Order Total: 5 units
2025-11-22 | 2025-11-22 | Saturday | W1 | MCB-HYG-026 | 2526202474 | Unknown | W1 | 5 | 1 | 2 | 2/5 (40%) | 2 | SP1 | KVCALPPSP001 | 3099.00 | 6.198 | 12 min | 1 | 24 min | Order Total: 5 units
2025-11-24 | 2025-11-24 | Monday | W1 | MCB-HYG-026 | 2526202474 | Unknown | W1 | 5 | 2 | 5 | 5/5 COMPLETE ✓ | 3 | Grinding | KVCALHMGR001 | 3099.00 | 9.297 | 360 min | 1 | 1080 min | Order Total: 5 units
2025-11-24 | 2025-11-24 | Monday | W1 | MCB-HYG-026 | 2526202474 | Unknown | W1 | 5 | 2 | 5 | 5/5 COMPLETE ✓ | 3 | MC1 | KVCAD50MC001 | 3099.00 | 9.297 | 40 min | 1 | 120 min | Order Total: 5 units
2025-11-24 | 2025-11-24 | Monday | W1 | MCB-HYG-026 | 2526202474 | Unknown | W1 | 5 | 2 | 5 | 5/5 COMPLETE ✓ | 3 | SP1 | KVCALPPSP001 | 3099.00 | 9.297 | 12 min | 1 | 36 min | Order Total: 5 units
2025-11-22 | 2025-11-22 | Saturday | W1 | MCB-HYG-016 | 2526202705 | Unknown | W1 | 4 | 1 | 2 | 2/4 (50%) | 2 | Grinding | KVCALHMGR001 | 3243.00 | 6.486 | 450 min | 1 | 900 min | Order Total: 4 units
2025-11-22 | 2025-11-22 | Saturday | W1 | MCB-HYG-016 | 2526202705 | Unknown | W1 | 4 | 1 | 2 | 2/4 (50%) | 2 | MC1 | KVCAD50MC001 | 3243.00 | 6.486 | 45 min | 1 | 90 min | Order Total: 4 units
2025-11-24 | 2025-11-24 | Monday | W1 | MCB-HYG-016 | 2526202705 | Unknown | W1 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | Grinding | KVCALHMGR001 | 3243.00 | 6.486 | 450 min | 1 | 900 min | Order Total: 4 units
2025-11-24 | 2025-11-24 | Monday | W1 | MCB-HYG-016 | 2526202705 | Unknown | W1 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | MC1 | KVCAD50MC001 | 3243.00 | 6.486 | 45 min | 1 | 90 min | Order Total: 4 units
2025-11-22 | 2025-11-22 | Saturday | W1 | MCB-HYG-016 | 2526202706 | Unknown | W1 | 4 | 1 | 2 | 2/4 (50%) | 2 | Grinding | KVCALHMGR001 | 3243.00 | 6.486 | 450 min | 1 | 900 min | Order Total: 4 units
2025-11-22 | 2025-11-22 | Saturday | W1 | MCB-HYG-016 | 2526202706 | Unknown | W1 | 4 | 1 | 2 | 2/4 (50%) | 2 | MC1 | KVCAD50MC001 | 3243.00 | 6.486 | 45 min | 1 | 90 min | Order Total: 4 units
2025-11-24 | 2025-11-24 | Monday | W1 | MCB-HYG-016 | 2526202706 | Unknown | W1 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | Grinding | KVCALHMGR001 | 3243.00 | 6.486 | 450 min | 1 | 900 min | Order Total: 4 units
2025-11-24 | 2025-11-24 | Monday | W1 | MCB-HYG-016 | 2526202706 | Unknown | W1 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | MC1 | KVCAD50MC001 | 3243.00 | 6.486 | 45 min | 1 | 90 min | Order Total: 4 units
2025-11-22 | 2025-11-22 | Saturday | W1 | MCB-HYG-016 | 2526202707 | Unknown | W1 | 4 | 1 | 2 | 2/4 (50%) | 2 | Grinding | KVCALHMGR001 | 3243.00 | 6.486 | 450 min | 1 | 900 min | Order Total: 4 units
2025-11-22 | 2025-11-22 | Saturday | W1 | MCB-HYG-016 | 2526202707 | Unknown | W1 | 4 | 1 | 2 | 2/4 (50%) | 2 | MC1 | KVCAD50MC001 | 3243.00 | 6.486 | 45 min | 1 | 90 min | Order Total: 4 units
2025-11-24 | 2025-11-24 | Monday | W1 | MCB-HYG-016 | 2526202707 | Unknown | W1 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | Grinding | KVCALHMGR001 | 3243.00 | 6.486 | 450 min | 1 | 900 min | Order Total: 4 units
2025-11-24 | 2025-11-24 | Monday | W1 | MCB-HYG-016 | 2526202707 | Unknown | W1 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | MC1 | KVCAD50MC001 | 3243.00 | 6.486 | 45 min | 1 | 90 min | Order Total: 4 units
2025-11-22 | 2025-11-22 | Saturday | W1 | MCB-HYG-016 | 2526202708 | Unknown | W1 | 4 | 1 | 2 | 2/4 (50%) | 2 | Grinding | KVCALHMGR001 | 3243.00 | 6.486 | 450 min | 1 | 900 min | Order Total: 4 units
2025-11-22 | 2025-11-22 | Saturday | W1 | MCB-HYG-016 | 2526202708 | Unknown | W1 | 4 | 1 | 2 | 2/4 (50%) | 2 | MC1 | KVCAD50MC001 | 3243.00 | 6.486 | 45 min | 1 | 90 min | Order Total: 4 units
2025-11-24 | 2025-11-24 | Monday | W1 | MCB-HYG-016 | 2526202708 | Unknown | W1 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | Grinding | KVCALHMGR001 | 3243.00 | 6.486 | 450 min | 1 | 900 min | Order Total: 4 units
2025-11-24 | 2025-11-24 | Monday | W1 | MCB-HYG-016 | 2526202708 | Unknown | W1 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | MC1 | KVCAD50MC001 | 3243.00 | 6.486 | 45 min | 1 | 90 min | Order Total: 4 units
2025-11-22 | 2025-11-22 | Saturday | W1 | MCB-HYG-026 | 2526202709 | Unknown | W1 | 4 | 1 | 2 | 2/4 (50%) | 2 | Grinding | KVCALHMGR001 | 3099.00 | 6.198 | 360 min | 1 | 720 min | Order Total: 4 units
2025-11-22 | 2025-11-22 | Saturday | W1 | MCB-HYG-026 | 2526202709 | Unknown | W1 | 4 | 1 | 2 | 2/4 (50%) | 2 | MC1 | KVCAD50MC001 | 3099.00 | 6.198 | 40 min | 1 | 80 min | Order Total: 4 units
2025-11-22 | 2025-11-22 | Saturday | W1 | MCB-HYG-026 | 2526202709 | Unknown | W1 | 4 | 1 | 2 | 2/4 (50%) | 2 | SP1 | KVCALPPSP001 | 3099.00 | 6.198 | 12 min | 1 | 24 min | Order Total: 4 units
2025-11-24 | 2025-11-24 | Monday | W1 | MCB-HYG-026 | 2526202709 | Unknown | W1 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | Grinding | KVCALHMGR001 | 3099.00 | 6.198 | 360 min | 1 | 720 min | Order Total: 4 units
2025-11-24 | 2025-11-24 | Monday | W1 | MCB-HYG-026 | 2526202709 | Unknown | W1 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | MC1 | KVCAD50MC001 | 3099.00 | 6.198 | 40 min | 1 | 80 min | Order Total: 4 units
2025-11-24 | 2025-11-24 | Monday | W1 | MCB-HYG-026 | 2526202709 | Unknown | W1 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | SP1 | KVCALPPSP001 | 3099.00 | 6.198 | 12 min | 1 | 24 min | Order Total: 4 units
2025-11-22 | 2025-11-22 | Saturday | W1 | TAS-GN-004 | 2526202713 | Unknown | W1 | 2 | 1 | 1 | 1/2 (50%) | 1 | Casting | CS1-TAS-GN-004 | 2571.00 | 2.571 | 25 min | 1 | 25 min | Order Total: 2 units
2025-11-23 | 2025-11-22 | Sunday | W1 | TAS-GN-004 | 2526202713 | Unknown | W1 | 2 | 1 | 1 | 1/2 (50%) | 1 | Cooling/Shakeout | N/A | 2571.00 | 2.571 | - | 1 | - | Order Total: 2 units
2025-11-24 | 2025-11-24 | Monday | W1 | TAS-GN-004 | 2526202713 | Unknown | W1 | 2 | 2 | 2 | 2/2 COMPLETE ✓ | 1 | Casting | CS1-TAS-GN-004 | 2571.00 | 2.571 | 25 min | 1 | 25 min | Order Total: 2 units
2025-11-25 | 2025-11-24 | Tuesday | W1 | TAS-GN-004 | 2526202713 | Unknown | W1 | 2 | 2 | 2 | 2/2 COMPLETE ✓ | 1 | Cooling/Shakeout | N/A | 2571.00 | 2.571 | - | 1 | - | Order Total: 2 units
2025-12-20 | 2025-11-22 | Saturday | W5 | TAS-GN-004 | 2526202713 | Unknown | W1 | 2 | 1 | 1 | 1/2 (50%) | 1 | SP1 | KVCALPPSP001 | 2571.00 | 2.571 | 7 min | 1 | 7 min | Order Total: 2 units
2025-12-20 | 2025-11-22 | Saturday | W5 | TAS-GN-004 | 2526202713 | Unknown | W1 | 2 | 1 | 1 | 1/2 (50%) | 1 | SP2 | KVCALPPSP002 | 2571.00 | 2.571 | 7 min | 1 | 7 min | Order Total: 2 units
2025-12-20 | 2025-11-22 | Saturday | W5 | TAS-GN-004 | 2526202713 | Unknown | W1 | 2 | 1 | 1 | 1/2 (50%) | 1 | SP3 | KVCALFPSP001 | 2571.00 | 2.571 | 7 min | 1 | 7 min | Order Total: 2 units
2025-12-22 | 2025-11-24 | Monday | W5 | TAS-GN-004 | 2526202713 | Unknown | W1 | 2 | 2 | 2 | 2/2 COMPLETE ✓ | 1 | SP1 | KVCALPPSP001 | 2571.00 | 2.571 | 7 min | 1 | 7 min | Order Total: 2 units
2025-12-22 | 2025-11-24 | Monday | W5 | TAS-GN-004 | 2526202713 | Unknown | W1 | 2 | 2 | 2 | 2/2 COMPLETE ✓ | 1 | SP2 | KVCALPPSP002 | 2571.00 | 2.571 | 7 min | 1 | 7 min | Order Total: 2 units
2025-12-22 | 2025-11-24 | Monday | W5 | TAS-GN-004 | 2526202713 | Unknown | W1 | 2 | 2 | 2 | 2/2 COMPLETE ✓ | 1 | SP3 | KVCALFPSP001 | 2571.00 | 2.571 | 7 min | 1 | 7 min | Order Total: 2 units
2025-11-29 | 2025-11-29 | Saturday | W2 | MCB-HYG-023 | 2526202788 | Unknown | W1 | 6 | 1 | 2 | 2/6 (33%) | 2 | SP1 | KVCALPPSP001 | 2942.00 | 5.884 | 12 min | 1 | 24 min | Order Total: 6 units
2025-12-01 | 2025-12-01 | Monday | W2 | MCB-HYG-023 | 2526202788 | Unknown | W1 | 6 | 2 | 4 | 4/6 (66%) | 2 | SP1 | KVCALPPSP001 | 2942.00 | 5.884 | 12 min | 1 | 24 min | Order Total: 6 units
2025-12-02 | 2025-12-02 | Tuesday | W2 | MCB-HYG-023 | 2526202788 | Unknown | W1 | 6 | 3 | 6 | 6/6 COMPLETE ✓ | 2 | SP1 | KVCALPPSP001 | 2942.00 | 5.884 | 12 min | 1 | 24 min | Order Total: 6 units
2025-11-22 | 2025-11-22 | Saturday | W1 | MCB-JLG-046 | 2526202810 | Unknown | W1 | 3 | 1 | 1 | 1/4 (25%) | 1 | Grinding | KVCALHMGR001 | 1277.78 | 1.278 | 390 min | 1 | 390 min | Order Total: 3 units
2025-11-22 | 2025-11-22 | Saturday | W1 | MCB-JLG-046 | 2526202810 | Unknown | W1 | 1 | 2 | 2 | 2/4 (50%) | 1 | Grinding | KVCALHMGR001 | 1277.78 | 1.278 | 390 min | 1 | 390 min | Order Total: 1 units
2025-11-22 | 2025-11-22 | Saturday | W1 | MCB-JLG-046 | 2526202810 | Unknown | W1 | 3 | 1 | 1 | 1/4 (25%) | 1 | MC1 | KVCAD50MC001 | 1277.78 | 1.278 | 40 min | 1 | 40 min | Order Total: 3 units
2025-11-22 | 2025-11-22 | Saturday | W1 | MCB-JLG-046 | 2526202810 | Unknown | W1 | 1 | 2 | 2 | 2/4 (50%) | 1 | MC1 | KVCAD50MC001 | 1277.78 | 1.278 | 40 min | 1 | 40 min | Order Total: 1 units
2025-11-22 | 2025-11-22 | Saturday | W1 | MCB-JLG-046 | 2526202810 | Unknown | W1 | 3 | 1 | 1 | 1/4 (25%) | 1 | SP1 | KVCALPPSP001 | 1277.78 | 1.278 | 12 min | 1 | 12 min | Order Total: 3 units
2025-11-22 | 2025-11-22 | Saturday | W1 | MCB-JLG-046 | 2526202810 | Unknown | W1 | 1 | 2 | 2 | 2/4 (50%) | 1 | SP1 | KVCALPPSP001 | 1277.78 | 1.278 | 12 min | 1 | 12 min | Order Total: 1 units
2025-11-24 | 2025-11-24 | Monday | W1 | MCB-JLG-046 | 2526202810 | Unknown | W1 | 3 | 3 | 3 | 3/4 (75%) | 1 | Grinding | KVCALHMGR001 | 1277.78 | 1.278 | 390 min | 1 | 390 min | Order Total: 3 units
2025-11-24 | 2025-11-24 | Monday | W1 | MCB-JLG-046 | 2526202810 | Unknown | W1 | 3 | 3 | 3 | 3/4 (75%) | 1 | MC1 | KVCAD50MC001 | 1277.78 | 1.278 | 40 min | 1 | 40 min | Order Total: 3 units
2025-11-24 | 2025-11-24 | Monday | W1 | MCB-JLG-046 | 2526202810 | Unknown | W1 | 3 | 3 | 3 | 3/4 (75%) | 1 | SP1 | KVCALPPSP001 | 1277.78 | 1.278 | 12 min | 1 | 12 min | Order Total: 3 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | MCB-JLG-046 | 2526202810 | Unknown | W1 | 3 | 4 | 4 | 4/4 COMPLETE ✓ | 1 | Grinding | KVCALHMGR001 | 1277.78 | 1.278 | 390 min | 1 | 390 min | Order Total: 3 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | MCB-JLG-046 | 2526202810 | Unknown | W1 | 3 | 4 | 4 | 4/4 COMPLETE ✓ | 1 | MC1 | KVCAD50MC001 | 1277.78 | 1.278 | 40 min | 1 | 40 min | Order Total: 3 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | MCB-JLG-046 | 2526202810 | Unknown | W1 | 3 | 4 | 4 | 4/4 COMPLETE ✓ | 1 | SP1 | KVCALPPSP001 | 1277.78 | 1.278 | 12 min | 1 | 12 min | Order Total: 3 units
2025-11-29 | 2025-11-29 | Saturday | W2 | MCB-HYG-023 | 2526202818 | Unknown | W1 | 5 | 1 | 2 | 2/5 (40%) | 2 | SP1 | KVCALPPSP001 | 2942.00 | 5.884 | 12 min | 1 | 24 min | Order Total: 5 units
2025-12-01 | 2025-12-01 | Monday | W2 | MCB-HYG-023 | 2526202818 | Unknown | W1 | 5 | 2 | 5 | 5/5 COMPLETE ✓ | 3 | SP1 | KVCALPPSP001 | 2942.00 | 8.826 | 12 min | 1 | 36 min | Order Total: 5 units
2025-11-22 | 2025-11-29 | Saturday | W1 | MCB-HYG-016 | 2526202819 | Unknown | W2 | 5 | 1 | 2 | 2/5 (40%) | 2 | SP1 | KVCALPPSP001 | 3243.00 | 6.486 | 12 min | 1 | 24 min | Order Total: 5 units
2025-11-24 | 2025-12-01 | Monday | W1 | MCB-HYG-016 | 2526202819 | Unknown | W2 | 5 | 2 | 5 | 5/5 COMPLETE ✓ | 3 | SP1 | KVCALPPSP001 | 3243.00 | 9.729 | 12 min | 1 | 36 min | Order Total: 5 units
2025-11-29 | 2025-11-29 | Saturday | W2 | MCB-HYG-016 | 2526202819 | Unknown | W2 | 5 | 1 | 2 | 2/5 (40%) | 2 | Casting | CS2MCB-HYG-016 | 3243.00 | 6.486 | 30 min | 1 | 60 min | Order Total: 5 units
2025-11-29 | 2025-11-29 | Saturday | W2 | MCB-HYG-016 | 2526202819 | Unknown | W2 | 5 | 1 | 2 | 2/5 (40%) | 2 | Grinding | KVCALHMGR001 | 3243.00 | 6.486 | 450 min | 1 | 900 min | Order Total: 5 units
2025-11-29 | 2025-11-29 | Saturday | W2 | MCB-HYG-016 | 2526202819 | Unknown | W2 | 5 | 1 | 2 | 2/5 (40%) | 2 | MC1 | KVCAD50MC001 | 3243.00 | 6.486 | 45 min | 1 | 90 min | Order Total: 5 units
2025-11-30 | 2025-11-29 | Sunday | W2 | MCB-HYG-016 | 2526202819 | Unknown | W2 | 5 | 1 | 2 | 2/5 (40%) | 2 | Cooling/Shakeout | N/A | 3243.00 | 6.486 | - | 1 | - | Order Total: 5 units
2025-12-01 | 2025-12-01 | Monday | W2 | MCB-HYG-016 | 2526202819 | Unknown | W2 | 5 | 2 | 5 | 5/5 COMPLETE ✓ | 3 | Casting | CS2MCB-HYG-016 | 3243.00 | 9.729 | 30 min | 1 | 90 min | Order Total: 5 units
2025-12-01 | 2025-12-01 | Monday | W2 | MCB-HYG-016 | 2526202819 | Unknown | W2 | 5 | 2 | 5 | 5/5 COMPLETE ✓ | 3 | Grinding | KVCALHMGR001 | 3243.00 | 9.729 | 450 min | 1 | 1350 min | Order Total: 5 units
2025-12-01 | 2025-12-01 | Monday | W2 | MCB-HYG-016 | 2526202819 | Unknown | W2 | 5 | 2 | 5 | 5/5 COMPLETE ✓ | 3 | MC1 | KVCAD50MC001 | 3243.00 | 9.729 | 45 min | 1 | 135 min | Order Total: 5 units
2025-12-02 | 2025-12-01 | Tuesday | W2 | MCB-HYG-016 | 2526202819 | Unknown | W2 | 5 | 2 | 5 | 5/5 COMPLETE ✓ | 3 | Cooling/Shakeout | N/A | 3243.00 | 9.729 | - | 1 | - | Order Total: 5 units
2025-11-22 | 2025-11-29 | Saturday | W1 | MCB-HYG-016 | 2526202820 | Unknown | W2 | 5 | 1 | 2 | 2/5 (40%) | 2 | SP1 | KVCALPPSP001 | 3243.00 | 6.486 | 12 min | 1 | 24 min | Order Total: 5 units
2025-11-24 | 2025-12-01 | Monday | W1 | MCB-HYG-016 | 2526202820 | Unknown | W2 | 5 | 2 | 5 | 5/5 COMPLETE ✓ | 3 | SP1 | KVCALPPSP001 | 3243.00 | 9.729 | 12 min | 1 | 36 min | Order Total: 5 units
2025-11-29 | 2025-11-29 | Saturday | W2 | MCB-HYG-016 | 2526202820 | Unknown | W2 | 5 | 1 | 2 | 2/5 (40%) | 2 | Casting | CS2MCB-HYG-016 | 3243.00 | 6.486 | 30 min | 1 | 60 min | Order Total: 5 units
2025-11-29 | 2025-11-29 | Saturday | W2 | MCB-HYG-016 | 2526202820 | Unknown | W2 | 5 | 1 | 2 | 2/5 (40%) | 2 | Grinding | KVCALHMGR001 | 3243.00 | 6.486 | 450 min | 1 | 900 min | Order Total: 5 units
2025-11-29 | 2025-11-29 | Saturday | W2 | MCB-HYG-016 | 2526202820 | Unknown | W2 | 5 | 1 | 2 | 2/5 (40%) | 2 | MC1 | KVCAD50MC001 | 3243.00 | 6.486 | 45 min | 1 | 90 min | Order Total: 5 units
2025-11-30 | 2025-11-29 | Sunday | W2 | MCB-HYG-016 | 2526202820 | Unknown | W2 | 5 | 1 | 2 | 2/5 (40%) | 2 | Cooling/Shakeout | N/A | 3243.00 | 6.486 | - | 1 | - | Order Total: 5 units
2025-12-01 | 2025-12-01 | Monday | W2 | MCB-HYG-016 | 2526202820 | Unknown | W2 | 5 | 2 | 5 | 5/5 COMPLETE ✓ | 3 | Casting | CS2MCB-HYG-016 | 3243.00 | 9.729 | 30 min | 1 | 90 min | Order Total: 5 units
2025-12-01 | 2025-12-01 | Monday | W2 | MCB-HYG-016 | 2526202820 | Unknown | W2 | 5 | 2 | 5 | 5/5 COMPLETE ✓ | 3 | Grinding | KVCALHMGR001 | 3243.00 | 9.729 | 450 min | 1 | 1350 min | Order Total: 5 units
2025-12-01 | 2025-12-01 | Monday | W2 | MCB-HYG-016 | 2526202820 | Unknown | W2 | 5 | 2 | 5 | 5/5 COMPLETE ✓ | 3 | MC1 | KVCAD50MC001 | 3243.00 | 9.729 | 45 min | 1 | 135 min | Order Total: 5 units
2025-12-02 | 2025-12-01 | Tuesday | W2 | MCB-HYG-016 | 2526202820 | Unknown | W2 | 5 | 2 | 5 | 5/5 COMPLETE ✓ | 3 | Cooling/Shakeout | N/A | 3243.00 | 9.729 | - | 1 | - | Order Total: 5 units
2025-11-22 | 2025-11-22 | Saturday | W1 | TAS-GN-008 | 2526202929 | Unknown | W1 | 1 | 1 | 1 | 1/1 COMPLETE ✓ | 1 | MC1 | KVCAD50MC001 | 2693.18 | 2.693 | 40 min | 0 | - | Order Total: 1 units
2025-11-29 | 2025-11-29 | Saturday | W2 | TAS-GN-008 | 2526202929 | Unknown | W1 | 1 | 1 | 1 | 1/1 COMPLETE ✓ | 1 | Grinding | KVCALHMGR001 | 2693.18 | 2.693 | 360 min | 1 | 360 min | Order Total: 1 units
2025-11-22 | 2025-12-06 | Saturday | W1 | NMS-V-004 | 2526202939 | Unknown | W1 | 5 | 1 | 2 | 2/5 (40%) | 2 | Grinding | KVCALHMGR001 | 0.00 | 0.000 | 120 min | 1 | 240 min | Order Total: 5 units
2025-11-24 | 2025-12-08 | Monday | W1 | NMS-V-004 | 2526202939 | Unknown | W1 | 5 | 2 | 5 | 5/5 COMPLETE ✓ | 3 | Grinding | KVCALHMGR001 | 0.00 | 0.000 | 120 min | 1 | 360 min | Order Total: 5 units
2025-12-06 | 2025-12-06 | Saturday | W3 | NMS-V-004 | 2526202939 | Unknown | W1 | 5 | 1 | 2 | 2/5 (40%) | 2 | Casting | CS3CFC-NMS-H-004 | 0.00 | 0.000 | 20 min | 1 | 40 min | Order Total: 5 units
2025-12-07 | 2025-12-06 | Sunday | W3 | NMS-V-004 | 2526202939 | Unknown | W1 | 5 | 1 | 2 | 2/5 (40%) | 2 | Cooling/Shakeout | N/A | 0.00 | 0.000 | - | 1 | - | Order Total: 5 units
2025-12-08 | 2025-12-08 | Monday | W3 | NMS-V-004 | 2526202939 | Unknown | W1 | 5 | 2 | 5 | 5/5 COMPLETE ✓ | 3 | Casting | CS3CFC-NMS-H-004 | 0.00 | 0.000 | 20 min | 1 | 60 min | Order Total: 5 units
2025-12-09 | 2025-12-08 | Tuesday | W3 | NMS-V-004 | 2526202939 | Unknown | W1 | 5 | 2 | 5 | 5/5 COMPLETE ✓ | 3 | Cooling/Shakeout | N/A | 0.00 | 0.000 | - | 1 | - | Order Total: 5 units
2025-12-20 | 2025-12-06 | Saturday | W5 | NMS-V-004 | 2526202939 | Unknown | W1 | 5 | 1 | 2 | 2/5 (40%) | 2 | SP1 | KVCALPPSP001 | 0.00 | 0.000 | 12 min | 1 | 24 min | Order Total: 5 units
2025-12-20 | 2025-12-06 | Saturday | W5 | NMS-V-004 | 2526202939 | Unknown | W1 | 5 | 1 | 2 | 2/5 (40%) | 2 | SP2 | KVCALPPSP002 | 0.00 | 0.000 | 12 min | 1 | 24 min | Order Total: 5 units
2025-12-20 | 2025-12-06 | Saturday | W5 | NMS-V-004 | 2526202939 | Unknown | W1 | 5 | 1 | 2 | 2/5 (40%) | 2 | SP3 | SP3CFC-NMS-H-004 | 0.00 | 0.000 | - | 0 | - | Order Total: 5 units
2025-12-22 | 2025-12-08 | Monday | W5 | NMS-V-004 | 2526202939 | Unknown | W1 | 5 | 2 | 5 | 5/5 COMPLETE ✓ | 3 | SP1 | KVCALPPSP001 | 0.00 | 0.000 | 12 min | 1 | 36 min | Order Total: 5 units
2025-12-22 | 2025-12-08 | Monday | W5 | NMS-V-004 | 2526202939 | Unknown | W1 | 5 | 2 | 5 | 5/5 COMPLETE ✓ | 3 | SP2 | KVCALPPSP002 | 0.00 | 0.000 | 12 min | 1 | 36 min | Order Total: 5 units
2025-12-22 | 2025-12-08 | Monday | W5 | NMS-V-004 | 2526202939 | Unknown | W1 | 5 | 2 | 5 | 5/5 COMPLETE ✓ | 3 | SP3 | SP3CFC-NMS-H-004 | 0.00 | 0.000 | - | 0 | - | Order Total: 5 units
2025-11-22 | 2025-11-22 | Saturday | W1 | UBC-050 | 2526202947 | Unknown | W1 | 5 | 1 | 2 | 2/5 (40%) | 2 | Grinding | KVCALHMGR001 | 369.00 | 0.738 | 680 min | 1 | 1360 min | Order Total: 5 units
2025-11-24 | 2025-11-24 | Monday | W1 | UBC-050 | 2526202947 | Unknown | W1 | 5 | 2 | 5 | 5/5 COMPLETE ✓ | 3 | Grinding | KVCALHMGR001 | 369.00 | 1.107 | 680 min | 1 | 2040 min | Order Total: 5 units
2025-12-20 | 2025-12-20 | Saturday | W5 | ATT-002 | 2526202952 | Unknown | W1 | 4 | 1 | 2 | 2/4 (50%) | 2 | Grinding | KVCALHMGR001 | 640.00 | 1.280 | 330 min | 1 | 660 min | Order Total: 4 units
2025-12-22 | 2025-12-22 | Monday | W5 | ATT-002 | 2526202952 | Unknown | W1 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | Grinding | KVCALHMGR001 | 640.00 | 1.280 | 330 min | 1 | 660 min | Order Total: 4 units
2025-12-20 | 2025-12-20 | Saturday | W5 | ATT-002 | 2526202953 | Unknown | W1 | 4 | 1 | 2 | 2/4 (50%) | 2 | Grinding | KVCALHMGR001 | 640.00 | 1.280 | 330 min | 1 | 660 min | Order Total: 4 units
2025-12-22 | 2025-12-22 | Monday | W5 | ATT-002 | 2526202953 | Unknown | W1 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | Grinding | KVCALHMGR001 | 640.00 | 1.280 | 330 min | 1 | 660 min | Order Total: 4 units
2025-12-06 | 2025-12-06 | Saturday | W3 | ATT-001 | 2526202954 | Unknown | W4 | 3 | 1 | 1 | 1/9 (11%) | 1 | Grinding | KVCALHMGR001 | 1590.00 | 1.590 | 330 min | 1 | 330 min | Order Total: 3 units
2025-12-06 | 2025-12-06 | Saturday | W3 | ATT-001 | 2526202954 | Unknown | W4 | 6 | 2 | 3 | 3/9 (33%) | 2 | Grinding | KVCALHMGR001 | 1590.00 | 3.180 | 330 min | 1 | 660 min | Order Total: 6 units
2025-12-08 | 2025-12-08 | Monday | W3 | ATT-001 | 2526202954 | Unknown | W4 | 3 | 3 | 4 | 4/9 (44%) | 1 | Grinding | KVCALHMGR001 | 1590.00 | 1.590 | 330 min | 1 | 330 min | Order Total: 3 units
2025-12-08 | 2025-12-08 | Monday | W3 | ATT-001 | 2526202954 | Unknown | W4 | 6 | 4 | 6 | 6/9 (66%) | 2 | Grinding | KVCALHMGR001 | 1590.00 | 3.180 | 330 min | 1 | 660 min | Order Total: 6 units
2025-12-09 | 2025-12-09 | Tuesday | W3 | ATT-001 | 2526202954 | Unknown | W4 | 3 | 5 | 7 | 7/9 (77%) | 1 | Grinding | KVCALHMGR001 | 1590.00 | 1.590 | 330 min | 1 | 330 min | Order Total: 3 units
2025-12-09 | 2025-12-09 | Tuesday | W3 | ATT-001 | 2526202954 | Unknown | W4 | 6 | 6 | 9 | 9/9 COMPLETE ✓ | 2 | Grinding | KVCALHMGR001 | 1590.00 | 3.180 | 330 min | 1 | 660 min | Order Total: 6 units
2025-12-13 | 2025-12-13 | Saturday | W4 | ATT-002 | 2526202954 | Unknown | W4 | 2 | 1 | 1 | 1/8 (12%) | 1 | MC1 | KVCAD50MC001 | 640.00 | 0.640 | 40 min | 0 | - | Order Total: 2 units
2025-12-13 | 2025-12-13 | Saturday | W4 | ATT-002 | 2526202954 | Unknown | W4 | 6 | 2 | 3 | 3/8 (37%) | 2 | MC1 | KVCAD50MC001 | 640.00 | 1.280 | 40 min | 0 | - | Order Total: 6 units
2025-12-15 | 2025-12-15 | Monday | W4 | ATT-002 | 2526202954 | Unknown | W4 | 2 | 3 | 4 | 4/8 (50%) | 1 | MC1 | KVCAD50MC001 | 640.00 | 0.640 | 40 min | 0 | - | Order Total: 2 units
2025-12-15 | 2025-12-15 | Monday | W4 | ATT-002 | 2526202954 | Unknown | W4 | 6 | 4 | 6 | 6/8 (75%) | 2 | MC1 | KVCAD50MC001 | 640.00 | 1.280 | 40 min | 0 | - | Order Total: 6 units
2025-12-16 | 2025-12-16 | Tuesday | W4 | ATT-002 | 2526202954 | Unknown | W4 | 6 | 5 | 8 | 8/8 COMPLETE ✓ | 2 | MC1 | KVCAD50MC001 | 640.00 | 1.280 | 40 min | 0 | - | Order Total: 6 units
2025-12-06 | 2025-12-06 | Saturday | W3 | ATT-001 | 2526202955 | Unknown | W4 | 2 | 1 | 1 | 1/7 (14%) | 1 | Grinding | KVCALHMGR001 | 1590.00 | 1.590 | 330 min | 1 | 330 min | Order Total: 2 units
2025-12-06 | 2025-12-06 | Saturday | W3 | ATT-001 | 2526202955 | Unknown | W4 | 5 | 2 | 3 | 3/7 (42%) | 2 | Grinding | KVCALHMGR001 | 1590.00 | 3.180 | 330 min | 1 | 660 min | Order Total: 5 units
2025-12-08 | 2025-12-08 | Monday | W3 | ATT-001 | 2526202955 | Unknown | W4 | 2 | 3 | 4 | 4/7 (57%) | 1 | Grinding | KVCALHMGR001 | 1590.00 | 1.590 | 330 min | 1 | 330 min | Order Total: 2 units
2025-12-08 | 2025-12-08 | Monday | W3 | ATT-001 | 2526202955 | Unknown | W4 | 5 | 4 | 7 | 7/7 COMPLETE ✓ | 3 | Grinding | KVCALHMGR001 | 1590.00 | 4.770 | 330 min | 1 | 990 min | Order Total: 5 units
2025-12-13 | 2025-12-13 | Saturday | W4 | ATT-002 | 2526202955 | Unknown | W4 | 2 | 1 | 1 | 1/8 (12%) | 1 | MC1 | KVCAD50MC001 | 640.00 | 0.640 | 40 min | 0 | - | Order Total: 2 units
2025-12-13 | 2025-12-13 | Saturday | W4 | ATT-002 | 2526202955 | Unknown | W4 | 6 | 2 | 3 | 3/8 (37%) | 2 | MC1 | KVCAD50MC001 | 640.00 | 1.280 | 40 min | 0 | - | Order Total: 6 units
2025-12-15 | 2025-12-15 | Monday | W4 | ATT-002 | 2526202955 | Unknown | W4 | 2 | 3 | 4 | 4/8 (50%) | 1 | MC1 | KVCAD50MC001 | 640.00 | 0.640 | 40 min | 0 | - | Order Total: 2 units
2025-12-15 | 2025-12-15 | Monday | W4 | ATT-002 | 2526202955 | Unknown | W4 | 6 | 4 | 6 | 6/8 (75%) | 2 | MC1 | KVCAD50MC001 | 640.00 | 1.280 | 40 min | 0 | - | Order Total: 6 units
2025-12-16 | 2025-12-16 | Tuesday | W4 | ATT-002 | 2526202955 | Unknown | W4 | 6 | 5 | 8 | 8/8 COMPLETE ✓ | 2 | MC1 | KVCAD50MC001 | 640.00 | 1.280 | 40 min | 0 | - | Order Total: 6 units
2025-11-22 | 2025-11-22 | Saturday | W1 | ATT-002 | 2526202956 | Unknown | W8 | 8 | 1 | 2 | 2/8 (25%) | 2 | MC1 | KVCAD50MC001 | 640.00 | 1.280 | 40 min | 0 | - | Order Total: 8 units
2025-11-24 | 2025-11-24 | Monday | W1 | ATT-002 | 2526202956 | Unknown | W8 | 8 | 2 | 4 | 4/8 (50%) | 2 | MC1 | KVCAD50MC001 | 640.00 | 1.280 | 40 min | 0 | - | Order Total: 8 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | ATT-002 | 2526202956 | Unknown | W8 | 8 | 3 | 6 | 6/8 (75%) | 2 | MC1 | KVCAD50MC001 | 640.00 | 1.280 | 40 min | 0 | - | Order Total: 8 units
2025-11-26 | 2025-11-26 | Wednesday | W1 | ATT-002 | 2526202956 | Unknown | W8 | 8 | 4 | 8 | 8/8 COMPLETE ✓ | 2 | MC1 | KVCAD50MC001 | 640.00 | 1.280 | 40 min | 0 | - | Order Total: 8 units
2025-12-13 | 2025-12-20 | Saturday | W4 | ATT-001 | 2526202956 | Unknown | W8 | 8 | 1 | 2 | 2/8 (25%) | 2 | MC1 | KVCAD50MC001 | 1590.00 | 3.180 | 40 min | 0 | - | Order Total: 8 units
2025-12-13 | 2025-12-20 | Saturday | W4 | ATT-001 | 2526202956 | Unknown | W8 | 8 | 1 | 2 | 2/8 (25%) | 2 | SP1 | KVCALPPSP001 | 1590.00 | 3.180 | 12 min | 1 | 24 min | Order Total: 8 units
2025-12-13 | 2025-12-13 | Saturday | W4 | ATT-002 | 2526202956 | Unknown | W8 | 8 | 1 | 2 | 2/8 (25%) | 2 | SP1 | KVCALPPSP001 | 640.00 | 1.280 | 12 min | 1 | 24 min | Order Total: 8 units
2025-12-15 | 2025-12-22 | Monday | W4 | ATT-001 | 2526202956 | Unknown | W8 | 8 | 2 | 4 | 4/8 (50%) | 2 | MC1 | KVCAD50MC001 | 1590.00 | 3.180 | 40 min | 0 | - | Order Total: 8 units
2025-12-15 | 2025-12-22 | Monday | W4 | ATT-001 | 2526202956 | Unknown | W8 | 8 | 2 | 4 | 4/8 (50%) | 2 | SP1 | KVCALPPSP001 | 1590.00 | 3.180 | 12 min | 1 | 24 min | Order Total: 8 units
2025-12-15 | 2025-12-15 | Monday | W4 | ATT-002 | 2526202956 | Unknown | W8 | 8 | 2 | 4 | 4/8 (50%) | 2 | SP1 | KVCALPPSP001 | 640.00 | 1.280 | 12 min | 1 | 24 min | Order Total: 8 units
2025-12-16 | 2025-12-20 | Tuesday | W4 | ATT-001 | 2526202956 | Unknown | W8 | 8 | 3 | 6 | 6/8 (75%) | 2 | MC1 | KVCAD50MC001 | 1590.00 | 3.180 | 40 min | 0 | - | Order Total: 8 units
2025-12-16 | 2025-12-20 | Tuesday | W4 | ATT-001 | 2526202956 | Unknown | W8 | 8 | 3 | 6 | 6/8 (75%) | 2 | SP1 | KVCALPPSP001 | 1590.00 | 3.180 | 12 min | 1 | 24 min | Order Total: 8 units
2025-12-16 | 2025-12-16 | Tuesday | W4 | ATT-002 | 2526202956 | Unknown | W8 | 8 | 3 | 6 | 6/8 (75%) | 2 | SP1 | KVCALPPSP001 | 640.00 | 1.280 | 12 min | 1 | 24 min | Order Total: 8 units
2025-12-17 | 2025-12-20 | Wednesday | W4 | ATT-001 | 2526202956 | Unknown | W8 | 8 | 4 | 8 | 8/8 COMPLETE ✓ | 2 | MC1 | KVCAD50MC001 | 1590.00 | 3.180 | 40 min | 0 | - | Order Total: 8 units
2025-12-17 | 2025-12-20 | Wednesday | W4 | ATT-001 | 2526202956 | Unknown | W8 | 8 | 4 | 8 | 8/8 COMPLETE ✓ | 2 | SP1 | KVCALPPSP001 | 1590.00 | 3.180 | 12 min | 1 | 24 min | Order Total: 8 units
2025-12-17 | 2025-12-17 | Wednesday | W4 | ATT-002 | 2526202956 | Unknown | W8 | 8 | 4 | 8 | 8/8 COMPLETE ✓ | 2 | SP1 | KVCALPPSP001 | 640.00 | 1.280 | 12 min | 1 | 24 min | Order Total: 8 units
2025-12-20 | 2025-12-20 | Saturday | W5 | ATT-001 | 2526202956 | Unknown | W8 | 8 | 1 | 4 | 4/8 (50%) | 4 | Casting | CS-ATT-001 | 1590.00 | 6.360 | 20 min | 1 | 80 min | Order Total: 8 units
2025-12-21 | 2025-12-20 | Sunday | W5 | ATT-001 | 2526202956 | Unknown | W8 | 8 | 1 | 2 | 2/8 (25%) | 2 | Cooling/Shakeout | N/A | 1590.00 | 3.180 | - | 1 | - | Order Total: 8 units
2025-12-22 | 2025-12-22 | Monday | W5 | ATT-001 | 2526202956 | Unknown | W8 | 8 | 2 | 8 | 8/8 COMPLETE ✓ | 4 | Casting | CS-ATT-001 | 1590.00 | 6.360 | 20 min | 1 | 80 min | Order Total: 8 units
2025-12-23 | 2025-12-22 | Tuesday | W5 | ATT-001 | 2526202956 | Unknown | W8 | 8 | 2 | 4 | 4/8 (50%) | 2 | Cooling/Shakeout | N/A | 1590.00 | 3.180 | - | 1 | - | Order Total: 8 units
2025-12-24 | 2025-12-20 | Wednesday | W5 | ATT-001 | 2526202956 | Unknown | W8 | 8 | 3 | 6 | 6/8 (75%) | 2 | Cooling/Shakeout | N/A | 1590.00 | 3.180 | - | 1 | - | Order Total: 8 units
2025-12-25 | 2025-12-20 | Thursday | W5 | ATT-001 | 2526202956 | Unknown | W8 | 8 | 4 | 8 | 8/8 COMPLETE ✓ | 2 | Cooling/Shakeout | N/A | 1590.00 | 3.180 | - | 1 | - | Order Total: 8 units
2025-11-22 | 2025-11-22 | Saturday | W1 | ATT-002 | 2526202957 | Unknown | W8 | 8 | 1 | 2 | 2/8 (25%) | 2 | MC1 | KVCAD50MC001 | 640.00 | 1.280 | 40 min | 0 | - | Order Total: 8 units
2025-11-24 | 2025-11-24 | Monday | W1 | ATT-002 | 2526202957 | Unknown | W8 | 8 | 2 | 4 | 4/8 (50%) | 2 | MC1 | KVCAD50MC001 | 640.00 | 1.280 | 40 min | 0 | - | Order Total: 8 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | ATT-002 | 2526202957 | Unknown | W8 | 8 | 3 | 6 | 6/8 (75%) | 2 | MC1 | KVCAD50MC001 | 640.00 | 1.280 | 40 min | 0 | - | Order Total: 8 units
2025-11-26 | 2025-11-26 | Wednesday | W1 | ATT-002 | 2526202957 | Unknown | W8 | 8 | 4 | 8 | 8/8 COMPLETE ✓ | 2 | MC1 | KVCAD50MC001 | 640.00 | 1.280 | 40 min | 0 | - | Order Total: 8 units
2025-12-13 | 2025-12-20 | Saturday | W4 | ATT-001 | 2526202957 | Unknown | W8 | 8 | 1 | 2 | 2/8 (25%) | 2 | MC1 | KVCAD50MC001 | 1590.00 | 3.180 | 40 min | 0 | - | Order Total: 8 units
2025-12-13 | 2025-12-20 | Saturday | W4 | ATT-001 | 2526202957 | Unknown | W8 | 8 | 1 | 2 | 2/8 (25%) | 2 | SP1 | KVCALPPSP001 | 1590.00 | 3.180 | 12 min | 1 | 24 min | Order Total: 8 units
2025-12-13 | 2025-12-13 | Saturday | W4 | ATT-002 | 2526202957 | Unknown | W8 | 8 | 1 | 2 | 2/8 (25%) | 2 | SP1 | KVCALPPSP001 | 640.00 | 1.280 | 12 min | 1 | 24 min | Order Total: 8 units
2025-12-15 | 2025-12-22 | Monday | W4 | ATT-001 | 2526202957 | Unknown | W8 | 8 | 2 | 4 | 4/8 (50%) | 2 | MC1 | KVCAD50MC001 | 1590.00 | 3.180 | 40 min | 0 | - | Order Total: 8 units
2025-12-15 | 2025-12-22 | Monday | W4 | ATT-001 | 2526202957 | Unknown | W8 | 8 | 2 | 4 | 4/8 (50%) | 2 | SP1 | KVCALPPSP001 | 1590.00 | 3.180 | 12 min | 1 | 24 min | Order Total: 8 units
2025-12-15 | 2025-12-15 | Monday | W4 | ATT-002 | 2526202957 | Unknown | W8 | 8 | 2 | 4 | 4/8 (50%) | 2 | SP1 | KVCALPPSP001 | 640.00 | 1.280 | 12 min | 1 | 24 min | Order Total: 8 units
2025-12-16 | 2025-12-20 | Tuesday | W4 | ATT-001 | 2526202957 | Unknown | W8 | 8 | 3 | 6 | 6/8 (75%) | 2 | MC1 | KVCAD50MC001 | 1590.00 | 3.180 | 40 min | 0 | - | Order Total: 8 units
2025-12-16 | 2025-12-20 | Tuesday | W4 | ATT-001 | 2526202957 | Unknown | W8 | 8 | 3 | 6 | 6/8 (75%) | 2 | SP1 | KVCALPPSP001 | 1590.00 | 3.180 | 12 min | 1 | 24 min | Order Total: 8 units
2025-12-16 | 2025-12-16 | Tuesday | W4 | ATT-002 | 2526202957 | Unknown | W8 | 8 | 3 | 6 | 6/8 (75%) | 2 | SP1 | KVCALPPSP001 | 640.00 | 1.280 | 12 min | 1 | 24 min | Order Total: 8 units
2025-12-17 | 2025-12-20 | Wednesday | W4 | ATT-001 | 2526202957 | Unknown | W8 | 8 | 4 | 8 | 8/8 COMPLETE ✓ | 2 | MC1 | KVCAD50MC001 | 1590.00 | 3.180 | 40 min | 0 | - | Order Total: 8 units
2025-12-17 | 2025-12-20 | Wednesday | W4 | ATT-001 | 2526202957 | Unknown | W8 | 8 | 4 | 8 | 8/8 COMPLETE ✓ | 2 | SP1 | KVCALPPSP001 | 1590.00 | 3.180 | 12 min | 1 | 24 min | Order Total: 8 units
2025-12-17 | 2025-12-17 | Wednesday | W4 | ATT-002 | 2526202957 | Unknown | W8 | 8 | 4 | 8 | 8/8 COMPLETE ✓ | 2 | SP1 | KVCALPPSP001 | 640.00 | 1.280 | 12 min | 1 | 24 min | Order Total: 8 units
2025-12-20 | 2025-12-20 | Saturday | W5 | ATT-001 | 2526202957 | Unknown | W8 | 8 | 1 | 4 | 4/8 (50%) | 4 | Casting | CS-ATT-001 | 1590.00 | 6.360 | 20 min | 1 | 80 min | Order Total: 8 units
2025-12-21 | 2025-12-20 | Sunday | W5 | ATT-001 | 2526202957 | Unknown | W8 | 8 | 1 | 2 | 2/8 (25%) | 2 | Cooling/Shakeout | N/A | 1590.00 | 3.180 | - | 1 | - | Order Total: 8 units
2025-12-22 | 2025-12-22 | Monday | W5 | ATT-001 | 2526202957 | Unknown | W8 | 8 | 2 | 8 | 8/8 COMPLETE ✓ | 4 | Casting | CS-ATT-001 | 1590.00 | 6.360 | 20 min | 1 | 80 min | Order Total: 8 units
2025-12-23 | 2025-12-22 | Tuesday | W5 | ATT-001 | 2526202957 | Unknown | W8 | 8 | 2 | 4 | 4/8 (50%) | 2 | Cooling/Shakeout | N/A | 1590.00 | 3.180 | - | 1 | - | Order Total: 8 units
2025-12-24 | 2025-12-20 | Wednesday | W5 | ATT-001 | 2526202957 | Unknown | W8 | 8 | 3 | 6 | 6/8 (75%) | 2 | Cooling/Shakeout | N/A | 1590.00 | 3.180 | - | 1 | - | Order Total: 8 units
2025-12-25 | 2025-12-20 | Thursday | W5 | ATT-001 | 2526202957 | Unknown | W8 | 8 | 4 | 8 | 8/8 COMPLETE ✓ | 2 | Cooling/Shakeout | N/A | 1590.00 | 3.180 | - | 1 | - | Order Total: 8 units
2025-11-22 | 2025-11-22 | Saturday | W1 | ATT-001 | 2526202958 | Unknown | W13 | 8 | 1 | 2 | 2/8 (25%) | 2 | MC1 | KVCAD50MC001 | 1590.00 | 3.180 | 40 min | 0 | - | Order Total: 8 units
2025-11-22 | 2025-11-29 | Saturday | W1 | ATT-002 | 2526202958 | Unknown | W13 | 8 | 1 | 2 | 2/8 (25%) | 2 | SP1 | KVCALPPSP001 | 640.00 | 1.280 | 12 min | 1 | 24 min | Order Total: 8 units
2025-11-24 | 2025-11-24 | Monday | W1 | ATT-001 | 2526202958 | Unknown | W13 | 8 | 2 | 4 | 4/8 (50%) | 2 | MC1 | KVCAD50MC001 | 1590.00 | 3.180 | 40 min | 0 | - | Order Total: 8 units
2025-11-24 | 2025-12-01 | Monday | W1 | ATT-002 | 2526202958 | Unknown | W13 | 8 | 2 | 4 | 4/8 (50%) | 2 | SP1 | KVCALPPSP001 | 640.00 | 1.280 | 12 min | 1 | 24 min | Order Total: 8 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | ATT-001 | 2526202958 | Unknown | W13 | 8 | 3 | 6 | 6/8 (75%) | 2 | MC1 | KVCAD50MC001 | 1590.00 | 3.180 | 40 min | 0 | - | Order Total: 8 units
2025-11-25 | 2025-11-29 | Tuesday | W1 | ATT-002 | 2526202958 | Unknown | W13 | 8 | 3 | 6 | 6/8 (75%) | 2 | SP1 | KVCALPPSP001 | 640.00 | 1.280 | 12 min | 1 | 24 min | Order Total: 8 units
2025-11-26 | 2025-11-26 | Wednesday | W1 | ATT-001 | 2526202958 | Unknown | W13 | 8 | 4 | 8 | 8/8 COMPLETE ✓ | 2 | MC1 | KVCAD50MC001 | 1590.00 | 3.180 | 40 min | 0 | - | Order Total: 8 units
2025-11-26 | 2025-11-29 | Wednesday | W1 | ATT-002 | 2526202958 | Unknown | W13 | 8 | 4 | 8 | 8/8 COMPLETE ✓ | 2 | SP1 | KVCALPPSP001 | 640.00 | 1.280 | 12 min | 1 | 24 min | Order Total: 8 units
2025-11-29 | 2025-11-29 | Saturday | W2 | ATT-002 | 2526202958 | Unknown | W13 | 8 | 1 | 6 | 6/8 (75%) | 6 | Casting | CS-ATT-002 | 640.00 | 3.840 | 20 min | 1 | 120 min | Order Total: 8 units
2025-11-30 | 2025-11-29 | Sunday | W2 | ATT-002 | 2526202958 | Unknown | W13 | 8 | 1 | 2 | 2/8 (25%) | 2 | Cooling/Shakeout | N/A | 640.00 | 1.280 | - | 1 | - | Order Total: 8 units
2025-12-01 | 2025-12-01 | Monday | W2 | ATT-002 | 2526202958 | Unknown | W13 | 8 | 2 | 8 | 8/8 COMPLETE ✓ | 2 | Casting | CS-ATT-002 | 640.00 | 1.280 | 20 min | 1 | 40 min | Order Total: 8 units
2025-12-02 | 2025-12-01 | Tuesday | W2 | ATT-002 | 2526202958 | Unknown | W13 | 8 | 2 | 4 | 4/8 (50%) | 2 | Cooling/Shakeout | N/A | 640.00 | 1.280 | - | 1 | - | Order Total: 8 units
2025-12-03 | 2025-11-29 | Wednesday | W2 | ATT-002 | 2526202958 | Unknown | W13 | 8 | 3 | 6 | 6/8 (75%) | 2 | Cooling/Shakeout | N/A | 640.00 | 1.280 | - | 1 | - | Order Total: 8 units
2025-12-04 | 2025-11-29 | Thursday | W2 | ATT-002 | 2526202958 | Unknown | W13 | 8 | 4 | 8 | 8/8 COMPLETE ✓ | 2 | Cooling/Shakeout | N/A | 640.00 | 1.280 | - | 1 | - | Order Total: 8 units
2025-12-20 | 2025-12-20 | Saturday | W5 | ATT-001 | 2526202958 | Unknown | W13 | 8 | 1 | 2 | 2/8 (25%) | 2 | Grinding | KVCALHMGR001 | 1590.00 | 3.180 | 330 min | 1 | 660 min | Order Total: 8 units
2025-12-22 | 2025-12-22 | Monday | W5 | ATT-001 | 2526202958 | Unknown | W13 | 8 | 2 | 4 | 4/8 (50%) | 2 | Grinding | KVCALHMGR001 | 1590.00 | 3.180 | 330 min | 1 | 660 min | Order Total: 8 units
2025-12-23 | 2025-12-23 | Tuesday | W5 | ATT-001 | 2526202958 | Unknown | W13 | 8 | 3 | 6 | 6/8 (75%) | 2 | Grinding | KVCALHMGR001 | 1590.00 | 3.180 | 330 min | 1 | 660 min | Order Total: 8 units
2025-12-24 | 2025-12-24 | Wednesday | W5 | ATT-001 | 2526202958 | Unknown | W13 | 8 | 4 | 8 | 8/8 COMPLETE ✓ | 2 | Grinding | KVCALHMGR001 | 1590.00 | 3.180 | 330 min | 1 | 660 min | Order Total: 8 units
2025-11-22 | 2025-11-22 | Saturday | W1 | ATT-001 | 2526202959 | Unknown | W13 | 8 | 1 | 2 | 2/8 (25%) | 2 | MC1 | KVCAD50MC001 | 1590.00 | 3.180 | 40 min | 0 | - | Order Total: 8 units
2025-11-22 | 2025-11-29 | Saturday | W1 | ATT-002 | 2526202959 | Unknown | W13 | 8 | 1 | 2 | 2/8 (25%) | 2 | SP1 | KVCALPPSP001 | 640.00 | 1.280 | 12 min | 1 | 24 min | Order Total: 8 units
2025-11-24 | 2025-11-24 | Monday | W1 | ATT-001 | 2526202959 | Unknown | W13 | 8 | 2 | 4 | 4/8 (50%) | 2 | MC1 | KVCAD50MC001 | 1590.00 | 3.180 | 40 min | 0 | - | Order Total: 8 units
2025-11-24 | 2025-12-01 | Monday | W1 | ATT-002 | 2526202959 | Unknown | W13 | 8 | 2 | 4 | 4/8 (50%) | 2 | SP1 | KVCALPPSP001 | 640.00 | 1.280 | 12 min | 1 | 24 min | Order Total: 8 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | ATT-001 | 2526202959 | Unknown | W13 | 8 | 3 | 6 | 6/8 (75%) | 2 | MC1 | KVCAD50MC001 | 1590.00 | 3.180 | 40 min | 0 | - | Order Total: 8 units
2025-11-25 | 2025-11-29 | Tuesday | W1 | ATT-002 | 2526202959 | Unknown | W13 | 8 | 3 | 6 | 6/8 (75%) | 2 | SP1 | KVCALPPSP001 | 640.00 | 1.280 | 12 min | 1 | 24 min | Order Total: 8 units
2025-11-26 | 2025-11-26 | Wednesday | W1 | ATT-001 | 2526202959 | Unknown | W13 | 8 | 4 | 8 | 8/8 COMPLETE ✓ | 2 | MC1 | KVCAD50MC001 | 1590.00 | 3.180 | 40 min | 0 | - | Order Total: 8 units
2025-11-26 | 2025-11-29 | Wednesday | W1 | ATT-002 | 2526202959 | Unknown | W13 | 8 | 4 | 8 | 8/8 COMPLETE ✓ | 2 | SP1 | KVCALPPSP001 | 640.00 | 1.280 | 12 min | 1 | 24 min | Order Total: 8 units
2025-11-29 | 2025-11-29 | Saturday | W2 | ATT-002 | 2526202959 | Unknown | W13 | 8 | 1 | 6 | 6/8 (75%) | 6 | Casting | CS-ATT-002 | 640.00 | 3.840 | 20 min | 1 | 120 min | Order Total: 8 units
2025-11-30 | 2025-11-29 | Sunday | W2 | ATT-002 | 2526202959 | Unknown | W13 | 8 | 1 | 2 | 2/8 (25%) | 2 | Cooling/Shakeout | N/A | 640.00 | 1.280 | - | 1 | - | Order Total: 8 units
2025-12-01 | 2025-12-01 | Monday | W2 | ATT-002 | 2526202959 | Unknown | W13 | 8 | 2 | 8 | 8/8 COMPLETE ✓ | 2 | Casting | CS-ATT-002 | 640.00 | 1.280 | 20 min | 1 | 40 min | Order Total: 8 units
2025-12-02 | 2025-12-01 | Tuesday | W2 | ATT-002 | 2526202959 | Unknown | W13 | 8 | 2 | 4 | 4/8 (50%) | 2 | Cooling/Shakeout | N/A | 640.00 | 1.280 | - | 1 | - | Order Total: 8 units
2025-12-03 | 2025-11-29 | Wednesday | W2 | ATT-002 | 2526202959 | Unknown | W13 | 8 | 3 | 6 | 6/8 (75%) | 2 | Cooling/Shakeout | N/A | 640.00 | 1.280 | - | 1 | - | Order Total: 8 units
2025-12-04 | 2025-11-29 | Thursday | W2 | ATT-002 | 2526202959 | Unknown | W13 | 8 | 4 | 8 | 8/8 COMPLETE ✓ | 2 | Cooling/Shakeout | N/A | 640.00 | 1.280 | - | 1 | - | Order Total: 8 units
2025-12-20 | 2025-12-20 | Saturday | W5 | ATT-001 | 2526202959 | Unknown | W13 | 8 | 1 | 2 | 2/8 (25%) | 2 | Grinding | KVCALHMGR001 | 1590.00 | 3.180 | 330 min | 1 | 660 min | Order Total: 8 units
2025-12-22 | 2025-12-22 | Monday | W5 | ATT-001 | 2526202959 | Unknown | W13 | 8 | 2 | 4 | 4/8 (50%) | 2 | Grinding | KVCALHMGR001 | 1590.00 | 3.180 | 330 min | 1 | 660 min | Order Total: 8 units
2025-12-23 | 2025-12-23 | Tuesday | W5 | ATT-001 | 2526202959 | Unknown | W13 | 8 | 3 | 6 | 6/8 (75%) | 2 | Grinding | KVCALHMGR001 | 1590.00 | 3.180 | 330 min | 1 | 660 min | Order Total: 8 units
2025-12-24 | 2025-12-24 | Wednesday | W5 | ATT-001 | 2526202959 | Unknown | W13 | 8 | 4 | 8 | 8/8 COMPLETE ✓ | 2 | Grinding | KVCALHMGR001 | 1590.00 | 3.180 | 330 min | 1 | 660 min | Order Total: 8 units
2025-12-13 | 2025-12-13 | Saturday | W4 | ATT-002 | 2526202960 | Unknown | W17 | 8 | 1 | 2 | 2/8 (25%) | 2 | Grinding | KVCALHMGR001 | 640.00 | 1.280 | 330 min | 1 | 660 min | Order Total: 8 units
2025-12-15 | 2025-12-15 | Monday | W4 | ATT-002 | 2526202960 | Unknown | W17 | 8 | 2 | 4 | 4/8 (50%) | 2 | Grinding | KVCALHMGR001 | 640.00 | 1.280 | 330 min | 1 | 660 min | Order Total: 8 units
2025-12-16 | 2025-12-16 | Tuesday | W4 | ATT-002 | 2526202960 | Unknown | W17 | 8 | 3 | 6 | 6/8 (75%) | 2 | Grinding | KVCALHMGR001 | 640.00 | 1.280 | 330 min | 1 | 660 min | Order Total: 8 units
2025-12-17 | 2025-12-17 | Wednesday | W4 | ATT-002 | 2526202960 | Unknown | W17 | 8 | 4 | 8 | 8/8 COMPLETE ✓ | 2 | Grinding | KVCALHMGR001 | 640.00 | 1.280 | 330 min | 1 | 660 min | Order Total: 8 units
2025-12-13 | 2025-12-13 | Saturday | W4 | ATT-002 | 2526202961 | Unknown | W17 | 8 | 1 | 2 | 2/8 (25%) | 2 | Grinding | KVCALHMGR001 | 640.00 | 1.280 | 330 min | 1 | 660 min | Order Total: 8 units
2025-12-15 | 2025-12-15 | Monday | W4 | ATT-002 | 2526202961 | Unknown | W17 | 8 | 2 | 4 | 4/8 (50%) | 2 | Grinding | KVCALHMGR001 | 640.00 | 1.280 | 330 min | 1 | 660 min | Order Total: 8 units
2025-12-16 | 2025-12-16 | Tuesday | W4 | ATT-002 | 2526202961 | Unknown | W17 | 8 | 3 | 6 | 6/8 (75%) | 2 | Grinding | KVCALHMGR001 | 640.00 | 1.280 | 330 min | 1 | 660 min | Order Total: 8 units
2025-12-17 | 2025-12-17 | Wednesday | W4 | ATT-002 | 2526202961 | Unknown | W17 | 8 | 4 | 8 | 8/8 COMPLETE ✓ | 2 | Grinding | KVCALHMGR001 | 640.00 | 1.280 | 330 min | 1 | 660 min | Order Total: 8 units
2025-11-22 | 2025-12-13 | Saturday | W1 | LKK-01 | 2526202964 | Unknown | W2 | 8 | 1 | 2 | 2/8 (25%) | 2 | SP1 | KVCALPPSP001 | 199.66 | 0.399 | 7 min | 1 | 14 min | Order Total: 8 units
2025-11-24 | 2025-12-15 | Monday | W1 | LKK-01 | 2526202964 | Unknown | W2 | 8 | 2 | 4 | 4/8 (50%) | 2 | SP1 | KVCALPPSP001 | 199.66 | 0.399 | 7 min | 1 | 14 min | Order Total: 8 units
2025-11-25 | 2025-12-13 | Tuesday | W1 | LKK-01 | 2526202964 | Unknown | W2 | 8 | 3 | 6 | 6/8 (75%) | 2 | SP1 | KVCALPPSP001 | 199.66 | 0.399 | 7 min | 1 | 14 min | Order Total: 8 units
2025-11-26 | 2025-12-13 | Wednesday | W1 | LKK-01 | 2526202964 | Unknown | W2 | 8 | 4 | 8 | 8/8 COMPLETE ✓ | 2 | SP1 | KVCALPPSP001 | 199.66 | 0.399 | 7 min | 1 | 14 min | Order Total: 8 units
2025-11-29 | 2025-11-29 | Saturday | W2 | LKK-02 | 2526202964 | Unknown | W2 | 8 | 1 | 2 | 2/8 (25%) | 2 | MC1 | KVCAD50MC001 | 193.60 | 0.387 | 30 min | 0 | - | Order Total: 8 units
2025-12-01 | 2025-12-01 | Monday | W2 | LKK-02 | 2526202964 | Unknown | W2 | 8 | 2 | 4 | 4/8 (50%) | 2 | MC1 | KVCAD50MC001 | 193.60 | 0.387 | 30 min | 0 | - | Order Total: 8 units
2025-12-02 | 2025-12-02 | Tuesday | W2 | LKK-02 | 2526202964 | Unknown | W2 | 8 | 3 | 6 | 6/8 (75%) | 2 | MC1 | KVCAD50MC001 | 193.60 | 0.387 | 30 min | 0 | - | Order Total: 8 units
2025-12-03 | 2025-12-03 | Wednesday | W2 | LKK-02 | 2526202964 | Unknown | W2 | 8 | 4 | 8 | 8/8 COMPLETE ✓ | 2 | MC1 | KVCAD50MC001 | 193.60 | 0.387 | 30 min | 0 | - | Order Total: 8 units
2025-12-06 | 2025-12-06 | Saturday | W3 | LKK-03 | 2526202964 | Unknown | W2 | 8 | 1 | 2 | 2/8 (25%) | 2 | MC1 | KVCAD50MC001 | 1618.80 | 3.238 | 20 min | 0 | - | Order Total: 8 units
2025-12-08 | 2025-12-08 | Monday | W3 | LKK-03 | 2526202964 | Unknown | W2 | 8 | 2 | 4 | 4/8 (50%) | 2 | MC1 | KVCAD50MC001 | 1618.80 | 3.238 | 20 min | 0 | - | Order Total: 8 units
2025-12-09 | 2025-12-09 | Tuesday | W3 | LKK-03 | 2526202964 | Unknown | W2 | 8 | 3 | 6 | 6/8 (75%) | 2 | MC1 | KVCAD50MC001 | 1618.80 | 3.238 | 20 min | 0 | - | Order Total: 8 units
2025-12-10 | 2025-12-10 | Wednesday | W3 | LKK-03 | 2526202964 | Unknown | W2 | 8 | 4 | 8 | 8/8 COMPLETE ✓ | 2 | MC1 | KVCAD50MC001 | 1618.80 | 3.238 | 20 min | 0 | - | Order Total: 8 units
2025-12-13 | 2025-12-13 | Saturday | W4 | LKK-01 | 2526202964 | Unknown | W2 | 8 | 1 | 4 | 4/8 (50%) | 4 | Casting | CS1-LKK-001 | 199.66 | 0.799 | 22 min | 1 | 88 min | Order Total: 8 units
2025-12-14 | 2025-12-13 | Sunday | W4 | LKK-01 | 2526202964 | Unknown | W2 | 8 | 1 | 2 | 2/8 (25%) | 2 | Cooling/Shakeout | N/A | 199.66 | 0.399 | - | 1 | - | Order Total: 8 units
2025-12-15 | 2025-12-15 | Monday | W4 | LKK-01 | 2526202964 | Unknown | W2 | 8 | 2 | 8 | 8/8 COMPLETE ✓ | 4 | Casting | CS1-LKK-001 | 199.66 | 0.799 | 22 min | 1 | 88 min | Order Total: 8 units
2025-12-16 | 2025-12-15 | Tuesday | W4 | LKK-01 | 2526202964 | Unknown | W2 | 8 | 2 | 4 | 4/8 (50%) | 2 | Cooling/Shakeout | N/A | 199.66 | 0.399 | - | 1 | - | Order Total: 8 units
2025-12-17 | 2025-12-13 | Wednesday | W4 | LKK-01 | 2526202964 | Unknown | W2 | 8 | 3 | 6 | 6/8 (75%) | 2 | Cooling/Shakeout | N/A | 199.66 | 0.399 | - | 1 | - | Order Total: 8 units
2025-12-18 | 2025-12-13 | Thursday | W4 | LKK-01 | 2526202964 | Unknown | W2 | 8 | 4 | 8 | 8/8 COMPLETE ✓ | 2 | Cooling/Shakeout | N/A | 199.66 | 0.399 | - | 1 | - | Order Total: 8 units
2025-12-20 | 2025-12-13 | Saturday | W5 | LKK-01 | 2526202964 | Unknown | W2 | 8 | 1 | 2 | 2/8 (25%) | 2 | MC1 | KVCAD50MC001 | 199.66 | 0.399 | 30 min | 0 | - | Order Total: 8 units
2025-12-22 | 2025-12-15 | Monday | W5 | LKK-01 | 2526202964 | Unknown | W2 | 8 | 2 | 4 | 4/8 (50%) | 2 | MC1 | KVCAD50MC001 | 199.66 | 0.399 | 30 min | 0 | - | Order Total: 8 units
2025-12-23 | 2025-12-13 | Tuesday | W5 | LKK-01 | 2526202964 | Unknown | W2 | 8 | 3 | 6 | 6/8 (75%) | 2 | MC1 | KVCAD50MC001 | 199.66 | 0.399 | 30 min | 0 | - | Order Total: 8 units
2025-12-24 | 2025-12-13 | Wednesday | W5 | LKK-01 | 2526202964 | Unknown | W2 | 8 | 4 | 8 | 8/8 COMPLETE ✓ | 2 | MC1 | KVCAD50MC001 | 199.66 | 0.399 | 30 min | 0 | - | Order Total: 8 units
2025-11-22 | 2025-11-22 | Saturday | W1 | LKK-03 | 2526202965 | Unknown | W3 | 8 | 1 | 2 | 2/8 (25%) | 2 | MC1 | KVCAD50MC001 | 1618.80 | 3.238 | 20 min | 0 | - | Order Total: 8 units
2025-11-24 | 2025-11-24 | Monday | W1 | LKK-03 | 2526202965 | Unknown | W3 | 8 | 2 | 4 | 4/8 (50%) | 2 | MC1 | KVCAD50MC001 | 1618.80 | 3.238 | 20 min | 0 | - | Order Total: 8 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | LKK-03 | 2526202965 | Unknown | W3 | 8 | 3 | 6 | 6/8 (75%) | 2 | MC1 | KVCAD50MC001 | 1618.80 | 3.238 | 20 min | 0 | - | Order Total: 8 units
2025-11-26 | 2025-11-26 | Wednesday | W1 | LKK-03 | 2526202965 | Unknown | W3 | 8 | 4 | 8 | 8/8 COMPLETE ✓ | 2 | MC1 | KVCAD50MC001 | 1618.80 | 3.238 | 20 min | 0 | - | Order Total: 8 units
2025-12-06 | 2025-12-13 | Saturday | W3 | LKK-01 | 2526202965 | Unknown | W3 | 8 | 1 | 2 | 2/8 (25%) | 2 | SP1 | KVCALPPSP001 | 199.66 | 0.399 | 7 min | 1 | 14 min | Order Total: 8 units
2025-12-08 | 2025-12-15 | Monday | W3 | LKK-01 | 2526202965 | Unknown | W3 | 8 | 2 | 4 | 4/8 (50%) | 2 | SP1 | KVCALPPSP001 | 199.66 | 0.399 | 7 min | 1 | 14 min | Order Total: 8 units
2025-12-09 | 2025-12-13 | Tuesday | W3 | LKK-01 | 2526202965 | Unknown | W3 | 8 | 3 | 6 | 6/8 (75%) | 2 | SP1 | KVCALPPSP001 | 199.66 | 0.399 | 7 min | 1 | 14 min | Order Total: 8 units
2025-12-10 | 2025-12-13 | Wednesday | W3 | LKK-01 | 2526202965 | Unknown | W3 | 8 | 4 | 8 | 8/8 COMPLETE ✓ | 2 | SP1 | KVCALPPSP001 | 199.66 | 0.399 | 7 min | 1 | 14 min | Order Total: 8 units
2025-12-13 | 2025-12-13 | Saturday | W4 | LKK-01 | 2526202965 | Unknown | W3 | 8 | 1 | 4 | 4/8 (50%) | 4 | Casting | CS1-LKK-001 | 199.66 | 0.799 | 22 min | 1 | 88 min | Order Total: 8 units
2025-12-14 | 2025-12-13 | Sunday | W4 | LKK-01 | 2526202965 | Unknown | W3 | 8 | 1 | 2 | 2/8 (25%) | 2 | Cooling/Shakeout | N/A | 199.66 | 0.399 | - | 1 | - | Order Total: 8 units
2025-12-15 | 2025-12-15 | Monday | W4 | LKK-01 | 2526202965 | Unknown | W3 | 8 | 2 | 8 | 8/8 COMPLETE ✓ | 4 | Casting | CS1-LKK-001 | 199.66 | 0.799 | 22 min | 1 | 88 min | Order Total: 8 units
2025-12-16 | 2025-12-15 | Tuesday | W4 | LKK-01 | 2526202965 | Unknown | W3 | 8 | 2 | 4 | 4/8 (50%) | 2 | Cooling/Shakeout | N/A | 199.66 | 0.399 | - | 1 | - | Order Total: 8 units
2025-12-17 | 2025-12-13 | Wednesday | W4 | LKK-01 | 2526202965 | Unknown | W3 | 8 | 3 | 6 | 6/8 (75%) | 2 | Cooling/Shakeout | N/A | 199.66 | 0.399 | - | 1 | - | Order Total: 8 units
2025-12-18 | 2025-12-13 | Thursday | W4 | LKK-01 | 2526202965 | Unknown | W3 | 8 | 4 | 8 | 8/8 COMPLETE ✓ | 2 | Cooling/Shakeout | N/A | 199.66 | 0.399 | - | 1 | - | Order Total: 8 units
2025-11-29 | 2025-11-29 | Saturday | W2 | DGC-001 | 2526202970 | Unknown | W1 | 12 | 1 | 4 | 4/12 (33%) | 4 | Casting | CS1-DGC-001 | 396.00 | 1.584 | 20 min | 1 | 80 min | Order Total: 12 units
2025-11-30 | 2025-11-29 | Sunday | W2 | DGC-001 | 2526202970 | Unknown | W1 | 12 | 1 | 3 | 3/12 (25%) | 3 | Cooling/Shakeout | N/A | 396.00 | 1.188 | - | 1 | - | Order Total: 12 units
2025-12-01 | 2025-12-01 | Monday | W2 | DGC-001 | 2526202970 | Unknown | W1 | 12 | 2 | 8 | 8/12 (66%) | 4 | Casting | CS1-DGC-001 | 396.00 | 1.584 | 20 min | 1 | 80 min | Order Total: 12 units
2025-12-02 | 2025-12-02 | Tuesday | W2 | DGC-001 | 2526202970 | Unknown | W1 | 12 | 3 | 12 | 12/12 COMPLETE ✓ | 4 | Casting | CS1-DGC-001 | 396.00 | 1.584 | 20 min | 1 | 80 min | Order Total: 12 units
2025-12-02 | 2025-12-01 | Tuesday | W2 | DGC-001 | 2526202970 | Unknown | W1 | 12 | 2 | 6 | 6/12 (50%) | 3 | Cooling/Shakeout | N/A | 396.00 | 1.188 | - | 1 | - | Order Total: 12 units
2025-12-03 | 2025-12-02 | Wednesday | W2 | DGC-001 | 2526202970 | Unknown | W1 | 12 | 3 | 9 | 9/12 (75%) | 3 | Cooling/Shakeout | N/A | 396.00 | 1.188 | - | 1 | - | Order Total: 12 units
2025-12-04 | 2025-11-29 | Thursday | W2 | DGC-001 | 2526202970 | Unknown | W1 | 12 | 4 | 12 | 12/12 COMPLETE ✓ | 3 | Cooling/Shakeout | N/A | 396.00 | 1.188 | - | 1 | - | Order Total: 12 units
2025-11-29 | 2025-11-29 | Saturday | W2 | DGC-001 | 2526202971 | Unknown | W1 | 12 | 1 | 4 | 4/12 (33%) | 4 | Casting | CS1-DGC-001 | 396.00 | 1.584 | 20 min | 1 | 80 min | Order Total: 12 units
2025-11-30 | 2025-11-29 | Sunday | W2 | DGC-001 | 2526202971 | Unknown | W1 | 12 | 1 | 3 | 3/12 (25%) | 3 | Cooling/Shakeout | N/A | 396.00 | 1.188 | - | 1 | - | Order Total: 12 units
2025-12-01 | 2025-12-01 | Monday | W2 | DGC-001 | 2526202971 | Unknown | W1 | 12 | 2 | 8 | 8/12 (66%) | 4 | Casting | CS1-DGC-001 | 396.00 | 1.584 | 20 min | 1 | 80 min | Order Total: 12 units
2025-12-02 | 2025-12-02 | Tuesday | W2 | DGC-001 | 2526202971 | Unknown | W1 | 12 | 3 | 12 | 12/12 COMPLETE ✓ | 4 | Casting | CS1-DGC-001 | 396.00 | 1.584 | 20 min | 1 | 80 min | Order Total: 12 units
2025-12-02 | 2025-12-01 | Tuesday | W2 | DGC-001 | 2526202971 | Unknown | W1 | 12 | 2 | 6 | 6/12 (50%) | 3 | Cooling/Shakeout | N/A | 396.00 | 1.188 | - | 1 | - | Order Total: 12 units
2025-12-03 | 2025-12-02 | Wednesday | W2 | DGC-001 | 2526202971 | Unknown | W1 | 12 | 3 | 9 | 9/12 (75%) | 3 | Cooling/Shakeout | N/A | 396.00 | 1.188 | - | 1 | - | Order Total: 12 units
2025-12-04 | 2025-11-29 | Thursday | W2 | DGC-001 | 2526202971 | Unknown | W1 | 12 | 4 | 12 | 12/12 COMPLETE ✓ | 3 | Cooling/Shakeout | N/A | 396.00 | 1.188 | - | 1 | - | Order Total: 12 units
2025-11-22 | 2025-11-22 | Saturday | W1 | UBC-050 | 2526203022 | Unknown | W1 | 3 | 1 | 1 | 1/3 (33%) | 1 | Grinding | KVCALHMGR001 | 369.00 | 0.369 | 680 min | 1 | 680 min | Order Total: 3 units
2025-11-24 | 2025-11-24 | Monday | W1 | UBC-050 | 2526203022 | Unknown | W1 | 3 | 2 | 2 | 2/3 (66%) | 1 | Grinding | KVCALHMGR001 | 369.00 | 0.369 | 680 min | 1 | 680 min | Order Total: 3 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | UBC-050 | 2526203022 | Unknown | W1 | 3 | 3 | 3 | 3/3 COMPLETE ✓ | 1 | Grinding | KVCALHMGR001 | 369.00 | 0.369 | 680 min | 1 | 680 min | Order Total: 3 units
2025-11-29 | 2025-11-29 | Saturday | W2 | UBC-018 | 2526203023 | Unknown | W1 | 18 | 1 | 4 | 4/18 (22%) | 4 | SP1 | KVCALPPSP001 | 484.00 | 1.936 | 7 min | 1 | 28 min | Order Total: 18 units
2025-11-29 | 2025-11-29 | Saturday | W2 | UBC-018 | 2526203023 | Unknown | W1 | 18 | 1 | 4 | 4/18 (22%) | 4 | SP2 | KVCALPPSP002 | 484.00 | 1.936 | 7 min | 1 | 28 min | Order Total: 18 units
2025-11-29 | 2025-11-29 | Saturday | W2 | UBC-018 | 2526203023 | Unknown | W1 | 18 | 1 | 4 | 4/18 (22%) | 4 | SP3 | KVCALFPSP001 | 484.00 | 1.936 | 7 min | 1 | 28 min | Order Total: 18 units
2025-12-01 | 2025-12-01 | Monday | W2 | UBC-018 | 2526203023 | Unknown | W1 | 18 | 2 | 8 | 8/18 (44%) | 4 | SP1 | KVCALPPSP001 | 484.00 | 1.936 | 7 min | 1 | 28 min | Order Total: 18 units
2025-12-01 | 2025-12-01 | Monday | W2 | UBC-018 | 2526203023 | Unknown | W1 | 18 | 2 | 8 | 8/18 (44%) | 4 | SP2 | KVCALPPSP002 | 484.00 | 1.936 | 7 min | 1 | 28 min | Order Total: 18 units
2025-12-01 | 2025-12-01 | Monday | W2 | UBC-018 | 2526203023 | Unknown | W1 | 18 | 2 | 8 | 8/18 (44%) | 4 | SP3 | KVCALFPSP001 | 484.00 | 1.936 | 7 min | 1 | 28 min | Order Total: 18 units
2025-12-02 | 2025-12-02 | Tuesday | W2 | UBC-018 | 2526203023 | Unknown | W1 | 18 | 3 | 13 | 13/18 (72%) | 5 | SP1 | KVCALPPSP001 | 484.00 | 2.420 | 7 min | 1 | 35 min | Order Total: 18 units
2025-12-02 | 2025-12-02 | Tuesday | W2 | UBC-018 | 2526203023 | Unknown | W1 | 18 | 3 | 13 | 13/18 (72%) | 5 | SP2 | KVCALPPSP002 | 484.00 | 2.420 | 7 min | 1 | 35 min | Order Total: 18 units
2025-12-02 | 2025-12-02 | Tuesday | W2 | UBC-018 | 2526203023 | Unknown | W1 | 18 | 3 | 13 | 13/18 (72%) | 5 | SP3 | KVCALFPSP001 | 484.00 | 2.420 | 7 min | 1 | 35 min | Order Total: 18 units
2025-12-03 | 2025-12-03 | Wednesday | W2 | UBC-018 | 2526203023 | Unknown | W1 | 18 | 4 | 18 | 18/18 COMPLETE ✓ | 5 | SP1 | KVCALPPSP001 | 484.00 | 2.420 | 7 min | 1 | 35 min | Order Total: 18 units
2025-12-03 | 2025-12-03 | Wednesday | W2 | UBC-018 | 2526203023 | Unknown | W1 | 18 | 4 | 18 | 18/18 COMPLETE ✓ | 5 | SP2 | KVCALPPSP002 | 484.00 | 2.420 | 7 min | 1 | 35 min | Order Total: 18 units
2025-12-03 | 2025-12-03 | Wednesday | W2 | UBC-018 | 2526203023 | Unknown | W1 | 18 | 4 | 18 | 18/18 COMPLETE ✓ | 5 | SP3 | KVCALFPSP001 | 484.00 | 2.420 | 7 min | 1 | 35 min | Order Total: 18 units
2025-11-22 | 2025-11-22 | Saturday | W1 | MCB-009 | 2526203038 | Unknown | W1 | 7 | 1 | 2 | 2/7 (28%) | 2 | SP1 | KVCALPPSP001 | 1500.00 | 3.000 | 7 min | 1 | 14 min | Order Total: 7 units
2025-11-24 | 2025-11-24 | Monday | W1 | MCB-009 | 2526203038 | Unknown | W1 | 7 | 2 | 4 | 4/7 (57%) | 2 | SP1 | KVCALPPSP001 | 1500.00 | 3.000 | 7 min | 1 | 14 min | Order Total: 7 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | MCB-009 | 2526203038 | Unknown | W1 | 7 | 3 | 7 | 7/7 COMPLETE ✓ | 3 | SP1 | KVCALPPSP001 | 1500.00 | 4.500 | 7 min | 1 | 21 min | Order Total: 7 units
2025-11-22 | 2025-11-22 | Saturday | W1 | MCB-JLG-020 | 2526203039 | Unknown | W1 | 4 | 1 | 2 | 2/4 (50%) | 2 | Grinding | KVCALHMGR001 | 3863.64 | 7.727 | 480 min | 1 | 960 min | Order Total: 4 units
2025-11-24 | 2025-11-24 | Monday | W1 | MCB-JLG-020 | 2526203039 | Unknown | W1 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | Grinding | KVCALHMGR001 | 3863.64 | 7.727 | 480 min | 1 | 960 min | Order Total: 4 units
2025-11-22 | 2025-12-13 | Saturday | W1 | MCB-JLG-047 | 2526203057 | Unknown | W1 | 9 | 1 | 2 | 2/9 (22%) | 2 | MC1 | KVCAD50MC001 | 1592.40 | 3.185 | 40 min | 1 | 80 min | Order Total: 9 units
2025-11-24 | 2025-12-15 | Monday | W1 | MCB-JLG-047 | 2526203057 | Unknown | W1 | 9 | 2 | 4 | 4/9 (44%) | 2 | MC1 | KVCAD50MC001 | 1592.40 | 3.185 | 40 min | 1 | 80 min | Order Total: 9 units
2025-11-25 | 2025-12-13 | Tuesday | W1 | MCB-JLG-047 | 2526203057 | Unknown | W1 | 9 | 3 | 6 | 6/9 (66%) | 2 | MC1 | KVCAD50MC001 | 1592.40 | 3.185 | 40 min | 1 | 80 min | Order Total: 9 units
2025-11-26 | 2025-12-13 | Wednesday | W1 | MCB-JLG-047 | 2526203057 | Unknown | W1 | 9 | 4 | 9 | 9/9 COMPLETE ✓ | 3 | MC1 | KVCAD50MC001 | 1592.40 | 4.777 | 40 min | 1 | 120 min | Order Total: 9 units
2025-11-29 | 2025-12-13 | Saturday | W2 | MCB-JLG-047 | 2526203057 | Unknown | W1 | 9 | 1 | 2 | 2/9 (22%) | 2 | SP1 | KVCALPPSP001 | 1592.40 | 3.185 | 12 min | 1 | 24 min | Order Total: 9 units
2025-12-01 | 2025-12-15 | Monday | W2 | MCB-JLG-047 | 2526203057 | Unknown | W1 | 9 | 2 | 4 | 4/9 (44%) | 2 | SP1 | KVCALPPSP001 | 1592.40 | 3.185 | 12 min | 1 | 24 min | Order Total: 9 units
2025-12-02 | 2025-12-13 | Tuesday | W2 | MCB-JLG-047 | 2526203057 | Unknown | W1 | 9 | 3 | 6 | 6/9 (66%) | 2 | SP1 | KVCALPPSP001 | 1592.40 | 3.185 | 12 min | 1 | 24 min | Order Total: 9 units
2025-12-03 | 2025-12-13 | Wednesday | W2 | MCB-JLG-047 | 2526203057 | Unknown | W1 | 9 | 4 | 9 | 9/9 COMPLETE ✓ | 3 | SP1 | KVCALPPSP001 | 1592.40 | 4.777 | 12 min | 1 | 36 min | Order Total: 9 units
2025-12-13 | 2025-12-13 | Saturday | W4 | MCB-JLG-047 | 2526203057 | Unknown | W1 | 9 | 1 | 5 | 5/9 (55%) | 5 | Casting | CS1-MCB-JLG-047 | 1592.40 | 7.962 | 25 min | 1 | 125 min | Order Total: 9 units
2025-12-14 | 2025-12-13 | Sunday | W4 | MCB-JLG-047 | 2526203057 | Unknown | W1 | 9 | 1 | 2 | 2/9 (22%) | 2 | Cooling/Shakeout | N/A | 1592.40 | 3.185 | - | 1 | - | Order Total: 9 units
2025-12-15 | 2025-12-15 | Monday | W4 | MCB-JLG-047 | 2526203057 | Unknown | W1 | 9 | 2 | 9 | 9/9 COMPLETE ✓ | 4 | Casting | CS1-MCB-JLG-047 | 1592.40 | 6.370 | 25 min | 1 | 100 min | Order Total: 9 units
2025-12-16 | 2025-12-15 | Tuesday | W4 | MCB-JLG-047 | 2526203057 | Unknown | W1 | 9 | 2 | 4 | 4/9 (44%) | 2 | Cooling/Shakeout | N/A | 1592.40 | 3.185 | - | 1 | - | Order Total: 9 units
2025-12-17 | 2025-12-13 | Wednesday | W4 | MCB-JLG-047 | 2526203057 | Unknown | W1 | 9 | 3 | 6 | 6/9 (66%) | 2 | Cooling/Shakeout | N/A | 1592.40 | 3.185 | - | 1 | - | Order Total: 9 units
2025-12-18 | 2025-12-13 | Thursday | W4 | MCB-JLG-047 | 2526203057 | Unknown | W1 | 9 | 4 | 9 | 9/9 COMPLETE ✓ | 3 | Cooling/Shakeout | N/A | 1592.40 | 4.777 | - | 1 | - | Order Total: 9 units
2025-11-22 | 2025-11-22 | Saturday | W1 | UBC-022 | 2526203076 | Unknown | W2 | 4 | 1 | 2 | 2/4 (50%) | 2 | MC1 | MC1-UBC-022 | 1200.00 | 2.400 | 60 min | 0 | - | Order Total: 4 units
2025-11-22 | 2025-11-22 | Saturday | W1 | UBC-020 | 2526203076 | Unknown | W2 | 8 | 1 | 2 | 2/8 (25%) | 2 | SP1 | KVCALPPSP001 | 1667.00 | 3.334 | 12 min | 1 | 24 min | Order Total: 8 units
2025-11-24 | 2025-11-24 | Monday | W1 | UBC-022 | 2526203076 | Unknown | W2 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | MC1 | MC1-UBC-022 | 1200.00 | 2.400 | 60 min | 0 | - | Order Total: 4 units
2025-11-24 | 2025-11-24 | Monday | W1 | UBC-020 | 2526203076 | Unknown | W2 | 8 | 2 | 4 | 4/8 (50%) | 2 | SP1 | KVCALPPSP001 | 1667.00 | 3.334 | 12 min | 1 | 24 min | Order Total: 8 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | UBC-020 | 2526203076 | Unknown | W2 | 8 | 3 | 6 | 6/8 (75%) | 2 | SP1 | KVCALPPSP001 | 1667.00 | 3.334 | 12 min | 1 | 24 min | Order Total: 8 units
2025-11-26 | 2025-11-26 | Wednesday | W1 | UBC-020 | 2526203076 | Unknown | W2 | 8 | 4 | 8 | 8/8 COMPLETE ✓ | 2 | SP1 | KVCALPPSP001 | 1667.00 | 3.334 | 12 min | 1 | 24 min | Order Total: 8 units
2025-11-29 | 2025-11-29 | Saturday | W2 | UBC-022 | 2526203076 | Unknown | W2 | 4 | 1 | 2 | 2/4 (50%) | 2 | SP1 | SP1-UBC-022 | 1200.00 | 2.400 | - | 1 | - | Order Total: 4 units
2025-12-01 | 2025-12-01 | Monday | W2 | UBC-022 | 2526203076 | Unknown | W2 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | SP1 | SP1-UBC-022 | 1200.00 | 2.400 | - | 1 | - | Order Total: 4 units
2025-12-20 | 2025-12-20 | Saturday | W5 | UBC-022 | 2526203076 | Unknown | W2 | 4 | 1 | 2 | 2/4 (50%) | 2 | Grinding | GR1-UBC-022 | 1200.00 | 2.400 | 240 min | 1 | 480 min | Order Total: 4 units
2025-12-22 | 2025-12-22 | Monday | W5 | UBC-022 | 2526203076 | Unknown | W2 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | Grinding | GR1-UBC-022 | 1200.00 | 2.400 | 240 min | 1 | 480 min | Order Total: 4 units
2025-12-13 | 2025-12-13 | Saturday | W4 | UBC-014 | 2526203078 | Unknown | W2 | 20 | 1 | 7 | 7/20 (35%) | 7 | Casting | CS1-UBC-014 | 460.00 | 3.220 | 20 min | 1 | 140 min | Order Total: 20 units
2025-12-14 | 2025-12-13 | Sunday | W4 | UBC-014 | 2526203078 | Unknown | W2 | 20 | 1 | 5 | 5/20 (25%) | 5 | Cooling/Shakeout | N/A | 460.00 | 2.300 | - | 1 | - | Order Total: 20 units
2025-12-15 | 2025-12-15 | Monday | W4 | UBC-014 | 2526203078 | Unknown | W2 | 20 | 2 | 14 | 14/20 (70%) | 7 | Casting | CS1-UBC-014 | 460.00 | 3.220 | 20 min | 1 | 140 min | Order Total: 20 units
2025-12-16 | 2025-12-16 | Tuesday | W4 | UBC-014 | 2526203078 | Unknown | W2 | 20 | 3 | 20 | 20/20 COMPLETE ✓ | 6 | Casting | CS1-UBC-014 | 460.00 | 2.760 | 20 min | 1 | 120 min | Order Total: 20 units
2025-12-16 | 2025-12-15 | Tuesday | W4 | UBC-014 | 2526203078 | Unknown | W2 | 20 | 2 | 10 | 10/20 (50%) | 5 | Cooling/Shakeout | N/A | 460.00 | 2.300 | - | 1 | - | Order Total: 20 units
2025-12-17 | 2025-12-16 | Wednesday | W4 | UBC-014 | 2526203078 | Unknown | W2 | 20 | 3 | 15 | 15/20 (75%) | 5 | Cooling/Shakeout | N/A | 460.00 | 2.300 | - | 1 | - | Order Total: 20 units
2025-12-18 | 2025-12-13 | Thursday | W4 | UBC-014 | 2526203078 | Unknown | W2 | 20 | 4 | 20 | 20/20 COMPLETE ✓ | 5 | Cooling/Shakeout | N/A | 460.00 | 2.300 | - | 1 | - | Order Total: 20 units
2025-12-20 | 2025-12-13 | Saturday | W5 | UBC-014 | 2526203078 | Unknown | W2 | 20 | 1 | 5 | 5/20 (25%) | 5 | Grinding | KVCALHMGR001 | 460.00 | 2.300 | 30 min | 1 | 150 min | Order Total: 20 units
2025-12-20 | 2025-12-13 | Saturday | W5 | UBC-014 | 2526203078 | Unknown | W2 | 20 | 1 | 5 | 5/20 (25%) | 5 | MC1 | MC1-UBC-014 | 460.00 | 2.300 | - | 1 | - | Order Total: 20 units
2025-12-20 | 2025-12-13 | Saturday | W5 | UBC-014 | 2526203078 | Unknown | W2 | 20 | 1 | 5 | 5/20 (25%) | 5 | SP1 | KVCALPPSP001 | 460.00 | 2.300 | 7 min | 1 | 35 min | Order Total: 20 units
2025-12-22 | 2025-12-15 | Monday | W5 | UBC-014 | 2526203078 | Unknown | W2 | 20 | 2 | 10 | 10/20 (50%) | 5 | Grinding | KVCALHMGR001 | 460.00 | 2.300 | 30 min | 1 | 150 min | Order Total: 20 units
2025-12-22 | 2025-12-15 | Monday | W5 | UBC-014 | 2526203078 | Unknown | W2 | 20 | 2 | 10 | 10/20 (50%) | 5 | MC1 | MC1-UBC-014 | 460.00 | 2.300 | - | 1 | - | Order Total: 20 units
2025-12-22 | 2025-12-15 | Monday | W5 | UBC-014 | 2526203078 | Unknown | W2 | 20 | 2 | 10 | 10/20 (50%) | 5 | SP1 | KVCALPPSP001 | 460.00 | 2.300 | 7 min | 1 | 35 min | Order Total: 20 units
2025-12-23 | 2025-12-16 | Tuesday | W5 | UBC-014 | 2526203078 | Unknown | W2 | 20 | 3 | 15 | 15/20 (75%) | 5 | Grinding | KVCALHMGR001 | 460.00 | 2.300 | 30 min | 1 | 150 min | Order Total: 20 units
2025-12-23 | 2025-12-16 | Tuesday | W5 | UBC-014 | 2526203078 | Unknown | W2 | 20 | 3 | 15 | 15/20 (75%) | 5 | MC1 | MC1-UBC-014 | 460.00 | 2.300 | - | 1 | - | Order Total: 20 units
2025-12-23 | 2025-12-16 | Tuesday | W5 | UBC-014 | 2526203078 | Unknown | W2 | 20 | 3 | 15 | 15/20 (75%) | 5 | SP1 | KVCALPPSP001 | 460.00 | 2.300 | 7 min | 1 | 35 min | Order Total: 20 units
2025-12-24 | 2025-12-13 | Wednesday | W5 | UBC-014 | 2526203078 | Unknown | W2 | 20 | 4 | 20 | 20/20 COMPLETE ✓ | 5 | Grinding | KVCALHMGR001 | 460.00 | 2.300 | 30 min | 1 | 150 min | Order Total: 20 units
2025-12-24 | 2025-12-13 | Wednesday | W5 | UBC-014 | 2526203078 | Unknown | W2 | 20 | 4 | 20 | 20/20 COMPLETE ✓ | 5 | MC1 | MC1-UBC-014 | 460.00 | 2.300 | - | 1 | - | Order Total: 20 units
2025-12-24 | 2025-12-13 | Wednesday | W5 | UBC-014 | 2526203078 | Unknown | W2 | 20 | 4 | 20 | 20/20 COMPLETE ✓ | 5 | SP1 | KVCALPPSP001 | 460.00 | 2.300 | 7 min | 1 | 35 min | Order Total: 20 units
2025-11-22 | 2025-12-06 | Saturday | W1 | NMS-V-004 | 2526203090 | Unknown | W1 | 4 | 1 | 2 | 2/4 (50%) | 2 | Grinding | KVCALHMGR001 | 0.00 | 0.000 | 120 min | 1 | 240 min | Order Total: 4 units
2025-11-24 | 2025-12-08 | Monday | W1 | NMS-V-004 | 2526203090 | Unknown | W1 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | Grinding | KVCALHMGR001 | 0.00 | 0.000 | 120 min | 1 | 240 min | Order Total: 4 units
2025-12-06 | 2025-12-06 | Saturday | W3 | NMS-V-004 | 2526203090 | Unknown | W1 | 4 | 1 | 2 | 2/4 (50%) | 2 | Casting | CS3CFC-NMS-H-004 | 0.00 | 0.000 | 20 min | 1 | 40 min | Order Total: 4 units
2025-12-07 | 2025-12-06 | Sunday | W3 | NMS-V-004 | 2526203090 | Unknown | W1 | 4 | 1 | 2 | 2/4 (50%) | 2 | Cooling/Shakeout | N/A | 0.00 | 0.000 | - | 1 | - | Order Total: 4 units
2025-12-08 | 2025-12-08 | Monday | W3 | NMS-V-004 | 2526203090 | Unknown | W1 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | Casting | CS3CFC-NMS-H-004 | 0.00 | 0.000 | 20 min | 1 | 40 min | Order Total: 4 units
2025-12-09 | 2025-12-08 | Tuesday | W3 | NMS-V-004 | 2526203090 | Unknown | W1 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | Cooling/Shakeout | N/A | 0.00 | 0.000 | - | 1 | - | Order Total: 4 units
2025-12-20 | 2025-12-06 | Saturday | W5 | NMS-V-004 | 2526203090 | Unknown | W1 | 4 | 1 | 2 | 2/4 (50%) | 2 | SP1 | KVCALPPSP001 | 0.00 | 0.000 | 12 min | 1 | 24 min | Order Total: 4 units
2025-12-20 | 2025-12-06 | Saturday | W5 | NMS-V-004 | 2526203090 | Unknown | W1 | 4 | 1 | 2 | 2/4 (50%) | 2 | SP2 | KVCALPPSP002 | 0.00 | 0.000 | 12 min | 1 | 24 min | Order Total: 4 units
2025-12-20 | 2025-12-06 | Saturday | W5 | NMS-V-004 | 2526203090 | Unknown | W1 | 4 | 1 | 2 | 2/4 (50%) | 2 | SP3 | SP3CFC-NMS-H-004 | 0.00 | 0.000 | - | 0 | - | Order Total: 4 units
2025-12-22 | 2025-12-08 | Monday | W5 | NMS-V-004 | 2526203090 | Unknown | W1 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | SP1 | KVCALPPSP001 | 0.00 | 0.000 | 12 min | 1 | 24 min | Order Total: 4 units
2025-12-22 | 2025-12-08 | Monday | W5 | NMS-V-004 | 2526203090 | Unknown | W1 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | SP2 | KVCALPPSP002 | 0.00 | 0.000 | 12 min | 1 | 24 min | Order Total: 4 units
2025-12-22 | 2025-12-08 | Monday | W5 | NMS-V-004 | 2526203090 | Unknown | W1 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | SP3 | SP3CFC-NMS-H-004 | 0.00 | 0.000 | - | 0 | - | Order Total: 4 units
2025-11-22 | 2025-12-06 | Saturday | W1 | NMS-V-004 | 2526203091 | Unknown | W1 | 4 | 1 | 2 | 2/4 (50%) | 2 | Grinding | KVCALHMGR001 | 0.00 | 0.000 | 120 min | 1 | 240 min | Order Total: 4 units
2025-11-24 | 2025-12-08 | Monday | W1 | NMS-V-004 | 2526203091 | Unknown | W1 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | Grinding | KVCALHMGR001 | 0.00 | 0.000 | 120 min | 1 | 240 min | Order Total: 4 units
2025-12-06 | 2025-12-06 | Saturday | W3 | NMS-V-004 | 2526203091 | Unknown | W1 | 4 | 1 | 2 | 2/4 (50%) | 2 | Casting | CS3CFC-NMS-H-004 | 0.00 | 0.000 | 20 min | 1 | 40 min | Order Total: 4 units
2025-12-07 | 2025-12-06 | Sunday | W3 | NMS-V-004 | 2526203091 | Unknown | W1 | 4 | 1 | 2 | 2/4 (50%) | 2 | Cooling/Shakeout | N/A | 0.00 | 0.000 | - | 1 | - | Order Total: 4 units
2025-12-08 | 2025-12-08 | Monday | W3 | NMS-V-004 | 2526203091 | Unknown | W1 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | Casting | CS3CFC-NMS-H-004 | 0.00 | 0.000 | 20 min | 1 | 40 min | Order Total: 4 units
2025-12-09 | 2025-12-08 | Tuesday | W3 | NMS-V-004 | 2526203091 | Unknown | W1 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | Cooling/Shakeout | N/A | 0.00 | 0.000 | - | 1 | - | Order Total: 4 units
2025-12-20 | 2025-12-06 | Saturday | W5 | NMS-V-004 | 2526203091 | Unknown | W1 | 4 | 1 | 2 | 2/4 (50%) | 2 | SP1 | KVCALPPSP001 | 0.00 | 0.000 | 12 min | 1 | 24 min | Order Total: 4 units
2025-12-20 | 2025-12-06 | Saturday | W5 | NMS-V-004 | 2526203091 | Unknown | W1 | 4 | 1 | 2 | 2/4 (50%) | 2 | SP2 | KVCALPPSP002 | 0.00 | 0.000 | 12 min | 1 | 24 min | Order Total: 4 units
2025-12-20 | 2025-12-06 | Saturday | W5 | NMS-V-004 | 2526203091 | Unknown | W1 | 4 | 1 | 2 | 2/4 (50%) | 2 | SP3 | SP3CFC-NMS-H-004 | 0.00 | 0.000 | - | 0 | - | Order Total: 4 units
2025-12-22 | 2025-12-08 | Monday | W5 | NMS-V-004 | 2526203091 | Unknown | W1 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | SP1 | KVCALPPSP001 | 0.00 | 0.000 | 12 min | 1 | 24 min | Order Total: 4 units
2025-12-22 | 2025-12-08 | Monday | W5 | NMS-V-004 | 2526203091 | Unknown | W1 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | SP2 | KVCALPPSP002 | 0.00 | 0.000 | 12 min | 1 | 24 min | Order Total: 4 units
2025-12-22 | 2025-12-08 | Monday | W5 | NMS-V-004 | 2526203091 | Unknown | W1 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | SP3 | SP3CFC-NMS-H-004 | 0.00 | 0.000 | - | 0 | - | Order Total: 4 units
2025-11-22 | 2025-11-22 | Saturday | W1 | NMS-H-001 | 2526203092 | Unknown | W1 | 13 | 1 | 3 | 3/13 (23%) | 3 | Grinding | KVCALHMGR001 | 1428.80 | 4.286 | 360 min | 1 | 1080 min | Order Total: 13 units
2025-11-22 | 2025-11-22 | Saturday | W1 | NMS-H-001 | 2526203092 | Unknown | W1 | 13 | 1 | 3 | 3/13 (23%) | 3 | MC1 | KVCAD30MC001 | 1428.80 | 4.286 | 60 min | 1 | 180 min | Order Total: 13 units
2025-11-22 | 2025-11-22 | Saturday | W1 | NMS-H-001 | 2526203092 | Unknown | W1 | 13 | 1 | 3 | 3/13 (23%) | 3 | MC2 | KVCAD30MC001 | 1428.80 | 4.286 | 10 min | 1 | 30 min | Order Total: 13 units
2025-11-22 | 2025-11-22 | Saturday | W1 | NMS-H-001 | 2526203092 | Unknown | W1 | 13 | 1 | 3 | 3/13 (23%) | 3 | MC3 | MC3CFC-NMS-H-001 | 1428.80 | 4.286 | - | 0 | - | Order Total: 13 units
2025-11-22 | 2025-11-22 | Saturday | W1 | NMS-H-001 | 2526203092 | Unknown | W1 | 13 | 1 | 3 | 3/13 (23%) | 3 | SP1 | KVCALPPSP001 | 1428.80 | 4.286 | 7 min | 1 | 21 min | Order Total: 13 units
2025-11-22 | 2025-11-22 | Saturday | W1 | NMS-H-001 | 2526203092 | Unknown | W1 | 13 | 1 | 3 | 3/13 (23%) | 3 | SP2 | KVCALPPSP002 | 1428.80 | 4.286 | 7 min | 1 | 21 min | Order Total: 13 units
2025-11-22 | 2025-11-22 | Saturday | W1 | NMS-H-001 | 2526203092 | Unknown | W1 | 13 | 1 | 3 | 3/13 (23%) | 3 | SP3 | SP3CFC-NMS-H-001 | 1428.80 | 4.286 | - | 1 | - | Order Total: 13 units
2025-11-24 | 2025-11-24 | Monday | W1 | NMS-H-001 | 2526203092 | Unknown | W1 | 13 | 2 | 6 | 6/13 (46%) | 3 | Grinding | KVCALHMGR001 | 1428.80 | 4.286 | 360 min | 1 | 1080 min | Order Total: 13 units
2025-11-24 | 2025-11-24 | Monday | W1 | NMS-H-001 | 2526203092 | Unknown | W1 | 13 | 2 | 6 | 6/13 (46%) | 3 | MC1 | KVCAD30MC001 | 1428.80 | 4.286 | 60 min | 1 | 180 min | Order Total: 13 units
2025-11-24 | 2025-11-24 | Monday | W1 | NMS-H-001 | 2526203092 | Unknown | W1 | 13 | 2 | 6 | 6/13 (46%) | 3 | MC2 | KVCAD30MC001 | 1428.80 | 4.286 | 10 min | 1 | 30 min | Order Total: 13 units
2025-11-24 | 2025-11-24 | Monday | W1 | NMS-H-001 | 2526203092 | Unknown | W1 | 13 | 2 | 6 | 6/13 (46%) | 3 | MC3 | MC3CFC-NMS-H-001 | 1428.80 | 4.286 | - | 0 | - | Order Total: 13 units
2025-11-24 | 2025-11-24 | Monday | W1 | NMS-H-001 | 2526203092 | Unknown | W1 | 13 | 2 | 6 | 6/13 (46%) | 3 | SP1 | KVCALPPSP001 | 1428.80 | 4.286 | 7 min | 1 | 21 min | Order Total: 13 units
2025-11-24 | 2025-11-24 | Monday | W1 | NMS-H-001 | 2526203092 | Unknown | W1 | 13 | 2 | 6 | 6/13 (46%) | 3 | SP2 | KVCALPPSP002 | 1428.80 | 4.286 | 7 min | 1 | 21 min | Order Total: 13 units
2025-11-24 | 2025-11-24 | Monday | W1 | NMS-H-001 | 2526203092 | Unknown | W1 | 13 | 2 | 6 | 6/13 (46%) | 3 | SP3 | SP3CFC-NMS-H-001 | 1428.80 | 4.286 | - | 1 | - | Order Total: 13 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | NMS-H-001 | 2526203092 | Unknown | W1 | 13 | 3 | 9 | 9/13 (69%) | 3 | Grinding | KVCALHMGR001 | 1428.80 | 4.286 | 360 min | 1 | 1080 min | Order Total: 13 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | NMS-H-001 | 2526203092 | Unknown | W1 | 13 | 3 | 9 | 9/13 (69%) | 3 | MC1 | KVCAD30MC001 | 1428.80 | 4.286 | 60 min | 1 | 180 min | Order Total: 13 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | NMS-H-001 | 2526203092 | Unknown | W1 | 13 | 3 | 9 | 9/13 (69%) | 3 | MC2 | KVCAD30MC001 | 1428.80 | 4.286 | 10 min | 1 | 30 min | Order Total: 13 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | NMS-H-001 | 2526203092 | Unknown | W1 | 13 | 3 | 9 | 9/13 (69%) | 3 | MC3 | MC3CFC-NMS-H-001 | 1428.80 | 4.286 | - | 0 | - | Order Total: 13 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | NMS-H-001 | 2526203092 | Unknown | W1 | 13 | 3 | 9 | 9/13 (69%) | 3 | SP1 | KVCALPPSP001 | 1428.80 | 4.286 | 7 min | 1 | 21 min | Order Total: 13 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | NMS-H-001 | 2526203092 | Unknown | W1 | 13 | 3 | 9 | 9/13 (69%) | 3 | SP2 | KVCALPPSP002 | 1428.80 | 4.286 | 7 min | 1 | 21 min | Order Total: 13 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | NMS-H-001 | 2526203092 | Unknown | W1 | 13 | 3 | 9 | 9/13 (69%) | 3 | SP3 | SP3CFC-NMS-H-001 | 1428.80 | 4.286 | - | 1 | - | Order Total: 13 units
2025-11-26 | 2025-11-26 | Wednesday | W1 | NMS-H-001 | 2526203092 | Unknown | W1 | 13 | 4 | 13 | 13/13 COMPLETE ✓ | 4 | Grinding | KVCALHMGR001 | 1428.80 | 5.715 | 360 min | 1 | 1440 min | Order Total: 13 units
2025-11-26 | 2025-11-26 | Wednesday | W1 | NMS-H-001 | 2526203092 | Unknown | W1 | 13 | 4 | 13 | 13/13 COMPLETE ✓ | 4 | MC1 | KVCAD30MC001 | 1428.80 | 5.715 | 60 min | 1 | 240 min | Order Total: 13 units
2025-11-26 | 2025-11-26 | Wednesday | W1 | NMS-H-001 | 2526203092 | Unknown | W1 | 13 | 4 | 13 | 13/13 COMPLETE ✓ | 4 | MC2 | KVCAD30MC001 | 1428.80 | 5.715 | 10 min | 1 | 40 min | Order Total: 13 units
2025-11-26 | 2025-11-26 | Wednesday | W1 | NMS-H-001 | 2526203092 | Unknown | W1 | 13 | 4 | 13 | 13/13 COMPLETE ✓ | 4 | MC3 | MC3CFC-NMS-H-001 | 1428.80 | 5.715 | - | 0 | - | Order Total: 13 units
2025-11-26 | 2025-11-26 | Wednesday | W1 | NMS-H-001 | 2526203092 | Unknown | W1 | 13 | 4 | 13 | 13/13 COMPLETE ✓ | 4 | SP1 | KVCALPPSP001 | 1428.80 | 5.715 | 7 min | 1 | 28 min | Order Total: 13 units
2025-11-26 | 2025-11-26 | Wednesday | W1 | NMS-H-001 | 2526203092 | Unknown | W1 | 13 | 4 | 13 | 13/13 COMPLETE ✓ | 4 | SP2 | KVCALPPSP002 | 1428.80 | 5.715 | 7 min | 1 | 28 min | Order Total: 13 units
2025-11-26 | 2025-11-26 | Wednesday | W1 | NMS-H-001 | 2526203092 | Unknown | W1 | 13 | 4 | 13 | 13/13 COMPLETE ✓ | 4 | SP3 | SP3CFC-NMS-H-001 | 1428.80 | 5.715 | - | 1 | - | Order Total: 13 units
2025-11-22 | 2025-11-22 | Saturday | W1 | NMS-H-001 | 2526203093 | Unknown | W1 | 13 | 1 | 3 | 3/13 (23%) | 3 | Grinding | KVCALHMGR001 | 1428.80 | 4.286 | 360 min | 1 | 1080 min | Order Total: 13 units
2025-11-22 | 2025-11-22 | Saturday | W1 | NMS-H-001 | 2526203093 | Unknown | W1 | 13 | 1 | 3 | 3/13 (23%) | 3 | MC1 | KVCAD30MC001 | 1428.80 | 4.286 | 60 min | 1 | 180 min | Order Total: 13 units
2025-11-22 | 2025-11-22 | Saturday | W1 | NMS-H-001 | 2526203093 | Unknown | W1 | 13 | 1 | 3 | 3/13 (23%) | 3 | MC2 | KVCAD30MC001 | 1428.80 | 4.286 | 10 min | 1 | 30 min | Order Total: 13 units
2025-11-22 | 2025-11-22 | Saturday | W1 | NMS-H-001 | 2526203093 | Unknown | W1 | 13 | 1 | 3 | 3/13 (23%) | 3 | MC3 | MC3CFC-NMS-H-001 | 1428.80 | 4.286 | - | 0 | - | Order Total: 13 units
2025-11-22 | 2025-11-22 | Saturday | W1 | NMS-H-001 | 2526203093 | Unknown | W1 | 13 | 1 | 3 | 3/13 (23%) | 3 | SP1 | KVCALPPSP001 | 1428.80 | 4.286 | 7 min | 1 | 21 min | Order Total: 13 units
2025-11-22 | 2025-11-22 | Saturday | W1 | NMS-H-001 | 2526203093 | Unknown | W1 | 13 | 1 | 3 | 3/13 (23%) | 3 | SP2 | KVCALPPSP002 | 1428.80 | 4.286 | 7 min | 1 | 21 min | Order Total: 13 units
2025-11-22 | 2025-11-22 | Saturday | W1 | NMS-H-001 | 2526203093 | Unknown | W1 | 13 | 1 | 3 | 3/13 (23%) | 3 | SP3 | SP3CFC-NMS-H-001 | 1428.80 | 4.286 | - | 1 | - | Order Total: 13 units
2025-11-24 | 2025-11-24 | Monday | W1 | NMS-H-001 | 2526203093 | Unknown | W1 | 13 | 2 | 6 | 6/13 (46%) | 3 | Grinding | KVCALHMGR001 | 1428.80 | 4.286 | 360 min | 1 | 1080 min | Order Total: 13 units
2025-11-24 | 2025-11-24 | Monday | W1 | NMS-H-001 | 2526203093 | Unknown | W1 | 13 | 2 | 6 | 6/13 (46%) | 3 | MC1 | KVCAD30MC001 | 1428.80 | 4.286 | 60 min | 1 | 180 min | Order Total: 13 units
2025-11-24 | 2025-11-24 | Monday | W1 | NMS-H-001 | 2526203093 | Unknown | W1 | 13 | 2 | 6 | 6/13 (46%) | 3 | MC2 | KVCAD30MC001 | 1428.80 | 4.286 | 10 min | 1 | 30 min | Order Total: 13 units
2025-11-24 | 2025-11-24 | Monday | W1 | NMS-H-001 | 2526203093 | Unknown | W1 | 13 | 2 | 6 | 6/13 (46%) | 3 | MC3 | MC3CFC-NMS-H-001 | 1428.80 | 4.286 | - | 0 | - | Order Total: 13 units
2025-11-24 | 2025-11-24 | Monday | W1 | NMS-H-001 | 2526203093 | Unknown | W1 | 13 | 2 | 6 | 6/13 (46%) | 3 | SP1 | KVCALPPSP001 | 1428.80 | 4.286 | 7 min | 1 | 21 min | Order Total: 13 units
2025-11-24 | 2025-11-24 | Monday | W1 | NMS-H-001 | 2526203093 | Unknown | W1 | 13 | 2 | 6 | 6/13 (46%) | 3 | SP2 | KVCALPPSP002 | 1428.80 | 4.286 | 7 min | 1 | 21 min | Order Total: 13 units
2025-11-24 | 2025-11-24 | Monday | W1 | NMS-H-001 | 2526203093 | Unknown | W1 | 13 | 2 | 6 | 6/13 (46%) | 3 | SP3 | SP3CFC-NMS-H-001 | 1428.80 | 4.286 | - | 1 | - | Order Total: 13 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | NMS-H-001 | 2526203093 | Unknown | W1 | 13 | 3 | 9 | 9/13 (69%) | 3 | Grinding | KVCALHMGR001 | 1428.80 | 4.286 | 360 min | 1 | 1080 min | Order Total: 13 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | NMS-H-001 | 2526203093 | Unknown | W1 | 13 | 3 | 9 | 9/13 (69%) | 3 | MC1 | KVCAD30MC001 | 1428.80 | 4.286 | 60 min | 1 | 180 min | Order Total: 13 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | NMS-H-001 | 2526203093 | Unknown | W1 | 13 | 3 | 9 | 9/13 (69%) | 3 | MC2 | KVCAD30MC001 | 1428.80 | 4.286 | 10 min | 1 | 30 min | Order Total: 13 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | NMS-H-001 | 2526203093 | Unknown | W1 | 13 | 3 | 9 | 9/13 (69%) | 3 | MC3 | MC3CFC-NMS-H-001 | 1428.80 | 4.286 | - | 0 | - | Order Total: 13 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | NMS-H-001 | 2526203093 | Unknown | W1 | 13 | 3 | 9 | 9/13 (69%) | 3 | SP1 | KVCALPPSP001 | 1428.80 | 4.286 | 7 min | 1 | 21 min | Order Total: 13 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | NMS-H-001 | 2526203093 | Unknown | W1 | 13 | 3 | 9 | 9/13 (69%) | 3 | SP2 | KVCALPPSP002 | 1428.80 | 4.286 | 7 min | 1 | 21 min | Order Total: 13 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | NMS-H-001 | 2526203093 | Unknown | W1 | 13 | 3 | 9 | 9/13 (69%) | 3 | SP3 | SP3CFC-NMS-H-001 | 1428.80 | 4.286 | - | 1 | - | Order Total: 13 units
2025-11-26 | 2025-11-26 | Wednesday | W1 | NMS-H-001 | 2526203093 | Unknown | W1 | 13 | 4 | 13 | 13/13 COMPLETE ✓ | 4 | Grinding | KVCALHMGR001 | 1428.80 | 5.715 | 360 min | 1 | 1440 min | Order Total: 13 units
2025-11-26 | 2025-11-26 | Wednesday | W1 | NMS-H-001 | 2526203093 | Unknown | W1 | 13 | 4 | 13 | 13/13 COMPLETE ✓ | 4 | MC1 | KVCAD30MC001 | 1428.80 | 5.715 | 60 min | 1 | 240 min | Order Total: 13 units
2025-11-26 | 2025-11-26 | Wednesday | W1 | NMS-H-001 | 2526203093 | Unknown | W1 | 13 | 4 | 13 | 13/13 COMPLETE ✓ | 4 | MC2 | KVCAD30MC001 | 1428.80 | 5.715 | 10 min | 1 | 40 min | Order Total: 13 units
2025-11-26 | 2025-11-26 | Wednesday | W1 | NMS-H-001 | 2526203093 | Unknown | W1 | 13 | 4 | 13 | 13/13 COMPLETE ✓ | 4 | MC3 | MC3CFC-NMS-H-001 | 1428.80 | 5.715 | - | 0 | - | Order Total: 13 units
2025-11-26 | 2025-11-26 | Wednesday | W1 | NMS-H-001 | 2526203093 | Unknown | W1 | 13 | 4 | 13 | 13/13 COMPLETE ✓ | 4 | SP1 | KVCALPPSP001 | 1428.80 | 5.715 | 7 min | 1 | 28 min | Order Total: 13 units
2025-11-26 | 2025-11-26 | Wednesday | W1 | NMS-H-001 | 2526203093 | Unknown | W1 | 13 | 4 | 13 | 13/13 COMPLETE ✓ | 4 | SP2 | KVCALPPSP002 | 1428.80 | 5.715 | 7 min | 1 | 28 min | Order Total: 13 units
2025-11-26 | 2025-11-26 | Wednesday | W1 | NMS-H-001 | 2526203093 | Unknown | W1 | 13 | 4 | 13 | 13/13 COMPLETE ✓ | 4 | SP3 | SP3CFC-NMS-H-001 | 1428.80 | 5.715 | - | 1 | - | Order Total: 13 units
2025-11-22 | 2025-11-22 | Saturday | W1 | NMS-V-003 | 2526203094 | Unknown | W1 | 10 | 1 | 2 | 2/10 (20%) | 2 | Grinding | KVCALHMGR001 | 0.00 | 0.000 | 360 min | 1 | 720 min | Order Total: 10 units
2025-11-22 | 2025-11-22 | Saturday | W1 | NMS-V-003 | 2526203094 | Unknown | W1 | 10 | 1 | 2 | 2/10 (20%) | 2 | MC1 | KVCAD40MC001 | 0.00 | 0.000 | 90 min | 1 | 180 min | Order Total: 10 units
2025-11-22 | 2025-11-22 | Saturday | W1 | NMS-V-003 | 2526203094 | Unknown | W1 | 10 | 1 | 2 | 2/10 (20%) | 2 | MC2 | KVCAD40MC001 | 0.00 | 0.000 | 90 min | 1 | 180 min | Order Total: 10 units
2025-11-22 | 2025-11-22 | Saturday | W1 | NMS-V-003 | 2526203094 | Unknown | W1 | 10 | 1 | 2 | 2/10 (20%) | 2 | MC3 | MC3CFC-NMS-H-003 | 0.00 | 0.000 | - | 0 | - | Order Total: 10 units
2025-11-22 | 2025-11-22 | Saturday | W1 | NMS-V-003 | 2526203094 | Unknown | W1 | 10 | 1 | 2 | 2/10 (20%) | 2 | SP1 | KVCALPPSP001 | 0.00 | 0.000 | 12 min | 1 | 24 min | Order Total: 10 units
2025-11-22 | 2025-11-22 | Saturday | W1 | NMS-V-003 | 2526203094 | Unknown | W1 | 10 | 1 | 2 | 2/10 (20%) | 2 | SP2 | KVCALPPSP002 | 0.00 | 0.000 | 12 min | 1 | 24 min | Order Total: 10 units
2025-11-22 | 2025-11-22 | Saturday | W1 | NMS-V-003 | 2526203094 | Unknown | W1 | 10 | 1 | 2 | 2/10 (20%) | 2 | SP3 | SP3CFC-NMS-H-003 | 0.00 | 0.000 | - | 1 | - | Order Total: 10 units
2025-11-24 | 2025-11-24 | Monday | W1 | NMS-V-003 | 2526203094 | Unknown | W1 | 10 | 2 | 4 | 4/10 (40%) | 2 | Grinding | KVCALHMGR001 | 0.00 | 0.000 | 360 min | 1 | 720 min | Order Total: 10 units
2025-11-24 | 2025-11-24 | Monday | W1 | NMS-V-003 | 2526203094 | Unknown | W1 | 10 | 2 | 4 | 4/10 (40%) | 2 | MC1 | KVCAD40MC001 | 0.00 | 0.000 | 90 min | 1 | 180 min | Order Total: 10 units
2025-11-24 | 2025-11-24 | Monday | W1 | NMS-V-003 | 2526203094 | Unknown | W1 | 10 | 2 | 4 | 4/10 (40%) | 2 | MC2 | KVCAD40MC001 | 0.00 | 0.000 | 90 min | 1 | 180 min | Order Total: 10 units
2025-11-24 | 2025-11-24 | Monday | W1 | NMS-V-003 | 2526203094 | Unknown | W1 | 10 | 2 | 4 | 4/10 (40%) | 2 | MC3 | MC3CFC-NMS-H-003 | 0.00 | 0.000 | - | 0 | - | Order Total: 10 units
2025-11-24 | 2025-11-24 | Monday | W1 | NMS-V-003 | 2526203094 | Unknown | W1 | 10 | 2 | 4 | 4/10 (40%) | 2 | SP1 | KVCALPPSP001 | 0.00 | 0.000 | 12 min | 1 | 24 min | Order Total: 10 units
2025-11-24 | 2025-11-24 | Monday | W1 | NMS-V-003 | 2526203094 | Unknown | W1 | 10 | 2 | 4 | 4/10 (40%) | 2 | SP2 | KVCALPPSP002 | 0.00 | 0.000 | 12 min | 1 | 24 min | Order Total: 10 units
2025-11-24 | 2025-11-24 | Monday | W1 | NMS-V-003 | 2526203094 | Unknown | W1 | 10 | 2 | 4 | 4/10 (40%) | 2 | SP3 | SP3CFC-NMS-H-003 | 0.00 | 0.000 | - | 1 | - | Order Total: 10 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | NMS-V-003 | 2526203094 | Unknown | W1 | 10 | 3 | 7 | 7/10 (70%) | 3 | Grinding | KVCALHMGR001 | 0.00 | 0.000 | 360 min | 1 | 1080 min | Order Total: 10 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | NMS-V-003 | 2526203094 | Unknown | W1 | 10 | 3 | 7 | 7/10 (70%) | 3 | MC1 | KVCAD40MC001 | 0.00 | 0.000 | 90 min | 1 | 270 min | Order Total: 10 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | NMS-V-003 | 2526203094 | Unknown | W1 | 10 | 3 | 7 | 7/10 (70%) | 3 | MC2 | KVCAD40MC001 | 0.00 | 0.000 | 90 min | 1 | 270 min | Order Total: 10 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | NMS-V-003 | 2526203094 | Unknown | W1 | 10 | 3 | 7 | 7/10 (70%) | 3 | MC3 | MC3CFC-NMS-H-003 | 0.00 | 0.000 | - | 0 | - | Order Total: 10 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | NMS-V-003 | 2526203094 | Unknown | W1 | 10 | 3 | 7 | 7/10 (70%) | 3 | SP1 | KVCALPPSP001 | 0.00 | 0.000 | 12 min | 1 | 36 min | Order Total: 10 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | NMS-V-003 | 2526203094 | Unknown | W1 | 10 | 3 | 7 | 7/10 (70%) | 3 | SP2 | KVCALPPSP002 | 0.00 | 0.000 | 12 min | 1 | 36 min | Order Total: 10 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | NMS-V-003 | 2526203094 | Unknown | W1 | 10 | 3 | 7 | 7/10 (70%) | 3 | SP3 | SP3CFC-NMS-H-003 | 0.00 | 0.000 | - | 1 | - | Order Total: 10 units
2025-11-26 | 2025-11-26 | Wednesday | W1 | NMS-V-003 | 2526203094 | Unknown | W1 | 10 | 4 | 10 | 10/10 COMPLETE ✓ | 3 | Grinding | KVCALHMGR001 | 0.00 | 0.000 | 360 min | 1 | 1080 min | Order Total: 10 units
2025-11-26 | 2025-11-26 | Wednesday | W1 | NMS-V-003 | 2526203094 | Unknown | W1 | 10 | 4 | 10 | 10/10 COMPLETE ✓ | 3 | MC1 | KVCAD40MC001 | 0.00 | 0.000 | 90 min | 1 | 270 min | Order Total: 10 units
2025-11-26 | 2025-11-26 | Wednesday | W1 | NMS-V-003 | 2526203094 | Unknown | W1 | 10 | 4 | 10 | 10/10 COMPLETE ✓ | 3 | MC2 | KVCAD40MC001 | 0.00 | 0.000 | 90 min | 1 | 270 min | Order Total: 10 units
2025-11-26 | 2025-11-26 | Wednesday | W1 | NMS-V-003 | 2526203094 | Unknown | W1 | 10 | 4 | 10 | 10/10 COMPLETE ✓ | 3 | MC3 | MC3CFC-NMS-H-003 | 0.00 | 0.000 | - | 0 | - | Order Total: 10 units
2025-11-26 | 2025-11-26 | Wednesday | W1 | NMS-V-003 | 2526203094 | Unknown | W1 | 10 | 4 | 10 | 10/10 COMPLETE ✓ | 3 | SP1 | KVCALPPSP001 | 0.00 | 0.000 | 12 min | 1 | 36 min | Order Total: 10 units
2025-11-26 | 2025-11-26 | Wednesday | W1 | NMS-V-003 | 2526203094 | Unknown | W1 | 10 | 4 | 10 | 10/10 COMPLETE ✓ | 3 | SP2 | KVCALPPSP002 | 0.00 | 0.000 | 12 min | 1 | 36 min | Order Total: 10 units
2025-11-26 | 2025-11-26 | Wednesday | W1 | NMS-V-003 | 2526203094 | Unknown | W1 | 10 | 4 | 10 | 10/10 COMPLETE ✓ | 3 | SP3 | SP3CFC-NMS-H-003 | 0.00 | 0.000 | - | 1 | - | Order Total: 10 units
2025-11-22 | 2025-11-22 | Saturday | W1 | LKK-10 | 2526203095 | Unknown | W4 | 6 | 1 | 2 | 2/10 (20%) | 2 | SP1 | KVCALPPSP001 | 1208.55 | 2.417 | 7 min | 1 | 14 min | Order Total: 6 units
2025-11-22 | 2025-11-22 | Saturday | W1 | LKK-10 | 2526203095 | Unknown | W4 | 4 | 2 | 4 | 4/10 (40%) | 2 | SP1 | KVCALPPSP001 | 1208.55 | 2.417 | 7 min | 1 | 14 min | Order Total: 4 units
2025-11-24 | 2025-11-24 | Monday | W1 | LKK-10 | 2526203095 | Unknown | W4 | 6 | 3 | 6 | 6/10 (60%) | 2 | SP1 | KVCALPPSP001 | 1208.55 | 2.417 | 7 min | 1 | 14 min | Order Total: 6 units
2025-11-24 | 2025-11-24 | Monday | W1 | LKK-10 | 2526203095 | Unknown | W4 | 4 | 4 | 8 | 8/10 (80%) | 2 | SP1 | KVCALPPSP001 | 1208.55 | 2.417 | 7 min | 1 | 14 min | Order Total: 4 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | LKK-10 | 2526203095 | Unknown | W4 | 6 | 5 | 10 | 10/10 COMPLETE ✓ | 2 | SP1 | KVCALPPSP001 | 1208.55 | 2.417 | 7 min | 1 | 14 min | Order Total: 6 units
2025-11-29 | 2025-11-29 | Saturday | W2 | LKK-10 | 2526203096 | Unknown | W5 | 10 | 1 | 2 | 2/10 (20%) | 2 | Casting | CS1-LKK-010 | 1208.55 | 2.417 | 22 min | 1 | 44 min | Order Total: 10 units
2025-11-29 | 2025-11-29 | Saturday | W2 | LKK-11 | 2526203096 | Unknown | W5 | 10 | 1 | 5 | 5/10 (50%) | 5 | Casting | CS1-LKK-011 | 215.73 | 1.079 | 22 min | 1 | 110 min | Order Total: 10 units
2025-11-30 | 2025-11-29 | Sunday | W2 | LKK-10 | 2526203096 | Unknown | W5 | 10 | 1 | 2 | 2/10 (20%) | 2 | Cooling/Shakeout | N/A | 1208.55 | 2.417 | - | 1 | - | Order Total: 10 units
2025-11-30 | 2025-11-29 | Sunday | W2 | LKK-11 | 2526203096 | Unknown | W5 | 10 | 1 | 2 | 2/10 (20%) | 2 | Cooling/Shakeout | N/A | 215.73 | 0.431 | - | 1 | - | Order Total: 10 units
2025-12-01 | 2025-12-01 | Monday | W2 | LKK-10 | 2526203096 | Unknown | W5 | 10 | 2 | 4 | 4/10 (40%) | 2 | Casting | CS1-LKK-010 | 1208.55 | 2.417 | 22 min | 1 | 44 min | Order Total: 10 units
2025-12-01 | 2025-12-01 | Monday | W2 | LKK-11 | 2526203096 | Unknown | W5 | 10 | 2 | 10 | 10/10 COMPLETE ✓ | 5 | Casting | CS1-LKK-011 | 215.73 | 1.079 | 22 min | 1 | 110 min | Order Total: 10 units
2025-12-02 | 2025-12-02 | Tuesday | W2 | LKK-10 | 2526203096 | Unknown | W5 | 10 | 3 | 7 | 7/10 (70%) | 3 | Casting | CS1-LKK-010 | 1208.55 | 3.626 | 22 min | 1 | 66 min | Order Total: 10 units
2025-12-02 | 2025-12-01 | Tuesday | W2 | LKK-10 | 2526203096 | Unknown | W5 | 10 | 2 | 4 | 4/10 (40%) | 2 | Cooling/Shakeout | N/A | 1208.55 | 2.417 | - | 1 | - | Order Total: 10 units
2025-12-02 | 2025-12-01 | Tuesday | W2 | LKK-11 | 2526203096 | Unknown | W5 | 10 | 2 | 4 | 4/10 (40%) | 2 | Cooling/Shakeout | N/A | 215.73 | 0.431 | - | 1 | - | Order Total: 10 units
2025-12-03 | 2025-12-03 | Wednesday | W2 | LKK-10 | 2526203096 | Unknown | W5 | 10 | 4 | 10 | 10/10 COMPLETE ✓ | 3 | Casting | CS1-LKK-010 | 1208.55 | 3.626 | 22 min | 1 | 66 min | Order Total: 10 units
2025-12-03 | 2025-12-02 | Wednesday | W2 | LKK-10 | 2526203096 | Unknown | W5 | 10 | 3 | 7 | 7/10 (70%) | 3 | Cooling/Shakeout | N/A | 1208.55 | 3.626 | - | 1 | - | Order Total: 10 units
2025-12-03 | 2025-11-29 | Wednesday | W2 | LKK-11 | 2526203096 | Unknown | W5 | 10 | 3 | 7 | 7/10 (70%) | 3 | Cooling/Shakeout | N/A | 215.73 | 0.647 | - | 1 | - | Order Total: 10 units
2025-12-04 | 2025-12-03 | Thursday | W2 | LKK-10 | 2526203096 | Unknown | W5 | 10 | 4 | 10 | 10/10 COMPLETE ✓ | 3 | Cooling/Shakeout | N/A | 1208.55 | 3.626 | - | 1 | - | Order Total: 10 units
2025-12-04 | 2025-11-29 | Thursday | W2 | LKK-11 | 2526203096 | Unknown | W5 | 10 | 4 | 10 | 10/10 COMPLETE ✓ | 3 | Cooling/Shakeout | N/A | 215.73 | 0.647 | - | 1 | - | Order Total: 10 units
2025-12-06 | 2025-12-06 | Saturday | W3 | LKK-12 | 2526203096 | Unknown | W5 | 10 | 1 | 5 | 5/10 (50%) | 5 | Casting | CS1-LKK-012 | 208.39 | 1.042 | 22 min | 1 | 110 min | Order Total: 10 units
2025-12-07 | 2025-12-06 | Sunday | W3 | LKK-12 | 2526203096 | Unknown | W5 | 10 | 1 | 2 | 2/10 (20%) | 2 | Cooling/Shakeout | N/A | 208.39 | 0.417 | - | 1 | - | Order Total: 10 units
2025-12-08 | 2025-12-08 | Monday | W3 | LKK-12 | 2526203096 | Unknown | W5 | 10 | 2 | 10 | 10/10 COMPLETE ✓ | 5 | Casting | CS1-LKK-012 | 208.39 | 1.042 | 22 min | 1 | 110 min | Order Total: 10 units
2025-12-09 | 2025-12-08 | Tuesday | W3 | LKK-12 | 2526203096 | Unknown | W5 | 10 | 2 | 4 | 4/10 (40%) | 2 | Cooling/Shakeout | N/A | 208.39 | 0.417 | - | 1 | - | Order Total: 10 units
2025-12-10 | 2025-12-06 | Wednesday | W3 | LKK-12 | 2526203096 | Unknown | W5 | 10 | 3 | 7 | 7/10 (70%) | 3 | Cooling/Shakeout | N/A | 208.39 | 0.625 | - | 1 | - | Order Total: 10 units
2025-12-11 | 2025-12-06 | Thursday | W3 | LKK-12 | 2526203096 | Unknown | W5 | 10 | 4 | 10 | 10/10 COMPLETE ✓ | 3 | Cooling/Shakeout | N/A | 208.39 | 0.625 | - | 1 | - | Order Total: 10 units
2025-12-13 | 2025-11-29 | Saturday | W4 | LKK-11 | 2526203096 | Unknown | W5 | 10 | 1 | 2 | 2/10 (20%) | 2 | Grinding | KVCALHMGR001 | 215.73 | 0.431 | 70 min | 1 | 140 min | Order Total: 10 units
2025-12-13 | 2025-11-29 | Saturday | W4 | LKK-10 | 2526203096 | Unknown | W5 | 10 | 1 | 2 | 2/10 (20%) | 2 | SP1 | KVCALPPSP001 | 1208.55 | 2.417 | 7 min | 1 | 14 min | Order Total: 10 units
2025-12-15 | 2025-12-01 | Monday | W4 | LKK-11 | 2526203096 | Unknown | W5 | 10 | 2 | 4 | 4/10 (40%) | 2 | Grinding | KVCALHMGR001 | 215.73 | 0.431 | 70 min | 1 | 140 min | Order Total: 10 units
2025-12-15 | 2025-12-01 | Monday | W4 | LKK-10 | 2526203096 | Unknown | W5 | 10 | 2 | 4 | 4/10 (40%) | 2 | SP1 | KVCALPPSP001 | 1208.55 | 2.417 | 7 min | 1 | 14 min | Order Total: 10 units
2025-12-16 | 2025-11-29 | Tuesday | W4 | LKK-11 | 2526203096 | Unknown | W5 | 10 | 3 | 7 | 7/10 (70%) | 3 | Grinding | KVCALHMGR001 | 215.73 | 0.647 | 70 min | 1 | 210 min | Order Total: 10 units
2025-12-16 | 2025-12-02 | Tuesday | W4 | LKK-10 | 2526203096 | Unknown | W5 | 10 | 3 | 7 | 7/10 (70%) | 3 | SP1 | KVCALPPSP001 | 1208.55 | 3.626 | 7 min | 1 | 21 min | Order Total: 10 units
2025-12-17 | 2025-11-29 | Wednesday | W4 | LKK-11 | 2526203096 | Unknown | W5 | 10 | 4 | 10 | 10/10 COMPLETE ✓ | 3 | Grinding | KVCALHMGR001 | 215.73 | 0.647 | 70 min | 1 | 210 min | Order Total: 10 units
2025-12-17 | 2025-12-03 | Wednesday | W4 | LKK-10 | 2526203096 | Unknown | W5 | 10 | 4 | 10 | 10/10 COMPLETE ✓ | 3 | SP1 | KVCALPPSP001 | 1208.55 | 3.626 | 7 min | 1 | 21 min | Order Total: 10 units
2025-11-29 | 2025-11-29 | Saturday | W2 | LKK-10 | 2526203097 | Unknown | W5 | 10 | 1 | 2 | 2/10 (20%) | 2 | Casting | CS1-LKK-010 | 1208.55 | 2.417 | 22 min | 1 | 44 min | Order Total: 10 units
2025-11-29 | 2025-11-29 | Saturday | W2 | LKK-11 | 2526203097 | Unknown | W5 | 10 | 1 | 5 | 5/10 (50%) | 5 | Casting | CS1-LKK-011 | 215.73 | 1.079 | 22 min | 1 | 110 min | Order Total: 10 units
2025-11-30 | 2025-11-29 | Sunday | W2 | LKK-10 | 2526203097 | Unknown | W5 | 10 | 1 | 2 | 2/10 (20%) | 2 | Cooling/Shakeout | N/A | 1208.55 | 2.417 | - | 1 | - | Order Total: 10 units
2025-11-30 | 2025-11-29 | Sunday | W2 | LKK-11 | 2526203097 | Unknown | W5 | 10 | 1 | 2 | 2/10 (20%) | 2 | Cooling/Shakeout | N/A | 215.73 | 0.431 | - | 1 | - | Order Total: 10 units
2025-12-01 | 2025-12-01 | Monday | W2 | LKK-10 | 2526203097 | Unknown | W5 | 10 | 2 | 4 | 4/10 (40%) | 2 | Casting | CS1-LKK-010 | 1208.55 | 2.417 | 22 min | 1 | 44 min | Order Total: 10 units
2025-12-01 | 2025-12-01 | Monday | W2 | LKK-11 | 2526203097 | Unknown | W5 | 10 | 2 | 10 | 10/10 COMPLETE ✓ | 5 | Casting | CS1-LKK-011 | 215.73 | 1.079 | 22 min | 1 | 110 min | Order Total: 10 units
2025-12-02 | 2025-12-02 | Tuesday | W2 | LKK-10 | 2526203097 | Unknown | W5 | 10 | 3 | 7 | 7/10 (70%) | 3 | Casting | CS1-LKK-010 | 1208.55 | 3.626 | 22 min | 1 | 66 min | Order Total: 10 units
2025-12-02 | 2025-12-01 | Tuesday | W2 | LKK-10 | 2526203097 | Unknown | W5 | 10 | 2 | 4 | 4/10 (40%) | 2 | Cooling/Shakeout | N/A | 1208.55 | 2.417 | - | 1 | - | Order Total: 10 units
2025-12-02 | 2025-12-01 | Tuesday | W2 | LKK-11 | 2526203097 | Unknown | W5 | 10 | 2 | 4 | 4/10 (40%) | 2 | Cooling/Shakeout | N/A | 215.73 | 0.431 | - | 1 | - | Order Total: 10 units
2025-12-03 | 2025-12-03 | Wednesday | W2 | LKK-10 | 2526203097 | Unknown | W5 | 10 | 4 | 10 | 10/10 COMPLETE ✓ | 3 | Casting | CS1-LKK-010 | 1208.55 | 3.626 | 22 min | 1 | 66 min | Order Total: 10 units
2025-12-03 | 2025-12-02 | Wednesday | W2 | LKK-10 | 2526203097 | Unknown | W5 | 10 | 3 | 7 | 7/10 (70%) | 3 | Cooling/Shakeout | N/A | 1208.55 | 3.626 | - | 1 | - | Order Total: 10 units
2025-12-03 | 2025-11-29 | Wednesday | W2 | LKK-11 | 2526203097 | Unknown | W5 | 10 | 3 | 7 | 7/10 (70%) | 3 | Cooling/Shakeout | N/A | 215.73 | 0.647 | - | 1 | - | Order Total: 10 units
2025-12-04 | 2025-12-03 | Thursday | W2 | LKK-10 | 2526203097 | Unknown | W5 | 10 | 4 | 10 | 10/10 COMPLETE ✓ | 3 | Cooling/Shakeout | N/A | 1208.55 | 3.626 | - | 1 | - | Order Total: 10 units
2025-12-04 | 2025-11-29 | Thursday | W2 | LKK-11 | 2526203097 | Unknown | W5 | 10 | 4 | 10 | 10/10 COMPLETE ✓ | 3 | Cooling/Shakeout | N/A | 215.73 | 0.647 | - | 1 | - | Order Total: 10 units
2025-12-06 | 2025-12-06 | Saturday | W3 | LKK-12 | 2526203097 | Unknown | W5 | 10 | 1 | 5 | 5/10 (50%) | 5 | Casting | CS1-LKK-012 | 208.39 | 1.042 | 22 min | 1 | 110 min | Order Total: 10 units
2025-12-07 | 2025-12-06 | Sunday | W3 | LKK-12 | 2526203097 | Unknown | W5 | 10 | 1 | 2 | 2/10 (20%) | 2 | Cooling/Shakeout | N/A | 208.39 | 0.417 | - | 1 | - | Order Total: 10 units
2025-12-08 | 2025-12-08 | Monday | W3 | LKK-12 | 2526203097 | Unknown | W5 | 10 | 2 | 10 | 10/10 COMPLETE ✓ | 5 | Casting | CS1-LKK-012 | 208.39 | 1.042 | 22 min | 1 | 110 min | Order Total: 10 units
2025-12-09 | 2025-12-08 | Tuesday | W3 | LKK-12 | 2526203097 | Unknown | W5 | 10 | 2 | 4 | 4/10 (40%) | 2 | Cooling/Shakeout | N/A | 208.39 | 0.417 | - | 1 | - | Order Total: 10 units
2025-12-10 | 2025-12-06 | Wednesday | W3 | LKK-12 | 2526203097 | Unknown | W5 | 10 | 3 | 7 | 7/10 (70%) | 3 | Cooling/Shakeout | N/A | 208.39 | 0.625 | - | 1 | - | Order Total: 10 units
2025-12-11 | 2025-12-06 | Thursday | W3 | LKK-12 | 2526203097 | Unknown | W5 | 10 | 4 | 10 | 10/10 COMPLETE ✓ | 3 | Cooling/Shakeout | N/A | 208.39 | 0.625 | - | 1 | - | Order Total: 10 units
2025-12-13 | 2025-11-29 | Saturday | W4 | LKK-11 | 2526203097 | Unknown | W5 | 10 | 1 | 2 | 2/10 (20%) | 2 | Grinding | KVCALHMGR001 | 215.73 | 0.431 | 70 min | 1 | 140 min | Order Total: 10 units
2025-12-13 | 2025-11-29 | Saturday | W4 | LKK-10 | 2526203097 | Unknown | W5 | 10 | 1 | 2 | 2/10 (20%) | 2 | SP1 | KVCALPPSP001 | 1208.55 | 2.417 | 7 min | 1 | 14 min | Order Total: 10 units
2025-12-15 | 2025-12-01 | Monday | W4 | LKK-11 | 2526203097 | Unknown | W5 | 10 | 2 | 4 | 4/10 (40%) | 2 | Grinding | KVCALHMGR001 | 215.73 | 0.431 | 70 min | 1 | 140 min | Order Total: 10 units
2025-12-15 | 2025-12-01 | Monday | W4 | LKK-10 | 2526203097 | Unknown | W5 | 10 | 2 | 4 | 4/10 (40%) | 2 | SP1 | KVCALPPSP001 | 1208.55 | 2.417 | 7 min | 1 | 14 min | Order Total: 10 units
2025-12-16 | 2025-11-29 | Tuesday | W4 | LKK-11 | 2526203097 | Unknown | W5 | 10 | 3 | 7 | 7/10 (70%) | 3 | Grinding | KVCALHMGR001 | 215.73 | 0.647 | 70 min | 1 | 210 min | Order Total: 10 units
2025-12-16 | 2025-12-02 | Tuesday | W4 | LKK-10 | 2526203097 | Unknown | W5 | 10 | 3 | 7 | 7/10 (70%) | 3 | SP1 | KVCALPPSP001 | 1208.55 | 3.626 | 7 min | 1 | 21 min | Order Total: 10 units
2025-12-17 | 2025-11-29 | Wednesday | W4 | LKK-11 | 2526203097 | Unknown | W5 | 10 | 4 | 10 | 10/10 COMPLETE ✓ | 3 | Grinding | KVCALHMGR001 | 215.73 | 0.647 | 70 min | 1 | 210 min | Order Total: 10 units
2025-12-17 | 2025-12-03 | Wednesday | W4 | LKK-10 | 2526203097 | Unknown | W5 | 10 | 4 | 10 | 10/10 COMPLETE ✓ | 3 | SP1 | KVCALPPSP001 | 1208.55 | 3.626 | 7 min | 1 | 21 min | Order Total: 10 units
2025-12-13 | 2025-12-13 | Saturday | W4 | LKK-11 | 2526203098 | Unknown | W6 | 10 | 1 | 4 | 4/10 (40%) | 4 | MC1 | KVCAD50MC001 | 215.73 | 0.863 | 35 min | 3 | 70 min | Order Total: 10 units
2025-12-15 | 2025-12-15 | Monday | W4 | LKK-11 | 2526203098 | Unknown | W6 | 10 | 2 | 10 | 10/10 COMPLETE ✓ | 6 | MC1 | KVCAD50MC001 | 215.73 | 1.294 | 35 min | 3 | 70 min | Order Total: 10 units
2025-12-20 | 2025-12-20 | Saturday | W5 | LKK-12 | 2526203098 | Unknown | W6 | 10 | 1 | 2 | 2/10 (20%) | 2 | Grinding | KVCALHMGR001 | 208.39 | 0.417 | 70 min | 1 | 140 min | Order Total: 10 units
2025-12-22 | 2025-12-22 | Monday | W5 | LKK-12 | 2526203098 | Unknown | W6 | 10 | 2 | 4 | 4/10 (40%) | 2 | Grinding | KVCALHMGR001 | 208.39 | 0.417 | 70 min | 1 | 140 min | Order Total: 10 units
2025-12-23 | 2025-12-23 | Tuesday | W5 | LKK-12 | 2526203098 | Unknown | W6 | 10 | 3 | 7 | 7/10 (70%) | 3 | Grinding | KVCALHMGR001 | 208.39 | 0.625 | 70 min | 1 | 210 min | Order Total: 10 units
2025-12-24 | 2025-12-24 | Wednesday | W5 | LKK-12 | 2526203098 | Unknown | W6 | 10 | 4 | 10 | 10/10 COMPLETE ✓ | 3 | Grinding | KVCALHMGR001 | 208.39 | 0.625 | 70 min | 1 | 210 min | Order Total: 10 units
2025-11-22 | 2025-11-22 | Saturday | W1 | LKK-03 | 2526203099 | Unknown | W7 | 4 | 1 | 2 | 2/4 (50%) | 2 | Grinding | KVCALHMGR001 | 1618.80 | 3.238 | 240 min | 1 | 480 min | Order Total: 4 units
2025-11-22 | 2025-12-13 | Saturday | W1 | LKK-01 | 2526203099 | Unknown | W7 | 4 | 1 | 2 | 2/4 (50%) | 2 | Grinding | KVCALHMGR001 | 199.66 | 0.399 | 70 min | 1 | 140 min | Order Total: 4 units
2025-11-22 | 2025-11-22 | Saturday | W1 | LKK-03 | 2526203099 | Unknown | W7 | 4 | 1 | 2 | 2/4 (50%) | 2 | SP1 | KVCALPPSP001 | 1618.80 | 3.238 | 12 min | 1 | 24 min | Order Total: 4 units
2025-11-24 | 2025-11-24 | Monday | W1 | LKK-03 | 2526203099 | Unknown | W7 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | Grinding | KVCALHMGR001 | 1618.80 | 3.238 | 240 min | 1 | 480 min | Order Total: 4 units
2025-11-24 | 2025-12-13 | Monday | W1 | LKK-01 | 2526203099 | Unknown | W7 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | Grinding | KVCALHMGR001 | 199.66 | 0.399 | 70 min | 1 | 140 min | Order Total: 4 units
2025-11-24 | 2025-11-24 | Monday | W1 | LKK-03 | 2526203099 | Unknown | W7 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | SP1 | KVCALPPSP001 | 1618.80 | 3.238 | 12 min | 1 | 24 min | Order Total: 4 units
2025-11-29 | 2025-11-29 | Saturday | W2 | LKK-11 | 2526203099 | Unknown | W7 | 4 | 1 | 4 | 4/4 COMPLETE ✓ | 4 | Casting | CS1-LKK-011 | 215.73 | 0.863 | 22 min | 1 | 88 min | Order Total: 4 units
2025-11-29 | 2025-12-13 | Saturday | W2 | LKK-01 | 2526203099 | Unknown | W7 | 4 | 1 | 2 | 2/4 (50%) | 2 | MC1 | KVCAD50MC001 | 199.66 | 0.399 | 30 min | 0 | - | Order Total: 4 units
2025-11-30 | 2025-11-29 | Sunday | W2 | LKK-11 | 2526203099 | Unknown | W7 | 4 | 1 | 2 | 2/4 (50%) | 2 | Cooling/Shakeout | N/A | 215.73 | 0.431 | - | 1 | - | Order Total: 4 units
2025-12-01 | 2025-12-13 | Monday | W2 | LKK-01 | 2526203099 | Unknown | W7 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | MC1 | KVCAD50MC001 | 199.66 | 0.399 | 30 min | 0 | - | Order Total: 4 units
2025-12-02 | 2025-11-29 | Tuesday | W2 | LKK-11 | 2526203099 | Unknown | W7 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | Cooling/Shakeout | N/A | 215.73 | 0.431 | - | 1 | - | Order Total: 4 units
2025-12-06 | 2025-12-06 | Saturday | W3 | LKK-12 | 2526203099 | Unknown | W7 | 4 | 1 | 4 | 4/4 COMPLETE ✓ | 4 | Casting | CS1-LKK-012 | 208.39 | 0.834 | 22 min | 1 | 88 min | Order Total: 4 units
2025-12-06 | 2025-12-06 | Saturday | W3 | LKK-12 | 2526203099 | Unknown | W7 | 4 | 1 | 3 | 3/4 (75%) | 3 | MC1 | KVCAD50MC001 | 208.39 | 0.625 | 35 min | 3 | 35 min | Order Total: 4 units
2025-12-06 | 2025-12-06 | Saturday | W3 | LKK-12 | 2526203099 | Unknown | W7 | 4 | 1 | 2 | 2/4 (50%) | 2 | SP1 | KVCALPPSP001 | 208.39 | 0.417 | 7 min | 1 | 14 min | Order Total: 4 units
2025-12-07 | 2025-12-06 | Sunday | W3 | LKK-12 | 2526203099 | Unknown | W7 | 4 | 1 | 2 | 2/4 (50%) | 2 | Cooling/Shakeout | N/A | 208.39 | 0.417 | - | 1 | - | Order Total: 4 units
2025-12-08 | 2025-12-06 | Monday | W3 | LKK-12 | 2526203099 | Unknown | W7 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 1 | MC1 | KVCAD50MC001 | 208.39 | 0.208 | 35 min | 3 | 35 min | Order Total: 4 units
2025-12-08 | 2025-12-06 | Monday | W3 | LKK-12 | 2526203099 | Unknown | W7 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | SP1 | KVCALPPSP001 | 208.39 | 0.417 | 7 min | 1 | 14 min | Order Total: 4 units
2025-12-09 | 2025-12-06 | Tuesday | W3 | LKK-12 | 2526203099 | Unknown | W7 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | Cooling/Shakeout | N/A | 208.39 | 0.417 | - | 1 | - | Order Total: 4 units
2025-12-13 | 2025-12-13 | Saturday | W4 | LKK-01 | 2526203099 | Unknown | W7 | 4 | 1 | 4 | 4/4 COMPLETE ✓ | 4 | Casting | CS1-LKK-001 | 199.66 | 0.799 | 22 min | 1 | 88 min | Order Total: 4 units
2025-12-13 | 2025-12-13 | Saturday | W4 | LKK-10 | 2526203099 | Unknown | W7 | 4 | 1 | 2 | 2/4 (50%) | 2 | Grinding | KVCALHMGR001 | 1208.55 | 2.417 | 240 min | 1 | 480 min | Order Total: 4 units
2025-12-13 | 2025-12-13 | Saturday | W4 | LKK-02 | 2526203099 | Unknown | W7 | 4 | 1 | 2 | 2/4 (50%) | 2 | Grinding | KVCALHMGR001 | 193.60 | 0.387 | 70 min | 1 | 140 min | Order Total: 4 units
2025-12-13 | 2025-11-29 | Saturday | W4 | LKK-11 | 2526203099 | Unknown | W7 | 4 | 1 | 2 | 2/4 (50%) | 2 | SP1 | KVCALPPSP001 | 215.73 | 0.431 | 7 min | 1 | 14 min | Order Total: 4 units
2025-12-14 | 2025-12-13 | Sunday | W4 | LKK-01 | 2526203099 | Unknown | W7 | 4 | 1 | 2 | 2/4 (50%) | 2 | Cooling/Shakeout | N/A | 199.66 | 0.399 | - | 1 | - | Order Total: 4 units
2025-12-15 | 2025-12-15 | Monday | W4 | LKK-10 | 2526203099 | Unknown | W7 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | Grinding | KVCALHMGR001 | 1208.55 | 2.417 | 240 min | 1 | 480 min | Order Total: 4 units
2025-12-15 | 2025-12-15 | Monday | W4 | LKK-02 | 2526203099 | Unknown | W7 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | Grinding | KVCALHMGR001 | 193.60 | 0.387 | 70 min | 1 | 140 min | Order Total: 4 units
2025-12-15 | 2025-11-29 | Monday | W4 | LKK-11 | 2526203099 | Unknown | W7 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | SP1 | KVCALPPSP001 | 215.73 | 0.431 | 7 min | 1 | 14 min | Order Total: 4 units
2025-12-16 | 2025-12-13 | Tuesday | W4 | LKK-01 | 2526203099 | Unknown | W7 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | Cooling/Shakeout | N/A | 199.66 | 0.399 | - | 1 | - | Order Total: 4 units
2025-12-20 | 2025-12-13 | Saturday | W5 | LKK-01 | 2526203099 | Unknown | W7 | 4 | 1 | 2 | 2/4 (50%) | 2 | SP1 | KVCALPPSP001 | 199.66 | 0.399 | 7 min | 1 | 14 min | Order Total: 4 units
2025-12-22 | 2025-12-13 | Monday | W5 | LKK-01 | 2526203099 | Unknown | W7 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | SP1 | KVCALPPSP001 | 199.66 | 0.399 | 7 min | 1 | 14 min | Order Total: 4 units
2025-11-22 | 2025-12-06 | Saturday | W1 | NMS-V-004 | 2526203103 | Unknown | W6 | 5 | 1 | 2 | 2/5 (40%) | 2 | MC1 | KVCABM2MC001 | 0.00 | 0.000 | 120 min | 1 | 240 min | Order Total: 5 units
2025-11-22 | 2025-12-06 | Saturday | W1 | NMS-V-004 | 2526203103 | Unknown | W6 | 5 | 1 | 2 | 2/5 (40%) | 2 | MC2 | KVCAD30MC001 | 0.00 | 0.000 | 180 min | 1 | 360 min | Order Total: 5 units
2025-11-22 | 2025-12-06 | Saturday | W1 | NMS-V-004 | 2526203103 | Unknown | W6 | 5 | 1 | 2 | 2/5 (40%) | 2 | MC3 | KVCAD40MC001 | 0.00 | 0.000 | 40 min | 1 | 80 min | Order Total: 5 units
2025-11-22 | 2025-12-06 | Saturday | W1 | NMS-V-004 | 2526203103 | Unknown | W6 | 5 | 1 | 2 | 2/5 (40%) | 2 | SP1 | KVCALPPSP001 | 0.00 | 0.000 | 12 min | 1 | 24 min | Order Total: 5 units
2025-11-22 | 2025-12-06 | Saturday | W1 | NMS-V-004 | 2526203103 | Unknown | W6 | 5 | 1 | 2 | 2/5 (40%) | 2 | SP2 | KVCALPPSP002 | 0.00 | 0.000 | 12 min | 1 | 24 min | Order Total: 5 units
2025-11-22 | 2025-12-06 | Saturday | W1 | NMS-V-004 | 2526203103 | Unknown | W6 | 5 | 1 | 2 | 2/5 (40%) | 2 | SP3 | SP3CFC-NMS-H-004 | 0.00 | 0.000 | - | 0 | - | Order Total: 5 units
2025-11-24 | 2025-12-08 | Monday | W1 | NMS-V-004 | 2526203103 | Unknown | W6 | 5 | 2 | 5 | 5/5 COMPLETE ✓ | 3 | MC1 | KVCABM2MC001 | 0.00 | 0.000 | 120 min | 1 | 360 min | Order Total: 5 units
2025-11-24 | 2025-12-08 | Monday | W1 | NMS-V-004 | 2526203103 | Unknown | W6 | 5 | 2 | 5 | 5/5 COMPLETE ✓ | 3 | MC2 | KVCAD30MC001 | 0.00 | 0.000 | 180 min | 1 | 540 min | Order Total: 5 units
2025-11-24 | 2025-12-08 | Monday | W1 | NMS-V-004 | 2526203103 | Unknown | W6 | 5 | 2 | 5 | 5/5 COMPLETE ✓ | 3 | MC3 | KVCAD40MC001 | 0.00 | 0.000 | 40 min | 1 | 120 min | Order Total: 5 units
2025-11-24 | 2025-12-08 | Monday | W1 | NMS-V-004 | 2526203103 | Unknown | W6 | 5 | 2 | 5 | 5/5 COMPLETE ✓ | 3 | SP1 | KVCALPPSP001 | 0.00 | 0.000 | 12 min | 1 | 36 min | Order Total: 5 units
2025-11-24 | 2025-12-08 | Monday | W1 | NMS-V-004 | 2526203103 | Unknown | W6 | 5 | 2 | 5 | 5/5 COMPLETE ✓ | 3 | SP2 | KVCALPPSP002 | 0.00 | 0.000 | 12 min | 1 | 36 min | Order Total: 5 units
2025-11-24 | 2025-12-08 | Monday | W1 | NMS-V-004 | 2526203103 | Unknown | W6 | 5 | 2 | 5 | 5/5 COMPLETE ✓ | 3 | SP3 | SP3CFC-NMS-H-004 | 0.00 | 0.000 | - | 0 | - | Order Total: 5 units
2025-12-06 | 2025-12-06 | Saturday | W3 | NMS-V-004 | 2526203103 | Unknown | W6 | 5 | 1 | 2 | 2/5 (40%) | 2 | Casting | CS3CFC-NMS-H-004 | 0.00 | 0.000 | 20 min | 1 | 40 min | Order Total: 5 units
2025-12-07 | 2025-12-06 | Sunday | W3 | NMS-V-004 | 2526203103 | Unknown | W6 | 5 | 1 | 2 | 2/5 (40%) | 2 | Cooling/Shakeout | N/A | 0.00 | 0.000 | - | 1 | - | Order Total: 5 units
2025-12-08 | 2025-12-08 | Monday | W3 | NMS-V-004 | 2526203103 | Unknown | W6 | 5 | 2 | 5 | 5/5 COMPLETE ✓ | 3 | Casting | CS3CFC-NMS-H-004 | 0.00 | 0.000 | 20 min | 1 | 60 min | Order Total: 5 units
2025-12-09 | 2025-12-08 | Tuesday | W3 | NMS-V-004 | 2526203103 | Unknown | W6 | 5 | 2 | 5 | 5/5 COMPLETE ✓ | 3 | Cooling/Shakeout | N/A | 0.00 | 0.000 | - | 1 | - | Order Total: 5 units
2025-11-29 | 2025-11-29 | Saturday | W2 | MCB-009 | 2526203138 | Unknown | W2 | 12 | 1 | 3 | 3/12 (25%) | 3 | SP1 | KVCALPPSP001 | 1500.00 | 4.500 | 7 min | 1 | 21 min | Order Total: 12 units
2025-12-01 | 2025-12-01 | Monday | W2 | MCB-009 | 2526203138 | Unknown | W2 | 12 | 2 | 6 | 6/12 (50%) | 3 | SP1 | KVCALPPSP001 | 1500.00 | 4.500 | 7 min | 1 | 21 min | Order Total: 12 units
2025-12-02 | 2025-12-02 | Tuesday | W2 | MCB-009 | 2526203138 | Unknown | W2 | 12 | 3 | 9 | 9/12 (75%) | 3 | SP1 | KVCALPPSP001 | 1500.00 | 4.500 | 7 min | 1 | 21 min | Order Total: 12 units
2025-12-03 | 2025-12-03 | Wednesday | W2 | MCB-009 | 2526203138 | Unknown | W2 | 12 | 4 | 12 | 12/12 COMPLETE ✓ | 3 | SP1 | KVCALPPSP001 | 1500.00 | 4.500 | 7 min | 1 | 21 min | Order Total: 12 units
2025-12-20 | 2025-12-20 | Saturday | W5 | MCB-009 | 2526203138 | Unknown | W2 | 12 | 1 | 3 | 3/12 (25%) | 3 | MC1 | KVCAD50MC001 | 1500.00 | 4.500 | 100 min | 0 | - | Order Total: 12 units
2025-12-22 | 2025-12-22 | Monday | W5 | MCB-009 | 2526203138 | Unknown | W2 | 12 | 2 | 6 | 6/12 (50%) | 3 | MC1 | KVCAD50MC001 | 1500.00 | 4.500 | 100 min | 0 | - | Order Total: 12 units
2025-12-23 | 2025-12-23 | Tuesday | W5 | MCB-009 | 2526203138 | Unknown | W2 | 12 | 3 | 9 | 9/12 (75%) | 3 | MC1 | KVCAD50MC001 | 1500.00 | 4.500 | 100 min | 0 | - | Order Total: 12 units
2025-12-24 | 2025-12-24 | Wednesday | W5 | MCB-009 | 2526203138 | Unknown | W2 | 12 | 4 | 12 | 12/12 COMPLETE ✓ | 3 | MC1 | KVCAD50MC001 | 1500.00 | 4.500 | 100 min | 0 | - | Order Total: 12 units
2025-11-22 | 2025-11-22 | Saturday | W1 | MCB-009 | 2526203139 | Unknown | W1 | 6 | 1 | 2 | 2/6 (33%) | 2 | SP1 | KVCALPPSP001 | 1500.00 | 3.000 | 7 min | 1 | 14 min | Order Total: 6 units
2025-11-24 | 2025-11-24 | Monday | W1 | MCB-009 | 2526203139 | Unknown | W1 | 6 | 2 | 4 | 4/6 (66%) | 2 | SP1 | KVCALPPSP001 | 1500.00 | 3.000 | 7 min | 1 | 14 min | Order Total: 6 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | MCB-009 | 2526203139 | Unknown | W1 | 6 | 3 | 6 | 6/6 COMPLETE ✓ | 2 | SP1 | KVCALPPSP001 | 1500.00 | 3.000 | 7 min | 1 | 14 min | Order Total: 6 units
2025-12-06 | 2025-12-13 | Saturday | W3 | MCB-JLG-047 | 2526203140 | Unknown | W2 | 11 | 1 | 2 | 2/11 (18%) | 2 | Grinding | KVCALHMGR001 | 1592.40 | 3.185 | 390 min | 1 | 780 min | Order Total: 11 units
2025-12-08 | 2025-12-15 | Monday | W3 | MCB-JLG-047 | 2526203140 | Unknown | W2 | 11 | 2 | 5 | 5/11 (45%) | 3 | Grinding | KVCALHMGR001 | 1592.40 | 4.777 | 390 min | 1 | 1170 min | Order Total: 11 units
2025-12-09 | 2025-12-13 | Tuesday | W3 | MCB-JLG-047 | 2526203140 | Unknown | W2 | 11 | 3 | 8 | 8/11 (72%) | 3 | Grinding | KVCALHMGR001 | 1592.40 | 4.777 | 390 min | 1 | 1170 min | Order Total: 11 units
2025-12-10 | 2025-12-13 | Wednesday | W3 | MCB-JLG-047 | 2526203140 | Unknown | W2 | 11 | 4 | 11 | 11/11 COMPLETE ✓ | 3 | Grinding | KVCALHMGR001 | 1592.40 | 4.777 | 390 min | 1 | 1170 min | Order Total: 11 units
2025-12-13 | 2025-12-13 | Saturday | W4 | MCB-JLG-047 | 2526203140 | Unknown | W2 | 11 | 1 | 5 | 5/11 (45%) | 5 | Casting | CS1-MCB-JLG-047 | 1592.40 | 7.962 | 25 min | 1 | 125 min | Order Total: 11 units
2025-12-13 | 2025-12-13 | Saturday | W4 | MCB-JLG-047 | 2526203140 | Unknown | W2 | 11 | 1 | 2 | 2/11 (18%) | 2 | MC1 | KVCAD50MC001 | 1592.40 | 3.185 | 40 min | 1 | 80 min | Order Total: 11 units
2025-12-14 | 2025-12-13 | Sunday | W4 | MCB-JLG-047 | 2526203140 | Unknown | W2 | 11 | 1 | 2 | 2/11 (18%) | 2 | Cooling/Shakeout | N/A | 1592.40 | 3.185 | - | 1 | - | Order Total: 11 units
2025-12-15 | 2025-12-15 | Monday | W4 | MCB-JLG-047 | 2526203140 | Unknown | W2 | 11 | 2 | 11 | 11/11 COMPLETE ✓ | 6 | Casting | CS1-MCB-JLG-047 | 1592.40 | 9.554 | 25 min | 1 | 150 min | Order Total: 11 units
2025-12-15 | 2025-12-15 | Monday | W4 | MCB-JLG-047 | 2526203140 | Unknown | W2 | 11 | 2 | 5 | 5/11 (45%) | 3 | MC1 | KVCAD50MC001 | 1592.40 | 4.777 | 40 min | 1 | 120 min | Order Total: 11 units
2025-12-16 | 2025-12-15 | Tuesday | W4 | MCB-JLG-047 | 2526203140 | Unknown | W2 | 11 | 2 | 5 | 5/11 (45%) | 3 | Cooling/Shakeout | N/A | 1592.40 | 4.777 | - | 1 | - | Order Total: 11 units
2025-12-16 | 2025-12-13 | Tuesday | W4 | MCB-JLG-047 | 2526203140 | Unknown | W2 | 11 | 3 | 8 | 8/11 (72%) | 3 | MC1 | KVCAD50MC001 | 1592.40 | 4.777 | 40 min | 1 | 120 min | Order Total: 11 units
2025-12-17 | 2025-12-13 | Wednesday | W4 | MCB-JLG-047 | 2526203140 | Unknown | W2 | 11 | 3 | 8 | 8/11 (72%) | 3 | Cooling/Shakeout | N/A | 1592.40 | 4.777 | - | 1 | - | Order Total: 11 units
2025-12-17 | 2025-12-13 | Wednesday | W4 | MCB-JLG-047 | 2526203140 | Unknown | W2 | 11 | 4 | 11 | 11/11 COMPLETE ✓ | 3 | MC1 | KVCAD50MC001 | 1592.40 | 4.777 | 40 min | 1 | 120 min | Order Total: 11 units
2025-12-18 | 2025-12-13 | Thursday | W4 | MCB-JLG-047 | 2526203140 | Unknown | W2 | 11 | 4 | 11 | 11/11 COMPLETE ✓ | 3 | Cooling/Shakeout | N/A | 1592.40 | 4.777 | - | 1 | - | Order Total: 11 units
2025-11-22 | 2025-12-13 | Saturday | W1 | MCB-JLG-047 | 2526203141 | Unknown | W1 | 9 | 1 | 2 | 2/9 (22%) | 2 | MC1 | KVCAD50MC001 | 1592.40 | 3.185 | 40 min | 1 | 80 min | Order Total: 9 units
2025-11-24 | 2025-12-15 | Monday | W1 | MCB-JLG-047 | 2526203141 | Unknown | W1 | 9 | 2 | 4 | 4/9 (44%) | 2 | MC1 | KVCAD50MC001 | 1592.40 | 3.185 | 40 min | 1 | 80 min | Order Total: 9 units
2025-11-25 | 2025-12-13 | Tuesday | W1 | MCB-JLG-047 | 2526203141 | Unknown | W1 | 9 | 3 | 6 | 6/9 (66%) | 2 | MC1 | KVCAD50MC001 | 1592.40 | 3.185 | 40 min | 1 | 80 min | Order Total: 9 units
2025-11-26 | 2025-12-13 | Wednesday | W1 | MCB-JLG-047 | 2526203141 | Unknown | W1 | 9 | 4 | 9 | 9/9 COMPLETE ✓ | 3 | MC1 | KVCAD50MC001 | 1592.40 | 4.777 | 40 min | 1 | 120 min | Order Total: 9 units
2025-11-29 | 2025-12-13 | Saturday | W2 | MCB-JLG-047 | 2526203141 | Unknown | W1 | 9 | 1 | 2 | 2/9 (22%) | 2 | SP1 | KVCALPPSP001 | 1592.40 | 3.185 | 12 min | 1 | 24 min | Order Total: 9 units
2025-12-01 | 2025-12-15 | Monday | W2 | MCB-JLG-047 | 2526203141 | Unknown | W1 | 9 | 2 | 4 | 4/9 (44%) | 2 | SP1 | KVCALPPSP001 | 1592.40 | 3.185 | 12 min | 1 | 24 min | Order Total: 9 units
2025-12-02 | 2025-12-13 | Tuesday | W2 | MCB-JLG-047 | 2526203141 | Unknown | W1 | 9 | 3 | 6 | 6/9 (66%) | 2 | SP1 | KVCALPPSP001 | 1592.40 | 3.185 | 12 min | 1 | 24 min | Order Total: 9 units
2025-12-03 | 2025-12-13 | Wednesday | W2 | MCB-JLG-047 | 2526203141 | Unknown | W1 | 9 | 4 | 9 | 9/9 COMPLETE ✓ | 3 | SP1 | KVCALPPSP001 | 1592.40 | 4.777 | 12 min | 1 | 36 min | Order Total: 9 units
2025-12-13 | 2025-12-13 | Saturday | W4 | MCB-JLG-047 | 2526203141 | Unknown | W1 | 9 | 1 | 5 | 5/9 (55%) | 5 | Casting | CS1-MCB-JLG-047 | 1592.40 | 7.962 | 25 min | 1 | 125 min | Order Total: 9 units
2025-12-14 | 2025-12-13 | Sunday | W4 | MCB-JLG-047 | 2526203141 | Unknown | W1 | 9 | 1 | 2 | 2/9 (22%) | 2 | Cooling/Shakeout | N/A | 1592.40 | 3.185 | - | 1 | - | Order Total: 9 units
2025-12-15 | 2025-12-15 | Monday | W4 | MCB-JLG-047 | 2526203141 | Unknown | W1 | 9 | 2 | 9 | 9/9 COMPLETE ✓ | 4 | Casting | CS1-MCB-JLG-047 | 1592.40 | 6.370 | 25 min | 1 | 100 min | Order Total: 9 units
2025-12-16 | 2025-12-15 | Tuesday | W4 | MCB-JLG-047 | 2526203141 | Unknown | W1 | 9 | 2 | 4 | 4/9 (44%) | 2 | Cooling/Shakeout | N/A | 1592.40 | 3.185 | - | 1 | - | Order Total: 9 units
2025-12-17 | 2025-12-13 | Wednesday | W4 | MCB-JLG-047 | 2526203141 | Unknown | W1 | 9 | 3 | 6 | 6/9 (66%) | 2 | Cooling/Shakeout | N/A | 1592.40 | 3.185 | - | 1 | - | Order Total: 9 units
2025-12-18 | 2025-12-13 | Thursday | W4 | MCB-JLG-047 | 2526203141 | Unknown | W1 | 9 | 4 | 9 | 9/9 COMPLETE ✓ | 3 | Cooling/Shakeout | N/A | 1592.40 | 4.777 | - | 1 | - | Order Total: 9 units
2025-11-29 | 2025-11-29 | Saturday | W2 | MCB-JLG-020 | 2526203142 | Unknown | W2 | 4 | 1 | 2 | 2/4 (50%) | 2 | MC1 | KVCAD50MC001 | 3863.64 | 7.727 | 65 min | 0 | - | Order Total: 4 units
2025-12-01 | 2025-12-01 | Monday | W2 | MCB-JLG-020 | 2526203142 | Unknown | W2 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | MC1 | KVCAD50MC001 | 3863.64 | 7.727 | 65 min | 0 | - | Order Total: 4 units
2025-12-13 | 2025-12-13 | Saturday | W4 | MCB-JLG-020 | 2526203142 | Unknown | W2 | 4 | 1 | 2 | 2/4 (50%) | 2 | Grinding | KVCALHMGR001 | 3863.64 | 7.727 | 480 min | 1 | 960 min | Order Total: 4 units
2025-12-13 | 2025-12-13 | Saturday | W4 | MCB-JLG-020 | 2526203142 | Unknown | W2 | 4 | 1 | 2 | 2/4 (50%) | 2 | SP1 | KVCALPPSP001 | 3863.64 | 7.727 | 7 min | 1 | 14 min | Order Total: 4 units
2025-12-15 | 2025-12-15 | Monday | W4 | MCB-JLG-020 | 2526203142 | Unknown | W2 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | Grinding | KVCALHMGR001 | 3863.64 | 7.727 | 480 min | 1 | 960 min | Order Total: 4 units
2025-12-15 | 2025-12-15 | Monday | W4 | MCB-JLG-020 | 2526203142 | Unknown | W2 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | SP1 | KVCALPPSP001 | 3863.64 | 7.727 | 7 min | 1 | 14 min | Order Total: 4 units
2025-11-22 | 2025-11-22 | Saturday | W1 | MCB-JLG-020 | 2526203143 | Unknown | W1 | 4 | 1 | 2 | 2/4 (50%) | 2 | Grinding | KVCALHMGR001 | 3863.64 | 7.727 | 480 min | 1 | 960 min | Order Total: 4 units
2025-11-24 | 2025-11-24 | Monday | W1 | MCB-JLG-020 | 2526203143 | Unknown | W1 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | Grinding | KVCALHMGR001 | 3863.64 | 7.727 | 480 min | 1 | 960 min | Order Total: 4 units
2025-11-22 | 2025-12-06 | Saturday | W1 | NMS-V-004 | 2526203148 | Unknown | W6 | 5 | 1 | 2 | 2/5 (40%) | 2 | MC1 | KVCABM2MC001 | 0.00 | 0.000 | 120 min | 1 | 240 min | Order Total: 5 units
2025-11-22 | 2025-12-06 | Saturday | W1 | NMS-V-004 | 2526203148 | Unknown | W6 | 5 | 1 | 2 | 2/5 (40%) | 2 | MC2 | KVCAD30MC001 | 0.00 | 0.000 | 180 min | 1 | 360 min | Order Total: 5 units
2025-11-22 | 2025-12-06 | Saturday | W1 | NMS-V-004 | 2526203148 | Unknown | W6 | 5 | 1 | 2 | 2/5 (40%) | 2 | MC3 | KVCAD40MC001 | 0.00 | 0.000 | 40 min | 1 | 80 min | Order Total: 5 units
2025-11-22 | 2025-12-06 | Saturday | W1 | NMS-V-004 | 2526203148 | Unknown | W6 | 5 | 1 | 2 | 2/5 (40%) | 2 | SP1 | KVCALPPSP001 | 0.00 | 0.000 | 12 min | 1 | 24 min | Order Total: 5 units
2025-11-22 | 2025-12-06 | Saturday | W1 | NMS-V-004 | 2526203148 | Unknown | W6 | 5 | 1 | 2 | 2/5 (40%) | 2 | SP2 | KVCALPPSP002 | 0.00 | 0.000 | 12 min | 1 | 24 min | Order Total: 5 units
2025-11-22 | 2025-12-06 | Saturday | W1 | NMS-V-004 | 2526203148 | Unknown | W6 | 5 | 1 | 2 | 2/5 (40%) | 2 | SP3 | SP3CFC-NMS-H-004 | 0.00 | 0.000 | - | 0 | - | Order Total: 5 units
2025-11-24 | 2025-12-08 | Monday | W1 | NMS-V-004 | 2526203148 | Unknown | W6 | 5 | 2 | 5 | 5/5 COMPLETE ✓ | 3 | MC1 | KVCABM2MC001 | 0.00 | 0.000 | 120 min | 1 | 360 min | Order Total: 5 units
2025-11-24 | 2025-12-08 | Monday | W1 | NMS-V-004 | 2526203148 | Unknown | W6 | 5 | 2 | 5 | 5/5 COMPLETE ✓ | 3 | MC2 | KVCAD30MC001 | 0.00 | 0.000 | 180 min | 1 | 540 min | Order Total: 5 units
2025-11-24 | 2025-12-08 | Monday | W1 | NMS-V-004 | 2526203148 | Unknown | W6 | 5 | 2 | 5 | 5/5 COMPLETE ✓ | 3 | MC3 | KVCAD40MC001 | 0.00 | 0.000 | 40 min | 1 | 120 min | Order Total: 5 units
2025-11-24 | 2025-12-08 | Monday | W1 | NMS-V-004 | 2526203148 | Unknown | W6 | 5 | 2 | 5 | 5/5 COMPLETE ✓ | 3 | SP1 | KVCALPPSP001 | 0.00 | 0.000 | 12 min | 1 | 36 min | Order Total: 5 units
2025-11-24 | 2025-12-08 | Monday | W1 | NMS-V-004 | 2526203148 | Unknown | W6 | 5 | 2 | 5 | 5/5 COMPLETE ✓ | 3 | SP2 | KVCALPPSP002 | 0.00 | 0.000 | 12 min | 1 | 36 min | Order Total: 5 units
2025-11-24 | 2025-12-08 | Monday | W1 | NMS-V-004 | 2526203148 | Unknown | W6 | 5 | 2 | 5 | 5/5 COMPLETE ✓ | 3 | SP3 | SP3CFC-NMS-H-004 | 0.00 | 0.000 | - | 0 | - | Order Total: 5 units
2025-12-06 | 2025-12-06 | Saturday | W3 | NMS-V-004 | 2526203148 | Unknown | W6 | 5 | 1 | 2 | 2/5 (40%) | 2 | Casting | CS3CFC-NMS-H-004 | 0.00 | 0.000 | 20 min | 1 | 40 min | Order Total: 5 units
2025-12-07 | 2025-12-06 | Sunday | W3 | NMS-V-004 | 2526203148 | Unknown | W6 | 5 | 1 | 2 | 2/5 (40%) | 2 | Cooling/Shakeout | N/A | 0.00 | 0.000 | - | 1 | - | Order Total: 5 units
2025-12-08 | 2025-12-08 | Monday | W3 | NMS-V-004 | 2526203148 | Unknown | W6 | 5 | 2 | 5 | 5/5 COMPLETE ✓ | 3 | Casting | CS3CFC-NMS-H-004 | 0.00 | 0.000 | 20 min | 1 | 60 min | Order Total: 5 units
2025-12-09 | 2025-12-08 | Tuesday | W3 | NMS-V-004 | 2526203148 | Unknown | W6 | 5 | 2 | 5 | 5/5 COMPLETE ✓ | 3 | Cooling/Shakeout | N/A | 0.00 | 0.000 | - | 1 | - | Order Total: 5 units
2025-11-22 | 2025-11-22 | Saturday | W1 | MCB-008 | 2526203153 | Unknown | W2 | 3 | 1 | 1 | 1/3 (33%) | 1 | MC1 | KVCAD50MC001 | 2770.00 | 2.770 | 20 min | 1 | 20 min | Order Total: 3 units
2025-11-24 | 2025-11-24 | Monday | W1 | MCB-008 | 2526203153 | Unknown | W2 | 3 | 2 | 2 | 2/3 (66%) | 1 | MC1 | KVCAD50MC001 | 2770.00 | 2.770 | 20 min | 1 | 20 min | Order Total: 3 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | MCB-008 | 2526203153 | Unknown | W2 | 3 | 3 | 3 | 3/3 COMPLETE ✓ | 1 | MC1 | KVCAD50MC001 | 2770.00 | 2.770 | 20 min | 1 | 20 min | Order Total: 3 units
2025-11-22 | 2025-11-22 | Saturday | W1 | MCB-008 | 2526203154 | Unknown | W2 | 3 | 1 | 1 | 1/3 (33%) | 1 | MC1 | KVCAD50MC001 | 2770.00 | 2.770 | 20 min | 1 | 20 min | Order Total: 3 units
2025-11-24 | 2025-11-24 | Monday | W1 | MCB-008 | 2526203154 | Unknown | W2 | 3 | 2 | 2 | 2/3 (66%) | 1 | MC1 | KVCAD50MC001 | 2770.00 | 2.770 | 20 min | 1 | 20 min | Order Total: 3 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | MCB-008 | 2526203154 | Unknown | W2 | 3 | 3 | 3 | 3/3 COMPLETE ✓ | 1 | MC1 | KVCAD50MC001 | 2770.00 | 2.770 | 20 min | 1 | 20 min | Order Total: 3 units
2025-11-22 | 2025-11-22 | Saturday | W1 | MCB-008 | 2526203164 | Unknown | W2 | 2 | 1 | 1 | 1/2 (50%) | 1 | MC1 | KVCAD50MC001 | 2770.00 | 2.770 | 20 min | 1 | 20 min | Order Total: 2 units
2025-11-24 | 2025-11-24 | Monday | W1 | MCB-008 | 2526203164 | Unknown | W2 | 2 | 2 | 2 | 2/2 COMPLETE ✓ | 1 | MC1 | KVCAD50MC001 | 2770.00 | 2.770 | 20 min | 1 | 20 min | Order Total: 2 units
2025-11-22 | 2025-11-22 | Saturday | W1 | MCB-010 | 2526203171 | Unknown | W2 | 2 | 1 | 1 | 1/5 (20%) | 1 | Casting | CS2MCB-010 | 2650.00 | 2.650 | 20 min | 1 | 20 min | Order Total: 2 units
2025-11-22 | 2025-11-22 | Saturday | W1 | MCB-010 | 2526203171 | Unknown | W2 | 3 | 2 | 2 | 2/5 (40%) | 1 | Casting | CS2MCB-010 | 2650.00 | 2.650 | 20 min | 1 | 20 min | Order Total: 3 units
2025-11-22 | 2025-11-22 | Saturday | W1 | MCB-010 | 2526203171 | Unknown | W2 | 2 | 3 | 3 | 3/5 (60%) | 1 | Casting | CS2MCB-010 | 2650.00 | 2.650 | 20 min | 1 | 20 min | Order Total: 2 units
2025-11-23 | 2025-11-22 | Sunday | W1 | MCB-010 | 2526203171 | Unknown | W2 | 2 | 1 | 1 | 1/5 (20%) | 1 | Cooling/Shakeout | N/A | 2650.00 | 2.650 | - | 1 | - | Order Total: 2 units
2025-11-23 | 2025-11-22 | Sunday | W1 | MCB-010 | 2526203171 | Unknown | W2 | 3 | 2 | 2 | 2/5 (40%) | 1 | Cooling/Shakeout | N/A | 2650.00 | 2.650 | - | 1 | - | Order Total: 3 units
2025-11-23 | 2025-11-22 | Sunday | W1 | MCB-010 | 2526203171 | Unknown | W2 | 2 | 3 | 3 | 3/5 (60%) | 1 | Cooling/Shakeout | N/A | 2650.00 | 2.650 | - | 1 | - | Order Total: 2 units
2025-11-24 | 2025-11-24 | Monday | W1 | MCB-010 | 2526203171 | Unknown | W2 | 2 | 4 | 4 | 4/5 (80%) | 1 | Casting | CS2MCB-010 | 2650.00 | 2.650 | 20 min | 1 | 20 min | Order Total: 2 units
2025-11-24 | 2025-11-24 | Monday | W1 | MCB-010 | 2526203171 | Unknown | W2 | 3 | 5 | 5 | 5/5 COMPLETE ✓ | 1 | Casting | CS2MCB-010 | 2650.00 | 2.650 | 20 min | 1 | 20 min | Order Total: 3 units
2025-11-24 | 2025-11-24 | Monday | W1 | MCB-010 | 2526203171 | Unknown | W2 | 2 | 6 | 6 | 6/5 COMPLETE ✓ | 1 | Casting | CS2MCB-010 | 2650.00 | 2.650 | 20 min | 1 | 20 min | Order Total: 2 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | MCB-010 | 2526203171 | Unknown | W2 | 3 | 7 | 7 | 7/5 COMPLETE ✓ | 1 | Casting | CS2MCB-010 | 2650.00 | 2.650 | 20 min | 1 | 20 min | Order Total: 3 units
2025-11-25 | 2025-11-24 | Tuesday | W1 | MCB-010 | 2526203171 | Unknown | W2 | 2 | 4 | 4 | 4/5 (80%) | 1 | Cooling/Shakeout | N/A | 2650.00 | 2.650 | - | 1 | - | Order Total: 2 units
2025-11-25 | 2025-11-24 | Tuesday | W1 | MCB-010 | 2526203171 | Unknown | W2 | 3 | 5 | 5 | 5/5 COMPLETE ✓ | 1 | Cooling/Shakeout | N/A | 2650.00 | 2.650 | - | 1 | - | Order Total: 3 units
2025-11-25 | 2025-11-24 | Tuesday | W1 | MCB-010 | 2526203171 | Unknown | W2 | 2 | 6 | 6 | 6/5 COMPLETE ✓ | 1 | Cooling/Shakeout | N/A | 2650.00 | 2.650 | - | 1 | - | Order Total: 2 units
2025-11-26 | 2025-11-22 | Wednesday | W1 | MCB-010 | 2526203171 | Unknown | W2 | 3 | 7 | 7 | 7/5 COMPLETE ✓ | 1 | Cooling/Shakeout | N/A | 2650.00 | 2.650 | - | 1 | - | Order Total: 3 units
2025-11-29 | 2025-11-22 | Saturday | W2 | MCB-010 | 2526203171 | Unknown | W2 | 2 | 1 | 1 | 1/5 (20%) | 1 | Grinding | KVCALHMGR001 | 2650.00 | 2.650 | 300 min | 1 | 300 min | Order Total: 2 units
2025-11-29 | 2025-11-22 | Saturday | W2 | MCB-010 | 2526203171 | Unknown | W2 | 3 | 2 | 2 | 2/5 (40%) | 1 | Grinding | KVCALHMGR001 | 2650.00 | 2.650 | 300 min | 1 | 300 min | Order Total: 3 units
2025-11-29 | 2025-11-22 | Saturday | W2 | MCB-010 | 2526203171 | Unknown | W2 | 2 | 3 | 3 | 3/5 (60%) | 1 | Grinding | KVCALHMGR001 | 2650.00 | 2.650 | 300 min | 1 | 300 min | Order Total: 2 units
2025-11-29 | 2025-11-22 | Saturday | W2 | MCB-010 | 2526203171 | Unknown | W2 | 2 | 1 | 1 | 1/5 (20%) | 1 | MC1 | KVCAD50MC001 | 2650.00 | 2.650 | 60 min | 0 | - | Order Total: 2 units
2025-11-29 | 2025-11-22 | Saturday | W2 | MCB-010 | 2526203171 | Unknown | W2 | 3 | 2 | 2 | 2/5 (40%) | 1 | MC1 | KVCAD50MC001 | 2650.00 | 2.650 | 60 min | 0 | - | Order Total: 3 units
2025-11-29 | 2025-11-22 | Saturday | W2 | MCB-010 | 2526203171 | Unknown | W2 | 2 | 3 | 3 | 3/5 (60%) | 1 | MC1 | KVCAD50MC001 | 2650.00 | 2.650 | 60 min | 0 | - | Order Total: 2 units
2025-12-01 | 2025-11-24 | Monday | W2 | MCB-010 | 2526203171 | Unknown | W2 | 2 | 4 | 4 | 4/5 (80%) | 1 | Grinding | KVCALHMGR001 | 2650.00 | 2.650 | 300 min | 1 | 300 min | Order Total: 2 units
2025-12-01 | 2025-11-24 | Monday | W2 | MCB-010 | 2526203171 | Unknown | W2 | 3 | 5 | 5 | 5/5 COMPLETE ✓ | 1 | Grinding | KVCALHMGR001 | 2650.00 | 2.650 | 300 min | 1 | 300 min | Order Total: 3 units
2025-12-01 | 2025-11-24 | Monday | W2 | MCB-010 | 2526203171 | Unknown | W2 | 2 | 6 | 6 | 6/5 COMPLETE ✓ | 1 | Grinding | KVCALHMGR001 | 2650.00 | 2.650 | 300 min | 1 | 300 min | Order Total: 2 units
2025-12-01 | 2025-11-24 | Monday | W2 | MCB-010 | 2526203171 | Unknown | W2 | 2 | 4 | 4 | 4/5 (80%) | 1 | MC1 | KVCAD50MC001 | 2650.00 | 2.650 | 60 min | 0 | - | Order Total: 2 units
2025-12-01 | 2025-11-24 | Monday | W2 | MCB-010 | 2526203171 | Unknown | W2 | 3 | 5 | 5 | 5/5 COMPLETE ✓ | 1 | MC1 | KVCAD50MC001 | 2650.00 | 2.650 | 60 min | 0 | - | Order Total: 3 units
2025-12-01 | 2025-11-24 | Monday | W2 | MCB-010 | 2526203171 | Unknown | W2 | 2 | 6 | 6 | 6/5 COMPLETE ✓ | 1 | MC1 | KVCAD50MC001 | 2650.00 | 2.650 | 60 min | 0 | - | Order Total: 2 units
2025-12-02 | 2025-11-22 | Tuesday | W2 | MCB-010 | 2526203171 | Unknown | W2 | 3 | 7 | 7 | 7/5 COMPLETE ✓ | 1 | Grinding | KVCALHMGR001 | 2650.00 | 2.650 | 300 min | 1 | 300 min | Order Total: 3 units
2025-12-02 | 2025-11-22 | Tuesday | W2 | MCB-010 | 2526203171 | Unknown | W2 | 3 | 7 | 7 | 7/5 COMPLETE ✓ | 1 | MC1 | KVCAD50MC001 | 2650.00 | 2.650 | 60 min | 0 | - | Order Total: 3 units
2025-12-06 | 2025-11-22 | Saturday | W3 | MCB-010 | 2526203171 | Unknown | W2 | 2 | 1 | 1 | 1/5 (20%) | 1 | SP1 | KVCALPPSP001 | 2650.00 | 2.650 | 12 min | 1 | 12 min | Order Total: 2 units
2025-12-06 | 2025-11-22 | Saturday | W3 | MCB-010 | 2526203171 | Unknown | W2 | 3 | 2 | 2 | 2/5 (40%) | 1 | SP1 | KVCALPPSP001 | 2650.00 | 2.650 | 12 min | 1 | 12 min | Order Total: 3 units
2025-12-06 | 2025-11-22 | Saturday | W3 | MCB-010 | 2526203171 | Unknown | W2 | 2 | 3 | 3 | 3/5 (60%) | 1 | SP1 | KVCALPPSP001 | 2650.00 | 2.650 | 12 min | 1 | 12 min | Order Total: 2 units
2025-12-08 | 2025-11-24 | Monday | W3 | MCB-010 | 2526203171 | Unknown | W2 | 2 | 4 | 4 | 4/5 (80%) | 1 | SP1 | KVCALPPSP001 | 2650.00 | 2.650 | 12 min | 1 | 12 min | Order Total: 2 units
2025-12-08 | 2025-11-24 | Monday | W3 | MCB-010 | 2526203171 | Unknown | W2 | 3 | 5 | 5 | 5/5 COMPLETE ✓ | 1 | SP1 | KVCALPPSP001 | 2650.00 | 2.650 | 12 min | 1 | 12 min | Order Total: 3 units
2025-12-08 | 2025-11-24 | Monday | W3 | MCB-010 | 2526203171 | Unknown | W2 | 2 | 6 | 6 | 6/5 COMPLETE ✓ | 1 | SP1 | KVCALPPSP001 | 2650.00 | 2.650 | 12 min | 1 | 12 min | Order Total: 2 units
2025-12-09 | 2025-11-22 | Tuesday | W3 | MCB-010 | 2526203171 | Unknown | W2 | 3 | 7 | 7 | 7/5 COMPLETE ✓ | 1 | SP1 | KVCALPPSP001 | 2650.00 | 2.650 | 12 min | 1 | 12 min | Order Total: 3 units
2025-11-22 | 2025-11-22 | Saturday | W1 | MCB-010 | 2526203172 | Unknown | W2 | 2 | 1 | 1 | 1/5 (20%) | 1 | Casting | CS2MCB-010 | 2650.00 | 2.650 | 20 min | 1 | 20 min | Order Total: 2 units
2025-11-22 | 2025-11-22 | Saturday | W1 | MCB-010 | 2526203172 | Unknown | W2 | 3 | 2 | 2 | 2/5 (40%) | 1 | Casting | CS2MCB-010 | 2650.00 | 2.650 | 20 min | 1 | 20 min | Order Total: 3 units
2025-11-22 | 2025-11-22 | Saturday | W1 | MCB-010 | 2526203172 | Unknown | W2 | 2 | 3 | 3 | 3/5 (60%) | 1 | Casting | CS2MCB-010 | 2650.00 | 2.650 | 20 min | 1 | 20 min | Order Total: 2 units
2025-11-23 | 2025-11-22 | Sunday | W1 | MCB-010 | 2526203172 | Unknown | W2 | 2 | 1 | 1 | 1/5 (20%) | 1 | Cooling/Shakeout | N/A | 2650.00 | 2.650 | - | 1 | - | Order Total: 2 units
2025-11-23 | 2025-11-22 | Sunday | W1 | MCB-010 | 2526203172 | Unknown | W2 | 3 | 2 | 2 | 2/5 (40%) | 1 | Cooling/Shakeout | N/A | 2650.00 | 2.650 | - | 1 | - | Order Total: 3 units
2025-11-23 | 2025-11-22 | Sunday | W1 | MCB-010 | 2526203172 | Unknown | W2 | 2 | 3 | 3 | 3/5 (60%) | 1 | Cooling/Shakeout | N/A | 2650.00 | 2.650 | - | 1 | - | Order Total: 2 units
2025-11-24 | 2025-11-24 | Monday | W1 | MCB-010 | 2526203172 | Unknown | W2 | 2 | 4 | 4 | 4/5 (80%) | 1 | Casting | CS2MCB-010 | 2650.00 | 2.650 | 20 min | 1 | 20 min | Order Total: 2 units
2025-11-24 | 2025-11-24 | Monday | W1 | MCB-010 | 2526203172 | Unknown | W2 | 3 | 5 | 5 | 5/5 COMPLETE ✓ | 1 | Casting | CS2MCB-010 | 2650.00 | 2.650 | 20 min | 1 | 20 min | Order Total: 3 units
2025-11-24 | 2025-11-24 | Monday | W1 | MCB-010 | 2526203172 | Unknown | W2 | 2 | 6 | 6 | 6/5 COMPLETE ✓ | 1 | Casting | CS2MCB-010 | 2650.00 | 2.650 | 20 min | 1 | 20 min | Order Total: 2 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | MCB-010 | 2526203172 | Unknown | W2 | 3 | 7 | 7 | 7/5 COMPLETE ✓ | 1 | Casting | CS2MCB-010 | 2650.00 | 2.650 | 20 min | 1 | 20 min | Order Total: 3 units
2025-11-25 | 2025-11-24 | Tuesday | W1 | MCB-010 | 2526203172 | Unknown | W2 | 2 | 4 | 4 | 4/5 (80%) | 1 | Cooling/Shakeout | N/A | 2650.00 | 2.650 | - | 1 | - | Order Total: 2 units
2025-11-25 | 2025-11-24 | Tuesday | W1 | MCB-010 | 2526203172 | Unknown | W2 | 3 | 5 | 5 | 5/5 COMPLETE ✓ | 1 | Cooling/Shakeout | N/A | 2650.00 | 2.650 | - | 1 | - | Order Total: 3 units
2025-11-25 | 2025-11-24 | Tuesday | W1 | MCB-010 | 2526203172 | Unknown | W2 | 2 | 6 | 6 | 6/5 COMPLETE ✓ | 1 | Cooling/Shakeout | N/A | 2650.00 | 2.650 | - | 1 | - | Order Total: 2 units
2025-11-26 | 2025-11-22 | Wednesday | W1 | MCB-010 | 2526203172 | Unknown | W2 | 3 | 7 | 7 | 7/5 COMPLETE ✓ | 1 | Cooling/Shakeout | N/A | 2650.00 | 2.650 | - | 1 | - | Order Total: 3 units
2025-11-29 | 2025-11-22 | Saturday | W2 | MCB-010 | 2526203172 | Unknown | W2 | 2 | 1 | 1 | 1/5 (20%) | 1 | Grinding | KVCALHMGR001 | 2650.00 | 2.650 | 300 min | 1 | 300 min | Order Total: 2 units
2025-11-29 | 2025-11-22 | Saturday | W2 | MCB-010 | 2526203172 | Unknown | W2 | 3 | 2 | 2 | 2/5 (40%) | 1 | Grinding | KVCALHMGR001 | 2650.00 | 2.650 | 300 min | 1 | 300 min | Order Total: 3 units
2025-11-29 | 2025-11-22 | Saturday | W2 | MCB-010 | 2526203172 | Unknown | W2 | 2 | 3 | 3 | 3/5 (60%) | 1 | Grinding | KVCALHMGR001 | 2650.00 | 2.650 | 300 min | 1 | 300 min | Order Total: 2 units
2025-11-29 | 2025-11-22 | Saturday | W2 | MCB-010 | 2526203172 | Unknown | W2 | 2 | 1 | 1 | 1/5 (20%) | 1 | MC1 | KVCAD50MC001 | 2650.00 | 2.650 | 60 min | 0 | - | Order Total: 2 units
2025-11-29 | 2025-11-22 | Saturday | W2 | MCB-010 | 2526203172 | Unknown | W2 | 3 | 2 | 2 | 2/5 (40%) | 1 | MC1 | KVCAD50MC001 | 2650.00 | 2.650 | 60 min | 0 | - | Order Total: 3 units
2025-11-29 | 2025-11-22 | Saturday | W2 | MCB-010 | 2526203172 | Unknown | W2 | 2 | 3 | 3 | 3/5 (60%) | 1 | MC1 | KVCAD50MC001 | 2650.00 | 2.650 | 60 min | 0 | - | Order Total: 2 units
2025-12-01 | 2025-11-24 | Monday | W2 | MCB-010 | 2526203172 | Unknown | W2 | 2 | 4 | 4 | 4/5 (80%) | 1 | Grinding | KVCALHMGR001 | 2650.00 | 2.650 | 300 min | 1 | 300 min | Order Total: 2 units
2025-12-01 | 2025-11-24 | Monday | W2 | MCB-010 | 2526203172 | Unknown | W2 | 3 | 5 | 5 | 5/5 COMPLETE ✓ | 1 | Grinding | KVCALHMGR001 | 2650.00 | 2.650 | 300 min | 1 | 300 min | Order Total: 3 units
2025-12-01 | 2025-11-24 | Monday | W2 | MCB-010 | 2526203172 | Unknown | W2 | 2 | 6 | 6 | 6/5 COMPLETE ✓ | 1 | Grinding | KVCALHMGR001 | 2650.00 | 2.650 | 300 min | 1 | 300 min | Order Total: 2 units
2025-12-01 | 2025-11-24 | Monday | W2 | MCB-010 | 2526203172 | Unknown | W2 | 2 | 4 | 4 | 4/5 (80%) | 1 | MC1 | KVCAD50MC001 | 2650.00 | 2.650 | 60 min | 0 | - | Order Total: 2 units
2025-12-01 | 2025-11-24 | Monday | W2 | MCB-010 | 2526203172 | Unknown | W2 | 3 | 5 | 5 | 5/5 COMPLETE ✓ | 1 | MC1 | KVCAD50MC001 | 2650.00 | 2.650 | 60 min | 0 | - | Order Total: 3 units
2025-12-01 | 2025-11-24 | Monday | W2 | MCB-010 | 2526203172 | Unknown | W2 | 2 | 6 | 6 | 6/5 COMPLETE ✓ | 1 | MC1 | KVCAD50MC001 | 2650.00 | 2.650 | 60 min | 0 | - | Order Total: 2 units
2025-12-02 | 2025-11-22 | Tuesday | W2 | MCB-010 | 2526203172 | Unknown | W2 | 3 | 7 | 7 | 7/5 COMPLETE ✓ | 1 | Grinding | KVCALHMGR001 | 2650.00 | 2.650 | 300 min | 1 | 300 min | Order Total: 3 units
2025-12-02 | 2025-11-22 | Tuesday | W2 | MCB-010 | 2526203172 | Unknown | W2 | 3 | 7 | 7 | 7/5 COMPLETE ✓ | 1 | MC1 | KVCAD50MC001 | 2650.00 | 2.650 | 60 min | 0 | - | Order Total: 3 units
2025-12-06 | 2025-11-22 | Saturday | W3 | MCB-010 | 2526203172 | Unknown | W2 | 2 | 1 | 1 | 1/5 (20%) | 1 | SP1 | KVCALPPSP001 | 2650.00 | 2.650 | 12 min | 1 | 12 min | Order Total: 2 units
2025-12-06 | 2025-11-22 | Saturday | W3 | MCB-010 | 2526203172 | Unknown | W2 | 3 | 2 | 2 | 2/5 (40%) | 1 | SP1 | KVCALPPSP001 | 2650.00 | 2.650 | 12 min | 1 | 12 min | Order Total: 3 units
2025-12-06 | 2025-11-22 | Saturday | W3 | MCB-010 | 2526203172 | Unknown | W2 | 2 | 3 | 3 | 3/5 (60%) | 1 | SP1 | KVCALPPSP001 | 2650.00 | 2.650 | 12 min | 1 | 12 min | Order Total: 2 units
2025-12-08 | 2025-11-24 | Monday | W3 | MCB-010 | 2526203172 | Unknown | W2 | 2 | 4 | 4 | 4/5 (80%) | 1 | SP1 | KVCALPPSP001 | 2650.00 | 2.650 | 12 min | 1 | 12 min | Order Total: 2 units
2025-12-08 | 2025-11-24 | Monday | W3 | MCB-010 | 2526203172 | Unknown | W2 | 3 | 5 | 5 | 5/5 COMPLETE ✓ | 1 | SP1 | KVCALPPSP001 | 2650.00 | 2.650 | 12 min | 1 | 12 min | Order Total: 3 units
2025-12-08 | 2025-11-24 | Monday | W3 | MCB-010 | 2526203172 | Unknown | W2 | 2 | 6 | 6 | 6/5 COMPLETE ✓ | 1 | SP1 | KVCALPPSP001 | 2650.00 | 2.650 | 12 min | 1 | 12 min | Order Total: 2 units
2025-12-09 | 2025-11-22 | Tuesday | W3 | MCB-010 | 2526203172 | Unknown | W2 | 3 | 7 | 7 | 7/5 COMPLETE ✓ | 1 | SP1 | KVCALPPSP001 | 2650.00 | 2.650 | 12 min | 1 | 12 min | Order Total: 3 units
2025-11-22 | 2025-11-22 | Saturday | W1 | MCB-010 | 2526203173 | Unknown | W2 | 2 | 1 | 1 | 1/6 (16%) | 1 | Casting | CS2MCB-010 | 2650.00 | 2.650 | 20 min | 1 | 20 min | Order Total: 2 units
2025-11-22 | 2025-11-22 | Saturday | W1 | MCB-010 | 2526203173 | Unknown | W2 | 3 | 2 | 2 | 2/6 (33%) | 1 | Casting | CS2MCB-010 | 2650.00 | 2.650 | 20 min | 1 | 20 min | Order Total: 3 units
2025-11-22 | 2025-11-22 | Saturday | W1 | MCB-010 | 2526203173 | Unknown | W2 | 1 | 3 | 3 | 3/6 (50%) | 1 | Casting | CS2MCB-010 | 2650.00 | 2.650 | 20 min | 1 | 20 min | Order Total: 1 units
2025-11-23 | 2025-11-22 | Sunday | W1 | MCB-010 | 2526203173 | Unknown | W2 | 2 | 1 | 1 | 1/6 (16%) | 1 | Cooling/Shakeout | N/A | 2650.00 | 2.650 | - | 1 | - | Order Total: 2 units
2025-11-23 | 2025-11-22 | Sunday | W1 | MCB-010 | 2526203173 | Unknown | W2 | 3 | 2 | 2 | 2/6 (33%) | 1 | Cooling/Shakeout | N/A | 2650.00 | 2.650 | - | 1 | - | Order Total: 3 units
2025-11-23 | 2025-11-22 | Sunday | W1 | MCB-010 | 2526203173 | Unknown | W2 | 1 | 3 | 3 | 3/6 (50%) | 1 | Cooling/Shakeout | N/A | 2650.00 | 2.650 | - | 1 | - | Order Total: 1 units
2025-11-24 | 2025-11-24 | Monday | W1 | MCB-010 | 2526203173 | Unknown | W2 | 2 | 4 | 4 | 4/6 (66%) | 1 | Casting | CS2MCB-010 | 2650.00 | 2.650 | 20 min | 1 | 20 min | Order Total: 2 units
2025-11-24 | 2025-11-24 | Monday | W1 | MCB-010 | 2526203173 | Unknown | W2 | 3 | 5 | 5 | 5/6 (83%) | 1 | Casting | CS2MCB-010 | 2650.00 | 2.650 | 20 min | 1 | 20 min | Order Total: 3 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | MCB-010 | 2526203173 | Unknown | W2 | 3 | 6 | 6 | 6/6 COMPLETE ✓ | 1 | Casting | CS2MCB-010 | 2650.00 | 2.650 | 20 min | 1 | 20 min | Order Total: 3 units
2025-11-25 | 2025-11-24 | Tuesday | W1 | MCB-010 | 2526203173 | Unknown | W2 | 2 | 4 | 4 | 4/6 (66%) | 1 | Cooling/Shakeout | N/A | 2650.00 | 2.650 | - | 1 | - | Order Total: 2 units
2025-11-25 | 2025-11-24 | Tuesday | W1 | MCB-010 | 2526203173 | Unknown | W2 | 3 | 5 | 5 | 5/6 (83%) | 1 | Cooling/Shakeout | N/A | 2650.00 | 2.650 | - | 1 | - | Order Total: 3 units
2025-11-26 | 2025-11-22 | Wednesday | W1 | MCB-010 | 2526203173 | Unknown | W2 | 3 | 6 | 6 | 6/6 COMPLETE ✓ | 1 | Cooling/Shakeout | N/A | 2650.00 | 2.650 | - | 1 | - | Order Total: 3 units
2025-11-29 | 2025-11-22 | Saturday | W2 | MCB-010 | 2526203173 | Unknown | W2 | 2 | 1 | 1 | 1/6 (16%) | 1 | Grinding | KVCALHMGR001 | 2650.00 | 2.650 | 300 min | 1 | 300 min | Order Total: 2 units
2025-11-29 | 2025-11-22 | Saturday | W2 | MCB-010 | 2526203173 | Unknown | W2 | 3 | 2 | 2 | 2/6 (33%) | 1 | Grinding | KVCALHMGR001 | 2650.00 | 2.650 | 300 min | 1 | 300 min | Order Total: 3 units
2025-11-29 | 2025-11-22 | Saturday | W2 | MCB-010 | 2526203173 | Unknown | W2 | 1 | 3 | 3 | 3/6 (50%) | 1 | Grinding | KVCALHMGR001 | 2650.00 | 2.650 | 300 min | 1 | 300 min | Order Total: 1 units
2025-11-29 | 2025-11-22 | Saturday | W2 | MCB-010 | 2526203173 | Unknown | W2 | 2 | 1 | 1 | 1/6 (16%) | 1 | MC1 | KVCAD50MC001 | 2650.00 | 2.650 | 60 min | 0 | - | Order Total: 2 units
2025-11-29 | 2025-11-22 | Saturday | W2 | MCB-010 | 2526203173 | Unknown | W2 | 3 | 2 | 2 | 2/6 (33%) | 1 | MC1 | KVCAD50MC001 | 2650.00 | 2.650 | 60 min | 0 | - | Order Total: 3 units
2025-11-29 | 2025-11-22 | Saturday | W2 | MCB-010 | 2526203173 | Unknown | W2 | 1 | 3 | 3 | 3/6 (50%) | 1 | MC1 | KVCAD50MC001 | 2650.00 | 2.650 | 60 min | 0 | - | Order Total: 1 units
2025-12-01 | 2025-11-24 | Monday | W2 | MCB-010 | 2526203173 | Unknown | W2 | 2 | 4 | 4 | 4/6 (66%) | 1 | Grinding | KVCALHMGR001 | 2650.00 | 2.650 | 300 min | 1 | 300 min | Order Total: 2 units
2025-12-01 | 2025-11-24 | Monday | W2 | MCB-010 | 2526203173 | Unknown | W2 | 3 | 5 | 5 | 5/6 (83%) | 1 | Grinding | KVCALHMGR001 | 2650.00 | 2.650 | 300 min | 1 | 300 min | Order Total: 3 units
2025-12-01 | 2025-11-24 | Monday | W2 | MCB-010 | 2526203173 | Unknown | W2 | 2 | 4 | 4 | 4/6 (66%) | 1 | MC1 | KVCAD50MC001 | 2650.00 | 2.650 | 60 min | 0 | - | Order Total: 2 units
2025-12-01 | 2025-11-24 | Monday | W2 | MCB-010 | 2526203173 | Unknown | W2 | 3 | 5 | 5 | 5/6 (83%) | 1 | MC1 | KVCAD50MC001 | 2650.00 | 2.650 | 60 min | 0 | - | Order Total: 3 units
2025-12-02 | 2025-11-22 | Tuesday | W2 | MCB-010 | 2526203173 | Unknown | W2 | 3 | 6 | 6 | 6/6 COMPLETE ✓ | 1 | Grinding | KVCALHMGR001 | 2650.00 | 2.650 | 300 min | 1 | 300 min | Order Total: 3 units
2025-12-02 | 2025-11-22 | Tuesday | W2 | MCB-010 | 2526203173 | Unknown | W2 | 3 | 6 | 6 | 6/6 COMPLETE ✓ | 1 | MC1 | KVCAD50MC001 | 2650.00 | 2.650 | 60 min | 0 | - | Order Total: 3 units
2025-12-06 | 2025-11-22 | Saturday | W3 | MCB-010 | 2526203173 | Unknown | W2 | 2 | 1 | 1 | 1/6 (16%) | 1 | SP1 | KVCALPPSP001 | 2650.00 | 2.650 | 12 min | 1 | 12 min | Order Total: 2 units
2025-12-06 | 2025-11-22 | Saturday | W3 | MCB-010 | 2526203173 | Unknown | W2 | 3 | 2 | 2 | 2/6 (33%) | 1 | SP1 | KVCALPPSP001 | 2650.00 | 2.650 | 12 min | 1 | 12 min | Order Total: 3 units
2025-12-06 | 2025-11-22 | Saturday | W3 | MCB-010 | 2526203173 | Unknown | W2 | 1 | 3 | 3 | 3/6 (50%) | 1 | SP1 | KVCALPPSP001 | 2650.00 | 2.650 | 12 min | 1 | 12 min | Order Total: 1 units
2025-12-08 | 2025-11-24 | Monday | W3 | MCB-010 | 2526203173 | Unknown | W2 | 2 | 4 | 4 | 4/6 (66%) | 1 | SP1 | KVCALPPSP001 | 2650.00 | 2.650 | 12 min | 1 | 12 min | Order Total: 2 units
2025-12-08 | 2025-11-24 | Monday | W3 | MCB-010 | 2526203173 | Unknown | W2 | 3 | 5 | 5 | 5/6 (83%) | 1 | SP1 | KVCALPPSP001 | 2650.00 | 2.650 | 12 min | 1 | 12 min | Order Total: 3 units
2025-12-09 | 2025-11-22 | Tuesday | W3 | MCB-010 | 2526203173 | Unknown | W2 | 3 | 6 | 6 | 6/6 COMPLETE ✓ | 1 | SP1 | KVCALPPSP001 | 2650.00 | 2.650 | 12 min | 1 | 12 min | Order Total: 3 units
2025-11-22 | 2025-11-22 | Saturday | W1 | MCB-010 | 2526203174 | Unknown | W2 | 2 | 1 | 1 | 1/3 (33%) | 1 | Casting | CS2MCB-010 | 2650.00 | 2.650 | 20 min | 1 | 20 min | Order Total: 2 units
2025-11-22 | 2025-11-22 | Saturday | W1 | MCB-010 | 2526203174 | Unknown | W2 | 2 | 2 | 2 | 2/3 (66%) | 1 | Casting | CS2MCB-010 | 2650.00 | 2.650 | 20 min | 1 | 20 min | Order Total: 2 units
2025-11-22 | 2025-11-22 | Saturday | W1 | MCB-010 | 2526203174 | Unknown | W2 | 1 | 3 | 3 | 3/3 COMPLETE ✓ | 1 | Casting | CS2MCB-010 | 2650.00 | 2.650 | 20 min | 1 | 20 min | Order Total: 1 units
2025-11-23 | 2025-11-22 | Sunday | W1 | MCB-010 | 2526203174 | Unknown | W2 | 2 | 1 | 1 | 1/3 (33%) | 1 | Cooling/Shakeout | N/A | 2650.00 | 2.650 | - | 1 | - | Order Total: 2 units
2025-11-23 | 2025-11-22 | Sunday | W1 | MCB-010 | 2526203174 | Unknown | W2 | 2 | 2 | 2 | 2/3 (66%) | 1 | Cooling/Shakeout | N/A | 2650.00 | 2.650 | - | 1 | - | Order Total: 2 units
2025-11-23 | 2025-11-22 | Sunday | W1 | MCB-010 | 2526203174 | Unknown | W2 | 1 | 3 | 3 | 3/3 COMPLETE ✓ | 1 | Cooling/Shakeout | N/A | 2650.00 | 2.650 | - | 1 | - | Order Total: 1 units
2025-11-24 | 2025-11-24 | Monday | W1 | MCB-010 | 2526203174 | Unknown | W2 | 2 | 4 | 4 | 4/3 COMPLETE ✓ | 1 | Casting | CS2MCB-010 | 2650.00 | 2.650 | 20 min | 1 | 20 min | Order Total: 2 units
2025-11-24 | 2025-11-24 | Monday | W1 | MCB-010 | 2526203174 | Unknown | W2 | 2 | 5 | 5 | 5/3 COMPLETE ✓ | 1 | Casting | CS2MCB-010 | 2650.00 | 2.650 | 20 min | 1 | 20 min | Order Total: 2 units
2025-11-25 | 2025-11-24 | Tuesday | W1 | MCB-010 | 2526203174 | Unknown | W2 | 2 | 4 | 4 | 4/3 COMPLETE ✓ | 1 | Cooling/Shakeout | N/A | 2650.00 | 2.650 | - | 1 | - | Order Total: 2 units
2025-11-25 | 2025-11-24 | Tuesday | W1 | MCB-010 | 2526203174 | Unknown | W2 | 2 | 5 | 5 | 5/3 COMPLETE ✓ | 1 | Cooling/Shakeout | N/A | 2650.00 | 2.650 | - | 1 | - | Order Total: 2 units
2025-11-29 | 2025-11-22 | Saturday | W2 | MCB-010 | 2526203174 | Unknown | W2 | 2 | 1 | 1 | 1/3 (33%) | 1 | Grinding | KVCALHMGR001 | 2650.00 | 2.650 | 300 min | 1 | 300 min | Order Total: 2 units
2025-11-29 | 2025-11-22 | Saturday | W2 | MCB-010 | 2526203174 | Unknown | W2 | 2 | 2 | 2 | 2/3 (66%) | 1 | Grinding | KVCALHMGR001 | 2650.00 | 2.650 | 300 min | 1 | 300 min | Order Total: 2 units
2025-11-29 | 2025-11-22 | Saturday | W2 | MCB-010 | 2526203174 | Unknown | W2 | 1 | 3 | 3 | 3/3 COMPLETE ✓ | 1 | Grinding | KVCALHMGR001 | 2650.00 | 2.650 | 300 min | 1 | 300 min | Order Total: 1 units
2025-11-29 | 2025-11-22 | Saturday | W2 | MCB-010 | 2526203174 | Unknown | W2 | 2 | 1 | 1 | 1/3 (33%) | 1 | MC1 | KVCAD50MC001 | 2650.00 | 2.650 | 60 min | 0 | - | Order Total: 2 units
2025-11-29 | 2025-11-22 | Saturday | W2 | MCB-010 | 2526203174 | Unknown | W2 | 2 | 2 | 2 | 2/3 (66%) | 1 | MC1 | KVCAD50MC001 | 2650.00 | 2.650 | 60 min | 0 | - | Order Total: 2 units
2025-11-29 | 2025-11-22 | Saturday | W2 | MCB-010 | 2526203174 | Unknown | W2 | 1 | 3 | 3 | 3/3 COMPLETE ✓ | 1 | MC1 | KVCAD50MC001 | 2650.00 | 2.650 | 60 min | 0 | - | Order Total: 1 units
2025-12-01 | 2025-11-24 | Monday | W2 | MCB-010 | 2526203174 | Unknown | W2 | 2 | 4 | 4 | 4/3 COMPLETE ✓ | 1 | Grinding | KVCALHMGR001 | 2650.00 | 2.650 | 300 min | 1 | 300 min | Order Total: 2 units
2025-12-01 | 2025-11-24 | Monday | W2 | MCB-010 | 2526203174 | Unknown | W2 | 2 | 5 | 5 | 5/3 COMPLETE ✓ | 1 | Grinding | KVCALHMGR001 | 2650.00 | 2.650 | 300 min | 1 | 300 min | Order Total: 2 units
2025-12-01 | 2025-11-24 | Monday | W2 | MCB-010 | 2526203174 | Unknown | W2 | 2 | 4 | 4 | 4/3 COMPLETE ✓ | 1 | MC1 | KVCAD50MC001 | 2650.00 | 2.650 | 60 min | 0 | - | Order Total: 2 units
2025-12-01 | 2025-11-24 | Monday | W2 | MCB-010 | 2526203174 | Unknown | W2 | 2 | 5 | 5 | 5/3 COMPLETE ✓ | 1 | MC1 | KVCAD50MC001 | 2650.00 | 2.650 | 60 min | 0 | - | Order Total: 2 units
2025-12-06 | 2025-11-22 | Saturday | W3 | MCB-010 | 2526203174 | Unknown | W2 | 2 | 1 | 1 | 1/3 (33%) | 1 | SP1 | KVCALPPSP001 | 2650.00 | 2.650 | 12 min | 1 | 12 min | Order Total: 2 units
2025-12-06 | 2025-11-22 | Saturday | W3 | MCB-010 | 2526203174 | Unknown | W2 | 2 | 2 | 2 | 2/3 (66%) | 1 | SP1 | KVCALPPSP001 | 2650.00 | 2.650 | 12 min | 1 | 12 min | Order Total: 2 units
2025-12-06 | 2025-11-22 | Saturday | W3 | MCB-010 | 2526203174 | Unknown | W2 | 1 | 3 | 3 | 3/3 COMPLETE ✓ | 1 | SP1 | KVCALPPSP001 | 2650.00 | 2.650 | 12 min | 1 | 12 min | Order Total: 1 units
2025-12-08 | 2025-11-24 | Monday | W3 | MCB-010 | 2526203174 | Unknown | W2 | 2 | 4 | 4 | 4/3 COMPLETE ✓ | 1 | SP1 | KVCALPPSP001 | 2650.00 | 2.650 | 12 min | 1 | 12 min | Order Total: 2 units
2025-12-08 | 2025-11-24 | Monday | W3 | MCB-010 | 2526203174 | Unknown | W2 | 2 | 5 | 5 | 5/3 COMPLETE ✓ | 1 | SP1 | KVCALPPSP001 | 2650.00 | 2.650 | 12 min | 1 | 12 min | Order Total: 2 units
2025-11-22 | 2025-11-22 | Saturday | W1 | MCB-010 | 2526203175 | Unknown | W2 | 2 | 1 | 1 | 1/3 (33%) | 1 | Casting | CS2MCB-010 | 2650.00 | 2.650 | 20 min | 1 | 20 min | Order Total: 2 units
2025-11-22 | 2025-11-22 | Saturday | W1 | MCB-010 | 2526203175 | Unknown | W2 | 2 | 2 | 2 | 2/3 (66%) | 1 | Casting | CS2MCB-010 | 2650.00 | 2.650 | 20 min | 1 | 20 min | Order Total: 2 units
2025-11-22 | 2025-11-22 | Saturday | W1 | MCB-010 | 2526203175 | Unknown | W2 | 1 | 3 | 3 | 3/3 COMPLETE ✓ | 1 | Casting | CS2MCB-010 | 2650.00 | 2.650 | 20 min | 1 | 20 min | Order Total: 1 units
2025-11-23 | 2025-11-22 | Sunday | W1 | MCB-010 | 2526203175 | Unknown | W2 | 2 | 1 | 1 | 1/3 (33%) | 1 | Cooling/Shakeout | N/A | 2650.00 | 2.650 | - | 1 | - | Order Total: 2 units
2025-11-23 | 2025-11-22 | Sunday | W1 | MCB-010 | 2526203175 | Unknown | W2 | 2 | 2 | 2 | 2/3 (66%) | 1 | Cooling/Shakeout | N/A | 2650.00 | 2.650 | - | 1 | - | Order Total: 2 units
2025-11-23 | 2025-11-22 | Sunday | W1 | MCB-010 | 2526203175 | Unknown | W2 | 1 | 3 | 3 | 3/3 COMPLETE ✓ | 1 | Cooling/Shakeout | N/A | 2650.00 | 2.650 | - | 1 | - | Order Total: 1 units
2025-11-24 | 2025-11-24 | Monday | W1 | MCB-010 | 2526203175 | Unknown | W2 | 2 | 4 | 4 | 4/3 COMPLETE ✓ | 1 | Casting | CS2MCB-010 | 2650.00 | 2.650 | 20 min | 1 | 20 min | Order Total: 2 units
2025-11-24 | 2025-11-24 | Monday | W1 | MCB-010 | 2526203175 | Unknown | W2 | 2 | 5 | 5 | 5/3 COMPLETE ✓ | 1 | Casting | CS2MCB-010 | 2650.00 | 2.650 | 20 min | 1 | 20 min | Order Total: 2 units
2025-11-25 | 2025-11-24 | Tuesday | W1 | MCB-010 | 2526203175 | Unknown | W2 | 2 | 4 | 4 | 4/3 COMPLETE ✓ | 1 | Cooling/Shakeout | N/A | 2650.00 | 2.650 | - | 1 | - | Order Total: 2 units
2025-11-25 | 2025-11-24 | Tuesday | W1 | MCB-010 | 2526203175 | Unknown | W2 | 2 | 5 | 5 | 5/3 COMPLETE ✓ | 1 | Cooling/Shakeout | N/A | 2650.00 | 2.650 | - | 1 | - | Order Total: 2 units
2025-11-29 | 2025-11-22 | Saturday | W2 | MCB-010 | 2526203175 | Unknown | W2 | 2 | 1 | 1 | 1/3 (33%) | 1 | Grinding | KVCALHMGR001 | 2650.00 | 2.650 | 300 min | 1 | 300 min | Order Total: 2 units
2025-11-29 | 2025-11-22 | Saturday | W2 | MCB-010 | 2526203175 | Unknown | W2 | 2 | 2 | 2 | 2/3 (66%) | 1 | Grinding | KVCALHMGR001 | 2650.00 | 2.650 | 300 min | 1 | 300 min | Order Total: 2 units
2025-11-29 | 2025-11-22 | Saturday | W2 | MCB-010 | 2526203175 | Unknown | W2 | 1 | 3 | 3 | 3/3 COMPLETE ✓ | 1 | Grinding | KVCALHMGR001 | 2650.00 | 2.650 | 300 min | 1 | 300 min | Order Total: 1 units
2025-11-29 | 2025-11-22 | Saturday | W2 | MCB-010 | 2526203175 | Unknown | W2 | 2 | 1 | 1 | 1/3 (33%) | 1 | MC1 | KVCAD50MC001 | 2650.00 | 2.650 | 60 min | 0 | - | Order Total: 2 units
2025-11-29 | 2025-11-22 | Saturday | W2 | MCB-010 | 2526203175 | Unknown | W2 | 2 | 2 | 2 | 2/3 (66%) | 1 | MC1 | KVCAD50MC001 | 2650.00 | 2.650 | 60 min | 0 | - | Order Total: 2 units
2025-11-29 | 2025-11-22 | Saturday | W2 | MCB-010 | 2526203175 | Unknown | W2 | 1 | 3 | 3 | 3/3 COMPLETE ✓ | 1 | MC1 | KVCAD50MC001 | 2650.00 | 2.650 | 60 min | 0 | - | Order Total: 1 units
2025-12-01 | 2025-11-24 | Monday | W2 | MCB-010 | 2526203175 | Unknown | W2 | 2 | 4 | 4 | 4/3 COMPLETE ✓ | 1 | Grinding | KVCALHMGR001 | 2650.00 | 2.650 | 300 min | 1 | 300 min | Order Total: 2 units
2025-12-01 | 2025-11-24 | Monday | W2 | MCB-010 | 2526203175 | Unknown | W2 | 2 | 5 | 5 | 5/3 COMPLETE ✓ | 1 | Grinding | KVCALHMGR001 | 2650.00 | 2.650 | 300 min | 1 | 300 min | Order Total: 2 units
2025-12-01 | 2025-11-24 | Monday | W2 | MCB-010 | 2526203175 | Unknown | W2 | 2 | 4 | 4 | 4/3 COMPLETE ✓ | 1 | MC1 | KVCAD50MC001 | 2650.00 | 2.650 | 60 min | 0 | - | Order Total: 2 units
2025-12-01 | 2025-11-24 | Monday | W2 | MCB-010 | 2526203175 | Unknown | W2 | 2 | 5 | 5 | 5/3 COMPLETE ✓ | 1 | MC1 | KVCAD50MC001 | 2650.00 | 2.650 | 60 min | 0 | - | Order Total: 2 units
2025-12-06 | 2025-11-22 | Saturday | W3 | MCB-010 | 2526203175 | Unknown | W2 | 2 | 1 | 1 | 1/3 (33%) | 1 | SP1 | KVCALPPSP001 | 2650.00 | 2.650 | 12 min | 1 | 12 min | Order Total: 2 units
2025-12-06 | 2025-11-22 | Saturday | W3 | MCB-010 | 2526203175 | Unknown | W2 | 2 | 2 | 2 | 2/3 (66%) | 1 | SP1 | KVCALPPSP001 | 2650.00 | 2.650 | 12 min | 1 | 12 min | Order Total: 2 units
2025-12-06 | 2025-11-22 | Saturday | W3 | MCB-010 | 2526203175 | Unknown | W2 | 1 | 3 | 3 | 3/3 COMPLETE ✓ | 1 | SP1 | KVCALPPSP001 | 2650.00 | 2.650 | 12 min | 1 | 12 min | Order Total: 1 units
2025-12-08 | 2025-11-24 | Monday | W3 | MCB-010 | 2526203175 | Unknown | W2 | 2 | 4 | 4 | 4/3 COMPLETE ✓ | 1 | SP1 | KVCALPPSP001 | 2650.00 | 2.650 | 12 min | 1 | 12 min | Order Total: 2 units
2025-12-08 | 2025-11-24 | Monday | W3 | MCB-010 | 2526203175 | Unknown | W2 | 2 | 5 | 5 | 5/3 COMPLETE ✓ | 1 | SP1 | KVCALPPSP001 | 2650.00 | 2.650 | 12 min | 1 | 12 min | Order Total: 2 units
2025-11-22 | 2025-11-22 | Saturday | W1 | MCB-010 | 2526203176 | Unknown | W2 | 1 | 1 | 1 | 1/3 (33%) | 1 | Casting | CS2MCB-010 | 2650.00 | 2.650 | 20 min | 1 | 20 min | Order Total: 1 units
2025-11-22 | 2025-11-22 | Saturday | W1 | MCB-010 | 2526203176 | Unknown | W2 | 2 | 2 | 2 | 2/3 (66%) | 1 | Casting | CS2MCB-010 | 2650.00 | 2.650 | 20 min | 1 | 20 min | Order Total: 2 units
2025-11-22 | 2025-11-22 | Saturday | W1 | MCB-010 | 2526203176 | Unknown | W2 | 1 | 3 | 3 | 3/3 COMPLETE ✓ | 1 | Casting | CS2MCB-010 | 2650.00 | 2.650 | 20 min | 1 | 20 min | Order Total: 1 units
2025-11-23 | 2025-11-22 | Sunday | W1 | MCB-010 | 2526203176 | Unknown | W2 | 1 | 1 | 1 | 1/3 (33%) | 1 | Cooling/Shakeout | N/A | 2650.00 | 2.650 | - | 1 | - | Order Total: 1 units
2025-11-23 | 2025-11-22 | Sunday | W1 | MCB-010 | 2526203176 | Unknown | W2 | 2 | 2 | 2 | 2/3 (66%) | 1 | Cooling/Shakeout | N/A | 2650.00 | 2.650 | - | 1 | - | Order Total: 2 units
2025-11-23 | 2025-11-22 | Sunday | W1 | MCB-010 | 2526203176 | Unknown | W2 | 1 | 3 | 3 | 3/3 COMPLETE ✓ | 1 | Cooling/Shakeout | N/A | 2650.00 | 2.650 | - | 1 | - | Order Total: 1 units
2025-11-24 | 2025-11-24 | Monday | W1 | MCB-010 | 2526203176 | Unknown | W2 | 2 | 4 | 4 | 4/3 COMPLETE ✓ | 1 | Casting | CS2MCB-010 | 2650.00 | 2.650 | 20 min | 1 | 20 min | Order Total: 2 units
2025-11-25 | 2025-11-22 | Tuesday | W1 | MCB-010 | 2526203176 | Unknown | W2 | 2 | 4 | 4 | 4/3 COMPLETE ✓ | 1 | Cooling/Shakeout | N/A | 2650.00 | 2.650 | - | 1 | - | Order Total: 2 units
2025-11-29 | 2025-11-22 | Saturday | W2 | MCB-010 | 2526203176 | Unknown | W2 | 1 | 1 | 1 | 1/3 (33%) | 1 | Grinding | KVCALHMGR001 | 2650.00 | 2.650 | 300 min | 1 | 300 min | Order Total: 1 units
2025-11-29 | 2025-11-22 | Saturday | W2 | MCB-010 | 2526203176 | Unknown | W2 | 2 | 2 | 2 | 2/3 (66%) | 1 | Grinding | KVCALHMGR001 | 2650.00 | 2.650 | 300 min | 1 | 300 min | Order Total: 2 units
2025-11-29 | 2025-11-22 | Saturday | W2 | MCB-010 | 2526203176 | Unknown | W2 | 1 | 3 | 3 | 3/3 COMPLETE ✓ | 1 | Grinding | KVCALHMGR001 | 2650.00 | 2.650 | 300 min | 1 | 300 min | Order Total: 1 units
2025-11-29 | 2025-11-22 | Saturday | W2 | MCB-010 | 2526203176 | Unknown | W2 | 1 | 1 | 1 | 1/3 (33%) | 1 | MC1 | KVCAD50MC001 | 2650.00 | 2.650 | 60 min | 0 | - | Order Total: 1 units
2025-11-29 | 2025-11-22 | Saturday | W2 | MCB-010 | 2526203176 | Unknown | W2 | 2 | 2 | 2 | 2/3 (66%) | 1 | MC1 | KVCAD50MC001 | 2650.00 | 2.650 | 60 min | 0 | - | Order Total: 2 units
2025-11-29 | 2025-11-22 | Saturday | W2 | MCB-010 | 2526203176 | Unknown | W2 | 1 | 3 | 3 | 3/3 COMPLETE ✓ | 1 | MC1 | KVCAD50MC001 | 2650.00 | 2.650 | 60 min | 0 | - | Order Total: 1 units
2025-12-01 | 2025-11-22 | Monday | W2 | MCB-010 | 2526203176 | Unknown | W2 | 2 | 4 | 4 | 4/3 COMPLETE ✓ | 1 | Grinding | KVCALHMGR001 | 2650.00 | 2.650 | 300 min | 1 | 300 min | Order Total: 2 units
2025-12-01 | 2025-11-22 | Monday | W2 | MCB-010 | 2526203176 | Unknown | W2 | 2 | 4 | 4 | 4/3 COMPLETE ✓ | 1 | MC1 | KVCAD50MC001 | 2650.00 | 2.650 | 60 min | 0 | - | Order Total: 2 units
2025-12-06 | 2025-11-22 | Saturday | W3 | MCB-010 | 2526203176 | Unknown | W2 | 1 | 1 | 1 | 1/3 (33%) | 1 | SP1 | KVCALPPSP001 | 2650.00 | 2.650 | 12 min | 1 | 12 min | Order Total: 1 units
2025-12-06 | 2025-11-22 | Saturday | W3 | MCB-010 | 2526203176 | Unknown | W2 | 2 | 2 | 2 | 2/3 (66%) | 1 | SP1 | KVCALPPSP001 | 2650.00 | 2.650 | 12 min | 1 | 12 min | Order Total: 2 units
2025-12-06 | 2025-11-22 | Saturday | W3 | MCB-010 | 2526203176 | Unknown | W2 | 1 | 3 | 3 | 3/3 COMPLETE ✓ | 1 | SP1 | KVCALPPSP001 | 2650.00 | 2.650 | 12 min | 1 | 12 min | Order Total: 1 units
2025-12-08 | 2025-11-22 | Monday | W3 | MCB-010 | 2526203176 | Unknown | W2 | 2 | 4 | 4 | 4/3 COMPLETE ✓ | 1 | SP1 | KVCALPPSP001 | 2650.00 | 2.650 | 12 min | 1 | 12 min | Order Total: 2 units
2025-11-22 | 2025-11-22 | Saturday | W1 | MCB-010 | 2526203177 | Unknown | W2 | 1 | 1 | 1 | 1/3 (33%) | 1 | Casting | CS2MCB-010 | 2650.00 | 2.650 | 20 min | 1 | 20 min | Order Total: 1 units
2025-11-22 | 2025-11-22 | Saturday | W1 | MCB-010 | 2526203177 | Unknown | W2 | 2 | 2 | 2 | 2/3 (66%) | 1 | Casting | CS2MCB-010 | 2650.00 | 2.650 | 20 min | 1 | 20 min | Order Total: 2 units
2025-11-22 | 2025-11-22 | Saturday | W1 | MCB-010 | 2526203177 | Unknown | W2 | 1 | 3 | 3 | 3/3 COMPLETE ✓ | 1 | Casting | CS2MCB-010 | 2650.00 | 2.650 | 20 min | 1 | 20 min | Order Total: 1 units
2025-11-23 | 2025-11-22 | Sunday | W1 | MCB-010 | 2526203177 | Unknown | W2 | 1 | 1 | 1 | 1/3 (33%) | 1 | Cooling/Shakeout | N/A | 2650.00 | 2.650 | - | 1 | - | Order Total: 1 units
2025-11-23 | 2025-11-22 | Sunday | W1 | MCB-010 | 2526203177 | Unknown | W2 | 2 | 2 | 2 | 2/3 (66%) | 1 | Cooling/Shakeout | N/A | 2650.00 | 2.650 | - | 1 | - | Order Total: 2 units
2025-11-23 | 2025-11-22 | Sunday | W1 | MCB-010 | 2526203177 | Unknown | W2 | 1 | 3 | 3 | 3/3 COMPLETE ✓ | 1 | Cooling/Shakeout | N/A | 2650.00 | 2.650 | - | 1 | - | Order Total: 1 units
2025-11-24 | 2025-11-24 | Monday | W1 | MCB-010 | 2526203177 | Unknown | W2 | 2 | 4 | 4 | 4/3 COMPLETE ✓ | 1 | Casting | CS2MCB-010 | 2650.00 | 2.650 | 20 min | 1 | 20 min | Order Total: 2 units
2025-11-25 | 2025-11-22 | Tuesday | W1 | MCB-010 | 2526203177 | Unknown | W2 | 2 | 4 | 4 | 4/3 COMPLETE ✓ | 1 | Cooling/Shakeout | N/A | 2650.00 | 2.650 | - | 1 | - | Order Total: 2 units
2025-11-29 | 2025-11-22 | Saturday | W2 | MCB-010 | 2526203177 | Unknown | W2 | 1 | 1 | 1 | 1/3 (33%) | 1 | Grinding | KVCALHMGR001 | 2650.00 | 2.650 | 300 min | 1 | 300 min | Order Total: 1 units
2025-11-29 | 2025-11-22 | Saturday | W2 | MCB-010 | 2526203177 | Unknown | W2 | 2 | 2 | 2 | 2/3 (66%) | 1 | Grinding | KVCALHMGR001 | 2650.00 | 2.650 | 300 min | 1 | 300 min | Order Total: 2 units
2025-11-29 | 2025-11-22 | Saturday | W2 | MCB-010 | 2526203177 | Unknown | W2 | 1 | 3 | 3 | 3/3 COMPLETE ✓ | 1 | Grinding | KVCALHMGR001 | 2650.00 | 2.650 | 300 min | 1 | 300 min | Order Total: 1 units
2025-11-29 | 2025-11-22 | Saturday | W2 | MCB-010 | 2526203177 | Unknown | W2 | 1 | 1 | 1 | 1/3 (33%) | 1 | MC1 | KVCAD50MC001 | 2650.00 | 2.650 | 60 min | 0 | - | Order Total: 1 units
2025-11-29 | 2025-11-22 | Saturday | W2 | MCB-010 | 2526203177 | Unknown | W2 | 2 | 2 | 2 | 2/3 (66%) | 1 | MC1 | KVCAD50MC001 | 2650.00 | 2.650 | 60 min | 0 | - | Order Total: 2 units
2025-11-29 | 2025-11-22 | Saturday | W2 | MCB-010 | 2526203177 | Unknown | W2 | 1 | 3 | 3 | 3/3 COMPLETE ✓ | 1 | MC1 | KVCAD50MC001 | 2650.00 | 2.650 | 60 min | 0 | - | Order Total: 1 units
2025-12-01 | 2025-11-22 | Monday | W2 | MCB-010 | 2526203177 | Unknown | W2 | 2 | 4 | 4 | 4/3 COMPLETE ✓ | 1 | Grinding | KVCALHMGR001 | 2650.00 | 2.650 | 300 min | 1 | 300 min | Order Total: 2 units
2025-12-01 | 2025-11-22 | Monday | W2 | MCB-010 | 2526203177 | Unknown | W2 | 2 | 4 | 4 | 4/3 COMPLETE ✓ | 1 | MC1 | KVCAD50MC001 | 2650.00 | 2.650 | 60 min | 0 | - | Order Total: 2 units
2025-12-06 | 2025-11-22 | Saturday | W3 | MCB-010 | 2526203177 | Unknown | W2 | 1 | 1 | 1 | 1/3 (33%) | 1 | SP1 | KVCALPPSP001 | 2650.00 | 2.650 | 12 min | 1 | 12 min | Order Total: 1 units
2025-12-06 | 2025-11-22 | Saturday | W3 | MCB-010 | 2526203177 | Unknown | W2 | 2 | 2 | 2 | 2/3 (66%) | 1 | SP1 | KVCALPPSP001 | 2650.00 | 2.650 | 12 min | 1 | 12 min | Order Total: 2 units
2025-12-06 | 2025-11-22 | Saturday | W3 | MCB-010 | 2526203177 | Unknown | W2 | 1 | 3 | 3 | 3/3 COMPLETE ✓ | 1 | SP1 | KVCALPPSP001 | 2650.00 | 2.650 | 12 min | 1 | 12 min | Order Total: 1 units
2025-12-08 | 2025-11-22 | Monday | W3 | MCB-010 | 2526203177 | Unknown | W2 | 2 | 4 | 4 | 4/3 COMPLETE ✓ | 1 | SP1 | KVCALPPSP001 | 2650.00 | 2.650 | 12 min | 1 | 12 min | Order Total: 2 units
2025-11-29 | 2025-11-29 | Saturday | W2 | ATT-002 | 2526203236 | Unknown | W5 | 28 | 1 | 28 | 28/28 COMPLETE ✓ | 28 | Casting | CS-ATT-002 | 640.00 | 17.920 | 20 min | 1 | 560 min | Order Total: 28 units
2025-11-30 | 2025-11-29 | Sunday | W2 | ATT-002 | 2526203236 | Unknown | W5 | 28 | 1 | 28 | 28/28 COMPLETE ✓ | 28 | Cooling/Shakeout | N/A | 640.00 | 17.920 | - | 1 | - | Order Total: 28 units
2025-11-22 | 2025-11-22 | Saturday | W1 | MCB-JLG-019 | 2526203249 | Unknown | W2 | 1 | 1 | 1 | 1/16 (6%) | 1 | Casting | CS2MCB-JLG-019 | 1278.58 | 1.279 | 24 min | 1 | 24 min | Order Total: 1 units
2025-11-22 | 2025-11-22 | Saturday | W1 | MCB-JLG-019 | 2526203249 | Unknown | W2 | 15 | 2 | 6 | 6/16 (37%) | 5 | Casting | CS2MCB-JLG-019 | 1278.58 | 6.393 | 24 min | 1 | 120 min | Order Total: 15 units
2025-11-23 | 2025-11-22 | Sunday | W1 | MCB-JLG-019 | 2526203249 | Unknown | W2 | 1 | 1 | 1 | 1/16 (6%) | 1 | Cooling/Shakeout | N/A | 1278.58 | 1.279 | - | 1 | - | Order Total: 1 units
2025-11-23 | 2025-11-22 | Sunday | W1 | MCB-JLG-019 | 2526203249 | Unknown | W2 | 15 | 2 | 4 | 4/16 (25%) | 3 | Cooling/Shakeout | N/A | 1278.58 | 3.836 | - | 1 | - | Order Total: 15 units
2025-11-24 | 2025-11-24 | Monday | W1 | MCB-JLG-019 | 2526203249 | Unknown | W2 | 15 | 3 | 10 | 10/16 (62%) | 4 | Casting | CS2MCB-JLG-019 | 1278.58 | 5.114 | 24 min | 1 | 96 min | Order Total: 15 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | MCB-JLG-019 | 2526203249 | Unknown | W2 | 15 | 4 | 16 | 16/16 COMPLETE ✓ | 6 | Casting | CS2MCB-JLG-019 | 1278.58 | 7.671 | 24 min | 1 | 144 min | Order Total: 15 units
2025-11-25 | 2025-11-22 | Tuesday | W1 | MCB-JLG-019 | 2526203249 | Unknown | W2 | 15 | 3 | 8 | 8/16 (50%) | 4 | Cooling/Shakeout | N/A | 1278.58 | 5.114 | - | 1 | - | Order Total: 15 units
2025-11-26 | 2025-11-24 | Wednesday | W1 | MCB-JLG-019 | 2526203249 | Unknown | W2 | 15 | 4 | 12 | 12/16 (75%) | 4 | Cooling/Shakeout | N/A | 1278.58 | 5.114 | - | 1 | - | Order Total: 15 units
2025-11-27 | 2025-11-25 | Thursday | W1 | MCB-JLG-019 | 2526203249 | Unknown | W2 | 15 | 5 | 16 | 16/16 COMPLETE ✓ | 4 | Cooling/Shakeout | N/A | 1278.58 | 5.114 | - | 1 | - | Order Total: 15 units
2025-11-29 | 2025-11-22 | Saturday | W2 | MCB-JLG-019 | 2526203249 | Unknown | W2 | 1 | 1 | 1 | 1/16 (6%) | 1 | Grinding | KVCALHMGR001 | 1278.58 | 1.279 | 120 min | 1 | 120 min | Order Total: 1 units
2025-11-29 | 2025-11-22 | Saturday | W2 | MCB-JLG-019 | 2526203249 | Unknown | W2 | 15 | 2 | 4 | 4/16 (25%) | 3 | Grinding | KVCALHMGR001 | 1278.58 | 3.836 | 120 min | 1 | 360 min | Order Total: 15 units
2025-12-01 | 2025-11-22 | Monday | W2 | MCB-JLG-019 | 2526203249 | Unknown | W2 | 15 | 3 | 8 | 8/16 (50%) | 4 | Grinding | KVCALHMGR001 | 1278.58 | 5.114 | 120 min | 1 | 480 min | Order Total: 15 units
2025-12-02 | 2025-11-24 | Tuesday | W2 | MCB-JLG-019 | 2526203249 | Unknown | W2 | 15 | 4 | 12 | 12/16 (75%) | 4 | Grinding | KVCALHMGR001 | 1278.58 | 5.114 | 120 min | 1 | 480 min | Order Total: 15 units
2025-12-03 | 2025-11-25 | Wednesday | W2 | MCB-JLG-019 | 2526203249 | Unknown | W2 | 15 | 5 | 16 | 16/16 COMPLETE ✓ | 4 | Grinding | KVCALHMGR001 | 1278.58 | 5.114 | 120 min | 1 | 480 min | Order Total: 15 units
2025-12-06 | 2025-11-22 | Saturday | W3 | MCB-JLG-019 | 2526203249 | Unknown | W2 | 1 | 1 | 1 | 1/16 (6%) | 1 | SP1 | KVCALPPSP001 | 1278.58 | 1.279 | 7 min | 1 | 7 min | Order Total: 1 units
2025-12-06 | 2025-11-22 | Saturday | W3 | MCB-JLG-019 | 2526203249 | Unknown | W2 | 15 | 2 | 4 | 4/16 (25%) | 3 | SP1 | KVCALPPSP001 | 1278.58 | 3.836 | 7 min | 1 | 21 min | Order Total: 15 units
2025-12-08 | 2025-11-22 | Monday | W3 | MCB-JLG-019 | 2526203249 | Unknown | W2 | 15 | 3 | 8 | 8/16 (50%) | 4 | SP1 | KVCALPPSP001 | 1278.58 | 5.114 | 7 min | 1 | 28 min | Order Total: 15 units
2025-12-09 | 2025-11-24 | Tuesday | W3 | MCB-JLG-019 | 2526203249 | Unknown | W2 | 15 | 4 | 12 | 12/16 (75%) | 4 | SP1 | KVCALPPSP001 | 1278.58 | 5.114 | 7 min | 1 | 28 min | Order Total: 15 units
2025-12-10 | 2025-11-25 | Wednesday | W3 | MCB-JLG-019 | 2526203249 | Unknown | W2 | 15 | 5 | 16 | 16/16 COMPLETE ✓ | 4 | SP1 | KVCALPPSP001 | 1278.58 | 5.114 | 7 min | 1 | 28 min | Order Total: 15 units
2025-11-22 | 2025-11-22 | Saturday | W1 | MCB-JLG-019 | 2526203250 | Unknown | W2 | 1 | 1 | 1 | 1/15 (6%) | 1 | Casting | CS2MCB-JLG-019 | 1278.58 | 1.279 | 24 min | 1 | 24 min | Order Total: 1 units
2025-11-22 | 2025-11-22 | Saturday | W1 | MCB-JLG-019 | 2526203250 | Unknown | W2 | 14 | 2 | 5 | 5/15 (33%) | 4 | Casting | CS2MCB-JLG-019 | 1278.58 | 5.114 | 24 min | 1 | 96 min | Order Total: 14 units
2025-11-23 | 2025-11-22 | Sunday | W1 | MCB-JLG-019 | 2526203250 | Unknown | W2 | 1 | 1 | 1 | 1/15 (6%) | 1 | Cooling/Shakeout | N/A | 1278.58 | 1.279 | - | 1 | - | Order Total: 1 units
2025-11-23 | 2025-11-22 | Sunday | W1 | MCB-JLG-019 | 2526203250 | Unknown | W2 | 14 | 2 | 4 | 4/15 (26%) | 3 | Cooling/Shakeout | N/A | 1278.58 | 3.836 | - | 1 | - | Order Total: 14 units
2025-11-24 | 2025-11-24 | Monday | W1 | MCB-JLG-019 | 2526203250 | Unknown | W2 | 14 | 3 | 9 | 9/15 (60%) | 4 | Casting | CS2MCB-JLG-019 | 1278.58 | 5.114 | 24 min | 1 | 96 min | Order Total: 14 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | MCB-JLG-019 | 2526203250 | Unknown | W2 | 14 | 4 | 15 | 15/15 COMPLETE ✓ | 6 | Casting | CS2MCB-JLG-019 | 1278.58 | 7.671 | 24 min | 1 | 144 min | Order Total: 14 units
2025-11-25 | 2025-11-22 | Tuesday | W1 | MCB-JLG-019 | 2526203250 | Unknown | W2 | 14 | 3 | 7 | 7/15 (46%) | 3 | Cooling/Shakeout | N/A | 1278.58 | 3.836 | - | 1 | - | Order Total: 14 units
2025-11-26 | 2025-11-24 | Wednesday | W1 | MCB-JLG-019 | 2526203250 | Unknown | W2 | 14 | 4 | 11 | 11/15 (73%) | 4 | Cooling/Shakeout | N/A | 1278.58 | 5.114 | - | 1 | - | Order Total: 14 units
2025-11-27 | 2025-11-25 | Thursday | W1 | MCB-JLG-019 | 2526203250 | Unknown | W2 | 14 | 5 | 15 | 15/15 COMPLETE ✓ | 4 | Cooling/Shakeout | N/A | 1278.58 | 5.114 | - | 1 | - | Order Total: 14 units
2025-11-29 | 2025-11-22 | Saturday | W2 | MCB-JLG-019 | 2526203250 | Unknown | W2 | 1 | 1 | 1 | 1/15 (6%) | 1 | Grinding | KVCALHMGR001 | 1278.58 | 1.279 | 120 min | 1 | 120 min | Order Total: 1 units
2025-11-29 | 2025-11-22 | Saturday | W2 | MCB-JLG-019 | 2526203250 | Unknown | W2 | 14 | 2 | 4 | 4/15 (26%) | 3 | Grinding | KVCALHMGR001 | 1278.58 | 3.836 | 120 min | 1 | 360 min | Order Total: 14 units
2025-12-01 | 2025-11-22 | Monday | W2 | MCB-JLG-019 | 2526203250 | Unknown | W2 | 14 | 3 | 7 | 7/15 (46%) | 3 | Grinding | KVCALHMGR001 | 1278.58 | 3.836 | 120 min | 1 | 360 min | Order Total: 14 units
2025-12-02 | 2025-11-24 | Tuesday | W2 | MCB-JLG-019 | 2526203250 | Unknown | W2 | 14 | 4 | 11 | 11/15 (73%) | 4 | Grinding | KVCALHMGR001 | 1278.58 | 5.114 | 120 min | 1 | 480 min | Order Total: 14 units
2025-12-03 | 2025-11-25 | Wednesday | W2 | MCB-JLG-019 | 2526203250 | Unknown | W2 | 14 | 5 | 15 | 15/15 COMPLETE ✓ | 4 | Grinding | KVCALHMGR001 | 1278.58 | 5.114 | 120 min | 1 | 480 min | Order Total: 14 units
2025-12-06 | 2025-11-22 | Saturday | W3 | MCB-JLG-019 | 2526203250 | Unknown | W2 | 1 | 1 | 1 | 1/15 (6%) | 1 | SP1 | KVCALPPSP001 | 1278.58 | 1.279 | 7 min | 1 | 7 min | Order Total: 1 units
2025-12-06 | 2025-11-22 | Saturday | W3 | MCB-JLG-019 | 2526203250 | Unknown | W2 | 14 | 2 | 4 | 4/15 (26%) | 3 | SP1 | KVCALPPSP001 | 1278.58 | 3.836 | 7 min | 1 | 21 min | Order Total: 14 units
2025-12-08 | 2025-11-22 | Monday | W3 | MCB-JLG-019 | 2526203250 | Unknown | W2 | 14 | 3 | 7 | 7/15 (46%) | 3 | SP1 | KVCALPPSP001 | 1278.58 | 3.836 | 7 min | 1 | 21 min | Order Total: 14 units
2025-12-09 | 2025-11-24 | Tuesday | W3 | MCB-JLG-019 | 2526203250 | Unknown | W2 | 14 | 4 | 11 | 11/15 (73%) | 4 | SP1 | KVCALPPSP001 | 1278.58 | 5.114 | 7 min | 1 | 28 min | Order Total: 14 units
2025-12-10 | 2025-11-25 | Wednesday | W3 | MCB-JLG-019 | 2526203250 | Unknown | W2 | 14 | 5 | 15 | 15/15 COMPLETE ✓ | 4 | SP1 | KVCALPPSP001 | 1278.58 | 5.114 | 7 min | 1 | 28 min | Order Total: 14 units
2025-11-22 | 2025-11-22 | Saturday | W1 | MCB-JLG-019 | 2526203251 | Unknown | W2 | 14 | 1 | 4 | 4/14 (28%) | 4 | Casting | CS2MCB-JLG-019 | 1278.58 | 5.114 | 24 min | 1 | 96 min | Order Total: 14 units
2025-11-23 | 2025-11-22 | Sunday | W1 | MCB-JLG-019 | 2526203251 | Unknown | W2 | 14 | 1 | 3 | 3/14 (21%) | 3 | Cooling/Shakeout | N/A | 1278.58 | 3.836 | - | 1 | - | Order Total: 14 units
2025-11-24 | 2025-11-24 | Monday | W1 | MCB-JLG-019 | 2526203251 | Unknown | W2 | 14 | 2 | 8 | 8/14 (57%) | 4 | Casting | CS2MCB-JLG-019 | 1278.58 | 5.114 | 24 min | 1 | 96 min | Order Total: 14 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | MCB-JLG-019 | 2526203251 | Unknown | W2 | 14 | 3 | 14 | 14/14 COMPLETE ✓ | 6 | Casting | CS2MCB-JLG-019 | 1278.58 | 7.671 | 24 min | 1 | 144 min | Order Total: 14 units
2025-11-25 | 2025-11-24 | Tuesday | W1 | MCB-JLG-019 | 2526203251 | Unknown | W2 | 14 | 2 | 6 | 6/14 (42%) | 3 | Cooling/Shakeout | N/A | 1278.58 | 3.836 | - | 1 | - | Order Total: 14 units
2025-11-26 | 2025-11-25 | Wednesday | W1 | MCB-JLG-019 | 2526203251 | Unknown | W2 | 14 | 3 | 10 | 10/14 (71%) | 4 | Cooling/Shakeout | N/A | 1278.58 | 5.114 | - | 1 | - | Order Total: 14 units
2025-11-27 | 2025-11-22 | Thursday | W1 | MCB-JLG-019 | 2526203251 | Unknown | W2 | 14 | 4 | 14 | 14/14 COMPLETE ✓ | 4 | Cooling/Shakeout | N/A | 1278.58 | 5.114 | - | 1 | - | Order Total: 14 units
2025-11-29 | 2025-11-22 | Saturday | W2 | MCB-JLG-019 | 2526203251 | Unknown | W2 | 14 | 1 | 3 | 3/14 (21%) | 3 | Grinding | KVCALHMGR001 | 1278.58 | 3.836 | 120 min | 1 | 360 min | Order Total: 14 units
2025-12-01 | 2025-11-24 | Monday | W2 | MCB-JLG-019 | 2526203251 | Unknown | W2 | 14 | 2 | 6 | 6/14 (42%) | 3 | Grinding | KVCALHMGR001 | 1278.58 | 3.836 | 120 min | 1 | 360 min | Order Total: 14 units
2025-12-02 | 2025-11-25 | Tuesday | W2 | MCB-JLG-019 | 2526203251 | Unknown | W2 | 14 | 3 | 10 | 10/14 (71%) | 4 | Grinding | KVCALHMGR001 | 1278.58 | 5.114 | 120 min | 1 | 480 min | Order Total: 14 units
2025-12-03 | 2025-11-22 | Wednesday | W2 | MCB-JLG-019 | 2526203251 | Unknown | W2 | 14 | 4 | 14 | 14/14 COMPLETE ✓ | 4 | Grinding | KVCALHMGR001 | 1278.58 | 5.114 | 120 min | 1 | 480 min | Order Total: 14 units
2025-12-06 | 2025-11-22 | Saturday | W3 | MCB-JLG-019 | 2526203251 | Unknown | W2 | 14 | 1 | 3 | 3/14 (21%) | 3 | SP1 | KVCALPPSP001 | 1278.58 | 3.836 | 7 min | 1 | 21 min | Order Total: 14 units
2025-12-08 | 2025-11-24 | Monday | W3 | MCB-JLG-019 | 2526203251 | Unknown | W2 | 14 | 2 | 6 | 6/14 (42%) | 3 | SP1 | KVCALPPSP001 | 1278.58 | 3.836 | 7 min | 1 | 21 min | Order Total: 14 units
2025-12-09 | 2025-11-25 | Tuesday | W3 | MCB-JLG-019 | 2526203251 | Unknown | W2 | 14 | 3 | 10 | 10/14 (71%) | 4 | SP1 | KVCALPPSP001 | 1278.58 | 5.114 | 7 min | 1 | 28 min | Order Total: 14 units
2025-12-10 | 2025-11-22 | Wednesday | W3 | MCB-JLG-019 | 2526203251 | Unknown | W2 | 14 | 4 | 14 | 14/14 COMPLETE ✓ | 4 | SP1 | KVCALPPSP001 | 1278.58 | 5.114 | 7 min | 1 | 28 min | Order Total: 14 units
2025-11-22 | 2025-11-22 | Saturday | W1 | MCB-HYG-023 | 2526203252 | Unknown | W3 | 6 | 1 | 2 | 2/6 (33%) | 2 | SP1 | KVCALPPSP001 | 2942.00 | 5.884 | 12 min | 1 | 24 min | Order Total: 6 units
2025-11-24 | 2025-11-24 | Monday | W1 | MCB-HYG-023 | 2526203252 | Unknown | W3 | 6 | 2 | 4 | 4/6 (66%) | 2 | SP1 | KVCALPPSP001 | 2942.00 | 5.884 | 12 min | 1 | 24 min | Order Total: 6 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | MCB-HYG-023 | 2526203252 | Unknown | W3 | 6 | 3 | 6 | 6/6 COMPLETE ✓ | 2 | SP1 | KVCALPPSP001 | 2942.00 | 5.884 | 12 min | 1 | 24 min | Order Total: 6 units
2025-11-22 | 2025-11-22 | Saturday | W1 | MCB-HYG-015 | 2526203253 | Unknown | W3 | 8 | 1 | 2 | 2/8 (25%) | 2 | Grinding | KVCALHMGR001 | 2119.00 | 4.238 | 450 min | 1 | 900 min | Order Total: 8 units
2025-11-22 | 2025-11-22 | Saturday | W1 | MCB-HYG-015 | 2526203253 | Unknown | W3 | 8 | 1 | 2 | 2/8 (25%) | 2 | MC1 | KVCAD50MC001 | 2119.00 | 4.238 | 45 min | 0 | - | Order Total: 8 units
2025-11-24 | 2025-11-24 | Monday | W1 | MCB-HYG-015 | 2526203253 | Unknown | W3 | 8 | 2 | 4 | 4/8 (50%) | 2 | Grinding | KVCALHMGR001 | 2119.00 | 4.238 | 450 min | 1 | 900 min | Order Total: 8 units
2025-11-24 | 2025-11-24 | Monday | W1 | MCB-HYG-015 | 2526203253 | Unknown | W3 | 8 | 2 | 4 | 4/8 (50%) | 2 | MC1 | KVCAD50MC001 | 2119.00 | 4.238 | 45 min | 0 | - | Order Total: 8 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | MCB-HYG-015 | 2526203253 | Unknown | W3 | 8 | 3 | 6 | 6/8 (75%) | 2 | Grinding | KVCALHMGR001 | 2119.00 | 4.238 | 450 min | 1 | 900 min | Order Total: 8 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | MCB-HYG-015 | 2526203253 | Unknown | W3 | 8 | 3 | 6 | 6/8 (75%) | 2 | MC1 | KVCAD50MC001 | 2119.00 | 4.238 | 45 min | 0 | - | Order Total: 8 units
2025-11-26 | 2025-11-26 | Wednesday | W1 | MCB-HYG-015 | 2526203253 | Unknown | W3 | 8 | 4 | 8 | 8/8 COMPLETE ✓ | 2 | Grinding | KVCALHMGR001 | 2119.00 | 4.238 | 450 min | 1 | 900 min | Order Total: 8 units
2025-11-26 | 2025-11-26 | Wednesday | W1 | MCB-HYG-015 | 2526203253 | Unknown | W3 | 8 | 4 | 8 | 8/8 COMPLETE ✓ | 2 | MC1 | KVCAD50MC001 | 2119.00 | 4.238 | 45 min | 0 | - | Order Total: 8 units
2025-12-06 | 2025-12-06 | Saturday | W3 | MCB-HYG-015 | 2526203253 | Unknown | W3 | 8 | 1 | 2 | 2/8 (25%) | 2 | SP1 | KVCALPPSP001 | 2119.00 | 4.238 | 12 min | 1 | 24 min | Order Total: 8 units
2025-12-08 | 2025-12-08 | Monday | W3 | MCB-HYG-015 | 2526203253 | Unknown | W3 | 8 | 2 | 4 | 4/8 (50%) | 2 | SP1 | KVCALPPSP001 | 2119.00 | 4.238 | 12 min | 1 | 24 min | Order Total: 8 units
2025-12-09 | 2025-12-09 | Tuesday | W3 | MCB-HYG-015 | 2526203253 | Unknown | W3 | 8 | 3 | 6 | 6/8 (75%) | 2 | SP1 | KVCALPPSP001 | 2119.00 | 4.238 | 12 min | 1 | 24 min | Order Total: 8 units
2025-12-10 | 2025-12-10 | Wednesday | W3 | MCB-HYG-015 | 2526203253 | Unknown | W3 | 8 | 4 | 8 | 8/8 COMPLETE ✓ | 2 | SP1 | KVCALPPSP001 | 2119.00 | 4.238 | 12 min | 1 | 24 min | Order Total: 8 units
2025-11-29 | 2025-11-29 | Saturday | W2 | MCB-007 | 2526203256 | Unknown | W3 | 4 | 1 | 2 | 2/4 (50%) | 2 | MC1 | KVCAD50MC001 | 4070.00 | 8.140 | 90 min | 0 | - | Order Total: 4 units
2025-11-29 | 2025-11-29 | Saturday | W2 | MCB-007 | 2526203256 | Unknown | W3 | 4 | 1 | 2 | 2/4 (50%) | 2 | SP1 | KVCALPPSP001 | 4070.00 | 8.140 | 12 min | 1 | 24 min | Order Total: 4 units
2025-12-01 | 2025-12-01 | Monday | W2 | MCB-007 | 2526203256 | Unknown | W3 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | MC1 | KVCAD50MC001 | 4070.00 | 8.140 | 90 min | 0 | - | Order Total: 4 units
2025-12-01 | 2025-12-01 | Monday | W2 | MCB-007 | 2526203256 | Unknown | W3 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | SP1 | KVCALPPSP001 | 4070.00 | 8.140 | 12 min | 1 | 24 min | Order Total: 4 units
2025-12-13 | 2025-12-13 | Saturday | W4 | MCB-007 | 2526203256 | Unknown | W3 | 4 | 1 | 2 | 2/4 (50%) | 2 | Grinding | KVCALHMGR001 | 4070.00 | 8.140 | 330 min | 1 | 660 min | Order Total: 4 units
2025-12-15 | 2025-12-15 | Monday | W4 | MCB-007 | 2526203256 | Unknown | W3 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | Grinding | KVCALHMGR001 | 4070.00 | 8.140 | 330 min | 1 | 660 min | Order Total: 4 units
2025-11-22 | 2025-11-22 | Saturday | W1 | MCB-JLG-033 | 2526203258 | Unknown | W3 | 3 | 1 | 1 | 1/3 (33%) | 1 | Casting | CS-MCB-JLG-033 | 4309.00 | 4.309 | 25 min | 1 | 25 min | Order Total: 3 units
2025-11-22 | 2025-11-22 | Saturday | W1 | MCB-JLG-033 | 2526203258 | Unknown | W3 | 3 | 1 | 1 | 1/3 (33%) | 1 | Grinding | GR-MCB-JLG-033 | 4309.00 | 4.309 | 390 min | 1 | 390 min | Order Total: 3 units
2025-11-23 | 2025-11-22 | Sunday | W1 | MCB-JLG-033 | 2526203258 | Unknown | W3 | 3 | 1 | 1 | 1/3 (33%) | 1 | Cooling/Shakeout | N/A | 4309.00 | 4.309 | - | 1 | - | Order Total: 3 units
2025-11-24 | 2025-11-24 | Monday | W1 | MCB-JLG-033 | 2526203258 | Unknown | W3 | 3 | 2 | 2 | 2/3 (66%) | 1 | Casting | CS-MCB-JLG-033 | 4309.00 | 4.309 | 25 min | 1 | 25 min | Order Total: 3 units
2025-11-24 | 2025-11-24 | Monday | W1 | MCB-JLG-033 | 2526203258 | Unknown | W3 | 3 | 2 | 2 | 2/3 (66%) | 1 | Grinding | GR-MCB-JLG-033 | 4309.00 | 4.309 | 390 min | 1 | 390 min | Order Total: 3 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | MCB-JLG-033 | 2526203258 | Unknown | W3 | 3 | 3 | 3 | 3/3 COMPLETE ✓ | 1 | Casting | CS-MCB-JLG-033 | 4309.00 | 4.309 | 25 min | 1 | 25 min | Order Total: 3 units
2025-11-25 | 2025-11-24 | Tuesday | W1 | MCB-JLG-033 | 2526203258 | Unknown | W3 | 3 | 2 | 2 | 2/3 (66%) | 1 | Cooling/Shakeout | N/A | 4309.00 | 4.309 | - | 1 | - | Order Total: 3 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | MCB-JLG-033 | 2526203258 | Unknown | W3 | 3 | 3 | 3 | 3/3 COMPLETE ✓ | 1 | Grinding | GR-MCB-JLG-033 | 4309.00 | 4.309 | 390 min | 1 | 390 min | Order Total: 3 units
2025-11-26 | 2025-11-25 | Wednesday | W1 | MCB-JLG-033 | 2526203258 | Unknown | W3 | 3 | 3 | 3 | 3/3 COMPLETE ✓ | 1 | Cooling/Shakeout | N/A | 4309.00 | 4.309 | - | 1 | - | Order Total: 3 units
2025-11-29 | 2025-11-22 | Saturday | W2 | MCB-JLG-033 | 2526203258 | Unknown | W3 | 3 | 1 | 1 | 1/3 (33%) | 1 | MC1 | MC-MCB-JLG-033 | 4309.00 | 4.309 | 40 min | 0 | - | Order Total: 3 units
2025-12-01 | 2025-11-24 | Monday | W2 | MCB-JLG-033 | 2526203258 | Unknown | W3 | 3 | 2 | 2 | 2/3 (66%) | 1 | MC1 | MC-MCB-JLG-033 | 4309.00 | 4.309 | 40 min | 0 | - | Order Total: 3 units
2025-12-02 | 2025-11-25 | Tuesday | W2 | MCB-JLG-033 | 2526203258 | Unknown | W3 | 3 | 3 | 3 | 3/3 COMPLETE ✓ | 1 | MC1 | MC-MCB-JLG-033 | 4309.00 | 4.309 | 40 min | 0 | - | Order Total: 3 units
2025-12-06 | 2025-11-22 | Saturday | W3 | MCB-JLG-033 | 2526203258 | Unknown | W3 | 3 | 1 | 1 | 1/3 (33%) | 1 | SP1 | SP-MCB-JLG-033 | 4309.00 | 4.309 | - | 1 | - | Order Total: 3 units
2025-12-08 | 2025-11-24 | Monday | W3 | MCB-JLG-033 | 2526203258 | Unknown | W3 | 3 | 2 | 2 | 2/3 (66%) | 1 | SP1 | SP-MCB-JLG-033 | 4309.00 | 4.309 | - | 1 | - | Order Total: 3 units
2025-12-09 | 2025-11-25 | Tuesday | W3 | MCB-JLG-033 | 2526203258 | Unknown | W3 | 3 | 3 | 3 | 3/3 COMPLETE ✓ | 1 | SP1 | SP-MCB-JLG-033 | 4309.00 | 4.309 | - | 1 | - | Order Total: 3 units
2025-11-29 | 2025-12-06 | Saturday | W2 | MCB-009 | 2526203259 | Unknown | W6 | 12 | 1 | 3 | 3/12 (25%) | 3 | MC1 | KVCAD50MC001 | 1500.00 | 4.500 | 100 min | 0 | - | Order Total: 12 units
2025-12-01 | 2025-12-08 | Monday | W2 | MCB-009 | 2526203259 | Unknown | W6 | 12 | 2 | 6 | 6/12 (50%) | 3 | MC1 | KVCAD50MC001 | 1500.00 | 4.500 | 100 min | 0 | - | Order Total: 12 units
2025-12-02 | 2025-12-09 | Tuesday | W2 | MCB-009 | 2526203259 | Unknown | W6 | 12 | 3 | 9 | 9/12 (75%) | 3 | MC1 | KVCAD50MC001 | 1500.00 | 4.500 | 100 min | 0 | - | Order Total: 12 units
2025-12-03 | 2025-12-06 | Wednesday | W2 | MCB-009 | 2526203259 | Unknown | W6 | 12 | 4 | 12 | 12/12 COMPLETE ✓ | 3 | MC1 | KVCAD50MC001 | 1500.00 | 4.500 | 100 min | 0 | - | Order Total: 12 units
2025-12-06 | 2025-12-06 | Saturday | W3 | MCB-009 | 2526203259 | Unknown | W6 | 12 | 1 | 4 | 4/12 (33%) | 4 | Casting | CS2MCB-009 | 1500.00 | 6.000 | 20 min | 1 | 80 min | Order Total: 12 units
2025-12-06 | 2025-12-06 | Saturday | W3 | MCB-009 | 2526203259 | Unknown | W6 | 12 | 1 | 3 | 3/12 (25%) | 3 | Grinding | KVCALHMGR001 | 1500.00 | 4.500 | 210 min | 1 | 630 min | Order Total: 12 units
2025-12-07 | 2025-12-06 | Sunday | W3 | MCB-009 | 2526203259 | Unknown | W6 | 12 | 1 | 3 | 3/12 (25%) | 3 | Cooling/Shakeout | N/A | 1500.00 | 4.500 | - | 1 | - | Order Total: 12 units
2025-12-08 | 2025-12-08 | Monday | W3 | MCB-009 | 2526203259 | Unknown | W6 | 12 | 2 | 8 | 8/12 (66%) | 4 | Casting | CS2MCB-009 | 1500.00 | 6.000 | 20 min | 1 | 80 min | Order Total: 12 units
2025-12-08 | 2025-12-08 | Monday | W3 | MCB-009 | 2526203259 | Unknown | W6 | 12 | 2 | 6 | 6/12 (50%) | 3 | Grinding | KVCALHMGR001 | 1500.00 | 4.500 | 210 min | 1 | 630 min | Order Total: 12 units
2025-12-09 | 2025-12-09 | Tuesday | W3 | MCB-009 | 2526203259 | Unknown | W6 | 12 | 3 | 12 | 12/12 COMPLETE ✓ | 4 | Casting | CS2MCB-009 | 1500.00 | 6.000 | 20 min | 1 | 80 min | Order Total: 12 units
2025-12-09 | 2025-12-08 | Tuesday | W3 | MCB-009 | 2526203259 | Unknown | W6 | 12 | 2 | 6 | 6/12 (50%) | 3 | Cooling/Shakeout | N/A | 1500.00 | 4.500 | - | 1 | - | Order Total: 12 units
2025-12-09 | 2025-12-09 | Tuesday | W3 | MCB-009 | 2526203259 | Unknown | W6 | 12 | 3 | 9 | 9/12 (75%) | 3 | Grinding | KVCALHMGR001 | 1500.00 | 4.500 | 210 min | 1 | 630 min | Order Total: 12 units
2025-12-10 | 2025-12-09 | Wednesday | W3 | MCB-009 | 2526203259 | Unknown | W6 | 12 | 3 | 9 | 9/12 (75%) | 3 | Cooling/Shakeout | N/A | 1500.00 | 4.500 | - | 1 | - | Order Total: 12 units
2025-12-10 | 2025-12-06 | Wednesday | W3 | MCB-009 | 2526203259 | Unknown | W6 | 12 | 4 | 12 | 12/12 COMPLETE ✓ | 3 | Grinding | KVCALHMGR001 | 1500.00 | 4.500 | 210 min | 1 | 630 min | Order Total: 12 units
2025-12-11 | 2025-12-06 | Thursday | W3 | MCB-009 | 2526203259 | Unknown | W6 | 12 | 4 | 12 | 12/12 COMPLETE ✓ | 3 | Cooling/Shakeout | N/A | 1500.00 | 4.500 | - | 1 | - | Order Total: 12 units
2025-12-20 | 2025-12-06 | Saturday | W5 | MCB-009 | 2526203259 | Unknown | W6 | 12 | 1 | 3 | 3/12 (25%) | 3 | SP1 | KVCALPPSP001 | 1500.00 | 4.500 | 7 min | 1 | 21 min | Order Total: 12 units
2025-12-22 | 2025-12-08 | Monday | W5 | MCB-009 | 2526203259 | Unknown | W6 | 12 | 2 | 6 | 6/12 (50%) | 3 | SP1 | KVCALPPSP001 | 1500.00 | 4.500 | 7 min | 1 | 21 min | Order Total: 12 units
2025-12-23 | 2025-12-09 | Tuesday | W5 | MCB-009 | 2526203259 | Unknown | W6 | 12 | 3 | 9 | 9/12 (75%) | 3 | SP1 | KVCALPPSP001 | 1500.00 | 4.500 | 7 min | 1 | 21 min | Order Total: 12 units
2025-12-24 | 2025-12-06 | Wednesday | W5 | MCB-009 | 2526203259 | Unknown | W6 | 12 | 4 | 12 | 12/12 COMPLETE ✓ | 3 | SP1 | KVCALPPSP001 | 1500.00 | 4.500 | 7 min | 1 | 21 min | Order Total: 12 units
2025-11-22 | 2025-11-22 | Saturday | W1 | MCB-010 | 2526203260 | Unknown | W3 | 7 | 1 | 2 | 2/7 (28%) | 2 | Casting | CS2MCB-010 | 2650.00 | 5.300 | 20 min | 1 | 40 min | Order Total: 7 units
2025-11-22 | 2025-11-22 | Saturday | W1 | MCB-010 | 2526203260 | Unknown | W3 | 7 | 1 | 2 | 2/7 (28%) | 2 | SP1 | KVCALPPSP001 | 2650.00 | 5.300 | 12 min | 1 | 24 min | Order Total: 7 units
2025-11-23 | 2025-11-22 | Sunday | W1 | MCB-010 | 2526203260 | Unknown | W3 | 7 | 1 | 2 | 2/7 (28%) | 2 | Cooling/Shakeout | N/A | 2650.00 | 5.300 | - | 1 | - | Order Total: 7 units
2025-11-24 | 2025-11-24 | Monday | W1 | MCB-010 | 2526203260 | Unknown | W3 | 7 | 2 | 4 | 4/7 (57%) | 2 | Casting | CS2MCB-010 | 2650.00 | 5.300 | 20 min | 1 | 40 min | Order Total: 7 units
2025-11-24 | 2025-11-24 | Monday | W1 | MCB-010 | 2526203260 | Unknown | W3 | 7 | 2 | 4 | 4/7 (57%) | 2 | SP1 | KVCALPPSP001 | 2650.00 | 5.300 | 12 min | 1 | 24 min | Order Total: 7 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | MCB-010 | 2526203260 | Unknown | W3 | 7 | 3 | 7 | 7/7 COMPLETE ✓ | 3 | Casting | CS2MCB-010 | 2650.00 | 7.950 | 20 min | 1 | 60 min | Order Total: 7 units
2025-11-25 | 2025-11-24 | Tuesday | W1 | MCB-010 | 2526203260 | Unknown | W3 | 7 | 2 | 4 | 4/7 (57%) | 2 | Cooling/Shakeout | N/A | 2650.00 | 5.300 | - | 1 | - | Order Total: 7 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | MCB-010 | 2526203260 | Unknown | W3 | 7 | 3 | 7 | 7/7 COMPLETE ✓ | 3 | SP1 | KVCALPPSP001 | 2650.00 | 7.950 | 12 min | 1 | 36 min | Order Total: 7 units
2025-11-26 | 2025-11-25 | Wednesday | W1 | MCB-010 | 2526203260 | Unknown | W3 | 7 | 3 | 7 | 7/7 COMPLETE ✓ | 3 | Cooling/Shakeout | N/A | 2650.00 | 7.950 | - | 1 | - | Order Total: 7 units
2025-12-06 | 2025-11-22 | Saturday | W3 | MCB-010 | 2526203260 | Unknown | W3 | 7 | 1 | 2 | 2/7 (28%) | 2 | Grinding | KVCALHMGR001 | 2650.00 | 5.300 | 300 min | 1 | 600 min | Order Total: 7 units
2025-12-06 | 2025-11-22 | Saturday | W3 | MCB-010 | 2526203260 | Unknown | W3 | 7 | 1 | 2 | 2/7 (28%) | 2 | MC1 | KVCAD50MC001 | 2650.00 | 5.300 | 60 min | 0 | - | Order Total: 7 units
2025-12-08 | 2025-11-24 | Monday | W3 | MCB-010 | 2526203260 | Unknown | W3 | 7 | 2 | 4 | 4/7 (57%) | 2 | Grinding | KVCALHMGR001 | 2650.00 | 5.300 | 300 min | 1 | 600 min | Order Total: 7 units
2025-12-08 | 2025-11-24 | Monday | W3 | MCB-010 | 2526203260 | Unknown | W3 | 7 | 2 | 4 | 4/7 (57%) | 2 | MC1 | KVCAD50MC001 | 2650.00 | 5.300 | 60 min | 0 | - | Order Total: 7 units
2025-12-09 | 2025-11-25 | Tuesday | W3 | MCB-010 | 2526203260 | Unknown | W3 | 7 | 3 | 7 | 7/7 COMPLETE ✓ | 3 | Grinding | KVCALHMGR001 | 2650.00 | 7.950 | 300 min | 1 | 900 min | Order Total: 7 units
2025-12-09 | 2025-11-25 | Tuesday | W3 | MCB-010 | 2526203260 | Unknown | W3 | 7 | 3 | 7 | 7/7 COMPLETE ✓ | 3 | MC1 | KVCAD50MC001 | 2650.00 | 7.950 | 60 min | 0 | - | Order Total: 7 units
2025-11-29 | 2025-11-29 | Saturday | W2 | DGC-001 | 2526203269 | Unknown | W1 | 11 | 1 | 5 | 5/11 (45%) | 5 | Casting | CS1-DGC-001 | 396.00 | 1.980 | 20 min | 1 | 100 min | Order Total: 11 units
2025-11-30 | 2025-11-29 | Sunday | W2 | DGC-001 | 2526203269 | Unknown | W1 | 11 | 1 | 2 | 2/11 (18%) | 2 | Cooling/Shakeout | N/A | 396.00 | 0.792 | - | 1 | - | Order Total: 11 units
2025-12-01 | 2025-12-01 | Monday | W2 | DGC-001 | 2526203269 | Unknown | W1 | 11 | 2 | 11 | 11/11 COMPLETE ✓ | 6 | Casting | CS1-DGC-001 | 396.00 | 2.376 | 20 min | 1 | 120 min | Order Total: 11 units
2025-12-02 | 2025-12-01 | Tuesday | W2 | DGC-001 | 2526203269 | Unknown | W1 | 11 | 2 | 5 | 5/11 (45%) | 3 | Cooling/Shakeout | N/A | 396.00 | 1.188 | - | 1 | - | Order Total: 11 units
2025-12-03 | 2025-11-29 | Wednesday | W2 | DGC-001 | 2526203269 | Unknown | W1 | 11 | 3 | 8 | 8/11 (72%) | 3 | Cooling/Shakeout | N/A | 396.00 | 1.188 | - | 1 | - | Order Total: 11 units
2025-12-04 | 2025-11-29 | Thursday | W2 | DGC-001 | 2526203269 | Unknown | W1 | 11 | 4 | 11 | 11/11 COMPLETE ✓ | 3 | Cooling/Shakeout | N/A | 396.00 | 1.188 | - | 1 | - | Order Total: 11 units
2025-11-29 | 2025-11-29 | Saturday | W2 | DGC-001 | 2526203270 | Unknown | W1 | 7 | 1 | 3 | 3/7 (42%) | 3 | Casting | CS1-DGC-001 | 396.00 | 1.188 | 20 min | 1 | 60 min | Order Total: 7 units
2025-11-30 | 2025-11-29 | Sunday | W2 | DGC-001 | 2526203270 | Unknown | W1 | 7 | 1 | 2 | 2/7 (28%) | 2 | Cooling/Shakeout | N/A | 396.00 | 0.792 | - | 1 | - | Order Total: 7 units
2025-12-01 | 2025-12-01 | Monday | W2 | DGC-001 | 2526203270 | Unknown | W1 | 7 | 2 | 7 | 7/7 COMPLETE ✓ | 4 | Casting | CS1-DGC-001 | 396.00 | 1.584 | 20 min | 1 | 80 min | Order Total: 7 units
2025-12-02 | 2025-12-01 | Tuesday | W2 | DGC-001 | 2526203270 | Unknown | W1 | 7 | 2 | 4 | 4/7 (57%) | 2 | Cooling/Shakeout | N/A | 396.00 | 0.792 | - | 1 | - | Order Total: 7 units
2025-12-03 | 2025-11-29 | Wednesday | W2 | DGC-001 | 2526203270 | Unknown | W1 | 7 | 3 | 7 | 7/7 COMPLETE ✓ | 3 | Cooling/Shakeout | N/A | 396.00 | 1.188 | - | 1 | - | Order Total: 7 units
2025-12-20 | 2025-12-20 | Saturday | W5 | DGC-012 | 2526203271 | Unknown | W2 | 14 | 1 | 3 | 3/14 (21%) | 3 | Grinding | KVCALHMGR001 | 200.00 | 0.600 | 150 min | 1 | 450 min | Order Total: 14 units
2025-12-22 | 2025-12-22 | Monday | W5 | DGC-012 | 2526203271 | Unknown | W2 | 14 | 2 | 6 | 6/14 (42%) | 3 | Grinding | KVCALHMGR001 | 200.00 | 0.600 | 150 min | 1 | 450 min | Order Total: 14 units
2025-12-23 | 2025-12-23 | Tuesday | W5 | DGC-012 | 2526203271 | Unknown | W2 | 14 | 3 | 10 | 10/14 (71%) | 4 | Grinding | KVCALHMGR001 | 200.00 | 0.800 | 150 min | 1 | 600 min | Order Total: 14 units
2025-12-24 | 2025-12-24 | Wednesday | W5 | DGC-012 | 2526203271 | Unknown | W2 | 14 | 4 | 14 | 14/14 COMPLETE ✓ | 4 | Grinding | KVCALHMGR001 | 200.00 | 0.800 | 150 min | 1 | 600 min | Order Total: 14 units
2025-12-20 | 2025-12-20 | Saturday | W5 | DGC-001 | 2526203274 | Unknown | W4 | 56 | 1 | 50 | 50/56 (89%) | 50 | SP1 | KVCALPPSP001 | 396.00 | 19.800 | 7 min | 1 | 350 min | Order Total: 56 units
2025-12-20 | 2025-12-20 | Saturday | W5 | DGC-001 | 2526203274 | Unknown | W4 | 56 | 1 | 50 | 50/56 (89%) | 50 | SP2 | KVCALPPSP002 | 396.00 | 19.800 | 7 min | 1 | 350 min | Order Total: 56 units
2025-12-20 | 2025-12-20 | Saturday | W5 | DGC-001 | 2526203274 | Unknown | W4 | 56 | 1 | 50 | 50/56 (89%) | 50 | SP3 | KVCALFPSP001 | 396.00 | 19.800 | 7 min | 1 | 350 min | Order Total: 56 units
2025-12-22 | 2025-12-22 | Monday | W5 | DGC-001 | 2526203274 | Unknown | W4 | 56 | 2 | 56 | 56/56 COMPLETE ✓ | 6 | SP1 | KVCALPPSP001 | 396.00 | 2.376 | 7 min | 1 | 42 min | Order Total: 56 units
2025-12-22 | 2025-12-22 | Monday | W5 | DGC-001 | 2526203274 | Unknown | W4 | 56 | 2 | 56 | 56/56 COMPLETE ✓ | 6 | SP2 | KVCALPPSP002 | 396.00 | 2.376 | 7 min | 1 | 42 min | Order Total: 56 units
2025-12-22 | 2025-12-22 | Monday | W5 | DGC-001 | 2526203274 | Unknown | W4 | 56 | 2 | 56 | 56/56 COMPLETE ✓ | 6 | SP3 | KVCALFPSP001 | 396.00 | 2.376 | 7 min | 1 | 42 min | Order Total: 56 units
2025-11-22 | 2025-11-22 | Saturday | W1 | DGC-001 | 2526203276 | Unknown | W5 | 34 | 1 | 34 | 34/34 COMPLETE ✓ | 34 | SP1 | KVCALPPSP001 | 396.00 | 13.464 | 7 min | 1 | 238 min | Order Total: 34 units
2025-11-22 | 2025-11-22 | Saturday | W1 | DGC-001 | 2526203276 | Unknown | W5 | 34 | 1 | 34 | 34/34 COMPLETE ✓ | 34 | SP2 | KVCALPPSP002 | 396.00 | 13.464 | 7 min | 1 | 238 min | Order Total: 34 units
2025-11-22 | 2025-11-22 | Saturday | W1 | DGC-001 | 2526203276 | Unknown | W5 | 34 | 1 | 34 | 34/34 COMPLETE ✓ | 34 | SP3 | KVCALFPSP001 | 396.00 | 13.464 | 7 min | 1 | 238 min | Order Total: 34 units
2025-12-06 | 2025-12-06 | Saturday | W3 | DGC-011 | 2526203276 | Unknown | W5 | 4 | 1 | 4 | 4/4 COMPLETE ✓ | 4 | Casting | CS1-DGC-011 | 2200.00 | 8.800 | 20 min | 1 | 80 min | Order Total: 4 units
2025-12-07 | 2025-12-06 | Sunday | W3 | DGC-011 | 2526203276 | Unknown | W5 | 4 | 1 | 2 | 2/4 (50%) | 2 | Cooling/Shakeout | N/A | 2200.00 | 4.400 | - | 1 | - | Order Total: 4 units
2025-12-09 | 2025-12-06 | Tuesday | W3 | DGC-011 | 2526203276 | Unknown | W5 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | Cooling/Shakeout | N/A | 2200.00 | 4.400 | - | 1 | - | Order Total: 4 units
2025-11-22 | 2025-11-22 | Saturday | W1 | DGC-001 | 2526203277 | Unknown | W5 | 56 | 1 | 50 | 50/56 (89%) | 50 | SP1 | KVCALPPSP001 | 396.00 | 19.800 | 7 min | 1 | 350 min | Order Total: 56 units
2025-11-22 | 2025-11-22 | Saturday | W1 | DGC-001 | 2526203277 | Unknown | W5 | 56 | 1 | 50 | 50/56 (89%) | 50 | SP2 | KVCALPPSP002 | 396.00 | 19.800 | 7 min | 1 | 350 min | Order Total: 56 units
2025-11-22 | 2025-11-22 | Saturday | W1 | DGC-001 | 2526203277 | Unknown | W5 | 56 | 1 | 50 | 50/56 (89%) | 50 | SP3 | KVCALFPSP001 | 396.00 | 19.800 | 7 min | 1 | 350 min | Order Total: 56 units
2025-11-24 | 2025-11-24 | Monday | W1 | DGC-001 | 2526203277 | Unknown | W5 | 56 | 2 | 56 | 56/56 COMPLETE ✓ | 6 | SP1 | KVCALPPSP001 | 396.00 | 2.376 | 7 min | 1 | 42 min | Order Total: 56 units
2025-11-24 | 2025-11-24 | Monday | W1 | DGC-001 | 2526203277 | Unknown | W5 | 56 | 2 | 56 | 56/56 COMPLETE ✓ | 6 | SP2 | KVCALPPSP002 | 396.00 | 2.376 | 7 min | 1 | 42 min | Order Total: 56 units
2025-11-24 | 2025-11-24 | Monday | W1 | DGC-001 | 2526203277 | Unknown | W5 | 56 | 2 | 56 | 56/56 COMPLETE ✓ | 6 | SP3 | KVCALFPSP001 | 396.00 | 2.376 | 7 min | 1 | 42 min | Order Total: 56 units
2025-11-22 | 2025-11-22 | Saturday | W1 | UBC-050 | 2526203310 | Unknown | W4 | 4 | 1 | 2 | 2/4 (50%) | 2 | Grinding | KVCALHMGR001 | 369.00 | 0.738 | 680 min | 1 | 1360 min | Order Total: 4 units
2025-11-24 | 2025-11-24 | Monday | W1 | UBC-050 | 2526203310 | Unknown | W4 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | Grinding | KVCALHMGR001 | 369.00 | 0.738 | 680 min | 1 | 1360 min | Order Total: 4 units
2025-11-22 | 2025-11-22 | Saturday | W1 | UBC-019 | 2526203311 | Unknown | W4 | 14 | 1 | 7 | 7/14 (50%) | 7 | Casting | CS1-UBC-019 | 255.00 | 1.785 | 25 min | 1 | 175 min | Order Total: 14 units
2025-11-23 | 2025-11-22 | Sunday | W1 | UBC-019 | 2526203311 | Unknown | W4 | 14 | 1 | 3 | 3/14 (21%) | 3 | Cooling/Shakeout | N/A | 255.00 | 0.765 | - | 1 | - | Order Total: 14 units
2025-11-24 | 2025-11-24 | Monday | W1 | UBC-019 | 2526203311 | Unknown | W4 | 14 | 2 | 14 | 14/14 COMPLETE ✓ | 7 | Casting | CS1-UBC-019 | 255.00 | 1.785 | 25 min | 1 | 175 min | Order Total: 14 units
2025-11-25 | 2025-11-24 | Tuesday | W1 | UBC-019 | 2526203311 | Unknown | W4 | 14 | 2 | 6 | 6/14 (42%) | 3 | Cooling/Shakeout | N/A | 255.00 | 0.765 | - | 1 | - | Order Total: 14 units
2025-11-26 | 2025-11-22 | Wednesday | W1 | UBC-019 | 2526203311 | Unknown | W4 | 14 | 3 | 10 | 10/14 (71%) | 4 | Cooling/Shakeout | N/A | 255.00 | 1.020 | - | 1 | - | Order Total: 14 units
2025-11-27 | 2025-11-22 | Thursday | W1 | UBC-019 | 2526203311 | Unknown | W4 | 14 | 4 | 14 | 14/14 COMPLETE ✓ | 4 | Cooling/Shakeout | N/A | 255.00 | 1.020 | - | 1 | - | Order Total: 14 units
2025-11-29 | 2025-11-22 | Saturday | W2 | UBC-019 | 2526203311 | Unknown | W4 | 14 | 1 | 3 | 3/14 (21%) | 3 | Grinding | KVCALHMGR001 | 255.00 | 0.765 | 180 min | 1 | 540 min | Order Total: 14 units
2025-12-01 | 2025-11-24 | Monday | W2 | UBC-019 | 2526203311 | Unknown | W4 | 14 | 2 | 6 | 6/14 (42%) | 3 | Grinding | KVCALHMGR001 | 255.00 | 0.765 | 180 min | 1 | 540 min | Order Total: 14 units
2025-12-02 | 2025-11-22 | Tuesday | W2 | UBC-019 | 2526203311 | Unknown | W4 | 14 | 3 | 10 | 10/14 (71%) | 4 | Grinding | KVCALHMGR001 | 255.00 | 1.020 | 180 min | 1 | 720 min | Order Total: 14 units
2025-12-03 | 2025-11-22 | Wednesday | W2 | UBC-019 | 2526203311 | Unknown | W4 | 14 | 4 | 14 | 14/14 COMPLETE ✓ | 4 | Grinding | KVCALHMGR001 | 255.00 | 1.020 | 180 min | 1 | 720 min | Order Total: 14 units
2025-12-06 | 2025-11-22 | Saturday | W3 | UBC-019 | 2526203311 | Unknown | W4 | 14 | 1 | 3 | 3/14 (21%) | 3 | MC1 | KVCAD50MC001 | 255.00 | 0.765 | 20 min | 0 | - | Order Total: 14 units
2025-12-06 | 2025-11-22 | Saturday | W3 | UBC-019 | 2526203311 | Unknown | W4 | 14 | 1 | 3 | 3/14 (21%) | 3 | SP1 | KVCALPPSP001 | 255.00 | 0.765 | 7 min | 1 | 21 min | Order Total: 14 units
2025-12-06 | 2025-11-22 | Saturday | W3 | UBC-019 | 2526203311 | Unknown | W4 | 14 | 1 | 3 | 3/14 (21%) | 3 | SP2 | KVCALPPSP002 | 255.00 | 0.765 | 7 min | 1 | 21 min | Order Total: 14 units
2025-12-06 | 2025-11-22 | Saturday | W3 | UBC-019 | 2526203311 | Unknown | W4 | 14 | 1 | 3 | 3/14 (21%) | 3 | SP3 | KVCALFPSP001 | 255.00 | 0.765 | 7 min | 1 | 21 min | Order Total: 14 units
2025-12-08 | 2025-11-24 | Monday | W3 | UBC-019 | 2526203311 | Unknown | W4 | 14 | 2 | 6 | 6/14 (42%) | 3 | MC1 | KVCAD50MC001 | 255.00 | 0.765 | 20 min | 0 | - | Order Total: 14 units
2025-12-08 | 2025-11-24 | Monday | W3 | UBC-019 | 2526203311 | Unknown | W4 | 14 | 2 | 6 | 6/14 (42%) | 3 | SP1 | KVCALPPSP001 | 255.00 | 0.765 | 7 min | 1 | 21 min | Order Total: 14 units
2025-12-08 | 2025-11-24 | Monday | W3 | UBC-019 | 2526203311 | Unknown | W4 | 14 | 2 | 6 | 6/14 (42%) | 3 | SP2 | KVCALPPSP002 | 255.00 | 0.765 | 7 min | 1 | 21 min | Order Total: 14 units
2025-12-08 | 2025-11-24 | Monday | W3 | UBC-019 | 2526203311 | Unknown | W4 | 14 | 2 | 6 | 6/14 (42%) | 3 | SP3 | KVCALFPSP001 | 255.00 | 0.765 | 7 min | 1 | 21 min | Order Total: 14 units
2025-12-09 | 2025-11-22 | Tuesday | W3 | UBC-019 | 2526203311 | Unknown | W4 | 14 | 3 | 10 | 10/14 (71%) | 4 | MC1 | KVCAD50MC001 | 255.00 | 1.020 | 20 min | 0 | - | Order Total: 14 units
2025-12-09 | 2025-11-22 | Tuesday | W3 | UBC-019 | 2526203311 | Unknown | W4 | 14 | 3 | 10 | 10/14 (71%) | 4 | SP1 | KVCALPPSP001 | 255.00 | 1.020 | 7 min | 1 | 28 min | Order Total: 14 units
2025-12-09 | 2025-11-22 | Tuesday | W3 | UBC-019 | 2526203311 | Unknown | W4 | 14 | 3 | 10 | 10/14 (71%) | 4 | SP2 | KVCALPPSP002 | 255.00 | 1.020 | 7 min | 1 | 28 min | Order Total: 14 units
2025-12-09 | 2025-11-22 | Tuesday | W3 | UBC-019 | 2526203311 | Unknown | W4 | 14 | 3 | 10 | 10/14 (71%) | 4 | SP3 | KVCALFPSP001 | 255.00 | 1.020 | 7 min | 1 | 28 min | Order Total: 14 units
2025-12-10 | 2025-11-22 | Wednesday | W3 | UBC-019 | 2526203311 | Unknown | W4 | 14 | 4 | 14 | 14/14 COMPLETE ✓ | 4 | MC1 | KVCAD50MC001 | 255.00 | 1.020 | 20 min | 0 | - | Order Total: 14 units
2025-12-10 | 2025-11-22 | Wednesday | W3 | UBC-019 | 2526203311 | Unknown | W4 | 14 | 4 | 14 | 14/14 COMPLETE ✓ | 4 | SP1 | KVCALPPSP001 | 255.00 | 1.020 | 7 min | 1 | 28 min | Order Total: 14 units
2025-12-10 | 2025-11-22 | Wednesday | W3 | UBC-019 | 2526203311 | Unknown | W4 | 14 | 4 | 14 | 14/14 COMPLETE ✓ | 4 | SP2 | KVCALPPSP002 | 255.00 | 1.020 | 7 min | 1 | 28 min | Order Total: 14 units
2025-12-10 | 2025-11-22 | Wednesday | W3 | UBC-019 | 2526203311 | Unknown | W4 | 14 | 4 | 14 | 14/14 COMPLETE ✓ | 4 | SP3 | KVCALFPSP001 | 255.00 | 1.020 | 7 min | 1 | 28 min | Order Total: 14 units
2025-11-22 | 2025-11-22 | Saturday | W1 | UBC-019 | 2526203312 | Unknown | W4 | 1 | 1 | 1 | 1/1 COMPLETE ✓ | 1 | Casting | CS1-UBC-019 | 255.00 | 0.255 | 25 min | 1 | 25 min | Order Total: 1 units
2025-11-22 | 2025-11-22 | Saturday | W1 | UBC-019 | 2526203312 | Unknown | W4 | 1 | 2 | 2 | 2/1 COMPLETE ✓ | 1 | Casting | CS1-UBC-019 | 255.00 | 0.255 | 25 min | 1 | 25 min | Order Total: 1 units
2025-11-22 | 2025-11-22 | Saturday | W1 | UBC-018 | 2526203312 | Unknown | W4 | 12 | 1 | 3 | 3/36 (8%) | 3 | Grinding | KVCALHMGR001 | 484.00 | 1.452 | 180 min | 1 | 540 min | Order Total: 12 units
2025-11-22 | 2025-11-22 | Saturday | W1 | UBC-018 | 2526203312 | Unknown | W4 | 24 | 2 | 27 | 27/36 (75%) | 24 | Grinding | KVCALHMGR001 | 484.00 | 11.616 | 180 min | 1 | 4320 min | Order Total: 24 units
2025-11-23 | 2025-11-22 | Sunday | W1 | UBC-019 | 2526203312 | Unknown | W4 | 1 | 1 | 1 | 1/1 COMPLETE ✓ | 1 | Cooling/Shakeout | N/A | 255.00 | 0.255 | - | 1 | - | Order Total: 1 units
2025-11-23 | 2025-11-22 | Sunday | W1 | UBC-019 | 2526203312 | Unknown | W4 | 1 | 2 | 2 | 2/1 COMPLETE ✓ | 1 | Cooling/Shakeout | N/A | 255.00 | 0.255 | - | 1 | - | Order Total: 1 units
2025-11-24 | 2025-11-24 | Monday | W1 | UBC-018 | 2526203312 | Unknown | W4 | 12 | 3 | 30 | 30/36 (83%) | 3 | Grinding | KVCALHMGR001 | 484.00 | 1.452 | 180 min | 1 | 540 min | Order Total: 12 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | UBC-018 | 2526203312 | Unknown | W4 | 12 | 4 | 33 | 33/36 (91%) | 3 | Grinding | KVCALHMGR001 | 484.00 | 1.452 | 180 min | 1 | 540 min | Order Total: 12 units
2025-11-26 | 2025-11-26 | Wednesday | W1 | UBC-018 | 2526203312 | Unknown | W4 | 12 | 5 | 36 | 36/36 COMPLETE ✓ | 3 | Grinding | KVCALHMGR001 | 484.00 | 1.452 | 180 min | 1 | 540 min | Order Total: 12 units
2025-11-29 | 2025-11-22 | Saturday | W2 | UBC-019 | 2526203312 | Unknown | W4 | 1 | 1 | 1 | 1/1 COMPLETE ✓ | 1 | Grinding | KVCALHMGR001 | 255.00 | 0.255 | 180 min | 1 | 180 min | Order Total: 1 units
2025-11-29 | 2025-11-22 | Saturday | W2 | UBC-019 | 2526203312 | Unknown | W4 | 1 | 2 | 2 | 2/1 COMPLETE ✓ | 1 | Grinding | KVCALHMGR001 | 255.00 | 0.255 | 180 min | 1 | 180 min | Order Total: 1 units
2025-12-06 | 2025-11-22 | Saturday | W3 | UBC-019 | 2526203312 | Unknown | W4 | 1 | 1 | 1 | 1/1 COMPLETE ✓ | 1 | MC1 | KVCAD50MC001 | 255.00 | 0.255 | 20 min | 0 | - | Order Total: 1 units
2025-12-06 | 2025-11-22 | Saturday | W3 | UBC-019 | 2526203312 | Unknown | W4 | 1 | 2 | 2 | 2/1 COMPLETE ✓ | 1 | MC1 | KVCAD50MC001 | 255.00 | 0.255 | 20 min | 0 | - | Order Total: 1 units
2025-12-06 | 2025-11-22 | Saturday | W3 | UBC-019 | 2526203312 | Unknown | W4 | 1 | 1 | 1 | 1/1 COMPLETE ✓ | 1 | SP1 | KVCALPPSP001 | 255.00 | 0.255 | 7 min | 1 | 7 min | Order Total: 1 units
2025-12-06 | 2025-11-22 | Saturday | W3 | UBC-019 | 2526203312 | Unknown | W4 | 1 | 2 | 2 | 2/1 COMPLETE ✓ | 1 | SP1 | KVCALPPSP001 | 255.00 | 0.255 | 7 min | 1 | 7 min | Order Total: 1 units
2025-12-06 | 2025-11-22 | Saturday | W3 | UBC-019 | 2526203312 | Unknown | W4 | 1 | 1 | 1 | 1/1 COMPLETE ✓ | 1 | SP2 | KVCALPPSP002 | 255.00 | 0.255 | 7 min | 1 | 7 min | Order Total: 1 units
2025-12-06 | 2025-11-22 | Saturday | W3 | UBC-019 | 2526203312 | Unknown | W4 | 1 | 2 | 2 | 2/1 COMPLETE ✓ | 1 | SP2 | KVCALPPSP002 | 255.00 | 0.255 | 7 min | 1 | 7 min | Order Total: 1 units
2025-12-06 | 2025-11-22 | Saturday | W3 | UBC-019 | 2526203312 | Unknown | W4 | 1 | 1 | 1 | 1/1 COMPLETE ✓ | 1 | SP3 | KVCALFPSP001 | 255.00 | 0.255 | 7 min | 1 | 7 min | Order Total: 1 units
2025-12-06 | 2025-11-22 | Saturday | W3 | UBC-019 | 2526203312 | Unknown | W4 | 1 | 2 | 2 | 2/1 COMPLETE ✓ | 1 | SP3 | KVCALFPSP001 | 255.00 | 0.255 | 7 min | 1 | 7 min | Order Total: 1 units
2025-12-13 | 2025-12-13 | Saturday | W4 | UBC-018 | 2526203312 | Unknown | W4 | 12 | 1 | 3 | 3/36 (8%) | 3 | MC1 | KVCAD50MC001 | 484.00 | 1.452 | 20 min | 0 | - | Order Total: 12 units
2025-12-13 | 2025-12-13 | Saturday | W4 | UBC-018 | 2526203312 | Unknown | W4 | 24 | 2 | 27 | 27/36 (75%) | 24 | MC1 | KVCAD50MC001 | 484.00 | 11.616 | 20 min | 0 | - | Order Total: 24 units
2025-12-15 | 2025-12-15 | Monday | W4 | UBC-018 | 2526203312 | Unknown | W4 | 12 | 3 | 30 | 30/36 (83%) | 3 | MC1 | KVCAD50MC001 | 484.00 | 1.452 | 20 min | 0 | - | Order Total: 12 units
2025-12-16 | 2025-12-16 | Tuesday | W4 | UBC-018 | 2526203312 | Unknown | W4 | 12 | 4 | 33 | 33/36 (91%) | 3 | MC1 | KVCAD50MC001 | 484.00 | 1.452 | 20 min | 0 | - | Order Total: 12 units
2025-12-17 | 2025-12-17 | Wednesday | W4 | UBC-018 | 2526203312 | Unknown | W4 | 12 | 5 | 36 | 36/36 COMPLETE ✓ | 3 | MC1 | KVCAD50MC001 | 484.00 | 1.452 | 20 min | 0 | - | Order Total: 12 units
2025-11-22 | 2025-11-22 | Saturday | W1 | UBC-021 | 2526203331 | Unknown | W5 | 2 | 1 | 1 | 1/2 (50%) | 1 | Casting | CS1-UBC-021 | 3600.00 | 3.600 | 20 min | 1 | 20 min | Order Total: 2 units
2025-11-22 | 2025-11-22 | Saturday | W1 | UBC-022 | 2526203331 | Unknown | W5 | 8 | 1 | 2 | 2/8 (25%) | 2 | SP1 | SP1-UBC-022 | 1200.00 | 2.400 | - | 1 | - | Order Total: 8 units
2025-11-23 | 2025-11-22 | Sunday | W1 | UBC-021 | 2526203331 | Unknown | W5 | 2 | 1 | 1 | 1/2 (50%) | 1 | Cooling/Shakeout | N/A | 3600.00 | 3.600 | - | 1 | - | Order Total: 2 units
2025-11-24 | 2025-11-24 | Monday | W1 | UBC-021 | 2526203331 | Unknown | W5 | 2 | 2 | 2 | 2/2 COMPLETE ✓ | 1 | Casting | CS1-UBC-021 | 3600.00 | 3.600 | 20 min | 1 | 20 min | Order Total: 2 units
2025-11-24 | 2025-11-24 | Monday | W1 | UBC-022 | 2526203331 | Unknown | W5 | 8 | 2 | 4 | 4/8 (50%) | 2 | SP1 | SP1-UBC-022 | 1200.00 | 2.400 | - | 1 | - | Order Total: 8 units
2025-11-25 | 2025-11-24 | Tuesday | W1 | UBC-021 | 2526203331 | Unknown | W5 | 2 | 2 | 2 | 2/2 COMPLETE ✓ | 1 | Cooling/Shakeout | N/A | 3600.00 | 3.600 | - | 1 | - | Order Total: 2 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | UBC-022 | 2526203331 | Unknown | W5 | 8 | 3 | 6 | 6/8 (75%) | 2 | SP1 | SP1-UBC-022 | 1200.00 | 2.400 | - | 1 | - | Order Total: 8 units
2025-11-26 | 2025-11-26 | Wednesday | W1 | UBC-022 | 2526203331 | Unknown | W5 | 8 | 4 | 8 | 8/8 COMPLETE ✓ | 2 | SP1 | SP1-UBC-022 | 1200.00 | 2.400 | - | 1 | - | Order Total: 8 units
2025-11-22 | 2025-11-22 | Saturday | W1 | DGC-006 | 2526203332 | Unknown | W2 | 4 | 1 | 2 | 2/10 (20%) | 2 | Casting | CS1-DGC-006 | 1481.00 | 2.962 | 20 min | 1 | 40 min | Order Total: 4 units
2025-11-22 | 2025-11-22 | Saturday | W1 | DGC-006 | 2526203332 | Unknown | W2 | 6 | 2 | 4 | 4/10 (40%) | 2 | Casting | CS1-DGC-006 | 1481.00 | 2.962 | 20 min | 1 | 40 min | Order Total: 6 units
2025-11-22 | 2025-11-22 | Saturday | W1 | DGC-009 | 2526203332 | Unknown | W2 | 14 | 1 | 5 | 5/14 (35%) | 5 | Casting | CS1-DGC-009 | 500.00 | 2.500 | 20 min | 1 | 100 min | Order Total: 14 units
2025-11-22 | 2025-11-22 | Saturday | W1 | DGC-006 | 2526203332 | Unknown | W2 | 4 | 1 | 2 | 2/10 (20%) | 2 | Grinding | KVCALHMGR001 | 1481.00 | 2.962 | 180 min | 1 | 360 min | Order Total: 4 units
2025-11-22 | 2025-11-22 | Saturday | W1 | DGC-006 | 2526203332 | Unknown | W2 | 6 | 2 | 4 | 4/10 (40%) | 2 | Grinding | KVCALHMGR001 | 1481.00 | 2.962 | 180 min | 1 | 360 min | Order Total: 6 units
2025-11-22 | 2025-11-22 | Saturday | W1 | DGC-006 | 2526203332 | Unknown | W2 | 4 | 1 | 3 | 3/10 (30%) | 3 | MC1 | KVCAD30MC001 | 1481.00 | 4.443 | 90 min | 3 | 90 min | Order Total: 4 units
2025-11-22 | 2025-11-22 | Saturday | W1 | DGC-006 | 2526203332 | Unknown | W2 | 6 | 2 | 6 | 6/10 (60%) | 3 | MC1 | KVCAD30MC001 | 1481.00 | 4.443 | 90 min | 3 | 90 min | Order Total: 6 units
2025-11-22 | 2025-11-22 | Saturday | W1 | DGC-006 | 2526203332 | Unknown | W2 | 4 | 1 | 2 | 2/10 (20%) | 2 | SP1 | KVCALPPSP001 | 1481.00 | 2.962 | 7 min | 1 | 14 min | Order Total: 4 units
2025-11-22 | 2025-11-22 | Saturday | W1 | DGC-006 | 2526203332 | Unknown | W2 | 6 | 2 | 4 | 4/10 (40%) | 2 | SP1 | KVCALPPSP001 | 1481.00 | 2.962 | 7 min | 1 | 14 min | Order Total: 6 units
2025-11-23 | 2025-11-22 | Sunday | W1 | DGC-006 | 2526203332 | Unknown | W2 | 4 | 1 | 2 | 2/10 (20%) | 2 | Cooling/Shakeout | N/A | 1481.00 | 2.962 | - | 1 | - | Order Total: 4 units
2025-11-23 | 2025-11-22 | Sunday | W1 | DGC-006 | 2526203332 | Unknown | W2 | 6 | 2 | 4 | 4/10 (40%) | 2 | Cooling/Shakeout | N/A | 1481.00 | 2.962 | - | 1 | - | Order Total: 6 units
2025-11-23 | 2025-11-22 | Sunday | W1 | DGC-009 | 2526203332 | Unknown | W2 | 14 | 1 | 3 | 3/14 (21%) | 3 | Cooling/Shakeout | N/A | 500.00 | 1.500 | - | 1 | - | Order Total: 14 units
2025-11-24 | 2025-11-24 | Monday | W1 | DGC-006 | 2526203332 | Unknown | W2 | 4 | 3 | 6 | 6/10 (60%) | 2 | Casting | CS1-DGC-006 | 1481.00 | 2.962 | 20 min | 1 | 40 min | Order Total: 4 units
2025-11-24 | 2025-11-24 | Monday | W1 | DGC-006 | 2526203332 | Unknown | W2 | 6 | 4 | 10 | 10/10 COMPLETE ✓ | 4 | Casting | CS1-DGC-006 | 1481.00 | 5.924 | 20 min | 1 | 80 min | Order Total: 6 units
2025-11-24 | 2025-11-24 | Monday | W1 | DGC-009 | 2526203332 | Unknown | W2 | 14 | 2 | 14 | 14/14 COMPLETE ✓ | 9 | Casting | CS1-DGC-009 | 500.00 | 4.500 | 20 min | 1 | 180 min | Order Total: 14 units
2025-11-24 | 2025-11-24 | Monday | W1 | DGC-006 | 2526203332 | Unknown | W2 | 4 | 3 | 6 | 6/10 (60%) | 2 | Grinding | KVCALHMGR001 | 1481.00 | 2.962 | 180 min | 1 | 360 min | Order Total: 4 units
2025-11-24 | 2025-11-24 | Monday | W1 | DGC-006 | 2526203332 | Unknown | W2 | 6 | 4 | 8 | 8/10 (80%) | 2 | Grinding | KVCALHMGR001 | 1481.00 | 2.962 | 180 min | 1 | 360 min | Order Total: 6 units
2025-11-24 | 2025-11-24 | Monday | W1 | DGC-006 | 2526203332 | Unknown | W2 | 4 | 3 | 7 | 7/10 (70%) | 1 | MC1 | KVCAD30MC001 | 1481.00 | 1.481 | 90 min | 3 | 90 min | Order Total: 4 units
2025-11-24 | 2025-11-24 | Monday | W1 | DGC-006 | 2526203332 | Unknown | W2 | 6 | 4 | 10 | 10/10 COMPLETE ✓ | 3 | MC1 | KVCAD30MC001 | 1481.00 | 4.443 | 90 min | 3 | 90 min | Order Total: 6 units
2025-11-24 | 2025-11-24 | Monday | W1 | DGC-006 | 2526203332 | Unknown | W2 | 4 | 3 | 6 | 6/10 (60%) | 2 | SP1 | KVCALPPSP001 | 1481.00 | 2.962 | 7 min | 1 | 14 min | Order Total: 4 units
2025-11-24 | 2025-11-24 | Monday | W1 | DGC-006 | 2526203332 | Unknown | W2 | 6 | 4 | 8 | 8/10 (80%) | 2 | SP1 | KVCALPPSP001 | 1481.00 | 2.962 | 7 min | 1 | 14 min | Order Total: 6 units
2025-11-25 | 2025-11-24 | Tuesday | W1 | DGC-006 | 2526203332 | Unknown | W2 | 4 | 3 | 6 | 6/10 (60%) | 2 | Cooling/Shakeout | N/A | 1481.00 | 2.962 | - | 1 | - | Order Total: 4 units
2025-11-25 | 2025-11-24 | Tuesday | W1 | DGC-006 | 2526203332 | Unknown | W2 | 6 | 4 | 8 | 8/10 (80%) | 2 | Cooling/Shakeout | N/A | 1481.00 | 2.962 | - | 1 | - | Order Total: 6 units
2025-11-25 | 2025-11-24 | Tuesday | W1 | DGC-009 | 2526203332 | Unknown | W2 | 14 | 2 | 6 | 6/14 (42%) | 3 | Cooling/Shakeout | N/A | 500.00 | 1.500 | - | 1 | - | Order Total: 14 units
2025-11-25 | 2025-11-22 | Tuesday | W1 | DGC-006 | 2526203332 | Unknown | W2 | 6 | 5 | 10 | 10/10 COMPLETE ✓ | 2 | Grinding | KVCALHMGR001 | 1481.00 | 2.962 | 180 min | 1 | 360 min | Order Total: 6 units
2025-11-25 | 2025-11-22 | Tuesday | W1 | DGC-006 | 2526203332 | Unknown | W2 | 6 | 5 | 10 | 10/10 COMPLETE ✓ | 2 | SP1 | KVCALPPSP001 | 1481.00 | 2.962 | 7 min | 1 | 14 min | Order Total: 6 units
2025-11-26 | 2025-11-22 | Wednesday | W1 | DGC-006 | 2526203332 | Unknown | W2 | 6 | 5 | 10 | 10/10 COMPLETE ✓ | 2 | Cooling/Shakeout | N/A | 1481.00 | 2.962 | - | 1 | - | Order Total: 6 units
2025-11-26 | 2025-11-22 | Wednesday | W1 | DGC-009 | 2526203332 | Unknown | W2 | 14 | 3 | 10 | 10/14 (71%) | 4 | Cooling/Shakeout | N/A | 500.00 | 2.000 | - | 1 | - | Order Total: 14 units
2025-11-27 | 2025-11-22 | Thursday | W1 | DGC-009 | 2526203332 | Unknown | W2 | 14 | 4 | 14 | 14/14 COMPLETE ✓ | 4 | Cooling/Shakeout | N/A | 500.00 | 2.000 | - | 1 | - | Order Total: 14 units
2025-12-06 | 2025-11-22 | Saturday | W3 | DGC-009 | 2526203332 | Unknown | W2 | 14 | 1 | 3 | 3/14 (21%) | 3 | Grinding | GR1-DGC-009 | 500.00 | 1.500 | 180 min | 1 | 540 min | Order Total: 14 units
2025-12-06 | 2025-11-22 | Saturday | W3 | DGC-009 | 2526203332 | Unknown | W2 | 14 | 1 | 3 | 3/14 (21%) | 3 | MC1 | MC1-DGC-009 | 500.00 | 1.500 | 25 min | 1 | 75 min | Order Total: 14 units
2025-12-06 | 2025-11-22 | Saturday | W3 | DGC-009 | 2526203332 | Unknown | W2 | 14 | 1 | 3 | 3/14 (21%) | 3 | SP1 | SP1-DGC-009 | 500.00 | 1.500 | - | 1 | - | Order Total: 14 units
2025-12-08 | 2025-11-24 | Monday | W3 | DGC-009 | 2526203332 | Unknown | W2 | 14 | 2 | 6 | 6/14 (42%) | 3 | Grinding | GR1-DGC-009 | 500.00 | 1.500 | 180 min | 1 | 540 min | Order Total: 14 units
2025-12-08 | 2025-11-24 | Monday | W3 | DGC-009 | 2526203332 | Unknown | W2 | 14 | 2 | 6 | 6/14 (42%) | 3 | MC1 | MC1-DGC-009 | 500.00 | 1.500 | 25 min | 1 | 75 min | Order Total: 14 units
2025-12-08 | 2025-11-24 | Monday | W3 | DGC-009 | 2526203332 | Unknown | W2 | 14 | 2 | 6 | 6/14 (42%) | 3 | SP1 | SP1-DGC-009 | 500.00 | 1.500 | - | 1 | - | Order Total: 14 units
2025-12-09 | 2025-11-22 | Tuesday | W3 | DGC-009 | 2526203332 | Unknown | W2 | 14 | 3 | 10 | 10/14 (71%) | 4 | Grinding | GR1-DGC-009 | 500.00 | 2.000 | 180 min | 1 | 720 min | Order Total: 14 units
2025-12-09 | 2025-11-22 | Tuesday | W3 | DGC-009 | 2526203332 | Unknown | W2 | 14 | 3 | 10 | 10/14 (71%) | 4 | MC1 | MC1-DGC-009 | 500.00 | 2.000 | 25 min | 1 | 100 min | Order Total: 14 units
2025-12-09 | 2025-11-22 | Tuesday | W3 | DGC-009 | 2526203332 | Unknown | W2 | 14 | 3 | 10 | 10/14 (71%) | 4 | SP1 | SP1-DGC-009 | 500.00 | 2.000 | - | 1 | - | Order Total: 14 units
2025-12-10 | 2025-11-22 | Wednesday | W3 | DGC-009 | 2526203332 | Unknown | W2 | 14 | 4 | 14 | 14/14 COMPLETE ✓ | 4 | Grinding | GR1-DGC-009 | 500.00 | 2.000 | 180 min | 1 | 720 min | Order Total: 14 units
2025-12-10 | 2025-11-22 | Wednesday | W3 | DGC-009 | 2526203332 | Unknown | W2 | 14 | 4 | 14 | 14/14 COMPLETE ✓ | 4 | MC1 | MC1-DGC-009 | 500.00 | 2.000 | 25 min | 1 | 100 min | Order Total: 14 units
2025-12-10 | 2025-11-22 | Wednesday | W3 | DGC-009 | 2526203332 | Unknown | W2 | 14 | 4 | 14 | 14/14 COMPLETE ✓ | 4 | SP1 | SP1-DGC-009 | 500.00 | 2.000 | - | 1 | - | Order Total: 14 units
2025-11-22 | 2025-12-13 | Saturday | W1 | MCB-JLG-047 | 2526203370 | Unknown | W4 | 11 | 1 | 2 | 2/11 (18%) | 2 | Grinding | KVCALHMGR001 | 1592.40 | 3.185 | 390 min | 1 | 780 min | Order Total: 11 units
2025-11-22 | 2025-12-13 | Saturday | W1 | MCB-JLG-047 | 2526203370 | Unknown | W4 | 11 | 1 | 2 | 2/11 (18%) | 2 | SP1 | KVCALPPSP001 | 1592.40 | 3.185 | 12 min | 1 | 24 min | Order Total: 11 units
2025-11-24 | 2025-12-15 | Monday | W1 | MCB-JLG-047 | 2526203370 | Unknown | W4 | 11 | 2 | 5 | 5/11 (45%) | 3 | Grinding | KVCALHMGR001 | 1592.40 | 4.777 | 390 min | 1 | 1170 min | Order Total: 11 units
2025-11-24 | 2025-12-15 | Monday | W1 | MCB-JLG-047 | 2526203370 | Unknown | W4 | 11 | 2 | 5 | 5/11 (45%) | 3 | SP1 | KVCALPPSP001 | 1592.40 | 4.777 | 12 min | 1 | 36 min | Order Total: 11 units
2025-11-25 | 2025-12-13 | Tuesday | W1 | MCB-JLG-047 | 2526203370 | Unknown | W4 | 11 | 3 | 8 | 8/11 (72%) | 3 | Grinding | KVCALHMGR001 | 1592.40 | 4.777 | 390 min | 1 | 1170 min | Order Total: 11 units
2025-11-25 | 2025-12-13 | Tuesday | W1 | MCB-JLG-047 | 2526203370 | Unknown | W4 | 11 | 3 | 8 | 8/11 (72%) | 3 | SP1 | KVCALPPSP001 | 1592.40 | 4.777 | 12 min | 1 | 36 min | Order Total: 11 units
2025-11-26 | 2025-12-13 | Wednesday | W1 | MCB-JLG-047 | 2526203370 | Unknown | W4 | 11 | 4 | 11 | 11/11 COMPLETE ✓ | 3 | Grinding | KVCALHMGR001 | 1592.40 | 4.777 | 390 min | 1 | 1170 min | Order Total: 11 units
2025-11-26 | 2025-12-13 | Wednesday | W1 | MCB-JLG-047 | 2526203370 | Unknown | W4 | 11 | 4 | 11 | 11/11 COMPLETE ✓ | 3 | SP1 | KVCALPPSP001 | 1592.40 | 4.777 | 12 min | 1 | 36 min | Order Total: 11 units
2025-12-13 | 2025-12-13 | Saturday | W4 | MCB-JLG-047 | 2526203370 | Unknown | W4 | 11 | 1 | 5 | 5/11 (45%) | 5 | Casting | CS1-MCB-JLG-047 | 1592.40 | 7.962 | 25 min | 1 | 125 min | Order Total: 11 units
2025-12-14 | 2025-12-13 | Sunday | W4 | MCB-JLG-047 | 2526203370 | Unknown | W4 | 11 | 1 | 2 | 2/11 (18%) | 2 | Cooling/Shakeout | N/A | 1592.40 | 3.185 | - | 1 | - | Order Total: 11 units
2025-12-15 | 2025-12-15 | Monday | W4 | MCB-JLG-047 | 2526203370 | Unknown | W4 | 11 | 2 | 11 | 11/11 COMPLETE ✓ | 6 | Casting | CS1-MCB-JLG-047 | 1592.40 | 9.554 | 25 min | 1 | 150 min | Order Total: 11 units
2025-12-16 | 2025-12-15 | Tuesday | W4 | MCB-JLG-047 | 2526203370 | Unknown | W4 | 11 | 2 | 5 | 5/11 (45%) | 3 | Cooling/Shakeout | N/A | 1592.40 | 4.777 | - | 1 | - | Order Total: 11 units
2025-12-17 | 2025-12-13 | Wednesday | W4 | MCB-JLG-047 | 2526203370 | Unknown | W4 | 11 | 3 | 8 | 8/11 (72%) | 3 | Cooling/Shakeout | N/A | 1592.40 | 4.777 | - | 1 | - | Order Total: 11 units
2025-12-18 | 2025-12-13 | Thursday | W4 | MCB-JLG-047 | 2526203370 | Unknown | W4 | 11 | 4 | 11 | 11/11 COMPLETE ✓ | 3 | Cooling/Shakeout | N/A | 1592.40 | 4.777 | - | 1 | - | Order Total: 11 units
2025-11-22 | 2025-11-22 | Saturday | W1 | MCB-JLG-019 | 2526203373 | Unknown | W4 | 15 | 1 | 5 | 5/15 (33%) | 5 | Casting | CS2MCB-JLG-019 | 1278.58 | 6.393 | 24 min | 1 | 120 min | Order Total: 15 units
2025-11-23 | 2025-11-22 | Sunday | W1 | MCB-JLG-019 | 2526203373 | Unknown | W4 | 15 | 1 | 3 | 3/15 (20%) | 3 | Cooling/Shakeout | N/A | 1278.58 | 3.836 | - | 1 | - | Order Total: 15 units
2025-11-24 | 2025-11-24 | Monday | W1 | MCB-JLG-019 | 2526203373 | Unknown | W4 | 15 | 2 | 9 | 9/15 (60%) | 4 | Casting | CS2MCB-JLG-019 | 1278.58 | 5.114 | 24 min | 1 | 96 min | Order Total: 15 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | MCB-JLG-019 | 2526203373 | Unknown | W4 | 15 | 3 | 15 | 15/15 COMPLETE ✓ | 6 | Casting | CS2MCB-JLG-019 | 1278.58 | 7.671 | 24 min | 1 | 144 min | Order Total: 15 units
2025-11-25 | 2025-11-24 | Tuesday | W1 | MCB-JLG-019 | 2526203373 | Unknown | W4 | 15 | 2 | 7 | 7/15 (46%) | 4 | Cooling/Shakeout | N/A | 1278.58 | 5.114 | - | 1 | - | Order Total: 15 units
2025-11-26 | 2025-11-25 | Wednesday | W1 | MCB-JLG-019 | 2526203373 | Unknown | W4 | 15 | 3 | 11 | 11/15 (73%) | 4 | Cooling/Shakeout | N/A | 1278.58 | 5.114 | - | 1 | - | Order Total: 15 units
2025-11-27 | 2025-11-22 | Thursday | W1 | MCB-JLG-019 | 2526203373 | Unknown | W4 | 15 | 4 | 15 | 15/15 COMPLETE ✓ | 4 | Cooling/Shakeout | N/A | 1278.58 | 5.114 | - | 1 | - | Order Total: 15 units
2025-11-29 | 2025-11-22 | Saturday | W2 | MCB-JLG-019 | 2526203373 | Unknown | W4 | 15 | 1 | 3 | 3/15 (20%) | 3 | SP1 | KVCALPPSP001 | 1278.58 | 3.836 | 7 min | 1 | 21 min | Order Total: 15 units
2025-12-01 | 2025-11-24 | Monday | W2 | MCB-JLG-019 | 2526203373 | Unknown | W4 | 15 | 2 | 7 | 7/15 (46%) | 4 | SP1 | KVCALPPSP001 | 1278.58 | 5.114 | 7 min | 1 | 28 min | Order Total: 15 units
2025-12-02 | 2025-11-25 | Tuesday | W2 | MCB-JLG-019 | 2526203373 | Unknown | W4 | 15 | 3 | 11 | 11/15 (73%) | 4 | SP1 | KVCALPPSP001 | 1278.58 | 5.114 | 7 min | 1 | 28 min | Order Total: 15 units
2025-12-03 | 2025-11-22 | Wednesday | W2 | MCB-JLG-019 | 2526203373 | Unknown | W4 | 15 | 4 | 15 | 15/15 COMPLETE ✓ | 4 | SP1 | KVCALPPSP001 | 1278.58 | 5.114 | 7 min | 1 | 28 min | Order Total: 15 units
2025-12-06 | 2025-11-22 | Saturday | W3 | MCB-JLG-019 | 2526203373 | Unknown | W4 | 15 | 1 | 3 | 3/15 (20%) | 3 | MC1 | KVCAD50MC001 | 1278.58 | 3.836 | 40 min | 0 | - | Order Total: 15 units
2025-12-08 | 2025-11-24 | Monday | W3 | MCB-JLG-019 | 2526203373 | Unknown | W4 | 15 | 2 | 7 | 7/15 (46%) | 4 | MC1 | KVCAD50MC001 | 1278.58 | 5.114 | 40 min | 0 | - | Order Total: 15 units
2025-12-09 | 2025-11-25 | Tuesday | W3 | MCB-JLG-019 | 2526203373 | Unknown | W4 | 15 | 3 | 11 | 11/15 (73%) | 4 | MC1 | KVCAD50MC001 | 1278.58 | 5.114 | 40 min | 0 | - | Order Total: 15 units
2025-12-10 | 2025-11-22 | Wednesday | W3 | MCB-JLG-019 | 2526203373 | Unknown | W4 | 15 | 4 | 15 | 15/15 COMPLETE ✓ | 4 | MC1 | KVCAD50MC001 | 1278.58 | 5.114 | 40 min | 0 | - | Order Total: 15 units
2025-11-22 | 2025-11-29 | Saturday | W1 | MCB-JLG-020 | 2526203374 | Unknown | W4 | 4 | 1 | 2 | 2/4 (50%) | 2 | MC1 | KVCAD50MC001 | 3863.64 | 7.727 | 65 min | 0 | - | Order Total: 4 units
2025-11-22 | 2025-11-29 | Saturday | W1 | MCB-JLG-020 | 2526203374 | Unknown | W4 | 4 | 1 | 2 | 2/4 (50%) | 2 | SP1 | KVCALPPSP001 | 3863.64 | 7.727 | 7 min | 1 | 14 min | Order Total: 4 units
2025-11-24 | 2025-12-01 | Monday | W1 | MCB-JLG-020 | 2526203374 | Unknown | W4 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | MC1 | KVCAD50MC001 | 3863.64 | 7.727 | 65 min | 0 | - | Order Total: 4 units
2025-11-24 | 2025-12-01 | Monday | W1 | MCB-JLG-020 | 2526203374 | Unknown | W4 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | SP1 | KVCALPPSP001 | 3863.64 | 7.727 | 7 min | 1 | 14 min | Order Total: 4 units
2025-11-29 | 2025-11-29 | Saturday | W2 | MCB-JLG-020 | 2526203374 | Unknown | W4 | 4 | 1 | 2 | 2/4 (50%) | 2 | Casting | CS2MCB-JLG-020 | 3863.64 | 7.727 | 25 min | 1 | 50 min | Order Total: 4 units
2025-11-29 | 2025-11-29 | Saturday | W2 | MCB-JLG-020 | 2526203374 | Unknown | W4 | 4 | 1 | 2 | 2/4 (50%) | 2 | Grinding | KVCALHMGR001 | 3863.64 | 7.727 | 480 min | 1 | 960 min | Order Total: 4 units
2025-11-30 | 2025-11-29 | Sunday | W2 | MCB-JLG-020 | 2526203374 | Unknown | W4 | 4 | 1 | 2 | 2/4 (50%) | 2 | Cooling/Shakeout | N/A | 3863.64 | 7.727 | - | 1 | - | Order Total: 4 units
2025-12-01 | 2025-12-01 | Monday | W2 | MCB-JLG-020 | 2526203374 | Unknown | W4 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | Casting | CS2MCB-JLG-020 | 3863.64 | 7.727 | 25 min | 1 | 50 min | Order Total: 4 units
2025-12-01 | 2025-12-01 | Monday | W2 | MCB-JLG-020 | 2526203374 | Unknown | W4 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | Grinding | KVCALHMGR001 | 3863.64 | 7.727 | 480 min | 1 | 960 min | Order Total: 4 units
2025-12-02 | 2025-12-01 | Tuesday | W2 | MCB-JLG-020 | 2526203374 | Unknown | W4 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | Cooling/Shakeout | N/A | 3863.64 | 7.727 | - | 1 | - | Order Total: 4 units
2025-11-22 | 2025-11-22 | Saturday | W1 | MCB-007 | 2526203375 | Unknown | W4 | 4 | 1 | 2 | 2/4 (50%) | 2 | Casting | CS2MCB-007 | 4070.00 | 8.140 | 20 min | 1 | 40 min | Order Total: 4 units
2025-11-23 | 2025-11-22 | Sunday | W1 | MCB-007 | 2526203375 | Unknown | W4 | 4 | 1 | 2 | 2/4 (50%) | 2 | Cooling/Shakeout | N/A | 4070.00 | 8.140 | - | 1 | - | Order Total: 4 units
2025-11-24 | 2025-11-24 | Monday | W1 | MCB-007 | 2526203375 | Unknown | W4 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | Casting | CS2MCB-007 | 4070.00 | 8.140 | 20 min | 1 | 40 min | Order Total: 4 units
2025-11-25 | 2025-11-24 | Tuesday | W1 | MCB-007 | 2526203375 | Unknown | W4 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | Cooling/Shakeout | N/A | 4070.00 | 8.140 | - | 1 | - | Order Total: 4 units
2025-11-29 | 2025-11-22 | Saturday | W2 | MCB-007 | 2526203375 | Unknown | W4 | 4 | 1 | 2 | 2/4 (50%) | 2 | Grinding | KVCALHMGR001 | 4070.00 | 8.140 | 330 min | 1 | 660 min | Order Total: 4 units
2025-12-01 | 2025-11-24 | Monday | W2 | MCB-007 | 2526203375 | Unknown | W4 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | Grinding | KVCALHMGR001 | 4070.00 | 8.140 | 330 min | 1 | 660 min | Order Total: 4 units
2025-12-13 | 2025-11-22 | Saturday | W4 | MCB-007 | 2526203375 | Unknown | W4 | 4 | 1 | 2 | 2/4 (50%) | 2 | MC1 | KVCAD50MC001 | 4070.00 | 8.140 | 90 min | 0 | - | Order Total: 4 units
2025-12-13 | 2025-11-22 | Saturday | W4 | MCB-007 | 2526203375 | Unknown | W4 | 4 | 1 | 2 | 2/4 (50%) | 2 | SP1 | KVCALPPSP001 | 4070.00 | 8.140 | 12 min | 1 | 24 min | Order Total: 4 units
2025-12-15 | 2025-11-24 | Monday | W4 | MCB-007 | 2526203375 | Unknown | W4 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | MC1 | KVCAD50MC001 | 4070.00 | 8.140 | 90 min | 0 | - | Order Total: 4 units
2025-12-15 | 2025-11-24 | Monday | W4 | MCB-007 | 2526203375 | Unknown | W4 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | SP1 | KVCALPPSP001 | 4070.00 | 8.140 | 12 min | 1 | 24 min | Order Total: 4 units
2025-11-22 | 2025-11-22 | Saturday | W1 | MCB-007 | 2526203376 | Unknown | W4 | 4 | 1 | 2 | 2/4 (50%) | 2 | Casting | CS2MCB-007 | 4070.00 | 8.140 | 20 min | 1 | 40 min | Order Total: 4 units
2025-11-23 | 2025-11-22 | Sunday | W1 | MCB-007 | 2526203376 | Unknown | W4 | 4 | 1 | 2 | 2/4 (50%) | 2 | Cooling/Shakeout | N/A | 4070.00 | 8.140 | - | 1 | - | Order Total: 4 units
2025-11-24 | 2025-11-24 | Monday | W1 | MCB-007 | 2526203376 | Unknown | W4 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | Casting | CS2MCB-007 | 4070.00 | 8.140 | 20 min | 1 | 40 min | Order Total: 4 units
2025-11-25 | 2025-11-24 | Tuesday | W1 | MCB-007 | 2526203376 | Unknown | W4 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | Cooling/Shakeout | N/A | 4070.00 | 8.140 | - | 1 | - | Order Total: 4 units
2025-11-29 | 2025-11-22 | Saturday | W2 | MCB-007 | 2526203376 | Unknown | W4 | 4 | 1 | 2 | 2/4 (50%) | 2 | Grinding | KVCALHMGR001 | 4070.00 | 8.140 | 330 min | 1 | 660 min | Order Total: 4 units
2025-12-01 | 2025-11-24 | Monday | W2 | MCB-007 | 2526203376 | Unknown | W4 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | Grinding | KVCALHMGR001 | 4070.00 | 8.140 | 330 min | 1 | 660 min | Order Total: 4 units
2025-12-13 | 2025-11-22 | Saturday | W4 | MCB-007 | 2526203376 | Unknown | W4 | 4 | 1 | 2 | 2/4 (50%) | 2 | MC1 | KVCAD50MC001 | 4070.00 | 8.140 | 90 min | 0 | - | Order Total: 4 units
2025-12-13 | 2025-11-22 | Saturday | W4 | MCB-007 | 2526203376 | Unknown | W4 | 4 | 1 | 2 | 2/4 (50%) | 2 | SP1 | KVCALPPSP001 | 4070.00 | 8.140 | 12 min | 1 | 24 min | Order Total: 4 units
2025-12-15 | 2025-11-24 | Monday | W4 | MCB-007 | 2526203376 | Unknown | W4 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | MC1 | KVCAD50MC001 | 4070.00 | 8.140 | 90 min | 0 | - | Order Total: 4 units
2025-12-15 | 2025-11-24 | Monday | W4 | MCB-007 | 2526203376 | Unknown | W4 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | SP1 | KVCALPPSP001 | 4070.00 | 8.140 | 12 min | 1 | 24 min | Order Total: 4 units
2025-11-22 | 2025-11-22 | Saturday | W1 | MCB-007 | 2526203377 | Unknown | W4 | 4 | 1 | 2 | 2/4 (50%) | 2 | Casting | CS2MCB-007 | 4070.00 | 8.140 | 20 min | 1 | 40 min | Order Total: 4 units
2025-11-23 | 2025-11-22 | Sunday | W1 | MCB-007 | 2526203377 | Unknown | W4 | 4 | 1 | 2 | 2/4 (50%) | 2 | Cooling/Shakeout | N/A | 4070.00 | 8.140 | - | 1 | - | Order Total: 4 units
2025-11-24 | 2025-11-24 | Monday | W1 | MCB-007 | 2526203377 | Unknown | W4 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | Casting | CS2MCB-007 | 4070.00 | 8.140 | 20 min | 1 | 40 min | Order Total: 4 units
2025-11-25 | 2025-11-24 | Tuesday | W1 | MCB-007 | 2526203377 | Unknown | W4 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | Cooling/Shakeout | N/A | 4070.00 | 8.140 | - | 1 | - | Order Total: 4 units
2025-11-29 | 2025-11-22 | Saturday | W2 | MCB-007 | 2526203377 | Unknown | W4 | 4 | 1 | 2 | 2/4 (50%) | 2 | Grinding | KVCALHMGR001 | 4070.00 | 8.140 | 330 min | 1 | 660 min | Order Total: 4 units
2025-12-01 | 2025-11-24 | Monday | W2 | MCB-007 | 2526203377 | Unknown | W4 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | Grinding | KVCALHMGR001 | 4070.00 | 8.140 | 330 min | 1 | 660 min | Order Total: 4 units
2025-12-13 | 2025-11-22 | Saturday | W4 | MCB-007 | 2526203377 | Unknown | W4 | 4 | 1 | 2 | 2/4 (50%) | 2 | MC1 | KVCAD50MC001 | 4070.00 | 8.140 | 90 min | 0 | - | Order Total: 4 units
2025-12-13 | 2025-11-22 | Saturday | W4 | MCB-007 | 2526203377 | Unknown | W4 | 4 | 1 | 2 | 2/4 (50%) | 2 | SP1 | KVCALPPSP001 | 4070.00 | 8.140 | 12 min | 1 | 24 min | Order Total: 4 units
2025-12-15 | 2025-11-24 | Monday | W4 | MCB-007 | 2526203377 | Unknown | W4 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | MC1 | KVCAD50MC001 | 4070.00 | 8.140 | 90 min | 0 | - | Order Total: 4 units
2025-12-15 | 2025-11-24 | Monday | W4 | MCB-007 | 2526203377 | Unknown | W4 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | SP1 | KVCALPPSP001 | 4070.00 | 8.140 | 12 min | 1 | 24 min | Order Total: 4 units
2025-11-22 | 2025-11-22 | Saturday | W1 | MCB-007 | 2526203378 | Unknown | W4 | 4 | 1 | 2 | 2/4 (50%) | 2 | Casting | CS2MCB-007 | 4070.00 | 8.140 | 20 min | 1 | 40 min | Order Total: 4 units
2025-11-23 | 2025-11-22 | Sunday | W1 | MCB-007 | 2526203378 | Unknown | W4 | 4 | 1 | 2 | 2/4 (50%) | 2 | Cooling/Shakeout | N/A | 4070.00 | 8.140 | - | 1 | - | Order Total: 4 units
2025-11-24 | 2025-11-24 | Monday | W1 | MCB-007 | 2526203378 | Unknown | W4 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | Casting | CS2MCB-007 | 4070.00 | 8.140 | 20 min | 1 | 40 min | Order Total: 4 units
2025-11-25 | 2025-11-24 | Tuesday | W1 | MCB-007 | 2526203378 | Unknown | W4 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | Cooling/Shakeout | N/A | 4070.00 | 8.140 | - | 1 | - | Order Total: 4 units
2025-11-29 | 2025-11-22 | Saturday | W2 | MCB-007 | 2526203378 | Unknown | W4 | 4 | 1 | 2 | 2/4 (50%) | 2 | Grinding | KVCALHMGR001 | 4070.00 | 8.140 | 330 min | 1 | 660 min | Order Total: 4 units
2025-12-01 | 2025-11-24 | Monday | W2 | MCB-007 | 2526203378 | Unknown | W4 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | Grinding | KVCALHMGR001 | 4070.00 | 8.140 | 330 min | 1 | 660 min | Order Total: 4 units
2025-12-13 | 2025-11-22 | Saturday | W4 | MCB-007 | 2526203378 | Unknown | W4 | 4 | 1 | 2 | 2/4 (50%) | 2 | MC1 | KVCAD50MC001 | 4070.00 | 8.140 | 90 min | 0 | - | Order Total: 4 units
2025-12-13 | 2025-11-22 | Saturday | W4 | MCB-007 | 2526203378 | Unknown | W4 | 4 | 1 | 2 | 2/4 (50%) | 2 | SP1 | KVCALPPSP001 | 4070.00 | 8.140 | 12 min | 1 | 24 min | Order Total: 4 units
2025-12-15 | 2025-11-24 | Monday | W4 | MCB-007 | 2526203378 | Unknown | W4 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | MC1 | KVCAD50MC001 | 4070.00 | 8.140 | 90 min | 0 | - | Order Total: 4 units
2025-12-15 | 2025-11-24 | Monday | W4 | MCB-007 | 2526203378 | Unknown | W4 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | SP1 | KVCALPPSP001 | 4070.00 | 8.140 | 12 min | 1 | 24 min | Order Total: 4 units
2025-11-22 | 2025-11-22 | Saturday | W1 | MCB-007 | 2526203379 | Unknown | W4 | 4 | 1 | 2 | 2/4 (50%) | 2 | Casting | CS2MCB-007 | 4070.00 | 8.140 | 20 min | 1 | 40 min | Order Total: 4 units
2025-11-23 | 2025-11-22 | Sunday | W1 | MCB-007 | 2526203379 | Unknown | W4 | 4 | 1 | 2 | 2/4 (50%) | 2 | Cooling/Shakeout | N/A | 4070.00 | 8.140 | - | 1 | - | Order Total: 4 units
2025-11-24 | 2025-11-24 | Monday | W1 | MCB-007 | 2526203379 | Unknown | W4 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | Casting | CS2MCB-007 | 4070.00 | 8.140 | 20 min | 1 | 40 min | Order Total: 4 units
2025-11-25 | 2025-11-24 | Tuesday | W1 | MCB-007 | 2526203379 | Unknown | W4 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | Cooling/Shakeout | N/A | 4070.00 | 8.140 | - | 1 | - | Order Total: 4 units
2025-11-29 | 2025-11-22 | Saturday | W2 | MCB-007 | 2526203379 | Unknown | W4 | 4 | 1 | 2 | 2/4 (50%) | 2 | Grinding | KVCALHMGR001 | 4070.00 | 8.140 | 330 min | 1 | 660 min | Order Total: 4 units
2025-12-01 | 2025-11-24 | Monday | W2 | MCB-007 | 2526203379 | Unknown | W4 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | Grinding | KVCALHMGR001 | 4070.00 | 8.140 | 330 min | 1 | 660 min | Order Total: 4 units
2025-12-13 | 2025-11-22 | Saturday | W4 | MCB-007 | 2526203379 | Unknown | W4 | 4 | 1 | 2 | 2/4 (50%) | 2 | MC1 | KVCAD50MC001 | 4070.00 | 8.140 | 90 min | 0 | - | Order Total: 4 units
2025-12-13 | 2025-11-22 | Saturday | W4 | MCB-007 | 2526203379 | Unknown | W4 | 4 | 1 | 2 | 2/4 (50%) | 2 | SP1 | KVCALPPSP001 | 4070.00 | 8.140 | 12 min | 1 | 24 min | Order Total: 4 units
2025-12-15 | 2025-11-24 | Monday | W4 | MCB-007 | 2526203379 | Unknown | W4 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | MC1 | KVCAD50MC001 | 4070.00 | 8.140 | 90 min | 0 | - | Order Total: 4 units
2025-12-15 | 2025-11-24 | Monday | W4 | MCB-007 | 2526203379 | Unknown | W4 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | SP1 | KVCALPPSP001 | 4070.00 | 8.140 | 12 min | 1 | 24 min | Order Total: 4 units
2025-11-22 | 2025-11-22 | Saturday | W1 | MCB-007 | 2526203380 | Unknown | W4 | 4 | 1 | 2 | 2/4 (50%) | 2 | Casting | CS2MCB-007 | 4070.00 | 8.140 | 20 min | 1 | 40 min | Order Total: 4 units
2025-11-23 | 2025-11-22 | Sunday | W1 | MCB-007 | 2526203380 | Unknown | W4 | 4 | 1 | 2 | 2/4 (50%) | 2 | Cooling/Shakeout | N/A | 4070.00 | 8.140 | - | 1 | - | Order Total: 4 units
2025-11-24 | 2025-11-24 | Monday | W1 | MCB-007 | 2526203380 | Unknown | W4 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | Casting | CS2MCB-007 | 4070.00 | 8.140 | 20 min | 1 | 40 min | Order Total: 4 units
2025-11-25 | 2025-11-24 | Tuesday | W1 | MCB-007 | 2526203380 | Unknown | W4 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | Cooling/Shakeout | N/A | 4070.00 | 8.140 | - | 1 | - | Order Total: 4 units
2025-11-29 | 2025-11-22 | Saturday | W2 | MCB-007 | 2526203380 | Unknown | W4 | 4 | 1 | 2 | 2/4 (50%) | 2 | Grinding | KVCALHMGR001 | 4070.00 | 8.140 | 330 min | 1 | 660 min | Order Total: 4 units
2025-12-01 | 2025-11-24 | Monday | W2 | MCB-007 | 2526203380 | Unknown | W4 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | Grinding | KVCALHMGR001 | 4070.00 | 8.140 | 330 min | 1 | 660 min | Order Total: 4 units
2025-12-13 | 2025-11-22 | Saturday | W4 | MCB-007 | 2526203380 | Unknown | W4 | 4 | 1 | 2 | 2/4 (50%) | 2 | MC1 | KVCAD50MC001 | 4070.00 | 8.140 | 90 min | 0 | - | Order Total: 4 units
2025-12-13 | 2025-11-22 | Saturday | W4 | MCB-007 | 2526203380 | Unknown | W4 | 4 | 1 | 2 | 2/4 (50%) | 2 | SP1 | KVCALPPSP001 | 4070.00 | 8.140 | 12 min | 1 | 24 min | Order Total: 4 units
2025-12-15 | 2025-11-24 | Monday | W4 | MCB-007 | 2526203380 | Unknown | W4 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | MC1 | KVCAD50MC001 | 4070.00 | 8.140 | 90 min | 0 | - | Order Total: 4 units
2025-12-15 | 2025-11-24 | Monday | W4 | MCB-007 | 2526203380 | Unknown | W4 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | SP1 | KVCALPPSP001 | 4070.00 | 8.140 | 12 min | 1 | 24 min | Order Total: 4 units
2025-11-22 | 2025-11-22 | Saturday | W1 | MCB-007 | 2526203381 | Unknown | W4 | 4 | 1 | 2 | 2/4 (50%) | 2 | Casting | CS2MCB-007 | 4070.00 | 8.140 | 20 min | 1 | 40 min | Order Total: 4 units
2025-11-23 | 2025-11-22 | Sunday | W1 | MCB-007 | 2526203381 | Unknown | W4 | 4 | 1 | 2 | 2/4 (50%) | 2 | Cooling/Shakeout | N/A | 4070.00 | 8.140 | - | 1 | - | Order Total: 4 units
2025-11-24 | 2025-11-24 | Monday | W1 | MCB-007 | 2526203381 | Unknown | W4 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | Casting | CS2MCB-007 | 4070.00 | 8.140 | 20 min | 1 | 40 min | Order Total: 4 units
2025-11-25 | 2025-11-24 | Tuesday | W1 | MCB-007 | 2526203381 | Unknown | W4 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | Cooling/Shakeout | N/A | 4070.00 | 8.140 | - | 1 | - | Order Total: 4 units
2025-11-29 | 2025-11-22 | Saturday | W2 | MCB-007 | 2526203381 | Unknown | W4 | 4 | 1 | 2 | 2/4 (50%) | 2 | Grinding | KVCALHMGR001 | 4070.00 | 8.140 | 330 min | 1 | 660 min | Order Total: 4 units
2025-12-01 | 2025-11-24 | Monday | W2 | MCB-007 | 2526203381 | Unknown | W4 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | Grinding | KVCALHMGR001 | 4070.00 | 8.140 | 330 min | 1 | 660 min | Order Total: 4 units
2025-12-13 | 2025-11-22 | Saturday | W4 | MCB-007 | 2526203381 | Unknown | W4 | 4 | 1 | 2 | 2/4 (50%) | 2 | MC1 | KVCAD50MC001 | 4070.00 | 8.140 | 90 min | 0 | - | Order Total: 4 units
2025-12-13 | 2025-11-22 | Saturday | W4 | MCB-007 | 2526203381 | Unknown | W4 | 4 | 1 | 2 | 2/4 (50%) | 2 | SP1 | KVCALPPSP001 | 4070.00 | 8.140 | 12 min | 1 | 24 min | Order Total: 4 units
2025-12-15 | 2025-11-24 | Monday | W4 | MCB-007 | 2526203381 | Unknown | W4 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | MC1 | KVCAD50MC001 | 4070.00 | 8.140 | 90 min | 0 | - | Order Total: 4 units
2025-12-15 | 2025-11-24 | Monday | W4 | MCB-007 | 2526203381 | Unknown | W4 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | SP1 | KVCALPPSP001 | 4070.00 | 8.140 | 12 min | 1 | 24 min | Order Total: 4 units
2025-11-22 | 2025-11-22 | Saturday | W1 | MCB-007 | 2526203382 | Unknown | W4 | 4 | 1 | 2 | 2/4 (50%) | 2 | Casting | CS2MCB-007 | 4070.00 | 8.140 | 20 min | 1 | 40 min | Order Total: 4 units
2025-11-23 | 2025-11-22 | Sunday | W1 | MCB-007 | 2526203382 | Unknown | W4 | 4 | 1 | 2 | 2/4 (50%) | 2 | Cooling/Shakeout | N/A | 4070.00 | 8.140 | - | 1 | - | Order Total: 4 units
2025-11-24 | 2025-11-24 | Monday | W1 | MCB-007 | 2526203382 | Unknown | W4 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | Casting | CS2MCB-007 | 4070.00 | 8.140 | 20 min | 1 | 40 min | Order Total: 4 units
2025-11-25 | 2025-11-24 | Tuesday | W1 | MCB-007 | 2526203382 | Unknown | W4 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | Cooling/Shakeout | N/A | 4070.00 | 8.140 | - | 1 | - | Order Total: 4 units
2025-11-29 | 2025-11-22 | Saturday | W2 | MCB-007 | 2526203382 | Unknown | W4 | 4 | 1 | 2 | 2/4 (50%) | 2 | Grinding | KVCALHMGR001 | 4070.00 | 8.140 | 330 min | 1 | 660 min | Order Total: 4 units
2025-12-01 | 2025-11-24 | Monday | W2 | MCB-007 | 2526203382 | Unknown | W4 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | Grinding | KVCALHMGR001 | 4070.00 | 8.140 | 330 min | 1 | 660 min | Order Total: 4 units
2025-12-13 | 2025-11-22 | Saturday | W4 | MCB-007 | 2526203382 | Unknown | W4 | 4 | 1 | 2 | 2/4 (50%) | 2 | MC1 | KVCAD50MC001 | 4070.00 | 8.140 | 90 min | 0 | - | Order Total: 4 units
2025-12-13 | 2025-11-22 | Saturday | W4 | MCB-007 | 2526203382 | Unknown | W4 | 4 | 1 | 2 | 2/4 (50%) | 2 | SP1 | KVCALPPSP001 | 4070.00 | 8.140 | 12 min | 1 | 24 min | Order Total: 4 units
2025-12-15 | 2025-11-24 | Monday | W4 | MCB-007 | 2526203382 | Unknown | W4 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | MC1 | KVCAD50MC001 | 4070.00 | 8.140 | 90 min | 0 | - | Order Total: 4 units
2025-12-15 | 2025-11-24 | Monday | W4 | MCB-007 | 2526203382 | Unknown | W4 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | SP1 | KVCALPPSP001 | 4070.00 | 8.140 | 12 min | 1 | 24 min | Order Total: 4 units
2025-11-22 | 2025-11-22 | Saturday | W1 | MCB-007 | 2526203383 | Unknown | W4 | 4 | 1 | 2 | 2/4 (50%) | 2 | Casting | CS2MCB-007 | 4070.00 | 8.140 | 20 min | 1 | 40 min | Order Total: 4 units
2025-11-23 | 2025-11-22 | Sunday | W1 | MCB-007 | 2526203383 | Unknown | W4 | 4 | 1 | 2 | 2/4 (50%) | 2 | Cooling/Shakeout | N/A | 4070.00 | 8.140 | - | 1 | - | Order Total: 4 units
2025-11-24 | 2025-11-24 | Monday | W1 | MCB-007 | 2526203383 | Unknown | W4 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | Casting | CS2MCB-007 | 4070.00 | 8.140 | 20 min | 1 | 40 min | Order Total: 4 units
2025-11-25 | 2025-11-24 | Tuesday | W1 | MCB-007 | 2526203383 | Unknown | W4 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | Cooling/Shakeout | N/A | 4070.00 | 8.140 | - | 1 | - | Order Total: 4 units
2025-11-29 | 2025-11-22 | Saturday | W2 | MCB-007 | 2526203383 | Unknown | W4 | 4 | 1 | 2 | 2/4 (50%) | 2 | Grinding | KVCALHMGR001 | 4070.00 | 8.140 | 330 min | 1 | 660 min | Order Total: 4 units
2025-12-01 | 2025-11-24 | Monday | W2 | MCB-007 | 2526203383 | Unknown | W4 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | Grinding | KVCALHMGR001 | 4070.00 | 8.140 | 330 min | 1 | 660 min | Order Total: 4 units
2025-12-13 | 2025-11-22 | Saturday | W4 | MCB-007 | 2526203383 | Unknown | W4 | 4 | 1 | 2 | 2/4 (50%) | 2 | MC1 | KVCAD50MC001 | 4070.00 | 8.140 | 90 min | 0 | - | Order Total: 4 units
2025-12-13 | 2025-11-22 | Saturday | W4 | MCB-007 | 2526203383 | Unknown | W4 | 4 | 1 | 2 | 2/4 (50%) | 2 | SP1 | KVCALPPSP001 | 4070.00 | 8.140 | 12 min | 1 | 24 min | Order Total: 4 units
2025-12-15 | 2025-11-24 | Monday | W4 | MCB-007 | 2526203383 | Unknown | W4 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | MC1 | KVCAD50MC001 | 4070.00 | 8.140 | 90 min | 0 | - | Order Total: 4 units
2025-12-15 | 2025-11-24 | Monday | W4 | MCB-007 | 2526203383 | Unknown | W4 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | SP1 | KVCALPPSP001 | 4070.00 | 8.140 | 12 min | 1 | 24 min | Order Total: 4 units
2025-11-22 | 2025-11-22 | Saturday | W1 | MCB-007 | 2526203384 | Unknown | W4 | 4 | 1 | 2 | 2/4 (50%) | 2 | Casting | CS2MCB-007 | 4070.00 | 8.140 | 20 min | 1 | 40 min | Order Total: 4 units
2025-11-23 | 2025-11-22 | Sunday | W1 | MCB-007 | 2526203384 | Unknown | W4 | 4 | 1 | 2 | 2/4 (50%) | 2 | Cooling/Shakeout | N/A | 4070.00 | 8.140 | - | 1 | - | Order Total: 4 units
2025-11-24 | 2025-11-24 | Monday | W1 | MCB-007 | 2526203384 | Unknown | W4 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | Casting | CS2MCB-007 | 4070.00 | 8.140 | 20 min | 1 | 40 min | Order Total: 4 units
2025-11-25 | 2025-11-24 | Tuesday | W1 | MCB-007 | 2526203384 | Unknown | W4 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | Cooling/Shakeout | N/A | 4070.00 | 8.140 | - | 1 | - | Order Total: 4 units
2025-11-29 | 2025-11-22 | Saturday | W2 | MCB-007 | 2526203384 | Unknown | W4 | 4 | 1 | 2 | 2/4 (50%) | 2 | Grinding | KVCALHMGR001 | 4070.00 | 8.140 | 330 min | 1 | 660 min | Order Total: 4 units
2025-12-01 | 2025-11-24 | Monday | W2 | MCB-007 | 2526203384 | Unknown | W4 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | Grinding | KVCALHMGR001 | 4070.00 | 8.140 | 330 min | 1 | 660 min | Order Total: 4 units
2025-12-13 | 2025-11-22 | Saturday | W4 | MCB-007 | 2526203384 | Unknown | W4 | 4 | 1 | 2 | 2/4 (50%) | 2 | MC1 | KVCAD50MC001 | 4070.00 | 8.140 | 90 min | 0 | - | Order Total: 4 units
2025-12-13 | 2025-11-22 | Saturday | W4 | MCB-007 | 2526203384 | Unknown | W4 | 4 | 1 | 2 | 2/4 (50%) | 2 | SP1 | KVCALPPSP001 | 4070.00 | 8.140 | 12 min | 1 | 24 min | Order Total: 4 units
2025-12-15 | 2025-11-24 | Monday | W4 | MCB-007 | 2526203384 | Unknown | W4 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | MC1 | KVCAD50MC001 | 4070.00 | 8.140 | 90 min | 0 | - | Order Total: 4 units
2025-12-15 | 2025-11-24 | Monday | W4 | MCB-007 | 2526203384 | Unknown | W4 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | SP1 | KVCALPPSP001 | 4070.00 | 8.140 | 12 min | 1 | 24 min | Order Total: 4 units
2025-11-22 | 2025-11-22 | Saturday | W1 | MCB-007 | 2526203385 | Unknown | W4 | 4 | 1 | 2 | 2/4 (50%) | 2 | Casting | CS2MCB-007 | 4070.00 | 8.140 | 20 min | 1 | 40 min | Order Total: 4 units
2025-11-23 | 2025-11-22 | Sunday | W1 | MCB-007 | 2526203385 | Unknown | W4 | 4 | 1 | 2 | 2/4 (50%) | 2 | Cooling/Shakeout | N/A | 4070.00 | 8.140 | - | 1 | - | Order Total: 4 units
2025-11-24 | 2025-11-24 | Monday | W1 | MCB-007 | 2526203385 | Unknown | W4 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | Casting | CS2MCB-007 | 4070.00 | 8.140 | 20 min | 1 | 40 min | Order Total: 4 units
2025-11-25 | 2025-11-24 | Tuesday | W1 | MCB-007 | 2526203385 | Unknown | W4 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | Cooling/Shakeout | N/A | 4070.00 | 8.140 | - | 1 | - | Order Total: 4 units
2025-11-29 | 2025-11-22 | Saturday | W2 | MCB-007 | 2526203385 | Unknown | W4 | 4 | 1 | 2 | 2/4 (50%) | 2 | Grinding | KVCALHMGR001 | 4070.00 | 8.140 | 330 min | 1 | 660 min | Order Total: 4 units
2025-12-01 | 2025-11-24 | Monday | W2 | MCB-007 | 2526203385 | Unknown | W4 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | Grinding | KVCALHMGR001 | 4070.00 | 8.140 | 330 min | 1 | 660 min | Order Total: 4 units
2025-12-13 | 2025-11-22 | Saturday | W4 | MCB-007 | 2526203385 | Unknown | W4 | 4 | 1 | 2 | 2/4 (50%) | 2 | MC1 | KVCAD50MC001 | 4070.00 | 8.140 | 90 min | 0 | - | Order Total: 4 units
2025-12-13 | 2025-11-22 | Saturday | W4 | MCB-007 | 2526203385 | Unknown | W4 | 4 | 1 | 2 | 2/4 (50%) | 2 | SP1 | KVCALPPSP001 | 4070.00 | 8.140 | 12 min | 1 | 24 min | Order Total: 4 units
2025-12-15 | 2025-11-24 | Monday | W4 | MCB-007 | 2526203385 | Unknown | W4 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | MC1 | KVCAD50MC001 | 4070.00 | 8.140 | 90 min | 0 | - | Order Total: 4 units
2025-12-15 | 2025-11-24 | Monday | W4 | MCB-007 | 2526203385 | Unknown | W4 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | SP1 | KVCALPPSP001 | 4070.00 | 8.140 | 12 min | 1 | 24 min | Order Total: 4 units
2025-11-29 | 2025-11-29 | Saturday | W2 | MCB-007 | 2526203386 | Unknown | W3 | 4 | 1 | 2 | 2/4 (50%) | 2 | MC1 | KVCAD50MC001 | 4070.00 | 8.140 | 90 min | 0 | - | Order Total: 4 units
2025-11-29 | 2025-11-29 | Saturday | W2 | MCB-007 | 2526203386 | Unknown | W3 | 4 | 1 | 2 | 2/4 (50%) | 2 | SP1 | KVCALPPSP001 | 4070.00 | 8.140 | 12 min | 1 | 24 min | Order Total: 4 units
2025-12-01 | 2025-12-01 | Monday | W2 | MCB-007 | 2526203386 | Unknown | W3 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | MC1 | KVCAD50MC001 | 4070.00 | 8.140 | 90 min | 0 | - | Order Total: 4 units
2025-12-01 | 2025-12-01 | Monday | W2 | MCB-007 | 2526203386 | Unknown | W3 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | SP1 | KVCALPPSP001 | 4070.00 | 8.140 | 12 min | 1 | 24 min | Order Total: 4 units
2025-12-13 | 2025-12-13 | Saturday | W4 | MCB-007 | 2526203386 | Unknown | W3 | 4 | 1 | 2 | 2/4 (50%) | 2 | Grinding | KVCALHMGR001 | 4070.00 | 8.140 | 330 min | 1 | 660 min | Order Total: 4 units
2025-12-15 | 2025-12-15 | Monday | W4 | MCB-007 | 2526203386 | Unknown | W3 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | Grinding | KVCALHMGR001 | 4070.00 | 8.140 | 330 min | 1 | 660 min | Order Total: 4 units
2025-11-29 | 2025-11-29 | Saturday | W2 | MCB-007 | 2526203387 | Unknown | W3 | 4 | 1 | 2 | 2/4 (50%) | 2 | MC1 | KVCAD50MC001 | 4070.00 | 8.140 | 90 min | 0 | - | Order Total: 4 units
2025-11-29 | 2025-11-29 | Saturday | W2 | MCB-007 | 2526203387 | Unknown | W3 | 4 | 1 | 2 | 2/4 (50%) | 2 | SP1 | KVCALPPSP001 | 4070.00 | 8.140 | 12 min | 1 | 24 min | Order Total: 4 units
2025-12-01 | 2025-12-01 | Monday | W2 | MCB-007 | 2526203387 | Unknown | W3 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | MC1 | KVCAD50MC001 | 4070.00 | 8.140 | 90 min | 0 | - | Order Total: 4 units
2025-12-01 | 2025-12-01 | Monday | W2 | MCB-007 | 2526203387 | Unknown | W3 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | SP1 | KVCALPPSP001 | 4070.00 | 8.140 | 12 min | 1 | 24 min | Order Total: 4 units
2025-12-13 | 2025-12-13 | Saturday | W4 | MCB-007 | 2526203387 | Unknown | W3 | 4 | 1 | 2 | 2/4 (50%) | 2 | Grinding | KVCALHMGR001 | 4070.00 | 8.140 | 330 min | 1 | 660 min | Order Total: 4 units
2025-12-15 | 2025-12-15 | Monday | W4 | MCB-007 | 2526203387 | Unknown | W3 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | Grinding | KVCALHMGR001 | 4070.00 | 8.140 | 330 min | 1 | 660 min | Order Total: 4 units
2025-11-22 | 2025-11-22 | Saturday | W1 | MCB-JLG-032 | 2526203388 | Unknown | W2 | 4 | 1 | 2 | 2/4 (50%) | 2 | Casting | CS-MCB-JLG-032 | 3652.00 | 7.304 | 25 min | 1 | 50 min | Order Total: 4 units
2025-11-22 | 2025-11-22 | Saturday | W1 | MCB-JLG-032 | 2526203388 | Unknown | W2 | 4 | 1 | 2 | 2/4 (50%) | 2 | Grinding | KVCALHMGR001 | 3652.00 | 7.304 | 390 min | 1 | 780 min | Order Total: 4 units
2025-11-23 | 2025-11-22 | Sunday | W1 | MCB-JLG-032 | 2526203388 | Unknown | W2 | 4 | 1 | 2 | 2/4 (50%) | 2 | Cooling/Shakeout | N/A | 3652.00 | 7.304 | - | 1 | - | Order Total: 4 units
2025-11-24 | 2025-11-24 | Monday | W1 | MCB-JLG-032 | 2526203388 | Unknown | W2 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | Casting | CS-MCB-JLG-032 | 3652.00 | 7.304 | 25 min | 1 | 50 min | Order Total: 4 units
2025-11-24 | 2025-11-24 | Monday | W1 | MCB-JLG-032 | 2526203388 | Unknown | W2 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | Grinding | KVCALHMGR001 | 3652.00 | 7.304 | 390 min | 1 | 780 min | Order Total: 4 units
2025-11-25 | 2025-11-24 | Tuesday | W1 | MCB-JLG-032 | 2526203388 | Unknown | W2 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | Cooling/Shakeout | N/A | 3652.00 | 7.304 | - | 1 | - | Order Total: 4 units
2025-11-29 | 2025-11-22 | Saturday | W2 | MCB-JLG-032 | 2526203388 | Unknown | W2 | 4 | 1 | 2 | 2/4 (50%) | 2 | MC1 | KVCAD50MC001 | 3652.00 | 7.304 | 40 min | 0 | - | Order Total: 4 units
2025-11-29 | 2025-11-22 | Saturday | W2 | MCB-JLG-032 | 2526203388 | Unknown | W2 | 4 | 1 | 2 | 2/4 (50%) | 2 | SP1 | KVCALPPSP001 | 3652.00 | 7.304 | 12 min | 1 | 24 min | Order Total: 4 units
2025-12-01 | 2025-11-24 | Monday | W2 | MCB-JLG-032 | 2526203388 | Unknown | W2 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | MC1 | KVCAD50MC001 | 3652.00 | 7.304 | 40 min | 0 | - | Order Total: 4 units
2025-12-01 | 2025-11-24 | Monday | W2 | MCB-JLG-032 | 2526203388 | Unknown | W2 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | SP1 | KVCALPPSP001 | 3652.00 | 7.304 | 12 min | 1 | 24 min | Order Total: 4 units
2025-11-22 | 2025-12-13 | Saturday | W1 | MCB-JLG-047 | 2526203389 | Unknown | W4 | 11 | 1 | 2 | 2/11 (18%) | 2 | Grinding | KVCALHMGR001 | 1592.40 | 3.185 | 390 min | 1 | 780 min | Order Total: 11 units
2025-11-22 | 2025-12-13 | Saturday | W1 | MCB-JLG-047 | 2526203389 | Unknown | W4 | 11 | 1 | 2 | 2/11 (18%) | 2 | SP1 | KVCALPPSP001 | 1592.40 | 3.185 | 12 min | 1 | 24 min | Order Total: 11 units
2025-11-24 | 2025-12-15 | Monday | W1 | MCB-JLG-047 | 2526203389 | Unknown | W4 | 11 | 2 | 5 | 5/11 (45%) | 3 | Grinding | KVCALHMGR001 | 1592.40 | 4.777 | 390 min | 1 | 1170 min | Order Total: 11 units
2025-11-24 | 2025-12-15 | Monday | W1 | MCB-JLG-047 | 2526203389 | Unknown | W4 | 11 | 2 | 5 | 5/11 (45%) | 3 | SP1 | KVCALPPSP001 | 1592.40 | 4.777 | 12 min | 1 | 36 min | Order Total: 11 units
2025-11-25 | 2025-12-13 | Tuesday | W1 | MCB-JLG-047 | 2526203389 | Unknown | W4 | 11 | 3 | 8 | 8/11 (72%) | 3 | Grinding | KVCALHMGR001 | 1592.40 | 4.777 | 390 min | 1 | 1170 min | Order Total: 11 units
2025-11-25 | 2025-12-13 | Tuesday | W1 | MCB-JLG-047 | 2526203389 | Unknown | W4 | 11 | 3 | 8 | 8/11 (72%) | 3 | SP1 | KVCALPPSP001 | 1592.40 | 4.777 | 12 min | 1 | 36 min | Order Total: 11 units
2025-11-26 | 2025-12-13 | Wednesday | W1 | MCB-JLG-047 | 2526203389 | Unknown | W4 | 11 | 4 | 11 | 11/11 COMPLETE ✓ | 3 | Grinding | KVCALHMGR001 | 1592.40 | 4.777 | 390 min | 1 | 1170 min | Order Total: 11 units
2025-11-26 | 2025-12-13 | Wednesday | W1 | MCB-JLG-047 | 2526203389 | Unknown | W4 | 11 | 4 | 11 | 11/11 COMPLETE ✓ | 3 | SP1 | KVCALPPSP001 | 1592.40 | 4.777 | 12 min | 1 | 36 min | Order Total: 11 units
2025-12-13 | 2025-12-13 | Saturday | W4 | MCB-JLG-047 | 2526203389 | Unknown | W4 | 11 | 1 | 5 | 5/11 (45%) | 5 | Casting | CS1-MCB-JLG-047 | 1592.40 | 7.962 | 25 min | 1 | 125 min | Order Total: 11 units
2025-12-14 | 2025-12-13 | Sunday | W4 | MCB-JLG-047 | 2526203389 | Unknown | W4 | 11 | 1 | 2 | 2/11 (18%) | 2 | Cooling/Shakeout | N/A | 1592.40 | 3.185 | - | 1 | - | Order Total: 11 units
2025-12-15 | 2025-12-15 | Monday | W4 | MCB-JLG-047 | 2526203389 | Unknown | W4 | 11 | 2 | 11 | 11/11 COMPLETE ✓ | 6 | Casting | CS1-MCB-JLG-047 | 1592.40 | 9.554 | 25 min | 1 | 150 min | Order Total: 11 units
2025-12-16 | 2025-12-15 | Tuesday | W4 | MCB-JLG-047 | 2526203389 | Unknown | W4 | 11 | 2 | 5 | 5/11 (45%) | 3 | Cooling/Shakeout | N/A | 1592.40 | 4.777 | - | 1 | - | Order Total: 11 units
2025-12-17 | 2025-12-13 | Wednesday | W4 | MCB-JLG-047 | 2526203389 | Unknown | W4 | 11 | 3 | 8 | 8/11 (72%) | 3 | Cooling/Shakeout | N/A | 1592.40 | 4.777 | - | 1 | - | Order Total: 11 units
2025-12-18 | 2025-12-13 | Thursday | W4 | MCB-JLG-047 | 2526203389 | Unknown | W4 | 11 | 4 | 11 | 11/11 COMPLETE ✓ | 3 | Cooling/Shakeout | N/A | 1592.40 | 4.777 | - | 1 | - | Order Total: 11 units
2025-11-29 | 2025-12-06 | Saturday | W2 | MCB-009 | 2526203390 | Unknown | W6 | 12 | 1 | 3 | 3/12 (25%) | 3 | MC1 | KVCAD50MC001 | 1500.00 | 4.500 | 100 min | 0 | - | Order Total: 12 units
2025-12-01 | 2025-12-08 | Monday | W2 | MCB-009 | 2526203390 | Unknown | W6 | 12 | 2 | 6 | 6/12 (50%) | 3 | MC1 | KVCAD50MC001 | 1500.00 | 4.500 | 100 min | 0 | - | Order Total: 12 units
2025-12-02 | 2025-12-09 | Tuesday | W2 | MCB-009 | 2526203390 | Unknown | W6 | 12 | 3 | 9 | 9/12 (75%) | 3 | MC1 | KVCAD50MC001 | 1500.00 | 4.500 | 100 min | 0 | - | Order Total: 12 units
2025-12-03 | 2025-12-06 | Wednesday | W2 | MCB-009 | 2526203390 | Unknown | W6 | 12 | 4 | 12 | 12/12 COMPLETE ✓ | 3 | MC1 | KVCAD50MC001 | 1500.00 | 4.500 | 100 min | 0 | - | Order Total: 12 units
2025-12-06 | 2025-12-06 | Saturday | W3 | MCB-009 | 2526203390 | Unknown | W6 | 12 | 1 | 4 | 4/12 (33%) | 4 | Casting | CS2MCB-009 | 1500.00 | 6.000 | 20 min | 1 | 80 min | Order Total: 12 units
2025-12-06 | 2025-12-06 | Saturday | W3 | MCB-009 | 2526203390 | Unknown | W6 | 12 | 1 | 3 | 3/12 (25%) | 3 | Grinding | KVCALHMGR001 | 1500.00 | 4.500 | 210 min | 1 | 630 min | Order Total: 12 units
2025-12-07 | 2025-12-06 | Sunday | W3 | MCB-009 | 2526203390 | Unknown | W6 | 12 | 1 | 3 | 3/12 (25%) | 3 | Cooling/Shakeout | N/A | 1500.00 | 4.500 | - | 1 | - | Order Total: 12 units
2025-12-08 | 2025-12-08 | Monday | W3 | MCB-009 | 2526203390 | Unknown | W6 | 12 | 2 | 8 | 8/12 (66%) | 4 | Casting | CS2MCB-009 | 1500.00 | 6.000 | 20 min | 1 | 80 min | Order Total: 12 units
2025-12-08 | 2025-12-08 | Monday | W3 | MCB-009 | 2526203390 | Unknown | W6 | 12 | 2 | 6 | 6/12 (50%) | 3 | Grinding | KVCALHMGR001 | 1500.00 | 4.500 | 210 min | 1 | 630 min | Order Total: 12 units
2025-12-09 | 2025-12-09 | Tuesday | W3 | MCB-009 | 2526203390 | Unknown | W6 | 12 | 3 | 12 | 12/12 COMPLETE ✓ | 4 | Casting | CS2MCB-009 | 1500.00 | 6.000 | 20 min | 1 | 80 min | Order Total: 12 units
2025-12-09 | 2025-12-08 | Tuesday | W3 | MCB-009 | 2526203390 | Unknown | W6 | 12 | 2 | 6 | 6/12 (50%) | 3 | Cooling/Shakeout | N/A | 1500.00 | 4.500 | - | 1 | - | Order Total: 12 units
2025-12-09 | 2025-12-09 | Tuesday | W3 | MCB-009 | 2526203390 | Unknown | W6 | 12 | 3 | 9 | 9/12 (75%) | 3 | Grinding | KVCALHMGR001 | 1500.00 | 4.500 | 210 min | 1 | 630 min | Order Total: 12 units
2025-12-10 | 2025-12-09 | Wednesday | W3 | MCB-009 | 2526203390 | Unknown | W6 | 12 | 3 | 9 | 9/12 (75%) | 3 | Cooling/Shakeout | N/A | 1500.00 | 4.500 | - | 1 | - | Order Total: 12 units
2025-12-10 | 2025-12-06 | Wednesday | W3 | MCB-009 | 2526203390 | Unknown | W6 | 12 | 4 | 12 | 12/12 COMPLETE ✓ | 3 | Grinding | KVCALHMGR001 | 1500.00 | 4.500 | 210 min | 1 | 630 min | Order Total: 12 units
2025-12-11 | 2025-12-06 | Thursday | W3 | MCB-009 | 2526203390 | Unknown | W6 | 12 | 4 | 12 | 12/12 COMPLETE ✓ | 3 | Cooling/Shakeout | N/A | 1500.00 | 4.500 | - | 1 | - | Order Total: 12 units
2025-12-20 | 2025-12-06 | Saturday | W5 | MCB-009 | 2526203390 | Unknown | W6 | 12 | 1 | 3 | 3/12 (25%) | 3 | SP1 | KVCALPPSP001 | 1500.00 | 4.500 | 7 min | 1 | 21 min | Order Total: 12 units
2025-12-22 | 2025-12-08 | Monday | W5 | MCB-009 | 2526203390 | Unknown | W6 | 12 | 2 | 6 | 6/12 (50%) | 3 | SP1 | KVCALPPSP001 | 1500.00 | 4.500 | 7 min | 1 | 21 min | Order Total: 12 units
2025-12-23 | 2025-12-09 | Tuesday | W5 | MCB-009 | 2526203390 | Unknown | W6 | 12 | 3 | 9 | 9/12 (75%) | 3 | SP1 | KVCALPPSP001 | 1500.00 | 4.500 | 7 min | 1 | 21 min | Order Total: 12 units
2025-12-24 | 2025-12-06 | Wednesday | W5 | MCB-009 | 2526203390 | Unknown | W6 | 12 | 4 | 12 | 12/12 COMPLETE ✓ | 3 | SP1 | KVCALPPSP001 | 1500.00 | 4.500 | 7 min | 1 | 21 min | Order Total: 12 units
2025-11-22 | 2025-11-22 | Saturday | W1 | MCB-008 | 2526203394 | Unknown | W4 | 6 | 1 | 2 | 2/6 (33%) | 2 | SP1 | KVCALPPSP001 | 2770.00 | 5.540 | 12 min | 1 | 24 min | Order Total: 6 units
2025-11-24 | 2025-11-24 | Monday | W1 | MCB-008 | 2526203394 | Unknown | W4 | 6 | 2 | 4 | 4/6 (66%) | 2 | SP1 | KVCALPPSP001 | 2770.00 | 5.540 | 12 min | 1 | 24 min | Order Total: 6 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | MCB-008 | 2526203394 | Unknown | W4 | 6 | 3 | 6 | 6/6 COMPLETE ✓ | 2 | SP1 | KVCALPPSP001 | 2770.00 | 5.540 | 12 min | 1 | 24 min | Order Total: 6 units
2025-11-22 | 2025-11-22 | Saturday | W1 | MCB-010 | 2526203396 | Unknown | W3 | 7 | 1 | 2 | 2/7 (28%) | 2 | Casting | CS2MCB-010 | 2650.00 | 5.300 | 20 min | 1 | 40 min | Order Total: 7 units
2025-11-22 | 2025-11-22 | Saturday | W1 | MCB-010 | 2526203396 | Unknown | W3 | 7 | 1 | 2 | 2/7 (28%) | 2 | SP1 | KVCALPPSP001 | 2650.00 | 5.300 | 12 min | 1 | 24 min | Order Total: 7 units
2025-11-23 | 2025-11-22 | Sunday | W1 | MCB-010 | 2526203396 | Unknown | W3 | 7 | 1 | 2 | 2/7 (28%) | 2 | Cooling/Shakeout | N/A | 2650.00 | 5.300 | - | 1 | - | Order Total: 7 units
2025-11-24 | 2025-11-24 | Monday | W1 | MCB-010 | 2526203396 | Unknown | W3 | 7 | 2 | 4 | 4/7 (57%) | 2 | Casting | CS2MCB-010 | 2650.00 | 5.300 | 20 min | 1 | 40 min | Order Total: 7 units
2025-11-24 | 2025-11-24 | Monday | W1 | MCB-010 | 2526203396 | Unknown | W3 | 7 | 2 | 4 | 4/7 (57%) | 2 | SP1 | KVCALPPSP001 | 2650.00 | 5.300 | 12 min | 1 | 24 min | Order Total: 7 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | MCB-010 | 2526203396 | Unknown | W3 | 7 | 3 | 7 | 7/7 COMPLETE ✓ | 3 | Casting | CS2MCB-010 | 2650.00 | 7.950 | 20 min | 1 | 60 min | Order Total: 7 units
2025-11-25 | 2025-11-24 | Tuesday | W1 | MCB-010 | 2526203396 | Unknown | W3 | 7 | 2 | 4 | 4/7 (57%) | 2 | Cooling/Shakeout | N/A | 2650.00 | 5.300 | - | 1 | - | Order Total: 7 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | MCB-010 | 2526203396 | Unknown | W3 | 7 | 3 | 7 | 7/7 COMPLETE ✓ | 3 | SP1 | KVCALPPSP001 | 2650.00 | 7.950 | 12 min | 1 | 36 min | Order Total: 7 units
2025-11-26 | 2025-11-25 | Wednesday | W1 | MCB-010 | 2526203396 | Unknown | W3 | 7 | 3 | 7 | 7/7 COMPLETE ✓ | 3 | Cooling/Shakeout | N/A | 2650.00 | 7.950 | - | 1 | - | Order Total: 7 units
2025-12-06 | 2025-11-22 | Saturday | W3 | MCB-010 | 2526203396 | Unknown | W3 | 7 | 1 | 2 | 2/7 (28%) | 2 | Grinding | KVCALHMGR001 | 2650.00 | 5.300 | 300 min | 1 | 600 min | Order Total: 7 units
2025-12-06 | 2025-11-22 | Saturday | W3 | MCB-010 | 2526203396 | Unknown | W3 | 7 | 1 | 2 | 2/7 (28%) | 2 | MC1 | KVCAD50MC001 | 2650.00 | 5.300 | 60 min | 0 | - | Order Total: 7 units
2025-12-08 | 2025-11-24 | Monday | W3 | MCB-010 | 2526203396 | Unknown | W3 | 7 | 2 | 4 | 4/7 (57%) | 2 | Grinding | KVCALHMGR001 | 2650.00 | 5.300 | 300 min | 1 | 600 min | Order Total: 7 units
2025-12-08 | 2025-11-24 | Monday | W3 | MCB-010 | 2526203396 | Unknown | W3 | 7 | 2 | 4 | 4/7 (57%) | 2 | MC1 | KVCAD50MC001 | 2650.00 | 5.300 | 60 min | 0 | - | Order Total: 7 units
2025-12-09 | 2025-11-25 | Tuesday | W3 | MCB-010 | 2526203396 | Unknown | W3 | 7 | 3 | 7 | 7/7 COMPLETE ✓ | 3 | Grinding | KVCALHMGR001 | 2650.00 | 7.950 | 300 min | 1 | 900 min | Order Total: 7 units
2025-12-09 | 2025-11-25 | Tuesday | W3 | MCB-010 | 2526203396 | Unknown | W3 | 7 | 3 | 7 | 7/7 COMPLETE ✓ | 3 | MC1 | KVCAD50MC001 | 2650.00 | 7.950 | 60 min | 0 | - | Order Total: 7 units
2025-11-22 | 2025-11-22 | Saturday | W1 | MCB-010 | 2526203397 | Unknown | W3 | 7 | 1 | 2 | 2/7 (28%) | 2 | Casting | CS2MCB-010 | 2650.00 | 5.300 | 20 min | 1 | 40 min | Order Total: 7 units
2025-11-22 | 2025-11-22 | Saturday | W1 | MCB-010 | 2526203397 | Unknown | W3 | 7 | 1 | 2 | 2/7 (28%) | 2 | SP1 | KVCALPPSP001 | 2650.00 | 5.300 | 12 min | 1 | 24 min | Order Total: 7 units
2025-11-23 | 2025-11-22 | Sunday | W1 | MCB-010 | 2526203397 | Unknown | W3 | 7 | 1 | 2 | 2/7 (28%) | 2 | Cooling/Shakeout | N/A | 2650.00 | 5.300 | - | 1 | - | Order Total: 7 units
2025-11-24 | 2025-11-24 | Monday | W1 | MCB-010 | 2526203397 | Unknown | W3 | 7 | 2 | 4 | 4/7 (57%) | 2 | Casting | CS2MCB-010 | 2650.00 | 5.300 | 20 min | 1 | 40 min | Order Total: 7 units
2025-11-24 | 2025-11-24 | Monday | W1 | MCB-010 | 2526203397 | Unknown | W3 | 7 | 2 | 4 | 4/7 (57%) | 2 | SP1 | KVCALPPSP001 | 2650.00 | 5.300 | 12 min | 1 | 24 min | Order Total: 7 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | MCB-010 | 2526203397 | Unknown | W3 | 7 | 3 | 7 | 7/7 COMPLETE ✓ | 3 | Casting | CS2MCB-010 | 2650.00 | 7.950 | 20 min | 1 | 60 min | Order Total: 7 units
2025-11-25 | 2025-11-24 | Tuesday | W1 | MCB-010 | 2526203397 | Unknown | W3 | 7 | 2 | 4 | 4/7 (57%) | 2 | Cooling/Shakeout | N/A | 2650.00 | 5.300 | - | 1 | - | Order Total: 7 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | MCB-010 | 2526203397 | Unknown | W3 | 7 | 3 | 7 | 7/7 COMPLETE ✓ | 3 | SP1 | KVCALPPSP001 | 2650.00 | 7.950 | 12 min | 1 | 36 min | Order Total: 7 units
2025-11-26 | 2025-11-25 | Wednesday | W1 | MCB-010 | 2526203397 | Unknown | W3 | 7 | 3 | 7 | 7/7 COMPLETE ✓ | 3 | Cooling/Shakeout | N/A | 2650.00 | 7.950 | - | 1 | - | Order Total: 7 units
2025-12-06 | 2025-11-22 | Saturday | W3 | MCB-010 | 2526203397 | Unknown | W3 | 7 | 1 | 2 | 2/7 (28%) | 2 | Grinding | KVCALHMGR001 | 2650.00 | 5.300 | 300 min | 1 | 600 min | Order Total: 7 units
2025-12-06 | 2025-11-22 | Saturday | W3 | MCB-010 | 2526203397 | Unknown | W3 | 7 | 1 | 2 | 2/7 (28%) | 2 | MC1 | KVCAD50MC001 | 2650.00 | 5.300 | 60 min | 0 | - | Order Total: 7 units
2025-12-08 | 2025-11-24 | Monday | W3 | MCB-010 | 2526203397 | Unknown | W3 | 7 | 2 | 4 | 4/7 (57%) | 2 | Grinding | KVCALHMGR001 | 2650.00 | 5.300 | 300 min | 1 | 600 min | Order Total: 7 units
2025-12-08 | 2025-11-24 | Monday | W3 | MCB-010 | 2526203397 | Unknown | W3 | 7 | 2 | 4 | 4/7 (57%) | 2 | MC1 | KVCAD50MC001 | 2650.00 | 5.300 | 60 min | 0 | - | Order Total: 7 units
2025-12-09 | 2025-11-25 | Tuesday | W3 | MCB-010 | 2526203397 | Unknown | W3 | 7 | 3 | 7 | 7/7 COMPLETE ✓ | 3 | Grinding | KVCALHMGR001 | 2650.00 | 7.950 | 300 min | 1 | 900 min | Order Total: 7 units
2025-12-09 | 2025-11-25 | Tuesday | W3 | MCB-010 | 2526203397 | Unknown | W3 | 7 | 3 | 7 | 7/7 COMPLETE ✓ | 3 | MC1 | KVCAD50MC001 | 2650.00 | 7.950 | 60 min | 0 | - | Order Total: 7 units
2025-11-22 | 2025-11-22 | Saturday | W1 | MCB-HYG-023 | 2526203398 | Unknown | W4 | 6 | 1 | 2 | 2/6 (33%) | 2 | MC1 | KVCAD50MC001 | 2942.00 | 5.884 | 55 min | 1 | 110 min | Order Total: 6 units
2025-11-24 | 2025-11-24 | Monday | W1 | MCB-HYG-023 | 2526203398 | Unknown | W4 | 6 | 2 | 4 | 4/6 (66%) | 2 | MC1 | KVCAD50MC001 | 2942.00 | 5.884 | 55 min | 1 | 110 min | Order Total: 6 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | MCB-HYG-023 | 2526203398 | Unknown | W4 | 6 | 3 | 6 | 6/6 COMPLETE ✓ | 2 | MC1 | KVCAD50MC001 | 2942.00 | 5.884 | 55 min | 1 | 110 min | Order Total: 6 units
2025-11-22 | 2025-11-22 | Saturday | W1 | UBC-021 | 2526203427 | Unknown | W6 | 2 | 1 | 1 | 1/2 (50%) | 1 | Casting | CS1-UBC-021 | 3600.00 | 3.600 | 20 min | 1 | 20 min | Order Total: 2 units
2025-11-22 | 2025-11-22 | Saturday | W1 | UBC-022 | 2526203427 | Unknown | W6 | 8 | 1 | 2 | 2/8 (25%) | 2 | Casting | CS1-UBC-022 | 1200.00 | 2.400 | 22 min | 1 | 44 min | Order Total: 8 units
2025-11-22 | 2025-11-22 | Saturday | W1 | UBC-051 | 2526203427 | Unknown | W6 | 4 | 1 | 2 | 2/4 (50%) | 2 | SP1 | KVCALPPSP001 | 369.00 | 0.738 | 12 min | 1 | 24 min | Order Total: 4 units
2025-11-23 | 2025-11-22 | Sunday | W1 | UBC-021 | 2526203427 | Unknown | W6 | 2 | 1 | 1 | 1/2 (50%) | 1 | Cooling/Shakeout | N/A | 3600.00 | 3.600 | - | 1 | - | Order Total: 2 units
2025-11-23 | 2025-11-22 | Sunday | W1 | UBC-022 | 2526203427 | Unknown | W6 | 8 | 1 | 2 | 2/8 (25%) | 2 | Cooling/Shakeout | N/A | 1200.00 | 2.400 | - | 1 | - | Order Total: 8 units
2025-11-24 | 2025-11-24 | Monday | W1 | UBC-021 | 2526203427 | Unknown | W6 | 2 | 2 | 2 | 2/2 COMPLETE ✓ | 1 | Casting | CS1-UBC-021 | 3600.00 | 3.600 | 20 min | 1 | 20 min | Order Total: 2 units
2025-11-24 | 2025-11-24 | Monday | W1 | UBC-022 | 2526203427 | Unknown | W6 | 8 | 2 | 4 | 4/8 (50%) | 2 | Casting | CS1-UBC-022 | 1200.00 | 2.400 | 22 min | 1 | 44 min | Order Total: 8 units
2025-11-24 | 2025-11-24 | Monday | W1 | UBC-051 | 2526203427 | Unknown | W6 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | SP1 | KVCALPPSP001 | 369.00 | 0.738 | 12 min | 1 | 24 min | Order Total: 4 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | UBC-022 | 2526203427 | Unknown | W6 | 8 | 3 | 6 | 6/8 (75%) | 2 | Casting | CS1-UBC-022 | 1200.00 | 2.400 | 22 min | 1 | 44 min | Order Total: 8 units
2025-11-25 | 2025-11-24 | Tuesday | W1 | UBC-021 | 2526203427 | Unknown | W6 | 2 | 2 | 2 | 2/2 COMPLETE ✓ | 1 | Cooling/Shakeout | N/A | 3600.00 | 3.600 | - | 1 | - | Order Total: 2 units
2025-11-25 | 2025-11-24 | Tuesday | W1 | UBC-022 | 2526203427 | Unknown | W6 | 8 | 2 | 4 | 4/8 (50%) | 2 | Cooling/Shakeout | N/A | 1200.00 | 2.400 | - | 1 | - | Order Total: 8 units
2025-11-26 | 2025-11-26 | Wednesday | W1 | UBC-022 | 2526203427 | Unknown | W6 | 8 | 4 | 8 | 8/8 COMPLETE ✓ | 2 | Casting | CS1-UBC-022 | 1200.00 | 2.400 | 22 min | 1 | 44 min | Order Total: 8 units
2025-11-26 | 2025-11-25 | Wednesday | W1 | UBC-022 | 2526203427 | Unknown | W6 | 8 | 3 | 6 | 6/8 (75%) | 2 | Cooling/Shakeout | N/A | 1200.00 | 2.400 | - | 1 | - | Order Total: 8 units
2025-11-27 | 2025-11-26 | Thursday | W1 | UBC-022 | 2526203427 | Unknown | W6 | 8 | 4 | 8 | 8/8 COMPLETE ✓ | 2 | Cooling/Shakeout | N/A | 1200.00 | 2.400 | - | 1 | - | Order Total: 8 units
2025-11-29 | 2025-11-22 | Saturday | W2 | UBC-022 | 2526203427 | Unknown | W6 | 8 | 1 | 2 | 2/8 (25%) | 2 | Grinding | GR1-UBC-022 | 1200.00 | 2.400 | 240 min | 1 | 480 min | Order Total: 8 units
2025-12-01 | 2025-11-24 | Monday | W2 | UBC-022 | 2526203427 | Unknown | W6 | 8 | 2 | 4 | 4/8 (50%) | 2 | Grinding | GR1-UBC-022 | 1200.00 | 2.400 | 240 min | 1 | 480 min | Order Total: 8 units
2025-12-02 | 2025-11-25 | Tuesday | W2 | UBC-022 | 2526203427 | Unknown | W6 | 8 | 3 | 6 | 6/8 (75%) | 2 | Grinding | GR1-UBC-022 | 1200.00 | 2.400 | 240 min | 1 | 480 min | Order Total: 8 units
2025-12-03 | 2025-11-26 | Wednesday | W2 | UBC-022 | 2526203427 | Unknown | W6 | 8 | 4 | 8 | 8/8 COMPLETE ✓ | 2 | Grinding | GR1-UBC-022 | 1200.00 | 2.400 | 240 min | 1 | 480 min | Order Total: 8 units
2025-12-13 | 2025-11-22 | Saturday | W4 | UBC-021 | 2526203427 | Unknown | W6 | 2 | 1 | 1 | 1/2 (50%) | 1 | MC1 | KVCAD50MC001 | 3600.00 | 3.600 | 80 min | 0 | - | Order Total: 2 units
2025-12-15 | 2025-11-24 | Monday | W4 | UBC-021 | 2526203427 | Unknown | W6 | 2 | 2 | 2 | 2/2 COMPLETE ✓ | 1 | MC1 | KVCAD50MC001 | 3600.00 | 3.600 | 80 min | 0 | - | Order Total: 2 units
2025-12-20 | 2025-11-22 | Saturday | W5 | UBC-022 | 2526203427 | Unknown | W6 | 8 | 1 | 2 | 2/8 (25%) | 2 | SP1 | SP1-UBC-022 | 1200.00 | 2.400 | - | 1 | - | Order Total: 8 units
2025-12-22 | 2025-11-24 | Monday | W5 | UBC-022 | 2526203427 | Unknown | W6 | 8 | 2 | 4 | 4/8 (50%) | 2 | SP1 | SP1-UBC-022 | 1200.00 | 2.400 | - | 1 | - | Order Total: 8 units
2025-12-23 | 2025-11-25 | Tuesday | W5 | UBC-022 | 2526203427 | Unknown | W6 | 8 | 3 | 6 | 6/8 (75%) | 2 | SP1 | SP1-UBC-022 | 1200.00 | 2.400 | - | 1 | - | Order Total: 8 units
2025-12-24 | 2025-11-26 | Wednesday | W5 | UBC-022 | 2526203427 | Unknown | W6 | 8 | 4 | 8 | 8/8 COMPLETE ✓ | 2 | SP1 | SP1-UBC-022 | 1200.00 | 2.400 | - | 1 | - | Order Total: 8 units
2025-11-22 | 2025-11-22 | Saturday | W1 | UBC-064 | 2526203434 | Unknown | W1 | 1 | 1 | 1 | 1/1 COMPLETE ✓ | 1 | MC1 | KVCAD50MC001 | 650.00 | 0.650 | 90 min | 1 | 90 min | Order Total: 1 units
2025-11-22 | 2025-11-22 | Saturday | W1 | UBC-064 | 2526203434 | Unknown | W1 | 1 | 1 | 1 | 1/1 COMPLETE ✓ | 1 | SP1 | KVCALPPSP001 | 650.00 | 0.650 | 12 min | 1 | 12 min | Order Total: 1 units
2025-11-22 | 2025-11-22 | Saturday | W1 | UBC-064 | 2526203434 | Unknown | W1 | 1 | 1 | 1 | 1/1 COMPLETE ✓ | 1 | SP2 | KVCALPPSP002 | 650.00 | 0.650 | 12 min | 1 | 12 min | Order Total: 1 units
2025-11-22 | 2025-11-22 | Saturday | W1 | UBC-064 | 2526203434 | Unknown | W1 | 1 | 1 | 1 | 1/1 COMPLETE ✓ | 1 | SP3 | KVCALFPSP001 | 650.00 | 0.650 | 7 min | 1 | 7 min | Order Total: 1 units
2025-11-22 | 2025-11-22 | Saturday | W1 | TAS-GN-021 | 2526203454 | Unknown | W3 | 12 | 1 | 4 | 4/12 (33%) | 4 | Casting | CS1-TAS-GN-021 | 350.00 | 1.400 | 25 min | 1 | 100 min | Order Total: 12 units
2025-11-22 | 2025-11-22 | Saturday | W1 | TAS-GN-029 | 2526203454 | Unknown | W3 | 6 | 1 | 4 | 4/18 (22%) | 4 | Casting | CS1-TAS-GN-029 | 636.36 | 2.545 | 25 min | 1 | 100 min | Order Total: 6 units
2025-11-22 | 2025-11-22 | Saturday | W1 | TAS-GN-029 | 2526203454 | Unknown | W3 | 12 | 2 | 8 | 8/18 (44%) | 4 | Casting | CS1-TAS-GN-029 | 636.36 | 2.545 | 25 min | 1 | 100 min | Order Total: 12 units
2025-11-22 | 2025-11-22 | Saturday | W1 | TAS-GN-029 | 2526203454 | Unknown | W3 | 12 | 3 | 12 | 12/18 (66%) | 4 | Casting | CS1-TAS-GN-029 | 636.36 | 2.545 | 25 min | 1 | 100 min | Order Total: 12 units
2025-11-23 | 2025-11-22 | Sunday | W1 | TAS-GN-021 | 2526203454 | Unknown | W3 | 12 | 1 | 3 | 3/12 (25%) | 3 | Cooling/Shakeout | N/A | 350.00 | 1.050 | - | 1 | - | Order Total: 12 units
2025-11-23 | 2025-11-22 | Sunday | W1 | TAS-GN-029 | 2526203454 | Unknown | W3 | 6 | 1 | 2 | 2/18 (11%) | 2 | Cooling/Shakeout | N/A | 636.36 | 1.273 | - | 1 | - | Order Total: 6 units
2025-11-23 | 2025-11-22 | Sunday | W1 | TAS-GN-029 | 2526203454 | Unknown | W3 | 12 | 2 | 5 | 5/18 (27%) | 3 | Cooling/Shakeout | N/A | 636.36 | 1.909 | - | 1 | - | Order Total: 12 units
2025-11-23 | 2025-11-22 | Sunday | W1 | TAS-GN-029 | 2526203454 | Unknown | W3 | 12 | 3 | 8 | 8/18 (44%) | 3 | Cooling/Shakeout | N/A | 636.36 | 1.909 | - | 1 | - | Order Total: 12 units
2025-11-24 | 2025-11-24 | Monday | W1 | TAS-GN-021 | 2526203454 | Unknown | W3 | 12 | 2 | 12 | 12/12 COMPLETE ✓ | 8 | Casting | CS1-TAS-GN-021 | 350.00 | 2.800 | 25 min | 1 | 200 min | Order Total: 12 units
2025-11-24 | 2025-11-24 | Monday | W1 | TAS-GN-029 | 2526203454 | Unknown | W3 | 6 | 4 | 14 | 14/18 (77%) | 2 | Casting | CS1-TAS-GN-029 | 636.36 | 1.273 | 25 min | 1 | 50 min | Order Total: 6 units
2025-11-24 | 2025-11-24 | Monday | W1 | TAS-GN-029 | 2526203454 | Unknown | W3 | 12 | 5 | 22 | 22/18 COMPLETE ✓ | 8 | Casting | CS1-TAS-GN-029 | 636.36 | 5.091 | 25 min | 1 | 200 min | Order Total: 12 units
2025-11-24 | 2025-11-24 | Monday | W1 | TAS-GN-029 | 2526203454 | Unknown | W3 | 12 | 6 | 30 | 30/18 COMPLETE ✓ | 8 | Casting | CS1-TAS-GN-029 | 636.36 | 5.091 | 25 min | 1 | 200 min | Order Total: 12 units
2025-11-25 | 2025-11-24 | Tuesday | W1 | TAS-GN-021 | 2526203454 | Unknown | W3 | 12 | 2 | 6 | 6/12 (50%) | 3 | Cooling/Shakeout | N/A | 350.00 | 1.050 | - | 1 | - | Order Total: 12 units
2025-11-25 | 2025-11-24 | Tuesday | W1 | TAS-GN-029 | 2526203454 | Unknown | W3 | 6 | 4 | 10 | 10/18 (55%) | 2 | Cooling/Shakeout | N/A | 636.36 | 1.273 | - | 1 | - | Order Total: 6 units
2025-11-25 | 2025-11-24 | Tuesday | W1 | TAS-GN-029 | 2526203454 | Unknown | W3 | 12 | 5 | 13 | 13/18 (72%) | 3 | Cooling/Shakeout | N/A | 636.36 | 1.909 | - | 1 | - | Order Total: 12 units
2025-11-25 | 2025-11-24 | Tuesday | W1 | TAS-GN-029 | 2526203454 | Unknown | W3 | 12 | 6 | 16 | 16/18 (88%) | 3 | Cooling/Shakeout | N/A | 636.36 | 1.909 | - | 1 | - | Order Total: 12 units
2025-11-26 | 2025-11-22 | Wednesday | W1 | TAS-GN-021 | 2526203454 | Unknown | W3 | 12 | 3 | 9 | 9/12 (75%) | 3 | Cooling/Shakeout | N/A | 350.00 | 1.050 | - | 1 | - | Order Total: 12 units
2025-11-26 | 2025-11-22 | Wednesday | W1 | TAS-GN-029 | 2526203454 | Unknown | W3 | 6 | 7 | 18 | 18/18 COMPLETE ✓ | 2 | Cooling/Shakeout | N/A | 636.36 | 1.273 | - | 1 | - | Order Total: 6 units
2025-11-26 | 2025-11-22 | Wednesday | W1 | TAS-GN-029 | 2526203454 | Unknown | W3 | 12 | 8 | 21 | 21/18 COMPLETE ✓ | 3 | Cooling/Shakeout | N/A | 636.36 | 1.909 | - | 1 | - | Order Total: 12 units
2025-11-26 | 2025-11-22 | Wednesday | W1 | TAS-GN-029 | 2526203454 | Unknown | W3 | 12 | 9 | 24 | 24/18 COMPLETE ✓ | 3 | Cooling/Shakeout | N/A | 636.36 | 1.909 | - | 1 | - | Order Total: 12 units
2025-11-27 | 2025-11-22 | Thursday | W1 | TAS-GN-021 | 2526203454 | Unknown | W3 | 12 | 4 | 12 | 12/12 COMPLETE ✓ | 3 | Cooling/Shakeout | N/A | 350.00 | 1.050 | - | 1 | - | Order Total: 12 units
2025-11-27 | 2025-11-24 | Thursday | W1 | TAS-GN-029 | 2526203454 | Unknown | W3 | 12 | 10 | 27 | 27/18 COMPLETE ✓ | 3 | Cooling/Shakeout | N/A | 636.36 | 1.909 | - | 1 | - | Order Total: 12 units
2025-11-27 | 2025-11-24 | Thursday | W1 | TAS-GN-029 | 2526203454 | Unknown | W3 | 12 | 11 | 30 | 30/18 COMPLETE ✓ | 3 | Cooling/Shakeout | N/A | 636.36 | 1.909 | - | 1 | - | Order Total: 12 units
2025-12-06 | 2025-11-22 | Saturday | W3 | TAS-GN-029 | 2526203454 | Unknown | W3 | 6 | 1 | 2 | 2/18 (11%) | 2 | SP1 | KVCALPPSP001 | 636.36 | 1.273 | 7 min | 1 | 14 min | Order Total: 6 units
2025-12-06 | 2025-11-22 | Saturday | W3 | TAS-GN-029 | 2526203454 | Unknown | W3 | 12 | 2 | 5 | 5/18 (27%) | 3 | SP1 | KVCALPPSP001 | 636.36 | 1.909 | 7 min | 1 | 21 min | Order Total: 12 units
2025-12-06 | 2025-11-22 | Saturday | W3 | TAS-GN-029 | 2526203454 | Unknown | W3 | 12 | 3 | 8 | 8/18 (44%) | 3 | SP1 | KVCALPPSP001 | 636.36 | 1.909 | 7 min | 1 | 21 min | Order Total: 12 units
2025-12-06 | 2025-11-22 | Saturday | W3 | TAS-GN-029 | 2526203454 | Unknown | W3 | 6 | 1 | 2 | 2/18 (11%) | 2 | SP2 | KVCALPPSP002 | 636.36 | 1.273 | 7 min | 1 | 14 min | Order Total: 6 units
2025-12-06 | 2025-11-22 | Saturday | W3 | TAS-GN-029 | 2526203454 | Unknown | W3 | 12 | 2 | 5 | 5/18 (27%) | 3 | SP2 | KVCALPPSP002 | 636.36 | 1.909 | 7 min | 1 | 21 min | Order Total: 12 units
2025-12-06 | 2025-11-22 | Saturday | W3 | TAS-GN-029 | 2526203454 | Unknown | W3 | 12 | 3 | 8 | 8/18 (44%) | 3 | SP2 | KVCALPPSP002 | 636.36 | 1.909 | 7 min | 1 | 21 min | Order Total: 12 units
2025-12-06 | 2025-11-22 | Saturday | W3 | TAS-GN-029 | 2526203454 | Unknown | W3 | 6 | 1 | 2 | 2/18 (11%) | 2 | SP3 | KVCALFPSP001 | 636.36 | 1.273 | 7 min | 1 | 14 min | Order Total: 6 units
2025-12-06 | 2025-11-22 | Saturday | W3 | TAS-GN-029 | 2526203454 | Unknown | W3 | 12 | 2 | 5 | 5/18 (27%) | 3 | SP3 | KVCALFPSP001 | 636.36 | 1.909 | 7 min | 1 | 21 min | Order Total: 12 units
2025-12-06 | 2025-11-22 | Saturday | W3 | TAS-GN-029 | 2526203454 | Unknown | W3 | 12 | 3 | 8 | 8/18 (44%) | 3 | SP3 | KVCALFPSP001 | 636.36 | 1.909 | 7 min | 1 | 21 min | Order Total: 12 units
2025-12-08 | 2025-11-24 | Monday | W3 | TAS-GN-029 | 2526203454 | Unknown | W3 | 6 | 4 | 10 | 10/18 (55%) | 2 | SP1 | KVCALPPSP001 | 636.36 | 1.273 | 7 min | 1 | 14 min | Order Total: 6 units
2025-12-08 | 2025-11-24 | Monday | W3 | TAS-GN-029 | 2526203454 | Unknown | W3 | 12 | 5 | 13 | 13/18 (72%) | 3 | SP1 | KVCALPPSP001 | 636.36 | 1.909 | 7 min | 1 | 21 min | Order Total: 12 units
2025-12-08 | 2025-11-24 | Monday | W3 | TAS-GN-029 | 2526203454 | Unknown | W3 | 12 | 6 | 16 | 16/18 (88%) | 3 | SP1 | KVCALPPSP001 | 636.36 | 1.909 | 7 min | 1 | 21 min | Order Total: 12 units
2025-12-08 | 2025-11-24 | Monday | W3 | TAS-GN-029 | 2526203454 | Unknown | W3 | 6 | 4 | 10 | 10/18 (55%) | 2 | SP2 | KVCALPPSP002 | 636.36 | 1.273 | 7 min | 1 | 14 min | Order Total: 6 units
2025-12-08 | 2025-11-24 | Monday | W3 | TAS-GN-029 | 2526203454 | Unknown | W3 | 12 | 5 | 13 | 13/18 (72%) | 3 | SP2 | KVCALPPSP002 | 636.36 | 1.909 | 7 min | 1 | 21 min | Order Total: 12 units
2025-12-08 | 2025-11-24 | Monday | W3 | TAS-GN-029 | 2526203454 | Unknown | W3 | 12 | 6 | 16 | 16/18 (88%) | 3 | SP2 | KVCALPPSP002 | 636.36 | 1.909 | 7 min | 1 | 21 min | Order Total: 12 units
2025-12-08 | 2025-11-24 | Monday | W3 | TAS-GN-029 | 2526203454 | Unknown | W3 | 6 | 4 | 10 | 10/18 (55%) | 2 | SP3 | KVCALFPSP001 | 636.36 | 1.273 | 7 min | 1 | 14 min | Order Total: 6 units
2025-12-08 | 2025-11-24 | Monday | W3 | TAS-GN-029 | 2526203454 | Unknown | W3 | 12 | 5 | 13 | 13/18 (72%) | 3 | SP3 | KVCALFPSP001 | 636.36 | 1.909 | 7 min | 1 | 21 min | Order Total: 12 units
2025-12-08 | 2025-11-24 | Monday | W3 | TAS-GN-029 | 2526203454 | Unknown | W3 | 12 | 6 | 16 | 16/18 (88%) | 3 | SP3 | KVCALFPSP001 | 636.36 | 1.909 | 7 min | 1 | 21 min | Order Total: 12 units
2025-12-09 | 2025-11-22 | Tuesday | W3 | TAS-GN-029 | 2526203454 | Unknown | W3 | 6 | 7 | 18 | 18/18 COMPLETE ✓ | 2 | SP1 | KVCALPPSP001 | 636.36 | 1.273 | 7 min | 1 | 14 min | Order Total: 6 units
2025-12-09 | 2025-11-22 | Tuesday | W3 | TAS-GN-029 | 2526203454 | Unknown | W3 | 12 | 8 | 21 | 21/18 COMPLETE ✓ | 3 | SP1 | KVCALPPSP001 | 636.36 | 1.909 | 7 min | 1 | 21 min | Order Total: 12 units
2025-12-09 | 2025-11-22 | Tuesday | W3 | TAS-GN-029 | 2526203454 | Unknown | W3 | 12 | 9 | 24 | 24/18 COMPLETE ✓ | 3 | SP1 | KVCALPPSP001 | 636.36 | 1.909 | 7 min | 1 | 21 min | Order Total: 12 units
2025-12-09 | 2025-11-22 | Tuesday | W3 | TAS-GN-029 | 2526203454 | Unknown | W3 | 6 | 7 | 18 | 18/18 COMPLETE ✓ | 2 | SP2 | KVCALPPSP002 | 636.36 | 1.273 | 7 min | 1 | 14 min | Order Total: 6 units
2025-12-09 | 2025-11-22 | Tuesday | W3 | TAS-GN-029 | 2526203454 | Unknown | W3 | 12 | 8 | 21 | 21/18 COMPLETE ✓ | 3 | SP2 | KVCALPPSP002 | 636.36 | 1.909 | 7 min | 1 | 21 min | Order Total: 12 units
2025-12-09 | 2025-11-22 | Tuesday | W3 | TAS-GN-029 | 2526203454 | Unknown | W3 | 12 | 9 | 24 | 24/18 COMPLETE ✓ | 3 | SP2 | KVCALPPSP002 | 636.36 | 1.909 | 7 min | 1 | 21 min | Order Total: 12 units
2025-12-09 | 2025-11-22 | Tuesday | W3 | TAS-GN-029 | 2526203454 | Unknown | W3 | 6 | 7 | 18 | 18/18 COMPLETE ✓ | 2 | SP3 | KVCALFPSP001 | 636.36 | 1.273 | 7 min | 1 | 14 min | Order Total: 6 units
2025-12-09 | 2025-11-22 | Tuesday | W3 | TAS-GN-029 | 2526203454 | Unknown | W3 | 12 | 8 | 21 | 21/18 COMPLETE ✓ | 3 | SP3 | KVCALFPSP001 | 636.36 | 1.909 | 7 min | 1 | 21 min | Order Total: 12 units
2025-12-09 | 2025-11-22 | Tuesday | W3 | TAS-GN-029 | 2526203454 | Unknown | W3 | 12 | 9 | 24 | 24/18 COMPLETE ✓ | 3 | SP3 | KVCALFPSP001 | 636.36 | 1.909 | 7 min | 1 | 21 min | Order Total: 12 units
2025-12-10 | 2025-11-24 | Wednesday | W3 | TAS-GN-029 | 2526203454 | Unknown | W3 | 12 | 10 | 27 | 27/18 COMPLETE ✓ | 3 | SP1 | KVCALPPSP001 | 636.36 | 1.909 | 7 min | 1 | 21 min | Order Total: 12 units
2025-12-10 | 2025-11-24 | Wednesday | W3 | TAS-GN-029 | 2526203454 | Unknown | W3 | 12 | 11 | 30 | 30/18 COMPLETE ✓ | 3 | SP1 | KVCALPPSP001 | 636.36 | 1.909 | 7 min | 1 | 21 min | Order Total: 12 units
2025-12-10 | 2025-11-24 | Wednesday | W3 | TAS-GN-029 | 2526203454 | Unknown | W3 | 12 | 10 | 27 | 27/18 COMPLETE ✓ | 3 | SP2 | KVCALPPSP002 | 636.36 | 1.909 | 7 min | 1 | 21 min | Order Total: 12 units
2025-12-10 | 2025-11-24 | Wednesday | W3 | TAS-GN-029 | 2526203454 | Unknown | W3 | 12 | 11 | 30 | 30/18 COMPLETE ✓ | 3 | SP2 | KVCALPPSP002 | 636.36 | 1.909 | 7 min | 1 | 21 min | Order Total: 12 units
2025-12-10 | 2025-11-24 | Wednesday | W3 | TAS-GN-029 | 2526203454 | Unknown | W3 | 12 | 10 | 27 | 27/18 COMPLETE ✓ | 3 | SP3 | KVCALFPSP001 | 636.36 | 1.909 | 7 min | 1 | 21 min | Order Total: 12 units
2025-12-10 | 2025-11-24 | Wednesday | W3 | TAS-GN-029 | 2526203454 | Unknown | W3 | 12 | 11 | 30 | 30/18 COMPLETE ✓ | 3 | SP3 | KVCALFPSP001 | 636.36 | 1.909 | 7 min | 1 | 21 min | Order Total: 12 units
2025-11-22 | 2025-11-22 | Saturday | W1 | TAS-GN-021 | 2526203455 | Unknown | W4 | 14 | 1 | 5 | 5/14 (35%) | 5 | Casting | CS1-TAS-GN-021 | 350.00 | 1.750 | 25 min | 1 | 125 min | Order Total: 14 units
2025-11-22 | 2025-11-22 | Saturday | W1 | TAS-GN-029 | 2526203455 | Unknown | W4 | 3 | 1 | 1 | 1/3 (33%) | 1 | Casting | CS1-TAS-GN-029 | 636.36 | 0.636 | 25 min | 1 | 25 min | Order Total: 3 units
2025-11-22 | 2025-11-22 | Saturday | W1 | TAS-GN-021 | 2526203455 | Unknown | W4 | 14 | 1 | 3 | 3/14 (21%) | 3 | Grinding | KVCALHMGR001 | 350.00 | 1.050 | 120 min | 1 | 360 min | Order Total: 14 units
2025-11-22 | 2025-11-22 | Saturday | W1 | TAS-GN-021 | 2526203455 | Unknown | W4 | 14 | 1 | 3 | 3/14 (21%) | 3 | SP1 | KVCALPPSP001 | 350.00 | 1.050 | 7 min | 1 | 21 min | Order Total: 14 units
2025-11-22 | 2025-11-22 | Saturday | W1 | TAS-GN-021 | 2526203455 | Unknown | W4 | 14 | 1 | 3 | 3/14 (21%) | 3 | SP2 | KVCALPPSP002 | 350.00 | 1.050 | 7 min | 1 | 21 min | Order Total: 14 units
2025-11-22 | 2025-11-22 | Saturday | W1 | TAS-GN-021 | 2526203455 | Unknown | W4 | 14 | 1 | 3 | 3/14 (21%) | 3 | SP3 | KVCALFPSP001 | 350.00 | 1.050 | 7 min | 1 | 21 min | Order Total: 14 units
2025-11-23 | 2025-11-22 | Sunday | W1 | TAS-GN-021 | 2526203455 | Unknown | W4 | 14 | 1 | 3 | 3/14 (21%) | 3 | Cooling/Shakeout | N/A | 350.00 | 1.050 | - | 1 | - | Order Total: 14 units
2025-11-23 | 2025-11-22 | Sunday | W1 | TAS-GN-029 | 2526203455 | Unknown | W4 | 3 | 1 | 1 | 1/3 (33%) | 1 | Cooling/Shakeout | N/A | 636.36 | 0.636 | - | 1 | - | Order Total: 3 units
2025-11-24 | 2025-11-24 | Monday | W1 | TAS-GN-021 | 2526203455 | Unknown | W4 | 14 | 2 | 14 | 14/14 COMPLETE ✓ | 9 | Casting | CS1-TAS-GN-021 | 350.00 | 3.150 | 25 min | 1 | 225 min | Order Total: 14 units
2025-11-24 | 2025-11-24 | Monday | W1 | TAS-GN-029 | 2526203455 | Unknown | W4 | 3 | 2 | 2 | 2/3 (66%) | 1 | Casting | CS1-TAS-GN-029 | 636.36 | 0.636 | 25 min | 1 | 25 min | Order Total: 3 units
2025-11-24 | 2025-11-24 | Monday | W1 | TAS-GN-021 | 2526203455 | Unknown | W4 | 14 | 2 | 6 | 6/14 (42%) | 3 | Grinding | KVCALHMGR001 | 350.00 | 1.050 | 120 min | 1 | 360 min | Order Total: 14 units
2025-11-24 | 2025-11-24 | Monday | W1 | TAS-GN-021 | 2526203455 | Unknown | W4 | 14 | 2 | 6 | 6/14 (42%) | 3 | SP1 | KVCALPPSP001 | 350.00 | 1.050 | 7 min | 1 | 21 min | Order Total: 14 units
2025-11-24 | 2025-11-24 | Monday | W1 | TAS-GN-021 | 2526203455 | Unknown | W4 | 14 | 2 | 6 | 6/14 (42%) | 3 | SP2 | KVCALPPSP002 | 350.00 | 1.050 | 7 min | 1 | 21 min | Order Total: 14 units
2025-11-24 | 2025-11-24 | Monday | W1 | TAS-GN-021 | 2526203455 | Unknown | W4 | 14 | 2 | 6 | 6/14 (42%) | 3 | SP3 | KVCALFPSP001 | 350.00 | 1.050 | 7 min | 1 | 21 min | Order Total: 14 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | TAS-GN-029 | 2526203455 | Unknown | W4 | 3 | 3 | 3 | 3/3 COMPLETE ✓ | 1 | Casting | CS1-TAS-GN-029 | 636.36 | 0.636 | 25 min | 1 | 25 min | Order Total: 3 units
2025-11-25 | 2025-11-24 | Tuesday | W1 | TAS-GN-021 | 2526203455 | Unknown | W4 | 14 | 2 | 6 | 6/14 (42%) | 3 | Cooling/Shakeout | N/A | 350.00 | 1.050 | - | 1 | - | Order Total: 14 units
2025-11-25 | 2025-11-24 | Tuesday | W1 | TAS-GN-029 | 2526203455 | Unknown | W4 | 3 | 2 | 2 | 2/3 (66%) | 1 | Cooling/Shakeout | N/A | 636.36 | 0.636 | - | 1 | - | Order Total: 3 units
2025-11-25 | 2025-11-22 | Tuesday | W1 | TAS-GN-021 | 2526203455 | Unknown | W4 | 14 | 3 | 10 | 10/14 (71%) | 4 | Grinding | KVCALHMGR001 | 350.00 | 1.400 | 120 min | 1 | 480 min | Order Total: 14 units
2025-11-25 | 2025-11-22 | Tuesday | W1 | TAS-GN-021 | 2526203455 | Unknown | W4 | 14 | 3 | 10 | 10/14 (71%) | 4 | SP1 | KVCALPPSP001 | 350.00 | 1.400 | 7 min | 1 | 28 min | Order Total: 14 units
2025-11-25 | 2025-11-22 | Tuesday | W1 | TAS-GN-021 | 2526203455 | Unknown | W4 | 14 | 3 | 10 | 10/14 (71%) | 4 | SP2 | KVCALPPSP002 | 350.00 | 1.400 | 7 min | 1 | 28 min | Order Total: 14 units
2025-11-25 | 2025-11-22 | Tuesday | W1 | TAS-GN-021 | 2526203455 | Unknown | W4 | 14 | 3 | 10 | 10/14 (71%) | 4 | SP3 | KVCALFPSP001 | 350.00 | 1.400 | 7 min | 1 | 28 min | Order Total: 14 units
2025-11-26 | 2025-11-22 | Wednesday | W1 | TAS-GN-021 | 2526203455 | Unknown | W4 | 14 | 3 | 10 | 10/14 (71%) | 4 | Cooling/Shakeout | N/A | 350.00 | 1.400 | - | 1 | - | Order Total: 14 units
2025-11-26 | 2025-11-25 | Wednesday | W1 | TAS-GN-029 | 2526203455 | Unknown | W4 | 3 | 3 | 3 | 3/3 COMPLETE ✓ | 1 | Cooling/Shakeout | N/A | 636.36 | 0.636 | - | 1 | - | Order Total: 3 units
2025-11-26 | 2025-11-22 | Wednesday | W1 | TAS-GN-021 | 2526203455 | Unknown | W4 | 14 | 4 | 14 | 14/14 COMPLETE ✓ | 4 | Grinding | KVCALHMGR001 | 350.00 | 1.400 | 120 min | 1 | 480 min | Order Total: 14 units
2025-11-26 | 2025-11-22 | Wednesday | W1 | TAS-GN-021 | 2526203455 | Unknown | W4 | 14 | 4 | 14 | 14/14 COMPLETE ✓ | 4 | SP1 | KVCALPPSP001 | 350.00 | 1.400 | 7 min | 1 | 28 min | Order Total: 14 units
2025-11-26 | 2025-11-22 | Wednesday | W1 | TAS-GN-021 | 2526203455 | Unknown | W4 | 14 | 4 | 14 | 14/14 COMPLETE ✓ | 4 | SP2 | KVCALPPSP002 | 350.00 | 1.400 | 7 min | 1 | 28 min | Order Total: 14 units
2025-11-26 | 2025-11-22 | Wednesday | W1 | TAS-GN-021 | 2526203455 | Unknown | W4 | 14 | 4 | 14 | 14/14 COMPLETE ✓ | 4 | SP3 | KVCALFPSP001 | 350.00 | 1.400 | 7 min | 1 | 28 min | Order Total: 14 units
2025-11-27 | 2025-11-22 | Thursday | W1 | TAS-GN-021 | 2526203455 | Unknown | W4 | 14 | 4 | 14 | 14/14 COMPLETE ✓ | 4 | Cooling/Shakeout | N/A | 350.00 | 1.400 | - | 1 | - | Order Total: 14 units
2025-11-29 | 2025-11-29 | Saturday | W2 | TAS-GN-010 | 2526203455 | Unknown | W4 | 2 | 1 | 1 | 1/2 (50%) | 1 | Casting | CS1-TAS-GN-010 | 2313.64 | 2.314 | 30 min | 1 | 30 min | Order Total: 2 units
2025-11-29 | 2025-11-29 | Saturday | W2 | TAS-GN-011 | 2526203455 | Unknown | W4 | 2 | 1 | 1 | 1/2 (50%) | 1 | Casting | CS1-TAS-GN-011 | 4227.27 | 4.227 | 30 min | 1 | 30 min | Order Total: 2 units
2025-11-29 | 2025-11-29 | Saturday | W2 | TAS-GN-011 | 2526203455 | Unknown | W4 | 2 | 1 | 1 | 1/2 (50%) | 1 | Grinding | GR1-TAS-GN-011 | 4227.27 | 4.227 | 450 min | 1 | 450 min | Order Total: 2 units
2025-11-29 | 2025-11-29 | Saturday | W2 | TAS-GN-011 | 2526203455 | Unknown | W4 | 2 | 1 | 1 | 1/2 (50%) | 1 | MC1 | MC1-TAS-GN-011 | 4227.27 | 4.227 | 60 min | 1 | 60 min | Order Total: 2 units
2025-11-30 | 2025-11-29 | Sunday | W2 | TAS-GN-010 | 2526203455 | Unknown | W4 | 2 | 1 | 1 | 1/2 (50%) | 1 | Cooling/Shakeout | N/A | 2313.64 | 2.314 | - | 1 | - | Order Total: 2 units
2025-11-30 | 2025-11-29 | Sunday | W2 | TAS-GN-011 | 2526203455 | Unknown | W4 | 2 | 1 | 1 | 1/2 (50%) | 1 | Cooling/Shakeout | N/A | 4227.27 | 4.227 | - | 1 | - | Order Total: 2 units
2025-12-01 | 2025-12-01 | Monday | W2 | TAS-GN-010 | 2526203455 | Unknown | W4 | 2 | 2 | 2 | 2/2 COMPLETE ✓ | 1 | Casting | CS1-TAS-GN-010 | 2313.64 | 2.314 | 30 min | 1 | 30 min | Order Total: 2 units
2025-12-01 | 2025-12-01 | Monday | W2 | TAS-GN-011 | 2526203455 | Unknown | W4 | 2 | 2 | 2 | 2/2 COMPLETE ✓ | 1 | Casting | CS1-TAS-GN-011 | 4227.27 | 4.227 | 30 min | 1 | 30 min | Order Total: 2 units
2025-12-01 | 2025-12-01 | Monday | W2 | TAS-GN-011 | 2526203455 | Unknown | W4 | 2 | 2 | 2 | 2/2 COMPLETE ✓ | 1 | Grinding | GR1-TAS-GN-011 | 4227.27 | 4.227 | 450 min | 1 | 450 min | Order Total: 2 units
2025-12-01 | 2025-12-01 | Monday | W2 | TAS-GN-011 | 2526203455 | Unknown | W4 | 2 | 2 | 2 | 2/2 COMPLETE ✓ | 1 | MC1 | MC1-TAS-GN-011 | 4227.27 | 4.227 | 60 min | 1 | 60 min | Order Total: 2 units
2025-12-02 | 2025-12-01 | Tuesday | W2 | TAS-GN-010 | 2526203455 | Unknown | W4 | 2 | 2 | 2 | 2/2 COMPLETE ✓ | 1 | Cooling/Shakeout | N/A | 2313.64 | 2.314 | - | 1 | - | Order Total: 2 units
2025-12-02 | 2025-12-01 | Tuesday | W2 | TAS-GN-011 | 2526203455 | Unknown | W4 | 2 | 2 | 2 | 2/2 COMPLETE ✓ | 1 | Cooling/Shakeout | N/A | 4227.27 | 4.227 | - | 1 | - | Order Total: 2 units
2025-12-06 | 2025-11-22 | Saturday | W3 | TAS-GN-029 | 2526203455 | Unknown | W4 | 3 | 1 | 1 | 1/3 (33%) | 1 | Grinding | KVCALHMGR001 | 636.36 | 0.636 | 180 min | 1 | 180 min | Order Total: 3 units
2025-12-06 | 2025-11-29 | Saturday | W3 | TAS-GN-010 | 2526203455 | Unknown | W4 | 2 | 1 | 1 | 1/2 (50%) | 1 | Grinding | KVCALHMGR001 | 2313.64 | 2.314 | 450 min | 1 | 450 min | Order Total: 2 units
2025-12-06 | 2025-11-29 | Saturday | W3 | TAS-GN-010 | 2526203455 | Unknown | W4 | 2 | 1 | 1 | 1/2 (50%) | 1 | MC1 | KVCAD50MC001 | 2313.64 | 2.314 | 60 min | 1 | 60 min | Order Total: 2 units
2025-12-06 | 2025-11-29 | Saturday | W3 | TAS-GN-010 | 2526203455 | Unknown | W4 | 2 | 1 | 1 | 1/2 (50%) | 1 | SP1 | KVCALPPSP001 | 2313.64 | 2.314 | 7 min | 1 | 7 min | Order Total: 2 units
2025-12-06 | 2025-11-29 | Saturday | W3 | TAS-GN-011 | 2526203455 | Unknown | W4 | 2 | 1 | 1 | 1/2 (50%) | 1 | SP1 | SP1-TAS-GN-011 | 4227.27 | 4.227 | - | 1 | - | Order Total: 2 units
2025-12-06 | 2025-11-29 | Saturday | W3 | TAS-GN-010 | 2526203455 | Unknown | W4 | 2 | 1 | 1 | 1/2 (50%) | 1 | SP2 | KVCALPPSP002 | 2313.64 | 2.314 | 7 min | 1 | 7 min | Order Total: 2 units
2025-12-06 | 2025-11-29 | Saturday | W3 | TAS-GN-011 | 2526203455 | Unknown | W4 | 2 | 1 | 1 | 1/2 (50%) | 1 | SP2 | KVCALPPSP002 | 4227.27 | 4.227 | - | 1 | - | Order Total: 2 units
2025-12-06 | 2025-11-29 | Saturday | W3 | TAS-GN-010 | 2526203455 | Unknown | W4 | 2 | 1 | 1 | 1/2 (50%) | 1 | SP3 | KVCALFPSP001 | 2313.64 | 2.314 | 7 min | 1 | 7 min | Order Total: 2 units
2025-12-06 | 2025-11-29 | Saturday | W3 | TAS-GN-011 | 2526203455 | Unknown | W4 | 2 | 1 | 1 | 1/2 (50%) | 1 | SP3 | KVCALFPSP001 | 4227.27 | 4.227 | - | 1 | - | Order Total: 2 units
2025-12-08 | 2025-11-24 | Monday | W3 | TAS-GN-029 | 2526203455 | Unknown | W4 | 3 | 2 | 2 | 2/3 (66%) | 1 | Grinding | KVCALHMGR001 | 636.36 | 0.636 | 180 min | 1 | 180 min | Order Total: 3 units
2025-12-08 | 2025-12-01 | Monday | W3 | TAS-GN-010 | 2526203455 | Unknown | W4 | 2 | 2 | 2 | 2/2 COMPLETE ✓ | 1 | Grinding | KVCALHMGR001 | 2313.64 | 2.314 | 450 min | 1 | 450 min | Order Total: 2 units
2025-12-08 | 2025-12-01 | Monday | W3 | TAS-GN-010 | 2526203455 | Unknown | W4 | 2 | 2 | 2 | 2/2 COMPLETE ✓ | 1 | MC1 | KVCAD50MC001 | 2313.64 | 2.314 | 60 min | 1 | 60 min | Order Total: 2 units
2025-12-08 | 2025-12-01 | Monday | W3 | TAS-GN-010 | 2526203455 | Unknown | W4 | 2 | 2 | 2 | 2/2 COMPLETE ✓ | 1 | SP1 | KVCALPPSP001 | 2313.64 | 2.314 | 7 min | 1 | 7 min | Order Total: 2 units
2025-12-08 | 2025-12-01 | Monday | W3 | TAS-GN-011 | 2526203455 | Unknown | W4 | 2 | 2 | 2 | 2/2 COMPLETE ✓ | 1 | SP1 | SP1-TAS-GN-011 | 4227.27 | 4.227 | - | 1 | - | Order Total: 2 units
2025-12-08 | 2025-12-01 | Monday | W3 | TAS-GN-010 | 2526203455 | Unknown | W4 | 2 | 2 | 2 | 2/2 COMPLETE ✓ | 1 | SP2 | KVCALPPSP002 | 2313.64 | 2.314 | 7 min | 1 | 7 min | Order Total: 2 units
2025-12-08 | 2025-12-01 | Monday | W3 | TAS-GN-011 | 2526203455 | Unknown | W4 | 2 | 2 | 2 | 2/2 COMPLETE ✓ | 1 | SP2 | KVCALPPSP002 | 4227.27 | 4.227 | - | 1 | - | Order Total: 2 units
2025-12-08 | 2025-12-01 | Monday | W3 | TAS-GN-010 | 2526203455 | Unknown | W4 | 2 | 2 | 2 | 2/2 COMPLETE ✓ | 1 | SP3 | KVCALFPSP001 | 2313.64 | 2.314 | 7 min | 1 | 7 min | Order Total: 2 units
2025-12-08 | 2025-12-01 | Monday | W3 | TAS-GN-011 | 2526203455 | Unknown | W4 | 2 | 2 | 2 | 2/2 COMPLETE ✓ | 1 | SP3 | KVCALFPSP001 | 4227.27 | 4.227 | - | 1 | - | Order Total: 2 units
2025-12-09 | 2025-11-25 | Tuesday | W3 | TAS-GN-029 | 2526203455 | Unknown | W4 | 3 | 3 | 3 | 3/3 COMPLETE ✓ | 1 | Grinding | KVCALHMGR001 | 636.36 | 0.636 | 180 min | 1 | 180 min | Order Total: 3 units
2025-11-22 | 2025-11-22 | Saturday | W1 | TAS-GN-012 | 2526203456 | Unknown | W3 | 2 | 1 | 1 | 1/7 (14%) | 1 | Casting | CS1-TAS-GN-012 | 2422.73 | 2.423 | 25 min | 1 | 25 min | Order Total: 2 units
2025-11-22 | 2025-11-22 | Saturday | W1 | TAS-GN-012 | 2526203456 | Unknown | W3 | 5 | 2 | 3 | 3/7 (42%) | 2 | Casting | CS1-TAS-GN-012 | 2422.73 | 4.845 | 25 min | 1 | 50 min | Order Total: 5 units
2025-11-22 | 2025-11-29 | Saturday | W1 | TAS-GN-008 | 2526203456 | Unknown | W3 | 1 | 1 | 1 | 1/1 COMPLETE ✓ | 1 | SP1 | KVCALPPSP001 | 2693.18 | 2.693 | 7 min | 1 | 7 min | Order Total: 1 units
2025-11-22 | 2025-11-29 | Saturday | W1 | TAS-GN-008 | 2526203456 | Unknown | W3 | 1 | 1 | 1 | 1/1 COMPLETE ✓ | 1 | SP2 | KVCALPPSP002 | 2693.18 | 2.693 | 7 min | 1 | 7 min | Order Total: 1 units
2025-11-22 | 2025-11-29 | Saturday | W1 | TAS-GN-008 | 2526203456 | Unknown | W3 | 1 | 1 | 1 | 1/1 COMPLETE ✓ | 1 | SP3 | KVCALFPSP001 | 2693.18 | 2.693 | 7 min | 1 | 7 min | Order Total: 1 units
2025-11-23 | 2025-11-22 | Sunday | W1 | TAS-GN-012 | 2526203456 | Unknown | W3 | 2 | 1 | 1 | 1/7 (14%) | 1 | Cooling/Shakeout | N/A | 2422.73 | 2.423 | - | 1 | - | Order Total: 2 units
2025-11-23 | 2025-11-22 | Sunday | W1 | TAS-GN-012 | 2526203456 | Unknown | W3 | 5 | 2 | 3 | 3/7 (42%) | 2 | Cooling/Shakeout | N/A | 2422.73 | 4.845 | - | 1 | - | Order Total: 5 units
2025-11-24 | 2025-11-24 | Monday | W1 | TAS-GN-012 | 2526203456 | Unknown | W3 | 2 | 3 | 4 | 4/7 (57%) | 1 | Casting | CS1-TAS-GN-012 | 2422.73 | 2.423 | 25 min | 1 | 25 min | Order Total: 2 units
2025-11-24 | 2025-11-24 | Monday | W1 | TAS-GN-012 | 2526203456 | Unknown | W3 | 5 | 4 | 7 | 7/7 COMPLETE ✓ | 3 | Casting | CS1-TAS-GN-012 | 2422.73 | 7.268 | 25 min | 1 | 75 min | Order Total: 5 units
2025-11-25 | 2025-11-24 | Tuesday | W1 | TAS-GN-012 | 2526203456 | Unknown | W3 | 2 | 3 | 4 | 4/7 (57%) | 1 | Cooling/Shakeout | N/A | 2422.73 | 2.423 | - | 1 | - | Order Total: 2 units
2025-11-25 | 2025-11-24 | Tuesday | W1 | TAS-GN-012 | 2526203456 | Unknown | W3 | 5 | 4 | 7 | 7/7 COMPLETE ✓ | 3 | Cooling/Shakeout | N/A | 2422.73 | 7.268 | - | 1 | - | Order Total: 5 units
2025-11-29 | 2025-11-29 | Saturday | W2 | TAS-GN-008 | 2526203456 | Unknown | W3 | 1 | 1 | 1 | 1/1 COMPLETE ✓ | 1 | Casting | CS1-TAS-GN-008 | 2693.18 | 2.693 | 30 min | 1 | 30 min | Order Total: 1 units
2025-11-29 | 2025-11-22 | Saturday | W2 | TAS-GN-012 | 2526203456 | Unknown | W3 | 2 | 1 | 1 | 1/7 (14%) | 1 | Grinding | KVCALHMGR001 | 2422.73 | 2.423 | 360 min | 1 | 360 min | Order Total: 2 units
2025-11-29 | 2025-11-22 | Saturday | W2 | TAS-GN-012 | 2526203456 | Unknown | W3 | 5 | 2 | 3 | 3/7 (42%) | 2 | Grinding | KVCALHMGR001 | 2422.73 | 4.845 | 360 min | 1 | 720 min | Order Total: 5 units
2025-11-30 | 2025-11-29 | Sunday | W2 | TAS-GN-008 | 2526203456 | Unknown | W3 | 1 | 1 | 1 | 1/1 COMPLETE ✓ | 1 | Cooling/Shakeout | N/A | 2693.18 | 2.693 | - | 1 | - | Order Total: 1 units
2025-12-01 | 2025-11-24 | Monday | W2 | TAS-GN-012 | 2526203456 | Unknown | W3 | 2 | 3 | 4 | 4/7 (57%) | 1 | Grinding | KVCALHMGR001 | 2422.73 | 2.423 | 360 min | 1 | 360 min | Order Total: 2 units
2025-12-01 | 2025-11-24 | Monday | W2 | TAS-GN-012 | 2526203456 | Unknown | W3 | 5 | 4 | 7 | 7/7 COMPLETE ✓ | 3 | Grinding | KVCALHMGR001 | 2422.73 | 7.268 | 360 min | 1 | 1080 min | Order Total: 5 units
2025-12-06 | 2025-11-29 | Saturday | W3 | TAS-GN-008 | 2526203456 | Unknown | W3 | 1 | 1 | 1 | 1/1 COMPLETE ✓ | 1 | MC1 | KVCAD50MC001 | 2693.18 | 2.693 | 40 min | 0 | - | Order Total: 1 units
2025-12-13 | 2025-11-22 | Saturday | W4 | TAS-GN-012 | 2526203456 | Unknown | W3 | 2 | 1 | 1 | 1/7 (14%) | 1 | SP1 | KVCALPPSP001 | 2422.73 | 2.423 | 12 min | 1 | 12 min | Order Total: 2 units
2025-12-13 | 2025-11-22 | Saturday | W4 | TAS-GN-012 | 2526203456 | Unknown | W3 | 5 | 2 | 3 | 3/7 (42%) | 2 | SP1 | KVCALPPSP001 | 2422.73 | 4.845 | 12 min | 1 | 24 min | Order Total: 5 units
2025-12-13 | 2025-11-22 | Saturday | W4 | TAS-GN-012 | 2526203456 | Unknown | W3 | 2 | 1 | 1 | 1/7 (14%) | 1 | SP2 | KVCALPPSP002 | 2422.73 | 2.423 | 12 min | 1 | 12 min | Order Total: 2 units
2025-12-13 | 2025-11-22 | Saturday | W4 | TAS-GN-012 | 2526203456 | Unknown | W3 | 5 | 2 | 3 | 3/7 (42%) | 2 | SP2 | KVCALPPSP002 | 2422.73 | 4.845 | 12 min | 1 | 24 min | Order Total: 5 units
2025-12-13 | 2025-11-22 | Saturday | W4 | TAS-GN-012 | 2526203456 | Unknown | W3 | 2 | 1 | 1 | 1/7 (14%) | 1 | SP3 | KVCALFPSP001 | 2422.73 | 2.423 | 12 min | 1 | 12 min | Order Total: 2 units
2025-12-13 | 2025-11-22 | Saturday | W4 | TAS-GN-012 | 2526203456 | Unknown | W3 | 5 | 2 | 3 | 3/7 (42%) | 2 | SP3 | KVCALFPSP001 | 2422.73 | 4.845 | 12 min | 1 | 24 min | Order Total: 5 units
2025-12-15 | 2025-11-24 | Monday | W4 | TAS-GN-012 | 2526203456 | Unknown | W3 | 2 | 3 | 4 | 4/7 (57%) | 1 | SP1 | KVCALPPSP001 | 2422.73 | 2.423 | 12 min | 1 | 12 min | Order Total: 2 units
2025-12-15 | 2025-11-24 | Monday | W4 | TAS-GN-012 | 2526203456 | Unknown | W3 | 5 | 4 | 7 | 7/7 COMPLETE ✓ | 3 | SP1 | KVCALPPSP001 | 2422.73 | 7.268 | 12 min | 1 | 36 min | Order Total: 5 units
2025-12-15 | 2025-11-24 | Monday | W4 | TAS-GN-012 | 2526203456 | Unknown | W3 | 2 | 3 | 4 | 4/7 (57%) | 1 | SP2 | KVCALPPSP002 | 2422.73 | 2.423 | 12 min | 1 | 12 min | Order Total: 2 units
2025-12-15 | 2025-11-24 | Monday | W4 | TAS-GN-012 | 2526203456 | Unknown | W3 | 5 | 4 | 7 | 7/7 COMPLETE ✓ | 3 | SP2 | KVCALPPSP002 | 2422.73 | 7.268 | 12 min | 1 | 36 min | Order Total: 5 units
2025-12-15 | 2025-11-24 | Monday | W4 | TAS-GN-012 | 2526203456 | Unknown | W3 | 2 | 3 | 4 | 4/7 (57%) | 1 | SP3 | KVCALFPSP001 | 2422.73 | 2.423 | 12 min | 1 | 12 min | Order Total: 2 units
2025-12-15 | 2025-11-24 | Monday | W4 | TAS-GN-012 | 2526203456 | Unknown | W3 | 5 | 4 | 7 | 7/7 COMPLETE ✓ | 3 | SP3 | KVCALFPSP001 | 2422.73 | 7.268 | 12 min | 1 | 36 min | Order Total: 5 units
2025-11-22 | 2025-11-22 | Saturday | W1 | TAS-GN-012 | 2526203457 | Unknown | W4 | 10 | 1 | 2 | 2/10 (20%) | 2 | Casting | CS1-TAS-GN-012 | 2422.73 | 4.845 | 25 min | 1 | 50 min | Order Total: 10 units
2025-11-23 | 2025-11-22 | Sunday | W1 | TAS-GN-012 | 2526203457 | Unknown | W4 | 10 | 1 | 2 | 2/10 (20%) | 2 | Cooling/Shakeout | N/A | 2422.73 | 4.845 | - | 1 | - | Order Total: 10 units
2025-11-24 | 2025-11-24 | Monday | W1 | TAS-GN-012 | 2526203457 | Unknown | W4 | 10 | 2 | 4 | 4/10 (40%) | 2 | Casting | CS1-TAS-GN-012 | 2422.73 | 4.845 | 25 min | 1 | 50 min | Order Total: 10 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | TAS-GN-012 | 2526203457 | Unknown | W4 | 10 | 3 | 7 | 7/10 (70%) | 3 | Casting | CS1-TAS-GN-012 | 2422.73 | 7.268 | 25 min | 1 | 75 min | Order Total: 10 units
2025-11-25 | 2025-11-24 | Tuesday | W1 | TAS-GN-012 | 2526203457 | Unknown | W4 | 10 | 2 | 4 | 4/10 (40%) | 2 | Cooling/Shakeout | N/A | 2422.73 | 4.845 | - | 1 | - | Order Total: 10 units
2025-11-26 | 2025-11-26 | Wednesday | W1 | TAS-GN-012 | 2526203457 | Unknown | W4 | 10 | 4 | 10 | 10/10 COMPLETE ✓ | 3 | Casting | CS1-TAS-GN-012 | 2422.73 | 7.268 | 25 min | 1 | 75 min | Order Total: 10 units
2025-11-26 | 2025-11-25 | Wednesday | W1 | TAS-GN-012 | 2526203457 | Unknown | W4 | 10 | 3 | 7 | 7/10 (70%) | 3 | Cooling/Shakeout | N/A | 2422.73 | 7.268 | - | 1 | - | Order Total: 10 units
2025-11-27 | 2025-11-26 | Thursday | W1 | TAS-GN-012 | 2526203457 | Unknown | W4 | 10 | 4 | 10 | 10/10 COMPLETE ✓ | 3 | Cooling/Shakeout | N/A | 2422.73 | 7.268 | - | 1 | - | Order Total: 10 units
2025-11-29 | 2025-11-22 | Saturday | W2 | TAS-GN-012 | 2526203457 | Unknown | W4 | 10 | 1 | 2 | 2/10 (20%) | 2 | MC1 | KVCAD50MC001 | 2422.73 | 4.845 | 60 min | 0 | - | Order Total: 10 units
2025-11-29 | 2025-11-22 | Saturday | W2 | TAS-GN-012 | 2526203457 | Unknown | W4 | 10 | 1 | 2 | 2/10 (20%) | 2 | SP1 | KVCALPPSP001 | 2422.73 | 4.845 | 12 min | 1 | 24 min | Order Total: 10 units
2025-11-29 | 2025-11-22 | Saturday | W2 | TAS-GN-012 | 2526203457 | Unknown | W4 | 10 | 1 | 2 | 2/10 (20%) | 2 | SP2 | KVCALPPSP002 | 2422.73 | 4.845 | 12 min | 1 | 24 min | Order Total: 10 units
2025-11-29 | 2025-11-22 | Saturday | W2 | TAS-GN-012 | 2526203457 | Unknown | W4 | 10 | 1 | 2 | 2/10 (20%) | 2 | SP3 | KVCALFPSP001 | 2422.73 | 4.845 | 12 min | 1 | 24 min | Order Total: 10 units
2025-12-01 | 2025-11-24 | Monday | W2 | TAS-GN-012 | 2526203457 | Unknown | W4 | 10 | 2 | 4 | 4/10 (40%) | 2 | MC1 | KVCAD50MC001 | 2422.73 | 4.845 | 60 min | 0 | - | Order Total: 10 units
2025-12-01 | 2025-11-24 | Monday | W2 | TAS-GN-012 | 2526203457 | Unknown | W4 | 10 | 2 | 4 | 4/10 (40%) | 2 | SP1 | KVCALPPSP001 | 2422.73 | 4.845 | 12 min | 1 | 24 min | Order Total: 10 units
2025-12-01 | 2025-11-24 | Monday | W2 | TAS-GN-012 | 2526203457 | Unknown | W4 | 10 | 2 | 4 | 4/10 (40%) | 2 | SP2 | KVCALPPSP002 | 2422.73 | 4.845 | 12 min | 1 | 24 min | Order Total: 10 units
2025-12-01 | 2025-11-24 | Monday | W2 | TAS-GN-012 | 2526203457 | Unknown | W4 | 10 | 2 | 4 | 4/10 (40%) | 2 | SP3 | KVCALFPSP001 | 2422.73 | 4.845 | 12 min | 1 | 24 min | Order Total: 10 units
2025-12-02 | 2025-11-25 | Tuesday | W2 | TAS-GN-012 | 2526203457 | Unknown | W4 | 10 | 3 | 7 | 7/10 (70%) | 3 | MC1 | KVCAD50MC001 | 2422.73 | 7.268 | 60 min | 0 | - | Order Total: 10 units
2025-12-02 | 2025-11-25 | Tuesday | W2 | TAS-GN-012 | 2526203457 | Unknown | W4 | 10 | 3 | 7 | 7/10 (70%) | 3 | SP1 | KVCALPPSP001 | 2422.73 | 7.268 | 12 min | 1 | 36 min | Order Total: 10 units
2025-12-02 | 2025-11-25 | Tuesday | W2 | TAS-GN-012 | 2526203457 | Unknown | W4 | 10 | 3 | 7 | 7/10 (70%) | 3 | SP2 | KVCALPPSP002 | 2422.73 | 7.268 | 12 min | 1 | 36 min | Order Total: 10 units
2025-12-02 | 2025-11-25 | Tuesday | W2 | TAS-GN-012 | 2526203457 | Unknown | W4 | 10 | 3 | 7 | 7/10 (70%) | 3 | SP3 | KVCALFPSP001 | 2422.73 | 7.268 | 12 min | 1 | 36 min | Order Total: 10 units
2025-12-03 | 2025-11-26 | Wednesday | W2 | TAS-GN-012 | 2526203457 | Unknown | W4 | 10 | 4 | 10 | 10/10 COMPLETE ✓ | 3 | MC1 | KVCAD50MC001 | 2422.73 | 7.268 | 60 min | 0 | - | Order Total: 10 units
2025-12-03 | 2025-11-26 | Wednesday | W2 | TAS-GN-012 | 2526203457 | Unknown | W4 | 10 | 4 | 10 | 10/10 COMPLETE ✓ | 3 | SP1 | KVCALPPSP001 | 2422.73 | 7.268 | 12 min | 1 | 36 min | Order Total: 10 units
2025-12-03 | 2025-11-26 | Wednesday | W2 | TAS-GN-012 | 2526203457 | Unknown | W4 | 10 | 4 | 10 | 10/10 COMPLETE ✓ | 3 | SP2 | KVCALPPSP002 | 2422.73 | 7.268 | 12 min | 1 | 36 min | Order Total: 10 units
2025-12-03 | 2025-11-26 | Wednesday | W2 | TAS-GN-012 | 2526203457 | Unknown | W4 | 10 | 4 | 10 | 10/10 COMPLETE ✓ | 3 | SP3 | KVCALFPSP001 | 2422.73 | 7.268 | 12 min | 1 | 36 min | Order Total: 10 units
2025-11-22 | 2025-11-22 | Saturday | W1 | TAS-GN-012 | 2526203458 | Unknown | W5 | 10 | 1 | 2 | 2/10 (20%) | 2 | Casting | CS1-TAS-GN-012 | 2422.73 | 4.845 | 25 min | 1 | 50 min | Order Total: 10 units
2025-11-23 | 2025-11-22 | Sunday | W1 | TAS-GN-012 | 2526203458 | Unknown | W5 | 10 | 1 | 2 | 2/10 (20%) | 2 | Cooling/Shakeout | N/A | 2422.73 | 4.845 | - | 1 | - | Order Total: 10 units
2025-11-24 | 2025-11-24 | Monday | W1 | TAS-GN-012 | 2526203458 | Unknown | W5 | 10 | 2 | 4 | 4/10 (40%) | 2 | Casting | CS1-TAS-GN-012 | 2422.73 | 4.845 | 25 min | 1 | 50 min | Order Total: 10 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | TAS-GN-012 | 2526203458 | Unknown | W5 | 10 | 3 | 7 | 7/10 (70%) | 3 | Casting | CS1-TAS-GN-012 | 2422.73 | 7.268 | 25 min | 1 | 75 min | Order Total: 10 units
2025-11-25 | 2025-11-24 | Tuesday | W1 | TAS-GN-012 | 2526203458 | Unknown | W5 | 10 | 2 | 4 | 4/10 (40%) | 2 | Cooling/Shakeout | N/A | 2422.73 | 4.845 | - | 1 | - | Order Total: 10 units
2025-11-26 | 2025-11-26 | Wednesday | W1 | TAS-GN-012 | 2526203458 | Unknown | W5 | 10 | 4 | 10 | 10/10 COMPLETE ✓ | 3 | Casting | CS1-TAS-GN-012 | 2422.73 | 7.268 | 25 min | 1 | 75 min | Order Total: 10 units
2025-11-26 | 2025-11-25 | Wednesday | W1 | TAS-GN-012 | 2526203458 | Unknown | W5 | 10 | 3 | 7 | 7/10 (70%) | 3 | Cooling/Shakeout | N/A | 2422.73 | 7.268 | - | 1 | - | Order Total: 10 units
2025-11-27 | 2025-11-26 | Thursday | W1 | TAS-GN-012 | 2526203458 | Unknown | W5 | 10 | 4 | 10 | 10/10 COMPLETE ✓ | 3 | Cooling/Shakeout | N/A | 2422.73 | 7.268 | - | 1 | - | Order Total: 10 units
2025-11-22 | 2025-11-22 | Saturday | W1 | TAS-GN-006 | 2526203459 | Unknown | W3 | 9 | 1 | 5 | 5/9 (55%) | 5 | Casting | CS1-TAS-GN-006 | 318.18 | 1.591 | 25 min | 1 | 125 min | Order Total: 9 units
2025-11-22 | 2025-11-22 | Saturday | W1 | TAS-GN-007 | 2526203459 | Unknown | W3 | 20 | 1 | 7 | 7/20 (35%) | 7 | Casting | CS1-TAS-GN-007 | 293.18 | 2.052 | 25 min | 1 | 175 min | Order Total: 20 units
2025-11-22 | 2025-11-22 | Saturday | W1 | TAS-GN-009 | 2526203459 | Unknown | W3 | 20 | 1 | 5 | 5/20 (25%) | 5 | Grinding | KVCALHMGR001 | 181.82 | 0.909 | 120 min | 1 | 600 min | Order Total: 20 units
2025-11-22 | 2025-11-22 | Saturday | W1 | TAS-GN-007 | 2526203459 | Unknown | W3 | 20 | 1 | 5 | 5/20 (25%) | 5 | Grinding | KVCALHMGR001 | 293.18 | 1.466 | 90 min | 1 | 450 min | Order Total: 20 units
2025-11-22 | 2025-11-22 | Saturday | W1 | TAS-GN-009 | 2526203459 | Unknown | W3 | 20 | 1 | 5 | 5/20 (25%) | 5 | SP1 | KVCALPPSP001 | 181.82 | 0.909 | 7 min | 1 | 35 min | Order Total: 20 units
2025-11-22 | 2025-11-22 | Saturday | W1 | TAS-GN-009 | 2526203459 | Unknown | W3 | 20 | 1 | 5 | 5/20 (25%) | 5 | SP2 | KVCALPPSP002 | 181.82 | 0.909 | 7 min | 1 | 35 min | Order Total: 20 units
2025-11-22 | 2025-11-22 | Saturday | W1 | TAS-GN-009 | 2526203459 | Unknown | W3 | 20 | 1 | 5 | 5/20 (25%) | 5 | SP3 | KVCALFPSP001 | 181.82 | 0.909 | 7 min | 1 | 35 min | Order Total: 20 units
2025-11-23 | 2025-11-22 | Sunday | W1 | TAS-GN-006 | 2526203459 | Unknown | W3 | 9 | 1 | 2 | 2/9 (22%) | 2 | Cooling/Shakeout | N/A | 318.18 | 0.636 | - | 1 | - | Order Total: 9 units
2025-11-23 | 2025-11-22 | Sunday | W1 | TAS-GN-007 | 2526203459 | Unknown | W3 | 20 | 1 | 5 | 5/20 (25%) | 5 | Cooling/Shakeout | N/A | 293.18 | 1.466 | - | 1 | - | Order Total: 20 units
2025-11-24 | 2025-11-24 | Monday | W1 | TAS-GN-006 | 2526203459 | Unknown | W3 | 9 | 2 | 9 | 9/9 COMPLETE ✓ | 4 | Casting | CS1-TAS-GN-006 | 318.18 | 1.273 | 25 min | 1 | 100 min | Order Total: 9 units
2025-11-24 | 2025-11-24 | Monday | W1 | TAS-GN-007 | 2526203459 | Unknown | W3 | 20 | 2 | 20 | 20/20 COMPLETE ✓ | 13 | Casting | CS1-TAS-GN-007 | 293.18 | 3.811 | 25 min | 1 | 325 min | Order Total: 20 units
2025-11-24 | 2025-11-24 | Monday | W1 | TAS-GN-009 | 2526203459 | Unknown | W3 | 20 | 2 | 10 | 10/20 (50%) | 5 | Grinding | KVCALHMGR001 | 181.82 | 0.909 | 120 min | 1 | 600 min | Order Total: 20 units
2025-11-24 | 2025-11-24 | Monday | W1 | TAS-GN-007 | 2526203459 | Unknown | W3 | 20 | 2 | 10 | 10/20 (50%) | 5 | Grinding | KVCALHMGR001 | 293.18 | 1.466 | 90 min | 1 | 450 min | Order Total: 20 units
2025-11-24 | 2025-11-24 | Monday | W1 | TAS-GN-009 | 2526203459 | Unknown | W3 | 20 | 2 | 10 | 10/20 (50%) | 5 | SP1 | KVCALPPSP001 | 181.82 | 0.909 | 7 min | 1 | 35 min | Order Total: 20 units
2025-11-24 | 2025-11-24 | Monday | W1 | TAS-GN-009 | 2526203459 | Unknown | W3 | 20 | 2 | 10 | 10/20 (50%) | 5 | SP2 | KVCALPPSP002 | 181.82 | 0.909 | 7 min | 1 | 35 min | Order Total: 20 units
2025-11-24 | 2025-11-24 | Monday | W1 | TAS-GN-009 | 2526203459 | Unknown | W3 | 20 | 2 | 10 | 10/20 (50%) | 5 | SP3 | KVCALFPSP001 | 181.82 | 0.909 | 7 min | 1 | 35 min | Order Total: 20 units
2025-11-25 | 2025-11-24 | Tuesday | W1 | TAS-GN-006 | 2526203459 | Unknown | W3 | 9 | 2 | 4 | 4/9 (44%) | 2 | Cooling/Shakeout | N/A | 318.18 | 0.636 | - | 1 | - | Order Total: 9 units
2025-11-25 | 2025-11-24 | Tuesday | W1 | TAS-GN-007 | 2526203459 | Unknown | W3 | 20 | 2 | 10 | 10/20 (50%) | 5 | Cooling/Shakeout | N/A | 293.18 | 1.466 | - | 1 | - | Order Total: 20 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | TAS-GN-009 | 2526203459 | Unknown | W3 | 20 | 3 | 15 | 15/20 (75%) | 5 | Grinding | KVCALHMGR001 | 181.82 | 0.909 | 120 min | 1 | 600 min | Order Total: 20 units
2025-11-25 | 2025-11-22 | Tuesday | W1 | TAS-GN-007 | 2526203459 | Unknown | W3 | 20 | 3 | 15 | 15/20 (75%) | 5 | Grinding | KVCALHMGR001 | 293.18 | 1.466 | 90 min | 1 | 450 min | Order Total: 20 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | TAS-GN-009 | 2526203459 | Unknown | W3 | 20 | 3 | 15 | 15/20 (75%) | 5 | SP1 | KVCALPPSP001 | 181.82 | 0.909 | 7 min | 1 | 35 min | Order Total: 20 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | TAS-GN-009 | 2526203459 | Unknown | W3 | 20 | 3 | 15 | 15/20 (75%) | 5 | SP2 | KVCALPPSP002 | 181.82 | 0.909 | 7 min | 1 | 35 min | Order Total: 20 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | TAS-GN-009 | 2526203459 | Unknown | W3 | 20 | 3 | 15 | 15/20 (75%) | 5 | SP3 | KVCALFPSP001 | 181.82 | 0.909 | 7 min | 1 | 35 min | Order Total: 20 units
2025-11-26 | 2025-11-22 | Wednesday | W1 | TAS-GN-006 | 2526203459 | Unknown | W3 | 9 | 3 | 6 | 6/9 (66%) | 2 | Cooling/Shakeout | N/A | 318.18 | 0.636 | - | 1 | - | Order Total: 9 units
2025-11-26 | 2025-11-22 | Wednesday | W1 | TAS-GN-007 | 2526203459 | Unknown | W3 | 20 | 3 | 15 | 15/20 (75%) | 5 | Cooling/Shakeout | N/A | 293.18 | 1.466 | - | 1 | - | Order Total: 20 units
2025-11-26 | 2025-11-26 | Wednesday | W1 | TAS-GN-009 | 2526203459 | Unknown | W3 | 20 | 4 | 20 | 20/20 COMPLETE ✓ | 5 | Grinding | KVCALHMGR001 | 181.82 | 0.909 | 120 min | 1 | 600 min | Order Total: 20 units
2025-11-26 | 2025-11-22 | Wednesday | W1 | TAS-GN-007 | 2526203459 | Unknown | W3 | 20 | 4 | 20 | 20/20 COMPLETE ✓ | 5 | Grinding | KVCALHMGR001 | 293.18 | 1.466 | 90 min | 1 | 450 min | Order Total: 20 units
2025-11-26 | 2025-11-26 | Wednesday | W1 | TAS-GN-009 | 2526203459 | Unknown | W3 | 20 | 4 | 20 | 20/20 COMPLETE ✓ | 5 | SP1 | KVCALPPSP001 | 181.82 | 0.909 | 7 min | 1 | 35 min | Order Total: 20 units
2025-11-26 | 2025-11-26 | Wednesday | W1 | TAS-GN-009 | 2526203459 | Unknown | W3 | 20 | 4 | 20 | 20/20 COMPLETE ✓ | 5 | SP2 | KVCALPPSP002 | 181.82 | 0.909 | 7 min | 1 | 35 min | Order Total: 20 units
2025-11-26 | 2025-11-26 | Wednesday | W1 | TAS-GN-009 | 2526203459 | Unknown | W3 | 20 | 4 | 20 | 20/20 COMPLETE ✓ | 5 | SP3 | KVCALFPSP001 | 181.82 | 0.909 | 7 min | 1 | 35 min | Order Total: 20 units
2025-11-27 | 2025-11-22 | Thursday | W1 | TAS-GN-006 | 2526203459 | Unknown | W3 | 9 | 4 | 9 | 9/9 COMPLETE ✓ | 3 | Cooling/Shakeout | N/A | 318.18 | 0.955 | - | 1 | - | Order Total: 9 units
2025-11-27 | 2025-11-22 | Thursday | W1 | TAS-GN-007 | 2526203459 | Unknown | W3 | 20 | 4 | 20 | 20/20 COMPLETE ✓ | 5 | Cooling/Shakeout | N/A | 293.18 | 1.466 | - | 1 | - | Order Total: 20 units
2025-11-29 | 2025-11-29 | Saturday | W2 | TAS-GN-014 | 2526203459 | Unknown | W3 | 10 | 1 | 2 | 2/10 (20%) | 2 | Grinding | KVCALHMGR001 | 1118.18 | 2.236 | 360 min | 1 | 720 min | Order Total: 10 units
2025-11-29 | 2025-11-29 | Saturday | W2 | TAS-GN-009 | 2526203459 | Unknown | W3 | 20 | 1 | 5 | 5/20 (25%) | 5 | MC1 | KVCAD50MC001 | 181.82 | 0.909 | 20 min | 0 | - | Order Total: 20 units
2025-11-29 | 2025-11-29 | Saturday | W2 | TAS-GN-014 | 2526203459 | Unknown | W3 | 10 | 1 | 2 | 2/10 (20%) | 2 | MC1 | KVCAD50MC001 | 1118.18 | 2.236 | 40 min | 0 | - | Order Total: 10 units
2025-11-29 | 2025-11-22 | Saturday | W2 | TAS-GN-007 | 2526203459 | Unknown | W3 | 20 | 1 | 5 | 5/20 (25%) | 5 | SP1 | KVCALPPSP001 | 293.18 | 1.466 | 7 min | 1 | 35 min | Order Total: 20 units
2025-11-29 | 2025-11-22 | Saturday | W2 | TAS-GN-007 | 2526203459 | Unknown | W3 | 20 | 1 | 5 | 5/20 (25%) | 5 | SP2 | KVCALPPSP002 | 293.18 | 1.466 | 7 min | 1 | 35 min | Order Total: 20 units
2025-11-29 | 2025-11-22 | Saturday | W2 | TAS-GN-007 | 2526203459 | Unknown | W3 | 20 | 1 | 5 | 5/20 (25%) | 5 | SP3 | KVCALFPSP001 | 293.18 | 1.466 | 7 min | 1 | 35 min | Order Total: 20 units
2025-12-01 | 2025-12-01 | Monday | W2 | TAS-GN-014 | 2526203459 | Unknown | W3 | 10 | 2 | 4 | 4/10 (40%) | 2 | Grinding | KVCALHMGR001 | 1118.18 | 2.236 | 360 min | 1 | 720 min | Order Total: 10 units
2025-12-01 | 2025-12-01 | Monday | W2 | TAS-GN-009 | 2526203459 | Unknown | W3 | 20 | 2 | 10 | 10/20 (50%) | 5 | MC1 | KVCAD50MC001 | 181.82 | 0.909 | 20 min | 0 | - | Order Total: 20 units
2025-12-01 | 2025-12-01 | Monday | W2 | TAS-GN-014 | 2526203459 | Unknown | W3 | 10 | 2 | 4 | 4/10 (40%) | 2 | MC1 | KVCAD50MC001 | 1118.18 | 2.236 | 40 min | 0 | - | Order Total: 10 units
2025-12-01 | 2025-11-24 | Monday | W2 | TAS-GN-007 | 2526203459 | Unknown | W3 | 20 | 2 | 10 | 10/20 (50%) | 5 | SP1 | KVCALPPSP001 | 293.18 | 1.466 | 7 min | 1 | 35 min | Order Total: 20 units
2025-12-01 | 2025-11-24 | Monday | W2 | TAS-GN-007 | 2526203459 | Unknown | W3 | 20 | 2 | 10 | 10/20 (50%) | 5 | SP2 | KVCALPPSP002 | 293.18 | 1.466 | 7 min | 1 | 35 min | Order Total: 20 units
2025-12-01 | 2025-11-24 | Monday | W2 | TAS-GN-007 | 2526203459 | Unknown | W3 | 20 | 2 | 10 | 10/20 (50%) | 5 | SP3 | KVCALFPSP001 | 293.18 | 1.466 | 7 min | 1 | 35 min | Order Total: 20 units
2025-12-02 | 2025-12-02 | Tuesday | W2 | TAS-GN-014 | 2526203459 | Unknown | W3 | 10 | 3 | 7 | 7/10 (70%) | 3 | Grinding | KVCALHMGR001 | 1118.18 | 3.355 | 360 min | 1 | 1080 min | Order Total: 10 units
2025-12-02 | 2025-12-02 | Tuesday | W2 | TAS-GN-009 | 2526203459 | Unknown | W3 | 20 | 3 | 15 | 15/20 (75%) | 5 | MC1 | KVCAD50MC001 | 181.82 | 0.909 | 20 min | 0 | - | Order Total: 20 units
2025-12-02 | 2025-12-02 | Tuesday | W2 | TAS-GN-014 | 2526203459 | Unknown | W3 | 10 | 3 | 7 | 7/10 (70%) | 3 | MC1 | KVCAD50MC001 | 1118.18 | 3.355 | 40 min | 0 | - | Order Total: 10 units
2025-12-02 | 2025-11-22 | Tuesday | W2 | TAS-GN-007 | 2526203459 | Unknown | W3 | 20 | 3 | 15 | 15/20 (75%) | 5 | SP1 | KVCALPPSP001 | 293.18 | 1.466 | 7 min | 1 | 35 min | Order Total: 20 units
2025-12-02 | 2025-11-22 | Tuesday | W2 | TAS-GN-007 | 2526203459 | Unknown | W3 | 20 | 3 | 15 | 15/20 (75%) | 5 | SP2 | KVCALPPSP002 | 293.18 | 1.466 | 7 min | 1 | 35 min | Order Total: 20 units
2025-12-02 | 2025-11-22 | Tuesday | W2 | TAS-GN-007 | 2526203459 | Unknown | W3 | 20 | 3 | 15 | 15/20 (75%) | 5 | SP3 | KVCALFPSP001 | 293.18 | 1.466 | 7 min | 1 | 35 min | Order Total: 20 units
2025-12-03 | 2025-12-03 | Wednesday | W2 | TAS-GN-014 | 2526203459 | Unknown | W3 | 10 | 4 | 10 | 10/10 COMPLETE ✓ | 3 | Grinding | KVCALHMGR001 | 1118.18 | 3.355 | 360 min | 1 | 1080 min | Order Total: 10 units
2025-12-03 | 2025-12-03 | Wednesday | W2 | TAS-GN-009 | 2526203459 | Unknown | W3 | 20 | 4 | 20 | 20/20 COMPLETE ✓ | 5 | MC1 | KVCAD50MC001 | 181.82 | 0.909 | 20 min | 0 | - | Order Total: 20 units
2025-12-03 | 2025-12-03 | Wednesday | W2 | TAS-GN-014 | 2526203459 | Unknown | W3 | 10 | 4 | 10 | 10/10 COMPLETE ✓ | 3 | MC1 | KVCAD50MC001 | 1118.18 | 3.355 | 40 min | 0 | - | Order Total: 10 units
2025-12-03 | 2025-11-22 | Wednesday | W2 | TAS-GN-007 | 2526203459 | Unknown | W3 | 20 | 4 | 20 | 20/20 COMPLETE ✓ | 5 | SP1 | KVCALPPSP001 | 293.18 | 1.466 | 7 min | 1 | 35 min | Order Total: 20 units
2025-12-03 | 2025-11-22 | Wednesday | W2 | TAS-GN-007 | 2526203459 | Unknown | W3 | 20 | 4 | 20 | 20/20 COMPLETE ✓ | 5 | SP2 | KVCALPPSP002 | 293.18 | 1.466 | 7 min | 1 | 35 min | Order Total: 20 units
2025-12-03 | 2025-11-22 | Wednesday | W2 | TAS-GN-007 | 2526203459 | Unknown | W3 | 20 | 4 | 20 | 20/20 COMPLETE ✓ | 5 | SP3 | KVCALFPSP001 | 293.18 | 1.466 | 7 min | 1 | 35 min | Order Total: 20 units
2025-12-06 | 2025-11-22 | Saturday | W3 | TAS-GN-006 | 2526203459 | Unknown | W3 | 9 | 1 | 2 | 2/9 (22%) | 2 | Grinding | KVCALHMGR001 | 318.18 | 0.636 | 120 min | 1 | 240 min | Order Total: 9 units
2025-12-06 | 2025-12-06 | Saturday | W3 | TAS-GN-014 | 2526203459 | Unknown | W3 | 10 | 1 | 2 | 2/10 (20%) | 2 | SP1 | KVCALPPSP001 | 1118.18 | 2.236 | 7 min | 1 | 14 min | Order Total: 10 units
2025-12-06 | 2025-12-06 | Saturday | W3 | TAS-GN-014 | 2526203459 | Unknown | W3 | 10 | 1 | 2 | 2/10 (20%) | 2 | SP2 | KVCALPPSP002 | 1118.18 | 2.236 | 7 min | 1 | 14 min | Order Total: 10 units
2025-12-06 | 2025-12-06 | Saturday | W3 | TAS-GN-014 | 2526203459 | Unknown | W3 | 10 | 1 | 2 | 2/10 (20%) | 2 | SP3 | KVCALFPSP001 | 1118.18 | 2.236 | 7 min | 1 | 14 min | Order Total: 10 units
2025-12-08 | 2025-11-24 | Monday | W3 | TAS-GN-006 | 2526203459 | Unknown | W3 | 9 | 2 | 4 | 4/9 (44%) | 2 | Grinding | KVCALHMGR001 | 318.18 | 0.636 | 120 min | 1 | 240 min | Order Total: 9 units
2025-12-08 | 2025-12-08 | Monday | W3 | TAS-GN-014 | 2526203459 | Unknown | W3 | 10 | 2 | 4 | 4/10 (40%) | 2 | SP1 | KVCALPPSP001 | 1118.18 | 2.236 | 7 min | 1 | 14 min | Order Total: 10 units
2025-12-08 | 2025-12-08 | Monday | W3 | TAS-GN-014 | 2526203459 | Unknown | W3 | 10 | 2 | 4 | 4/10 (40%) | 2 | SP2 | KVCALPPSP002 | 1118.18 | 2.236 | 7 min | 1 | 14 min | Order Total: 10 units
2025-12-08 | 2025-12-08 | Monday | W3 | TAS-GN-014 | 2526203459 | Unknown | W3 | 10 | 2 | 4 | 4/10 (40%) | 2 | SP3 | KVCALFPSP001 | 1118.18 | 2.236 | 7 min | 1 | 14 min | Order Total: 10 units
2025-12-09 | 2025-11-22 | Tuesday | W3 | TAS-GN-006 | 2526203459 | Unknown | W3 | 9 | 3 | 6 | 6/9 (66%) | 2 | Grinding | KVCALHMGR001 | 318.18 | 0.636 | 120 min | 1 | 240 min | Order Total: 9 units
2025-12-09 | 2025-12-09 | Tuesday | W3 | TAS-GN-014 | 2526203459 | Unknown | W3 | 10 | 3 | 7 | 7/10 (70%) | 3 | SP1 | KVCALPPSP001 | 1118.18 | 3.355 | 7 min | 1 | 21 min | Order Total: 10 units
2025-12-09 | 2025-12-09 | Tuesday | W3 | TAS-GN-014 | 2526203459 | Unknown | W3 | 10 | 3 | 7 | 7/10 (70%) | 3 | SP2 | KVCALPPSP002 | 1118.18 | 3.355 | 7 min | 1 | 21 min | Order Total: 10 units
2025-12-09 | 2025-12-09 | Tuesday | W3 | TAS-GN-014 | 2526203459 | Unknown | W3 | 10 | 3 | 7 | 7/10 (70%) | 3 | SP3 | KVCALFPSP001 | 1118.18 | 3.355 | 7 min | 1 | 21 min | Order Total: 10 units
2025-12-10 | 2025-11-22 | Wednesday | W3 | TAS-GN-006 | 2526203459 | Unknown | W3 | 9 | 4 | 9 | 9/9 COMPLETE ✓ | 3 | Grinding | KVCALHMGR001 | 318.18 | 0.955 | 120 min | 1 | 360 min | Order Total: 9 units
2025-12-10 | 2025-12-10 | Wednesday | W3 | TAS-GN-014 | 2526203459 | Unknown | W3 | 10 | 4 | 10 | 10/10 COMPLETE ✓ | 3 | SP1 | KVCALPPSP001 | 1118.18 | 3.355 | 7 min | 1 | 21 min | Order Total: 10 units
2025-12-10 | 2025-12-10 | Wednesday | W3 | TAS-GN-014 | 2526203459 | Unknown | W3 | 10 | 4 | 10 | 10/10 COMPLETE ✓ | 3 | SP2 | KVCALPPSP002 | 1118.18 | 3.355 | 7 min | 1 | 21 min | Order Total: 10 units
2025-12-10 | 2025-12-10 | Wednesday | W3 | TAS-GN-014 | 2526203459 | Unknown | W3 | 10 | 4 | 10 | 10/10 COMPLETE ✓ | 3 | SP3 | KVCALFPSP001 | 1118.18 | 3.355 | 7 min | 1 | 21 min | Order Total: 10 units
2025-11-22 | 2025-11-22 | Saturday | W1 | TAS-GN-004 | 2526203460 | Unknown | W4 | 2 | 1 | 1 | 1/9 (11%) | 1 | Casting | CS1-TAS-GN-004 | 2571.00 | 2.571 | 25 min | 1 | 25 min | Order Total: 2 units
2025-11-22 | 2025-11-22 | Saturday | W1 | TAS-GN-004 | 2526203460 | Unknown | W4 | 7 | 2 | 3 | 3/9 (33%) | 2 | Casting | CS1-TAS-GN-004 | 2571.00 | 5.142 | 25 min | 1 | 50 min | Order Total: 7 units
2025-11-22 | 2025-11-22 | Saturday | W1 | TAS-GN-004 | 2526203460 | Unknown | W4 | 2 | 1 | 1 | 1/9 (11%) | 1 | MC1 | KVCAD50MC001 | 2571.00 | 2.571 | 20 min | 0 | - | Order Total: 2 units
2025-11-22 | 2025-11-22 | Saturday | W1 | TAS-GN-004 | 2526203460 | Unknown | W4 | 7 | 2 | 3 | 3/9 (33%) | 2 | MC1 | KVCAD50MC001 | 2571.00 | 5.142 | 20 min | 0 | - | Order Total: 7 units
2025-11-22 | 2025-11-22 | Saturday | W1 | TAS-GN-004 | 2526203460 | Unknown | W4 | 2 | 1 | 1 | 1/9 (11%) | 1 | SP1 | KVCALPPSP001 | 2571.00 | 2.571 | 7 min | 1 | 7 min | Order Total: 2 units
2025-11-22 | 2025-11-22 | Saturday | W1 | TAS-GN-004 | 2526203460 | Unknown | W4 | 7 | 2 | 3 | 3/9 (33%) | 2 | SP1 | KVCALPPSP001 | 2571.00 | 5.142 | 7 min | 1 | 14 min | Order Total: 7 units
2025-11-22 | 2025-11-22 | Saturday | W1 | TAS-GN-004 | 2526203460 | Unknown | W4 | 2 | 1 | 1 | 1/9 (11%) | 1 | SP2 | KVCALPPSP002 | 2571.00 | 2.571 | 7 min | 1 | 7 min | Order Total: 2 units
2025-11-22 | 2025-11-22 | Saturday | W1 | TAS-GN-004 | 2526203460 | Unknown | W4 | 7 | 2 | 3 | 3/9 (33%) | 2 | SP2 | KVCALPPSP002 | 2571.00 | 5.142 | 7 min | 1 | 14 min | Order Total: 7 units
2025-11-22 | 2025-11-22 | Saturday | W1 | TAS-GN-004 | 2526203460 | Unknown | W4 | 2 | 1 | 1 | 1/9 (11%) | 1 | SP3 | KVCALFPSP001 | 2571.00 | 2.571 | 7 min | 1 | 7 min | Order Total: 2 units
2025-11-22 | 2025-11-22 | Saturday | W1 | TAS-GN-004 | 2526203460 | Unknown | W4 | 7 | 2 | 3 | 3/9 (33%) | 2 | SP3 | KVCALFPSP001 | 2571.00 | 5.142 | 7 min | 1 | 14 min | Order Total: 7 units
2025-11-23 | 2025-11-22 | Sunday | W1 | TAS-GN-004 | 2526203460 | Unknown | W4 | 2 | 1 | 1 | 1/9 (11%) | 1 | Cooling/Shakeout | N/A | 2571.00 | 2.571 | - | 1 | - | Order Total: 2 units
2025-11-23 | 2025-11-22 | Sunday | W1 | TAS-GN-004 | 2526203460 | Unknown | W4 | 7 | 2 | 3 | 3/9 (33%) | 2 | Cooling/Shakeout | N/A | 2571.00 | 5.142 | - | 1 | - | Order Total: 7 units
2025-11-24 | 2025-11-24 | Monday | W1 | TAS-GN-004 | 2526203460 | Unknown | W4 | 2 | 3 | 4 | 4/9 (44%) | 1 | Casting | CS1-TAS-GN-004 | 2571.00 | 2.571 | 25 min | 1 | 25 min | Order Total: 2 units
2025-11-24 | 2025-11-24 | Monday | W1 | TAS-GN-004 | 2526203460 | Unknown | W4 | 7 | 4 | 6 | 6/9 (66%) | 2 | Casting | CS1-TAS-GN-004 | 2571.00 | 5.142 | 25 min | 1 | 50 min | Order Total: 7 units
2025-11-24 | 2025-11-24 | Monday | W1 | TAS-GN-004 | 2526203460 | Unknown | W4 | 2 | 3 | 4 | 4/9 (44%) | 1 | MC1 | KVCAD50MC001 | 2571.00 | 2.571 | 20 min | 0 | - | Order Total: 2 units
2025-11-24 | 2025-11-24 | Monday | W1 | TAS-GN-004 | 2526203460 | Unknown | W4 | 7 | 4 | 6 | 6/9 (66%) | 2 | MC1 | KVCAD50MC001 | 2571.00 | 5.142 | 20 min | 0 | - | Order Total: 7 units
2025-11-24 | 2025-11-24 | Monday | W1 | TAS-GN-004 | 2526203460 | Unknown | W4 | 2 | 3 | 4 | 4/9 (44%) | 1 | SP1 | KVCALPPSP001 | 2571.00 | 2.571 | 7 min | 1 | 7 min | Order Total: 2 units
2025-11-24 | 2025-11-24 | Monday | W1 | TAS-GN-004 | 2526203460 | Unknown | W4 | 7 | 4 | 6 | 6/9 (66%) | 2 | SP1 | KVCALPPSP001 | 2571.00 | 5.142 | 7 min | 1 | 14 min | Order Total: 7 units
2025-11-24 | 2025-11-24 | Monday | W1 | TAS-GN-004 | 2526203460 | Unknown | W4 | 2 | 3 | 4 | 4/9 (44%) | 1 | SP2 | KVCALPPSP002 | 2571.00 | 2.571 | 7 min | 1 | 7 min | Order Total: 2 units
2025-11-24 | 2025-11-24 | Monday | W1 | TAS-GN-004 | 2526203460 | Unknown | W4 | 7 | 4 | 6 | 6/9 (66%) | 2 | SP2 | KVCALPPSP002 | 2571.00 | 5.142 | 7 min | 1 | 14 min | Order Total: 7 units
2025-11-24 | 2025-11-24 | Monday | W1 | TAS-GN-004 | 2526203460 | Unknown | W4 | 2 | 3 | 4 | 4/9 (44%) | 1 | SP3 | KVCALFPSP001 | 2571.00 | 2.571 | 7 min | 1 | 7 min | Order Total: 2 units
2025-11-24 | 2025-11-24 | Monday | W1 | TAS-GN-004 | 2526203460 | Unknown | W4 | 7 | 4 | 6 | 6/9 (66%) | 2 | SP3 | KVCALFPSP001 | 2571.00 | 5.142 | 7 min | 1 | 14 min | Order Total: 7 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | TAS-GN-004 | 2526203460 | Unknown | W4 | 7 | 5 | 9 | 9/9 COMPLETE ✓ | 3 | Casting | CS1-TAS-GN-004 | 2571.00 | 7.713 | 25 min | 1 | 75 min | Order Total: 7 units
2025-11-25 | 2025-11-24 | Tuesday | W1 | TAS-GN-004 | 2526203460 | Unknown | W4 | 2 | 3 | 4 | 4/9 (44%) | 1 | Cooling/Shakeout | N/A | 2571.00 | 2.571 | - | 1 | - | Order Total: 2 units
2025-11-25 | 2025-11-24 | Tuesday | W1 | TAS-GN-004 | 2526203460 | Unknown | W4 | 7 | 4 | 6 | 6/9 (66%) | 2 | Cooling/Shakeout | N/A | 2571.00 | 5.142 | - | 1 | - | Order Total: 7 units
2025-11-25 | 2025-11-22 | Tuesday | W1 | TAS-GN-004 | 2526203460 | Unknown | W4 | 7 | 5 | 9 | 9/9 COMPLETE ✓ | 3 | MC1 | KVCAD50MC001 | 2571.00 | 7.713 | 20 min | 0 | - | Order Total: 7 units
2025-11-25 | 2025-11-22 | Tuesday | W1 | TAS-GN-004 | 2526203460 | Unknown | W4 | 7 | 5 | 9 | 9/9 COMPLETE ✓ | 3 | SP1 | KVCALPPSP001 | 2571.00 | 7.713 | 7 min | 1 | 21 min | Order Total: 7 units
2025-11-25 | 2025-11-22 | Tuesday | W1 | TAS-GN-004 | 2526203460 | Unknown | W4 | 7 | 5 | 9 | 9/9 COMPLETE ✓ | 3 | SP2 | KVCALPPSP002 | 2571.00 | 7.713 | 7 min | 1 | 21 min | Order Total: 7 units
2025-11-25 | 2025-11-22 | Tuesday | W1 | TAS-GN-004 | 2526203460 | Unknown | W4 | 7 | 5 | 9 | 9/9 COMPLETE ✓ | 3 | SP3 | KVCALFPSP001 | 2571.00 | 7.713 | 7 min | 1 | 21 min | Order Total: 7 units
2025-11-26 | 2025-11-22 | Wednesday | W1 | TAS-GN-004 | 2526203460 | Unknown | W4 | 7 | 5 | 9 | 9/9 COMPLETE ✓ | 3 | Cooling/Shakeout | N/A | 2571.00 | 7.713 | - | 1 | - | Order Total: 7 units
2025-11-22 | 2025-11-22 | Saturday | W1 | TAS-GN-004 | 2526203461 | Unknown | W5 | 6 | 1 | 2 | 2/6 (33%) | 2 | Casting | CS1-TAS-GN-004 | 2571.00 | 5.142 | 25 min | 1 | 50 min | Order Total: 6 units
2025-11-22 | 2025-11-29 | Saturday | W1 | TAS-GN-008 | 2526203461 | Unknown | W5 | 3 | 1 | 1 | 1/3 (33%) | 1 | Grinding | KVCALHMGR001 | 2693.18 | 2.693 | 360 min | 1 | 360 min | Order Total: 3 units
2025-11-23 | 2025-11-22 | Sunday | W1 | TAS-GN-004 | 2526203461 | Unknown | W5 | 6 | 1 | 2 | 2/6 (33%) | 2 | Cooling/Shakeout | N/A | 2571.00 | 5.142 | - | 1 | - | Order Total: 6 units
2025-11-24 | 2025-11-24 | Monday | W1 | TAS-GN-004 | 2526203461 | Unknown | W5 | 6 | 2 | 4 | 4/6 (66%) | 2 | Casting | CS1-TAS-GN-004 | 2571.00 | 5.142 | 25 min | 1 | 50 min | Order Total: 6 units
2025-11-24 | 2025-12-01 | Monday | W1 | TAS-GN-008 | 2526203461 | Unknown | W5 | 3 | 2 | 2 | 2/3 (66%) | 1 | Grinding | KVCALHMGR001 | 2693.18 | 2.693 | 360 min | 1 | 360 min | Order Total: 3 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | TAS-GN-004 | 2526203461 | Unknown | W5 | 6 | 3 | 6 | 6/6 COMPLETE ✓ | 2 | Casting | CS1-TAS-GN-004 | 2571.00 | 5.142 | 25 min | 1 | 50 min | Order Total: 6 units
2025-11-25 | 2025-11-24 | Tuesday | W1 | TAS-GN-004 | 2526203461 | Unknown | W5 | 6 | 2 | 4 | 4/6 (66%) | 2 | Cooling/Shakeout | N/A | 2571.00 | 5.142 | - | 1 | - | Order Total: 6 units
2025-11-25 | 2025-12-02 | Tuesday | W1 | TAS-GN-008 | 2526203461 | Unknown | W5 | 3 | 3 | 3 | 3/3 COMPLETE ✓ | 1 | Grinding | KVCALHMGR001 | 2693.18 | 2.693 | 360 min | 1 | 360 min | Order Total: 3 units
2025-11-26 | 2025-11-25 | Wednesday | W1 | TAS-GN-004 | 2526203461 | Unknown | W5 | 6 | 3 | 6 | 6/6 COMPLETE ✓ | 2 | Cooling/Shakeout | N/A | 2571.00 | 5.142 | - | 1 | - | Order Total: 6 units
2025-11-29 | 2025-11-29 | Saturday | W2 | TAS-GN-008 | 2526203461 | Unknown | W5 | 3 | 1 | 1 | 1/3 (33%) | 1 | Casting | CS1-TAS-GN-008 | 2693.18 | 2.693 | 30 min | 1 | 30 min | Order Total: 3 units
2025-11-29 | 2025-11-22 | Saturday | W2 | TAS-GN-004 | 2526203461 | Unknown | W5 | 6 | 1 | 2 | 2/6 (33%) | 2 | SP1 | KVCALPPSP001 | 2571.00 | 5.142 | 7 min | 1 | 14 min | Order Total: 6 units
2025-11-29 | 2025-11-22 | Saturday | W2 | TAS-GN-004 | 2526203461 | Unknown | W5 | 6 | 1 | 2 | 2/6 (33%) | 2 | SP2 | KVCALPPSP002 | 2571.00 | 5.142 | 7 min | 1 | 14 min | Order Total: 6 units
2025-11-29 | 2025-11-22 | Saturday | W2 | TAS-GN-004 | 2526203461 | Unknown | W5 | 6 | 1 | 2 | 2/6 (33%) | 2 | SP3 | KVCALFPSP001 | 2571.00 | 5.142 | 7 min | 1 | 14 min | Order Total: 6 units
2025-11-30 | 2025-11-29 | Sunday | W2 | TAS-GN-008 | 2526203461 | Unknown | W5 | 3 | 1 | 1 | 1/3 (33%) | 1 | Cooling/Shakeout | N/A | 2693.18 | 2.693 | - | 1 | - | Order Total: 3 units
2025-12-01 | 2025-12-01 | Monday | W2 | TAS-GN-008 | 2526203461 | Unknown | W5 | 3 | 2 | 2 | 2/3 (66%) | 1 | Casting | CS1-TAS-GN-008 | 2693.18 | 2.693 | 30 min | 1 | 30 min | Order Total: 3 units
2025-12-01 | 2025-11-24 | Monday | W2 | TAS-GN-004 | 2526203461 | Unknown | W5 | 6 | 2 | 4 | 4/6 (66%) | 2 | SP1 | KVCALPPSP001 | 2571.00 | 5.142 | 7 min | 1 | 14 min | Order Total: 6 units
2025-12-01 | 2025-11-24 | Monday | W2 | TAS-GN-004 | 2526203461 | Unknown | W5 | 6 | 2 | 4 | 4/6 (66%) | 2 | SP2 | KVCALPPSP002 | 2571.00 | 5.142 | 7 min | 1 | 14 min | Order Total: 6 units
2025-12-01 | 2025-11-24 | Monday | W2 | TAS-GN-004 | 2526203461 | Unknown | W5 | 6 | 2 | 4 | 4/6 (66%) | 2 | SP3 | KVCALFPSP001 | 2571.00 | 5.142 | 7 min | 1 | 14 min | Order Total: 6 units
2025-12-02 | 2025-12-02 | Tuesday | W2 | TAS-GN-008 | 2526203461 | Unknown | W5 | 3 | 3 | 3 | 3/3 COMPLETE ✓ | 1 | Casting | CS1-TAS-GN-008 | 2693.18 | 2.693 | 30 min | 1 | 30 min | Order Total: 3 units
2025-12-02 | 2025-12-01 | Tuesday | W2 | TAS-GN-008 | 2526203461 | Unknown | W5 | 3 | 2 | 2 | 2/3 (66%) | 1 | Cooling/Shakeout | N/A | 2693.18 | 2.693 | - | 1 | - | Order Total: 3 units
2025-12-02 | 2025-11-25 | Tuesday | W2 | TAS-GN-004 | 2526203461 | Unknown | W5 | 6 | 3 | 6 | 6/6 COMPLETE ✓ | 2 | SP1 | KVCALPPSP001 | 2571.00 | 5.142 | 7 min | 1 | 14 min | Order Total: 6 units
2025-12-02 | 2025-11-25 | Tuesday | W2 | TAS-GN-004 | 2526203461 | Unknown | W5 | 6 | 3 | 6 | 6/6 COMPLETE ✓ | 2 | SP2 | KVCALPPSP002 | 2571.00 | 5.142 | 7 min | 1 | 14 min | Order Total: 6 units
2025-12-02 | 2025-11-25 | Tuesday | W2 | TAS-GN-004 | 2526203461 | Unknown | W5 | 6 | 3 | 6 | 6/6 COMPLETE ✓ | 2 | SP3 | KVCALFPSP001 | 2571.00 | 5.142 | 7 min | 1 | 14 min | Order Total: 6 units
2025-12-03 | 2025-12-02 | Wednesday | W2 | TAS-GN-008 | 2526203461 | Unknown | W5 | 3 | 3 | 3 | 3/3 COMPLETE ✓ | 1 | Cooling/Shakeout | N/A | 2693.18 | 2.693 | - | 1 | - | Order Total: 3 units
2025-12-06 | 2025-11-29 | Saturday | W3 | TAS-GN-008 | 2526203461 | Unknown | W5 | 3 | 1 | 1 | 1/3 (33%) | 1 | MC1 | KVCAD50MC001 | 2693.18 | 2.693 | 40 min | 0 | - | Order Total: 3 units
2025-12-08 | 2025-12-01 | Monday | W3 | TAS-GN-008 | 2526203461 | Unknown | W5 | 3 | 2 | 2 | 2/3 (66%) | 1 | MC1 | KVCAD50MC001 | 2693.18 | 2.693 | 40 min | 0 | - | Order Total: 3 units
2025-12-09 | 2025-12-02 | Tuesday | W3 | TAS-GN-008 | 2526203461 | Unknown | W5 | 3 | 3 | 3 | 3/3 COMPLETE ✓ | 1 | MC1 | KVCAD50MC001 | 2693.18 | 2.693 | 40 min | 0 | - | Order Total: 3 units
2025-12-13 | 2025-11-22 | Saturday | W4 | TAS-GN-004 | 2526203461 | Unknown | W5 | 6 | 1 | 2 | 2/6 (33%) | 2 | Grinding | KVCALHMGR001 | 2571.00 | 5.142 | 360 min | 1 | 720 min | Order Total: 6 units
2025-12-13 | 2025-11-22 | Saturday | W4 | TAS-GN-004 | 2526203461 | Unknown | W5 | 6 | 1 | 2 | 2/6 (33%) | 2 | MC1 | KVCAD50MC001 | 2571.00 | 5.142 | 20 min | 0 | - | Order Total: 6 units
2025-12-15 | 2025-11-24 | Monday | W4 | TAS-GN-004 | 2526203461 | Unknown | W5 | 6 | 2 | 4 | 4/6 (66%) | 2 | Grinding | KVCALHMGR001 | 2571.00 | 5.142 | 360 min | 1 | 720 min | Order Total: 6 units
2025-12-15 | 2025-11-24 | Monday | W4 | TAS-GN-004 | 2526203461 | Unknown | W5 | 6 | 2 | 4 | 4/6 (66%) | 2 | MC1 | KVCAD50MC001 | 2571.00 | 5.142 | 20 min | 0 | - | Order Total: 6 units
2025-12-16 | 2025-11-25 | Tuesday | W4 | TAS-GN-004 | 2526203461 | Unknown | W5 | 6 | 3 | 6 | 6/6 COMPLETE ✓ | 2 | Grinding | KVCALHMGR001 | 2571.00 | 5.142 | 360 min | 1 | 720 min | Order Total: 6 units
2025-12-16 | 2025-11-25 | Tuesday | W4 | TAS-GN-004 | 2526203461 | Unknown | W5 | 6 | 3 | 6 | 6/6 COMPLETE ✓ | 2 | MC1 | KVCAD50MC001 | 2571.00 | 5.142 | 20 min | 0 | - | Order Total: 6 units
2025-12-20 | 2025-11-29 | Saturday | W5 | TAS-GN-008 | 2526203461 | Unknown | W5 | 3 | 1 | 1 | 1/3 (33%) | 1 | SP1 | KVCALPPSP001 | 2693.18 | 2.693 | 7 min | 1 | 7 min | Order Total: 3 units
2025-12-20 | 2025-11-29 | Saturday | W5 | TAS-GN-008 | 2526203461 | Unknown | W5 | 3 | 1 | 1 | 1/3 (33%) | 1 | SP2 | KVCALPPSP002 | 2693.18 | 2.693 | 7 min | 1 | 7 min | Order Total: 3 units
2025-12-20 | 2025-11-29 | Saturday | W5 | TAS-GN-008 | 2526203461 | Unknown | W5 | 3 | 1 | 1 | 1/3 (33%) | 1 | SP3 | KVCALFPSP001 | 2693.18 | 2.693 | 7 min | 1 | 7 min | Order Total: 3 units
2025-12-22 | 2025-12-01 | Monday | W5 | TAS-GN-008 | 2526203461 | Unknown | W5 | 3 | 2 | 2 | 2/3 (66%) | 1 | SP1 | KVCALPPSP001 | 2693.18 | 2.693 | 7 min | 1 | 7 min | Order Total: 3 units
2025-12-22 | 2025-12-01 | Monday | W5 | TAS-GN-008 | 2526203461 | Unknown | W5 | 3 | 2 | 2 | 2/3 (66%) | 1 | SP2 | KVCALPPSP002 | 2693.18 | 2.693 | 7 min | 1 | 7 min | Order Total: 3 units
2025-12-22 | 2025-12-01 | Monday | W5 | TAS-GN-008 | 2526203461 | Unknown | W5 | 3 | 2 | 2 | 2/3 (66%) | 1 | SP3 | KVCALFPSP001 | 2693.18 | 2.693 | 7 min | 1 | 7 min | Order Total: 3 units
2025-12-23 | 2025-12-02 | Tuesday | W5 | TAS-GN-008 | 2526203461 | Unknown | W5 | 3 | 3 | 3 | 3/3 COMPLETE ✓ | 1 | SP1 | KVCALPPSP001 | 2693.18 | 2.693 | 7 min | 1 | 7 min | Order Total: 3 units
2025-12-23 | 2025-12-02 | Tuesday | W5 | TAS-GN-008 | 2526203461 | Unknown | W5 | 3 | 3 | 3 | 3/3 COMPLETE ✓ | 1 | SP2 | KVCALPPSP002 | 2693.18 | 2.693 | 7 min | 1 | 7 min | Order Total: 3 units
2025-12-23 | 2025-12-02 | Tuesday | W5 | TAS-GN-008 | 2526203461 | Unknown | W5 | 3 | 3 | 3 | 3/3 COMPLETE ✓ | 1 | SP3 | KVCALFPSP001 | 2693.18 | 2.693 | 7 min | 1 | 7 min | Order Total: 3 units
2025-11-22 | 2025-11-29 | Saturday | W1 | TAS-GN-008 | 2526203462 | Unknown | W5 | 3 | 1 | 1 | 1/9 (11%) | 1 | Grinding | KVCALHMGR001 | 2693.18 | 2.693 | 360 min | 1 | 360 min | Order Total: 3 units
2025-11-22 | 2025-11-29 | Saturday | W1 | TAS-GN-008 | 2526203462 | Unknown | W5 | 6 | 2 | 3 | 3/9 (33%) | 2 | Grinding | KVCALHMGR001 | 2693.18 | 5.386 | 360 min | 1 | 720 min | Order Total: 6 units
2025-11-24 | 2025-12-01 | Monday | W1 | TAS-GN-008 | 2526203462 | Unknown | W5 | 3 | 3 | 4 | 4/9 (44%) | 1 | Grinding | KVCALHMGR001 | 2693.18 | 2.693 | 360 min | 1 | 360 min | Order Total: 3 units
2025-11-24 | 2025-12-01 | Monday | W1 | TAS-GN-008 | 2526203462 | Unknown | W5 | 6 | 4 | 6 | 6/9 (66%) | 2 | Grinding | KVCALHMGR001 | 2693.18 | 5.386 | 360 min | 1 | 720 min | Order Total: 6 units
2025-11-25 | 2025-12-02 | Tuesday | W1 | TAS-GN-008 | 2526203462 | Unknown | W5 | 3 | 5 | 7 | 7/9 (77%) | 1 | Grinding | KVCALHMGR001 | 2693.18 | 2.693 | 360 min | 1 | 360 min | Order Total: 3 units
2025-11-25 | 2025-12-02 | Tuesday | W1 | TAS-GN-008 | 2526203462 | Unknown | W5 | 6 | 6 | 9 | 9/9 COMPLETE ✓ | 2 | Grinding | KVCALHMGR001 | 2693.18 | 5.386 | 360 min | 1 | 720 min | Order Total: 6 units
2025-11-29 | 2025-11-29 | Saturday | W2 | TAS-GN-008 | 2526203462 | Unknown | W5 | 3 | 1 | 1 | 1/9 (11%) | 1 | Casting | CS1-TAS-GN-008 | 2693.18 | 2.693 | 30 min | 1 | 30 min | Order Total: 3 units
2025-11-29 | 2025-11-29 | Saturday | W2 | TAS-GN-008 | 2526203462 | Unknown | W5 | 6 | 2 | 3 | 3/9 (33%) | 2 | Casting | CS1-TAS-GN-008 | 2693.18 | 5.386 | 30 min | 1 | 60 min | Order Total: 6 units
2025-11-30 | 2025-11-29 | Sunday | W2 | TAS-GN-008 | 2526203462 | Unknown | W5 | 3 | 1 | 1 | 1/9 (11%) | 1 | Cooling/Shakeout | N/A | 2693.18 | 2.693 | - | 1 | - | Order Total: 3 units
2025-11-30 | 2025-11-29 | Sunday | W2 | TAS-GN-008 | 2526203462 | Unknown | W5 | 6 | 2 | 3 | 3/9 (33%) | 2 | Cooling/Shakeout | N/A | 2693.18 | 5.386 | - | 1 | - | Order Total: 6 units
2025-12-01 | 2025-12-01 | Monday | W2 | TAS-GN-008 | 2526203462 | Unknown | W5 | 3 | 3 | 4 | 4/9 (44%) | 1 | Casting | CS1-TAS-GN-008 | 2693.18 | 2.693 | 30 min | 1 | 30 min | Order Total: 3 units
2025-12-01 | 2025-12-01 | Monday | W2 | TAS-GN-008 | 2526203462 | Unknown | W5 | 6 | 4 | 6 | 6/9 (66%) | 2 | Casting | CS1-TAS-GN-008 | 2693.18 | 5.386 | 30 min | 1 | 60 min | Order Total: 6 units
2025-12-02 | 2025-12-02 | Tuesday | W2 | TAS-GN-008 | 2526203462 | Unknown | W5 | 3 | 5 | 7 | 7/9 (77%) | 1 | Casting | CS1-TAS-GN-008 | 2693.18 | 2.693 | 30 min | 1 | 30 min | Order Total: 3 units
2025-12-02 | 2025-12-02 | Tuesday | W2 | TAS-GN-008 | 2526203462 | Unknown | W5 | 6 | 6 | 9 | 9/9 COMPLETE ✓ | 2 | Casting | CS1-TAS-GN-008 | 2693.18 | 5.386 | 30 min | 1 | 60 min | Order Total: 6 units
2025-12-02 | 2025-12-01 | Tuesday | W2 | TAS-GN-008 | 2526203462 | Unknown | W5 | 3 | 3 | 4 | 4/9 (44%) | 1 | Cooling/Shakeout | N/A | 2693.18 | 2.693 | - | 1 | - | Order Total: 3 units
2025-12-02 | 2025-12-01 | Tuesday | W2 | TAS-GN-008 | 2526203462 | Unknown | W5 | 6 | 4 | 6 | 6/9 (66%) | 2 | Cooling/Shakeout | N/A | 2693.18 | 5.386 | - | 1 | - | Order Total: 6 units
2025-12-03 | 2025-12-02 | Wednesday | W2 | TAS-GN-008 | 2526203462 | Unknown | W5 | 3 | 5 | 7 | 7/9 (77%) | 1 | Cooling/Shakeout | N/A | 2693.18 | 2.693 | - | 1 | - | Order Total: 3 units
2025-12-03 | 2025-12-02 | Wednesday | W2 | TAS-GN-008 | 2526203462 | Unknown | W5 | 6 | 6 | 9 | 9/9 COMPLETE ✓ | 2 | Cooling/Shakeout | N/A | 2693.18 | 5.386 | - | 1 | - | Order Total: 6 units
2025-12-06 | 2025-11-29 | Saturday | W3 | TAS-GN-008 | 2526203462 | Unknown | W5 | 3 | 1 | 1 | 1/9 (11%) | 1 | MC1 | KVCAD50MC001 | 2693.18 | 2.693 | 40 min | 0 | - | Order Total: 3 units
2025-12-06 | 2025-11-29 | Saturday | W3 | TAS-GN-008 | 2526203462 | Unknown | W5 | 6 | 2 | 3 | 3/9 (33%) | 2 | MC1 | KVCAD50MC001 | 2693.18 | 5.386 | 40 min | 0 | - | Order Total: 6 units
2025-12-08 | 2025-12-01 | Monday | W3 | TAS-GN-008 | 2526203462 | Unknown | W5 | 3 | 3 | 4 | 4/9 (44%) | 1 | MC1 | KVCAD50MC001 | 2693.18 | 2.693 | 40 min | 0 | - | Order Total: 3 units
2025-12-08 | 2025-12-01 | Monday | W3 | TAS-GN-008 | 2526203462 | Unknown | W5 | 6 | 4 | 6 | 6/9 (66%) | 2 | MC1 | KVCAD50MC001 | 2693.18 | 5.386 | 40 min | 0 | - | Order Total: 6 units
2025-12-09 | 2025-12-02 | Tuesday | W3 | TAS-GN-008 | 2526203462 | Unknown | W5 | 3 | 5 | 7 | 7/9 (77%) | 1 | MC1 | KVCAD50MC001 | 2693.18 | 2.693 | 40 min | 0 | - | Order Total: 3 units
2025-12-09 | 2025-12-02 | Tuesday | W3 | TAS-GN-008 | 2526203462 | Unknown | W5 | 6 | 6 | 9 | 9/9 COMPLETE ✓ | 2 | MC1 | KVCAD50MC001 | 2693.18 | 5.386 | 40 min | 0 | - | Order Total: 6 units
2025-12-20 | 2025-11-29 | Saturday | W5 | TAS-GN-008 | 2526203462 | Unknown | W5 | 3 | 1 | 1 | 1/9 (11%) | 1 | SP1 | KVCALPPSP001 | 2693.18 | 2.693 | 7 min | 1 | 7 min | Order Total: 3 units
2025-12-20 | 2025-11-29 | Saturday | W5 | TAS-GN-008 | 2526203462 | Unknown | W5 | 6 | 2 | 3 | 3/9 (33%) | 2 | SP1 | KVCALPPSP001 | 2693.18 | 5.386 | 7 min | 1 | 14 min | Order Total: 6 units
2025-12-20 | 2025-11-29 | Saturday | W5 | TAS-GN-008 | 2526203462 | Unknown | W5 | 3 | 1 | 1 | 1/9 (11%) | 1 | SP2 | KVCALPPSP002 | 2693.18 | 2.693 | 7 min | 1 | 7 min | Order Total: 3 units
2025-12-20 | 2025-11-29 | Saturday | W5 | TAS-GN-008 | 2526203462 | Unknown | W5 | 6 | 2 | 3 | 3/9 (33%) | 2 | SP2 | KVCALPPSP002 | 2693.18 | 5.386 | 7 min | 1 | 14 min | Order Total: 6 units
2025-12-20 | 2025-11-29 | Saturday | W5 | TAS-GN-008 | 2526203462 | Unknown | W5 | 3 | 1 | 1 | 1/9 (11%) | 1 | SP3 | KVCALFPSP001 | 2693.18 | 2.693 | 7 min | 1 | 7 min | Order Total: 3 units
2025-12-20 | 2025-11-29 | Saturday | W5 | TAS-GN-008 | 2526203462 | Unknown | W5 | 6 | 2 | 3 | 3/9 (33%) | 2 | SP3 | KVCALFPSP001 | 2693.18 | 5.386 | 7 min | 1 | 14 min | Order Total: 6 units
2025-12-22 | 2025-12-01 | Monday | W5 | TAS-GN-008 | 2526203462 | Unknown | W5 | 3 | 3 | 4 | 4/9 (44%) | 1 | SP1 | KVCALPPSP001 | 2693.18 | 2.693 | 7 min | 1 | 7 min | Order Total: 3 units
2025-12-22 | 2025-12-01 | Monday | W5 | TAS-GN-008 | 2526203462 | Unknown | W5 | 6 | 4 | 6 | 6/9 (66%) | 2 | SP1 | KVCALPPSP001 | 2693.18 | 5.386 | 7 min | 1 | 14 min | Order Total: 6 units
2025-12-22 | 2025-12-01 | Monday | W5 | TAS-GN-008 | 2526203462 | Unknown | W5 | 3 | 3 | 4 | 4/9 (44%) | 1 | SP2 | KVCALPPSP002 | 2693.18 | 2.693 | 7 min | 1 | 7 min | Order Total: 3 units
2025-12-22 | 2025-12-01 | Monday | W5 | TAS-GN-008 | 2526203462 | Unknown | W5 | 6 | 4 | 6 | 6/9 (66%) | 2 | SP2 | KVCALPPSP002 | 2693.18 | 5.386 | 7 min | 1 | 14 min | Order Total: 6 units
2025-12-22 | 2025-12-01 | Monday | W5 | TAS-GN-008 | 2526203462 | Unknown | W5 | 3 | 3 | 4 | 4/9 (44%) | 1 | SP3 | KVCALFPSP001 | 2693.18 | 2.693 | 7 min | 1 | 7 min | Order Total: 3 units
2025-12-22 | 2025-12-01 | Monday | W5 | TAS-GN-008 | 2526203462 | Unknown | W5 | 6 | 4 | 6 | 6/9 (66%) | 2 | SP3 | KVCALFPSP001 | 2693.18 | 5.386 | 7 min | 1 | 14 min | Order Total: 6 units
2025-12-23 | 2025-12-02 | Tuesday | W5 | TAS-GN-008 | 2526203462 | Unknown | W5 | 3 | 5 | 7 | 7/9 (77%) | 1 | SP1 | KVCALPPSP001 | 2693.18 | 2.693 | 7 min | 1 | 7 min | Order Total: 3 units
2025-12-23 | 2025-12-02 | Tuesday | W5 | TAS-GN-008 | 2526203462 | Unknown | W5 | 6 | 6 | 9 | 9/9 COMPLETE ✓ | 2 | SP1 | KVCALPPSP001 | 2693.18 | 5.386 | 7 min | 1 | 14 min | Order Total: 6 units
2025-12-23 | 2025-12-02 | Tuesday | W5 | TAS-GN-008 | 2526203462 | Unknown | W5 | 3 | 5 | 7 | 7/9 (77%) | 1 | SP2 | KVCALPPSP002 | 2693.18 | 2.693 | 7 min | 1 | 7 min | Order Total: 3 units
2025-12-23 | 2025-12-02 | Tuesday | W5 | TAS-GN-008 | 2526203462 | Unknown | W5 | 6 | 6 | 9 | 9/9 COMPLETE ✓ | 2 | SP2 | KVCALPPSP002 | 2693.18 | 5.386 | 7 min | 1 | 14 min | Order Total: 6 units
2025-12-23 | 2025-12-02 | Tuesday | W5 | TAS-GN-008 | 2526203462 | Unknown | W5 | 3 | 5 | 7 | 7/9 (77%) | 1 | SP3 | KVCALFPSP001 | 2693.18 | 2.693 | 7 min | 1 | 7 min | Order Total: 3 units
2025-12-23 | 2025-12-02 | Tuesday | W5 | TAS-GN-008 | 2526203462 | Unknown | W5 | 6 | 6 | 9 | 9/9 COMPLETE ✓ | 2 | SP3 | KVCALFPSP001 | 2693.18 | 5.386 | 7 min | 1 | 14 min | Order Total: 6 units
2025-11-22 | 2025-11-22 | Saturday | W1 | LKK-17 | 2526203463 | Unknown | W2 | 5 | 1 | 2 | 2/12 (16%) | 2 | MC1 | KVCAD50MC001 | 354.85 | 0.710 | 40 min | 1 | 80 min | Order Total: 5 units
2025-11-22 | 2025-11-22 | Saturday | W1 | LKK-17 | 2526203463 | Unknown | W2 | 7 | 2 | 4 | 4/12 (33%) | 2 | MC1 | KVCAD50MC001 | 354.85 | 0.710 | 40 min | 1 | 80 min | Order Total: 7 units
2025-11-22 | 2025-11-22 | Saturday | W1 | LKK-17 | 2526203463 | Unknown | W2 | 5 | 1 | 2 | 2/12 (16%) | 2 | SP1 | KVCALPPSP001 | 354.85 | 0.710 | 7 min | 1 | 14 min | Order Total: 5 units
2025-11-22 | 2025-11-22 | Saturday | W1 | LKK-04 | 2526203463 | Unknown | W2 | 4 | 1 | 2 | 2/4 (50%) | 2 | SP1 | KVCALPPSP001 | 1457.00 | 2.914 | 7 min | 1 | 14 min | Order Total: 4 units
2025-11-22 | 2025-11-22 | Saturday | W1 | LKK-17 | 2526203463 | Unknown | W2 | 7 | 2 | 4 | 4/12 (33%) | 2 | SP1 | KVCALPPSP001 | 354.85 | 0.710 | 7 min | 1 | 14 min | Order Total: 7 units
2025-11-24 | 2025-11-24 | Monday | W1 | LKK-17 | 2526203463 | Unknown | W2 | 5 | 3 | 7 | 7/12 (58%) | 3 | MC1 | KVCAD50MC001 | 354.85 | 1.065 | 40 min | 1 | 120 min | Order Total: 5 units
2025-11-24 | 2025-11-24 | Monday | W1 | LKK-17 | 2526203463 | Unknown | W2 | 7 | 4 | 9 | 9/12 (75%) | 2 | MC1 | KVCAD50MC001 | 354.85 | 0.710 | 40 min | 1 | 80 min | Order Total: 7 units
2025-11-24 | 2025-11-24 | Monday | W1 | LKK-17 | 2526203463 | Unknown | W2 | 5 | 3 | 7 | 7/12 (58%) | 3 | SP1 | KVCALPPSP001 | 354.85 | 1.065 | 7 min | 1 | 21 min | Order Total: 5 units
2025-11-24 | 2025-11-24 | Monday | W1 | LKK-04 | 2526203463 | Unknown | W2 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | SP1 | KVCALPPSP001 | 1457.00 | 2.914 | 7 min | 1 | 14 min | Order Total: 4 units
2025-11-24 | 2025-11-24 | Monday | W1 | LKK-17 | 2526203463 | Unknown | W2 | 7 | 4 | 9 | 9/12 (75%) | 2 | SP1 | KVCALPPSP001 | 354.85 | 0.710 | 7 min | 1 | 14 min | Order Total: 7 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | LKK-17 | 2526203463 | Unknown | W2 | 7 | 5 | 12 | 12/12 COMPLETE ✓ | 3 | MC1 | KVCAD50MC001 | 354.85 | 1.065 | 40 min | 1 | 120 min | Order Total: 7 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | LKK-17 | 2526203463 | Unknown | W2 | 7 | 5 | 12 | 12/12 COMPLETE ✓ | 3 | SP1 | KVCALPPSP001 | 354.85 | 1.065 | 7 min | 1 | 21 min | Order Total: 7 units
2025-11-29 | 2025-11-29 | Saturday | W2 | LKK-05 | 2526203463 | Unknown | W2 | 4 | 1 | 4 | 4/4 COMPLETE ✓ | 4 | Casting | CS1-LKK-005 | 250.00 | 1.000 | 22 min | 1 | 88 min | Order Total: 4 units
2025-11-29 | 2025-11-29 | Saturday | W2 | LKK-17 | 2526203463 | Unknown | W2 | 5 | 1 | 2 | 2/12 (16%) | 2 | Grinding | KVCALHMGR001 | 354.85 | 0.710 | 180 min | 1 | 360 min | Order Total: 5 units
2025-11-29 | 2025-11-29 | Saturday | W2 | LKK-16 | 2526203463 | Unknown | W2 | 12 | 1 | 3 | 3/12 (25%) | 3 | Grinding | KVCALHMGR001 | 443.22 | 1.330 | 180 min | 1 | 540 min | Order Total: 12 units
2025-11-29 | 2025-11-29 | Saturday | W2 | LKK-17 | 2526203463 | Unknown | W2 | 7 | 2 | 4 | 4/12 (33%) | 2 | Grinding | KVCALHMGR001 | 354.85 | 0.710 | 180 min | 1 | 360 min | Order Total: 7 units
2025-11-29 | 2025-11-29 | Saturday | W2 | LKK-16 | 2526203463 | Unknown | W2 | 12 | 1 | 3 | 3/12 (25%) | 3 | MC1 | KVCAD50MC001 | 443.22 | 1.330 | 90 min | 0 | - | Order Total: 12 units
2025-11-29 | 2025-11-29 | Saturday | W2 | LKK-05 | 2526203463 | Unknown | W2 | 4 | 1 | 2 | 2/4 (50%) | 2 | SP1 | KVCALPPSP001 | 250.00 | 0.500 | 7 min | 1 | 14 min | Order Total: 4 units
2025-11-29 | 2025-11-29 | Saturday | W2 | LKK-06 | 2526203463 | Unknown | W2 | 4 | 1 | 2 | 2/4 (50%) | 2 | SP1 | KVCALPPSP001 | 250.00 | 0.500 | 7 min | 1 | 14 min | Order Total: 4 units
2025-11-29 | 2025-11-29 | Saturday | W2 | LKK-16 | 2526203463 | Unknown | W2 | 12 | 1 | 3 | 3/12 (25%) | 3 | SP1 | KVCALPPSP001 | 443.22 | 1.330 | 7 min | 1 | 21 min | Order Total: 12 units
2025-11-30 | 2025-11-29 | Sunday | W2 | LKK-05 | 2526203463 | Unknown | W2 | 4 | 1 | 2 | 2/4 (50%) | 2 | Cooling/Shakeout | N/A | 250.00 | 0.500 | - | 1 | - | Order Total: 4 units
2025-12-01 | 2025-12-01 | Monday | W2 | LKK-17 | 2526203463 | Unknown | W2 | 5 | 3 | 7 | 7/12 (58%) | 3 | Grinding | KVCALHMGR001 | 354.85 | 1.065 | 180 min | 1 | 540 min | Order Total: 5 units
2025-12-01 | 2025-12-01 | Monday | W2 | LKK-16 | 2526203463 | Unknown | W2 | 12 | 2 | 6 | 6/12 (50%) | 3 | Grinding | KVCALHMGR001 | 443.22 | 1.330 | 180 min | 1 | 540 min | Order Total: 12 units
2025-12-01 | 2025-12-01 | Monday | W2 | LKK-17 | 2526203463 | Unknown | W2 | 7 | 4 | 9 | 9/12 (75%) | 2 | Grinding | KVCALHMGR001 | 354.85 | 0.710 | 180 min | 1 | 360 min | Order Total: 7 units
2025-12-01 | 2025-12-01 | Monday | W2 | LKK-16 | 2526203463 | Unknown | W2 | 12 | 2 | 6 | 6/12 (50%) | 3 | MC1 | KVCAD50MC001 | 443.22 | 1.330 | 90 min | 0 | - | Order Total: 12 units
2025-12-01 | 2025-11-29 | Monday | W2 | LKK-05 | 2526203463 | Unknown | W2 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | SP1 | KVCALPPSP001 | 250.00 | 0.500 | 7 min | 1 | 14 min | Order Total: 4 units
2025-12-01 | 2025-12-01 | Monday | W2 | LKK-06 | 2526203463 | Unknown | W2 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | SP1 | KVCALPPSP001 | 250.00 | 0.500 | 7 min | 1 | 14 min | Order Total: 4 units
2025-12-01 | 2025-12-01 | Monday | W2 | LKK-16 | 2526203463 | Unknown | W2 | 12 | 2 | 6 | 6/12 (50%) | 3 | SP1 | KVCALPPSP001 | 443.22 | 1.330 | 7 min | 1 | 21 min | Order Total: 12 units
2025-12-02 | 2025-11-29 | Tuesday | W2 | LKK-05 | 2526203463 | Unknown | W2 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | Cooling/Shakeout | N/A | 250.00 | 0.500 | - | 1 | - | Order Total: 4 units
2025-12-02 | 2025-12-02 | Tuesday | W2 | LKK-16 | 2526203463 | Unknown | W2 | 12 | 3 | 9 | 9/12 (75%) | 3 | Grinding | KVCALHMGR001 | 443.22 | 1.330 | 180 min | 1 | 540 min | Order Total: 12 units
2025-12-02 | 2025-12-02 | Tuesday | W2 | LKK-17 | 2526203463 | Unknown | W2 | 7 | 5 | 12 | 12/12 COMPLETE ✓ | 3 | Grinding | KVCALHMGR001 | 354.85 | 1.065 | 180 min | 1 | 540 min | Order Total: 7 units
2025-12-02 | 2025-12-02 | Tuesday | W2 | LKK-16 | 2526203463 | Unknown | W2 | 12 | 3 | 9 | 9/12 (75%) | 3 | MC1 | KVCAD50MC001 | 443.22 | 1.330 | 90 min | 0 | - | Order Total: 12 units
2025-12-02 | 2025-12-02 | Tuesday | W2 | LKK-16 | 2526203463 | Unknown | W2 | 12 | 3 | 9 | 9/12 (75%) | 3 | SP1 | KVCALPPSP001 | 443.22 | 1.330 | 7 min | 1 | 21 min | Order Total: 12 units
2025-12-03 | 2025-12-03 | Wednesday | W2 | LKK-16 | 2526203463 | Unknown | W2 | 12 | 4 | 12 | 12/12 COMPLETE ✓ | 3 | Grinding | KVCALHMGR001 | 443.22 | 1.330 | 180 min | 1 | 540 min | Order Total: 12 units
2025-12-03 | 2025-12-03 | Wednesday | W2 | LKK-16 | 2526203463 | Unknown | W2 | 12 | 4 | 12 | 12/12 COMPLETE ✓ | 3 | MC1 | KVCAD50MC001 | 443.22 | 1.330 | 90 min | 0 | - | Order Total: 12 units
2025-12-03 | 2025-12-03 | Wednesday | W2 | LKK-16 | 2526203463 | Unknown | W2 | 12 | 4 | 12 | 12/12 COMPLETE ✓ | 3 | SP1 | KVCALPPSP001 | 443.22 | 1.330 | 7 min | 1 | 21 min | Order Total: 12 units
2025-11-22 | 2025-11-22 | Saturday | W1 | LKK-033 | 2526203464 | Unknown | W3 | 2 | 1 | 1 | 1/6 (16%) | 1 | Casting | CS1-LKK-033 | 105.00 | 0.105 | 20 min | 1 | 20 min | Order Total: 2 units
2025-11-22 | 2025-11-22 | Saturday | W1 | LKK-034 | 2526203464 | Unknown | W3 | 1 | 1 | 1 | 1/3 (33%) | 1 | Casting | CS1-LKK-034 | 199.00 | 0.199 | 20 min | 1 | 20 min | Order Total: 1 units
2025-11-22 | 2025-11-22 | Saturday | W1 | LKK-030 | 2526203464 | Unknown | W3 | 3 | 1 | 1 | 1/3 (33%) | 1 | Casting | CS-LKK-030 | 2047.00 | 2.047 | 20 min | 1 | 20 min | Order Total: 3 units
2025-11-22 | 2025-11-22 | Saturday | W1 | LKK-032 | 2526203464 | Unknown | W3 | 3 | 1 | 1 | 1/3 (33%) | 1 | Casting | CS1-LKK-032 | 1311.00 | 1.311 | 20 min | 1 | 20 min | Order Total: 3 units
2025-11-22 | 2025-11-22 | Saturday | W1 | LKK-033 | 2526203464 | Unknown | W3 | 4 | 2 | 3 | 3/6 (50%) | 2 | Casting | CS1-LKK-033 | 105.00 | 0.210 | 20 min | 1 | 40 min | Order Total: 4 units
2025-11-22 | 2025-11-22 | Saturday | W1 | LKK-034 | 2526203464 | Unknown | W3 | 2 | 2 | 2 | 2/3 (66%) | 1 | Casting | CS1-LKK-034 | 199.00 | 0.199 | 20 min | 1 | 20 min | Order Total: 2 units
2025-11-22 | 2025-11-22 | Saturday | W1 | LKK-031 | 2526203464 | Unknown | W3 | 3 | 1 | 1 | 1/3 (33%) | 1 | Grinding | BVCALHMGR001 | 2047.00 | 2.047 | 50 min | 1 | 50 min | Order Total: 3 units
2025-11-22 | 2025-11-22 | Saturday | W1 | LKK-033 | 2526203464 | Unknown | W3 | 2 | 1 | 1 | 1/6 (16%) | 1 | Grinding | KVCALHMGR001 | 105.00 | 0.105 | 50 min | 1 | 50 min | Order Total: 2 units
2025-11-22 | 2025-11-22 | Saturday | W1 | LKK-034 | 2526203464 | Unknown | W3 | 1 | 1 | 1 | 1/3 (33%) | 1 | Grinding | KVCALHMGR001 | 199.00 | 0.199 | 50 min | 1 | 50 min | Order Total: 1 units
2025-11-22 | 2025-11-22 | Saturday | W1 | LKK-030 | 2526203464 | Unknown | W3 | 3 | 1 | 1 | 1/3 (33%) | 1 | Grinding | BVCALHMGR001 | 2047.00 | 2.047 | 50 min | 1 | 50 min | Order Total: 3 units
2025-11-22 | 2025-11-22 | Saturday | W1 | LKK-033 | 2526203464 | Unknown | W3 | 4 | 2 | 3 | 3/6 (50%) | 2 | Grinding | KVCALHMGR001 | 105.00 | 0.210 | 50 min | 1 | 100 min | Order Total: 4 units
2025-11-22 | 2025-11-22 | Saturday | W1 | LKK-034 | 2526203464 | Unknown | W3 | 2 | 2 | 2 | 2/3 (66%) | 1 | Grinding | KVCALHMGR001 | 199.00 | 0.199 | 50 min | 1 | 50 min | Order Total: 2 units
2025-11-22 | 2025-11-22 | Saturday | W1 | LKK-031 | 2526203464 | Unknown | W3 | 3 | 1 | 1 | 1/3 (33%) | 1 | MC1 | KVCAD20MC001 | 2047.00 | 2.047 | 170 min | 1 | 170 min | Order Total: 3 units
2025-11-22 | 2025-11-22 | Saturday | W1 | LKK-031 | 2526203464 | Unknown | W3 | 3 | 1 | 1 | 1/3 (33%) | 1 | SP1 | KVCALPPSP001 | 2047.00 | 2.047 | 7 min | 1 | 7 min | Order Total: 3 units
2025-11-22 | 2025-11-22 | Saturday | W1 | LKK-033 | 2526203464 | Unknown | W3 | 2 | 1 | 1 | 1/6 (16%) | 1 | SP1 | KVCALPPSP001 | 105.00 | 0.105 | 7 min | 1 | 7 min | Order Total: 2 units
2025-11-22 | 2025-11-22 | Saturday | W1 | LKK-034 | 2526203464 | Unknown | W3 | 1 | 1 | 1 | 1/3 (33%) | 1 | SP1 | KVCALPPSP001 | 199.00 | 0.199 | 7 min | 1 | 7 min | Order Total: 1 units
2025-11-22 | 2025-11-22 | Saturday | W1 | LKK-033 | 2526203464 | Unknown | W3 | 4 | 2 | 3 | 3/6 (50%) | 2 | SP1 | KVCALPPSP001 | 105.00 | 0.210 | 7 min | 1 | 14 min | Order Total: 4 units
2025-11-22 | 2025-11-22 | Saturday | W1 | LKK-034 | 2526203464 | Unknown | W3 | 2 | 2 | 2 | 2/3 (66%) | 1 | SP1 | KVCALPPSP001 | 199.00 | 0.199 | 7 min | 1 | 7 min | Order Total: 2 units
2025-11-23 | 2025-11-22 | Sunday | W1 | LKK-033 | 2526203464 | Unknown | W3 | 2 | 1 | 1 | 1/6 (16%) | 1 | Cooling/Shakeout | N/A | 105.00 | 0.105 | - | 1 | - | Order Total: 2 units
2025-11-23 | 2025-11-22 | Sunday | W1 | LKK-034 | 2526203464 | Unknown | W3 | 1 | 1 | 1 | 1/3 (33%) | 1 | Cooling/Shakeout | N/A | 199.00 | 0.199 | - | 1 | - | Order Total: 1 units
2025-11-23 | 2025-11-22 | Sunday | W1 | LKK-030 | 2526203464 | Unknown | W3 | 3 | 1 | 1 | 1/3 (33%) | 1 | Cooling/Shakeout | N/A | 2047.00 | 2.047 | - | 1 | - | Order Total: 3 units
2025-11-23 | 2025-11-22 | Sunday | W1 | LKK-032 | 2526203464 | Unknown | W3 | 3 | 1 | 1 | 1/3 (33%) | 1 | Cooling/Shakeout | N/A | 1311.00 | 1.311 | - | 1 | - | Order Total: 3 units
2025-11-23 | 2025-11-22 | Sunday | W1 | LKK-033 | 2526203464 | Unknown | W3 | 4 | 2 | 3 | 3/6 (50%) | 2 | Cooling/Shakeout | N/A | 105.00 | 0.210 | - | 1 | - | Order Total: 4 units
2025-11-23 | 2025-11-22 | Sunday | W1 | LKK-034 | 2526203464 | Unknown | W3 | 2 | 2 | 2 | 2/3 (66%) | 1 | Cooling/Shakeout | N/A | 199.00 | 0.199 | - | 1 | - | Order Total: 2 units
2025-11-24 | 2025-11-24 | Monday | W1 | LKK-033 | 2526203464 | Unknown | W3 | 2 | 3 | 4 | 4/6 (66%) | 1 | Casting | CS1-LKK-033 | 105.00 | 0.105 | 20 min | 1 | 20 min | Order Total: 2 units
2025-11-24 | 2025-11-24 | Monday | W1 | LKK-030 | 2526203464 | Unknown | W3 | 3 | 2 | 2 | 2/3 (66%) | 1 | Casting | CS-LKK-030 | 2047.00 | 2.047 | 20 min | 1 | 20 min | Order Total: 3 units
2025-11-24 | 2025-11-24 | Monday | W1 | LKK-032 | 2526203464 | Unknown | W3 | 3 | 2 | 2 | 2/3 (66%) | 1 | Casting | CS1-LKK-032 | 1311.00 | 1.311 | 20 min | 1 | 20 min | Order Total: 3 units
2025-11-24 | 2025-11-24 | Monday | W1 | LKK-033 | 2526203464 | Unknown | W3 | 4 | 4 | 6 | 6/6 COMPLETE ✓ | 2 | Casting | CS1-LKK-033 | 105.00 | 0.210 | 20 min | 1 | 40 min | Order Total: 4 units
2025-11-24 | 2025-11-24 | Monday | W1 | LKK-034 | 2526203464 | Unknown | W3 | 2 | 3 | 3 | 3/3 COMPLETE ✓ | 1 | Casting | CS1-LKK-034 | 199.00 | 0.199 | 20 min | 1 | 20 min | Order Total: 2 units
2025-11-24 | 2025-11-24 | Monday | W1 | LKK-031 | 2526203464 | Unknown | W3 | 3 | 2 | 2 | 2/3 (66%) | 1 | Grinding | BVCALHMGR001 | 2047.00 | 2.047 | 50 min | 1 | 50 min | Order Total: 3 units
2025-11-24 | 2025-11-24 | Monday | W1 | LKK-033 | 2526203464 | Unknown | W3 | 2 | 3 | 4 | 4/6 (66%) | 1 | Grinding | KVCALHMGR001 | 105.00 | 0.105 | 50 min | 1 | 50 min | Order Total: 2 units
2025-11-24 | 2025-11-24 | Monday | W1 | LKK-030 | 2526203464 | Unknown | W3 | 3 | 2 | 2 | 2/3 (66%) | 1 | Grinding | BVCALHMGR001 | 2047.00 | 2.047 | 50 min | 1 | 50 min | Order Total: 3 units
2025-11-24 | 2025-11-24 | Monday | W1 | LKK-033 | 2526203464 | Unknown | W3 | 4 | 4 | 6 | 6/6 COMPLETE ✓ | 2 | Grinding | KVCALHMGR001 | 105.00 | 0.210 | 50 min | 1 | 100 min | Order Total: 4 units
2025-11-24 | 2025-11-22 | Monday | W1 | LKK-034 | 2526203464 | Unknown | W3 | 2 | 3 | 3 | 3/3 COMPLETE ✓ | 1 | Grinding | KVCALHMGR001 | 199.00 | 0.199 | 50 min | 1 | 50 min | Order Total: 2 units
2025-11-24 | 2025-11-24 | Monday | W1 | LKK-031 | 2526203464 | Unknown | W3 | 3 | 2 | 2 | 2/3 (66%) | 1 | MC1 | KVCAD20MC001 | 2047.00 | 2.047 | 170 min | 1 | 170 min | Order Total: 3 units
2025-11-24 | 2025-11-24 | Monday | W1 | LKK-031 | 2526203464 | Unknown | W3 | 3 | 2 | 2 | 2/3 (66%) | 1 | SP1 | KVCALPPSP001 | 2047.00 | 2.047 | 7 min | 1 | 7 min | Order Total: 3 units
2025-11-24 | 2025-11-24 | Monday | W1 | LKK-033 | 2526203464 | Unknown | W3 | 2 | 3 | 4 | 4/6 (66%) | 1 | SP1 | KVCALPPSP001 | 105.00 | 0.105 | 7 min | 1 | 7 min | Order Total: 2 units
2025-11-24 | 2025-11-24 | Monday | W1 | LKK-033 | 2526203464 | Unknown | W3 | 4 | 4 | 6 | 6/6 COMPLETE ✓ | 2 | SP1 | KVCALPPSP001 | 105.00 | 0.210 | 7 min | 1 | 14 min | Order Total: 4 units
2025-11-24 | 2025-11-22 | Monday | W1 | LKK-034 | 2526203464 | Unknown | W3 | 2 | 3 | 3 | 3/3 COMPLETE ✓ | 1 | SP1 | KVCALPPSP001 | 199.00 | 0.199 | 7 min | 1 | 7 min | Order Total: 2 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | LKK-030 | 2526203464 | Unknown | W3 | 3 | 3 | 3 | 3/3 COMPLETE ✓ | 1 | Casting | CS-LKK-030 | 2047.00 | 2.047 | 20 min | 1 | 20 min | Order Total: 3 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | LKK-032 | 2526203464 | Unknown | W3 | 3 | 3 | 3 | 3/3 COMPLETE ✓ | 1 | Casting | CS1-LKK-032 | 1311.00 | 1.311 | 20 min | 1 | 20 min | Order Total: 3 units
2025-11-25 | 2025-11-24 | Tuesday | W1 | LKK-033 | 2526203464 | Unknown | W3 | 2 | 3 | 4 | 4/6 (66%) | 1 | Cooling/Shakeout | N/A | 105.00 | 0.105 | - | 1 | - | Order Total: 2 units
2025-11-25 | 2025-11-24 | Tuesday | W1 | LKK-030 | 2526203464 | Unknown | W3 | 3 | 2 | 2 | 2/3 (66%) | 1 | Cooling/Shakeout | N/A | 2047.00 | 2.047 | - | 1 | - | Order Total: 3 units
2025-11-25 | 2025-11-24 | Tuesday | W1 | LKK-032 | 2526203464 | Unknown | W3 | 3 | 2 | 2 | 2/3 (66%) | 1 | Cooling/Shakeout | N/A | 1311.00 | 1.311 | - | 1 | - | Order Total: 3 units
2025-11-25 | 2025-11-24 | Tuesday | W1 | LKK-033 | 2526203464 | Unknown | W3 | 4 | 4 | 6 | 6/6 COMPLETE ✓ | 2 | Cooling/Shakeout | N/A | 105.00 | 0.210 | - | 1 | - | Order Total: 4 units
2025-11-25 | 2025-11-22 | Tuesday | W1 | LKK-034 | 2526203464 | Unknown | W3 | 2 | 3 | 3 | 3/3 COMPLETE ✓ | 1 | Cooling/Shakeout | N/A | 199.00 | 0.199 | - | 1 | - | Order Total: 2 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | LKK-031 | 2526203464 | Unknown | W3 | 3 | 3 | 3 | 3/3 COMPLETE ✓ | 1 | Grinding | BVCALHMGR001 | 2047.00 | 2.047 | 50 min | 1 | 50 min | Order Total: 3 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | LKK-030 | 2526203464 | Unknown | W3 | 3 | 3 | 3 | 3/3 COMPLETE ✓ | 1 | Grinding | BVCALHMGR001 | 2047.00 | 2.047 | 50 min | 1 | 50 min | Order Total: 3 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | LKK-031 | 2526203464 | Unknown | W3 | 3 | 3 | 3 | 3/3 COMPLETE ✓ | 1 | MC1 | KVCAD20MC001 | 2047.00 | 2.047 | 170 min | 1 | 170 min | Order Total: 3 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | LKK-031 | 2526203464 | Unknown | W3 | 3 | 3 | 3 | 3/3 COMPLETE ✓ | 1 | SP1 | KVCALPPSP001 | 2047.00 | 2.047 | 7 min | 1 | 7 min | Order Total: 3 units
2025-11-26 | 2025-11-25 | Wednesday | W1 | LKK-030 | 2526203464 | Unknown | W3 | 3 | 3 | 3 | 3/3 COMPLETE ✓ | 1 | Cooling/Shakeout | N/A | 2047.00 | 2.047 | - | 1 | - | Order Total: 3 units
2025-11-26 | 2025-11-25 | Wednesday | W1 | LKK-032 | 2526203464 | Unknown | W3 | 3 | 3 | 3 | 3/3 COMPLETE ✓ | 1 | Cooling/Shakeout | N/A | 1311.00 | 1.311 | - | 1 | - | Order Total: 3 units
2025-11-29 | 2025-11-22 | Saturday | W2 | LKK-032 | 2526203464 | Unknown | W3 | 3 | 1 | 1 | 1/3 (33%) | 1 | Grinding | KVCALHMGR001 | 1311.00 | 1.311 | 50 min | 1 | 50 min | Order Total: 3 units
2025-11-29 | 2025-11-22 | Saturday | W2 | LKK-030 | 2526203464 | Unknown | W3 | 3 | 1 | 1 | 1/3 (33%) | 1 | MC1 | KVCAD20MC001 | 2047.00 | 2.047 | 170 min | 1 | 170 min | Order Total: 3 units
2025-12-01 | 2025-11-24 | Monday | W2 | LKK-032 | 2526203464 | Unknown | W3 | 3 | 2 | 2 | 2/3 (66%) | 1 | Grinding | KVCALHMGR001 | 1311.00 | 1.311 | 50 min | 1 | 50 min | Order Total: 3 units
2025-12-01 | 2025-11-24 | Monday | W2 | LKK-030 | 2526203464 | Unknown | W3 | 3 | 2 | 2 | 2/3 (66%) | 1 | MC1 | KVCAD20MC001 | 2047.00 | 2.047 | 170 min | 1 | 170 min | Order Total: 3 units
2025-12-02 | 2025-11-25 | Tuesday | W2 | LKK-032 | 2526203464 | Unknown | W3 | 3 | 3 | 3 | 3/3 COMPLETE ✓ | 1 | Grinding | KVCALHMGR001 | 1311.00 | 1.311 | 50 min | 1 | 50 min | Order Total: 3 units
2025-12-02 | 2025-11-25 | Tuesday | W2 | LKK-030 | 2526203464 | Unknown | W3 | 3 | 3 | 3 | 3/3 COMPLETE ✓ | 1 | MC1 | KVCAD20MC001 | 2047.00 | 2.047 | 170 min | 1 | 170 min | Order Total: 3 units
2025-12-06 | 2025-11-22 | Saturday | W3 | LKK-032 | 2526203464 | Unknown | W3 | 3 | 1 | 1 | 1/3 (33%) | 1 | MC1 | KVCAD50MC001 | 1311.00 | 1.311 | 30 min | 1 | 30 min | Order Total: 3 units
2025-12-06 | 2025-11-22 | Saturday | W3 | LKK-030 | 2526203464 | Unknown | W3 | 3 | 1 | 1 | 1/3 (33%) | 1 | SP1 | KVCALPPSP001 | 2047.00 | 2.047 | 7 min | 1 | 7 min | Order Total: 3 units
2025-12-06 | 2025-11-22 | Saturday | W3 | LKK-032 | 2526203464 | Unknown | W3 | 3 | 1 | 1 | 1/3 (33%) | 1 | SP1 | KVCALPPSP001 | 1311.00 | 1.311 | 7 min | 1 | 7 min | Order Total: 3 units
2025-12-08 | 2025-11-24 | Monday | W3 | LKK-032 | 2526203464 | Unknown | W3 | 3 | 2 | 2 | 2/3 (66%) | 1 | MC1 | KVCAD50MC001 | 1311.00 | 1.311 | 30 min | 1 | 30 min | Order Total: 3 units
2025-12-08 | 2025-11-24 | Monday | W3 | LKK-030 | 2526203464 | Unknown | W3 | 3 | 2 | 2 | 2/3 (66%) | 1 | SP1 | KVCALPPSP001 | 2047.00 | 2.047 | 7 min | 1 | 7 min | Order Total: 3 units
2025-12-08 | 2025-11-24 | Monday | W3 | LKK-032 | 2526203464 | Unknown | W3 | 3 | 2 | 2 | 2/3 (66%) | 1 | SP1 | KVCALPPSP001 | 1311.00 | 1.311 | 7 min | 1 | 7 min | Order Total: 3 units
2025-12-09 | 2025-11-25 | Tuesday | W3 | LKK-032 | 2526203464 | Unknown | W3 | 3 | 3 | 3 | 3/3 COMPLETE ✓ | 1 | MC1 | KVCAD50MC001 | 1311.00 | 1.311 | 30 min | 1 | 30 min | Order Total: 3 units
2025-12-09 | 2025-11-25 | Tuesday | W3 | LKK-030 | 2526203464 | Unknown | W3 | 3 | 3 | 3 | 3/3 COMPLETE ✓ | 1 | SP1 | KVCALPPSP001 | 2047.00 | 2.047 | 7 min | 1 | 7 min | Order Total: 3 units
2025-12-09 | 2025-11-25 | Tuesday | W3 | LKK-032 | 2526203464 | Unknown | W3 | 3 | 3 | 3 | 3/3 COMPLETE ✓ | 1 | SP1 | KVCALPPSP001 | 1311.00 | 1.311 | 7 min | 1 | 7 min | Order Total: 3 units
2025-11-22 | 2025-11-22 | Saturday | W1 | LKK-035 | 2526203465 | Unknown | W4 | 9 | 1 | 2 | 2/9 (22%) | 2 | Casting | CS1-LKK-035 | 1968.00 | 3.936 | 20 min | 1 | 40 min | Order Total: 9 units
2025-11-23 | 2025-11-22 | Sunday | W1 | LKK-035 | 2526203465 | Unknown | W4 | 9 | 1 | 2 | 2/9 (22%) | 2 | Cooling/Shakeout | N/A | 1968.00 | 3.936 | - | 1 | - | Order Total: 9 units
2025-11-24 | 2025-11-24 | Monday | W1 | LKK-035 | 2526203465 | Unknown | W4 | 9 | 2 | 4 | 4/9 (44%) | 2 | Casting | CS1-LKK-035 | 1968.00 | 3.936 | 20 min | 1 | 40 min | Order Total: 9 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | LKK-035 | 2526203465 | Unknown | W4 | 9 | 3 | 6 | 6/9 (66%) | 2 | Casting | CS1-LKK-035 | 1968.00 | 3.936 | 20 min | 1 | 40 min | Order Total: 9 units
2025-11-25 | 2025-11-24 | Tuesday | W1 | LKK-035 | 2526203465 | Unknown | W4 | 9 | 2 | 4 | 4/9 (44%) | 2 | Cooling/Shakeout | N/A | 1968.00 | 3.936 | - | 1 | - | Order Total: 9 units
2025-11-26 | 2025-11-26 | Wednesday | W1 | LKK-035 | 2526203465 | Unknown | W4 | 9 | 4 | 9 | 9/9 COMPLETE ✓ | 3 | Casting | CS1-LKK-035 | 1968.00 | 5.904 | 20 min | 1 | 60 min | Order Total: 9 units
2025-11-26 | 2025-11-25 | Wednesday | W1 | LKK-035 | 2526203465 | Unknown | W4 | 9 | 3 | 6 | 6/9 (66%) | 2 | Cooling/Shakeout | N/A | 1968.00 | 3.936 | - | 1 | - | Order Total: 9 units
2025-11-27 | 2025-11-26 | Thursday | W1 | LKK-035 | 2526203465 | Unknown | W4 | 9 | 4 | 9 | 9/9 COMPLETE ✓ | 3 | Cooling/Shakeout | N/A | 1968.00 | 5.904 | - | 1 | - | Order Total: 9 units
2025-12-06 | 2025-11-22 | Saturday | W3 | LKK-035 | 2526203465 | Unknown | W4 | 9 | 1 | 2 | 2/9 (22%) | 2 | Grinding | KVCALHMGR001 | 1968.00 | 3.936 | 50 min | 1 | 100 min | Order Total: 9 units
2025-12-06 | 2025-11-22 | Saturday | W3 | LKK-035 | 2526203465 | Unknown | W4 | 9 | 1 | 2 | 2/9 (22%) | 2 | MC1 | KVCAD20MC001 | 1968.00 | 3.936 | 170 min | 1 | 340 min | Order Total: 9 units
2025-12-06 | 2025-11-22 | Saturday | W3 | LKK-035 | 2526203465 | Unknown | W4 | 9 | 1 | 2 | 2/9 (22%) | 2 | SP1 | KVCALPPSP001 | 1968.00 | 3.936 | 7 min | 1 | 14 min | Order Total: 9 units
2025-12-08 | 2025-11-24 | Monday | W3 | LKK-035 | 2526203465 | Unknown | W4 | 9 | 2 | 4 | 4/9 (44%) | 2 | Grinding | KVCALHMGR001 | 1968.00 | 3.936 | 50 min | 1 | 100 min | Order Total: 9 units
2025-12-08 | 2025-11-24 | Monday | W3 | LKK-035 | 2526203465 | Unknown | W4 | 9 | 2 | 4 | 4/9 (44%) | 2 | MC1 | KVCAD20MC001 | 1968.00 | 3.936 | 170 min | 1 | 340 min | Order Total: 9 units
2025-12-08 | 2025-11-24 | Monday | W3 | LKK-035 | 2526203465 | Unknown | W4 | 9 | 2 | 4 | 4/9 (44%) | 2 | SP1 | KVCALPPSP001 | 1968.00 | 3.936 | 7 min | 1 | 14 min | Order Total: 9 units
2025-12-09 | 2025-11-25 | Tuesday | W3 | LKK-035 | 2526203465 | Unknown | W4 | 9 | 3 | 6 | 6/9 (66%) | 2 | Grinding | KVCALHMGR001 | 1968.00 | 3.936 | 50 min | 1 | 100 min | Order Total: 9 units
2025-12-09 | 2025-11-25 | Tuesday | W3 | LKK-035 | 2526203465 | Unknown | W4 | 9 | 3 | 6 | 6/9 (66%) | 2 | MC1 | KVCAD20MC001 | 1968.00 | 3.936 | 170 min | 1 | 340 min | Order Total: 9 units
2025-12-09 | 2025-11-25 | Tuesday | W3 | LKK-035 | 2526203465 | Unknown | W4 | 9 | 3 | 6 | 6/9 (66%) | 2 | SP1 | KVCALPPSP001 | 1968.00 | 3.936 | 7 min | 1 | 14 min | Order Total: 9 units
2025-12-10 | 2025-11-26 | Wednesday | W3 | LKK-035 | 2526203465 | Unknown | W4 | 9 | 4 | 9 | 9/9 COMPLETE ✓ | 3 | Grinding | KVCALHMGR001 | 1968.00 | 5.904 | 50 min | 1 | 150 min | Order Total: 9 units
2025-12-10 | 2025-11-26 | Wednesday | W3 | LKK-035 | 2526203465 | Unknown | W4 | 9 | 4 | 9 | 9/9 COMPLETE ✓ | 3 | MC1 | KVCAD20MC001 | 1968.00 | 5.904 | 170 min | 1 | 510 min | Order Total: 9 units
2025-12-10 | 2025-11-26 | Wednesday | W3 | LKK-035 | 2526203465 | Unknown | W4 | 9 | 4 | 9 | 9/9 COMPLETE ✓ | 3 | SP1 | KVCALPPSP001 | 1968.00 | 5.904 | 7 min | 1 | 21 min | Order Total: 9 units
2025-11-22 | 2025-11-22 | Saturday | W1 | UBC-021 | 2526203482 | Unknown | W7 | 2 | 1 | 1 | 1/2 (50%) | 1 | Casting | CS1-UBC-021 | 3600.00 | 3.600 | 20 min | 1 | 20 min | Order Total: 2 units
2025-11-22 | 2025-11-22 | Saturday | W1 | UBC-050 | 2526203482 | Unknown | W7 | 4 | 1 | 2 | 2/4 (50%) | 2 | SP1 | KVCALPPSP001 | 369.00 | 0.738 | 12 min | 1 | 24 min | Order Total: 4 units
2025-11-23 | 2025-11-22 | Sunday | W1 | UBC-021 | 2526203482 | Unknown | W7 | 2 | 1 | 1 | 1/2 (50%) | 1 | Cooling/Shakeout | N/A | 3600.00 | 3.600 | - | 1 | - | Order Total: 2 units
2025-11-24 | 2025-11-24 | Monday | W1 | UBC-021 | 2526203482 | Unknown | W7 | 2 | 2 | 2 | 2/2 COMPLETE ✓ | 1 | Casting | CS1-UBC-021 | 3600.00 | 3.600 | 20 min | 1 | 20 min | Order Total: 2 units
2025-11-24 | 2025-11-24 | Monday | W1 | UBC-050 | 2526203482 | Unknown | W7 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | SP1 | KVCALPPSP001 | 369.00 | 0.738 | 12 min | 1 | 24 min | Order Total: 4 units
2025-11-25 | 2025-11-24 | Tuesday | W1 | UBC-021 | 2526203482 | Unknown | W7 | 2 | 2 | 2 | 2/2 COMPLETE ✓ | 1 | Cooling/Shakeout | N/A | 3600.00 | 3.600 | - | 1 | - | Order Total: 2 units
2025-11-29 | 2025-11-29 | Saturday | W2 | UBC-022 | 2526203482 | Unknown | W7 | 8 | 1 | 2 | 2/8 (25%) | 2 | MC1 | MC1-UBC-022 | 1200.00 | 2.400 | 60 min | 0 | - | Order Total: 8 units
2025-12-01 | 2025-12-01 | Monday | W2 | UBC-022 | 2526203482 | Unknown | W7 | 8 | 2 | 4 | 4/8 (50%) | 2 | MC1 | MC1-UBC-022 | 1200.00 | 2.400 | 60 min | 0 | - | Order Total: 8 units
2025-12-02 | 2025-12-02 | Tuesday | W2 | UBC-022 | 2526203482 | Unknown | W7 | 8 | 3 | 6 | 6/8 (75%) | 2 | MC1 | MC1-UBC-022 | 1200.00 | 2.400 | 60 min | 0 | - | Order Total: 8 units
2025-12-03 | 2025-12-03 | Wednesday | W2 | UBC-022 | 2526203482 | Unknown | W7 | 8 | 4 | 8 | 8/8 COMPLETE ✓ | 2 | MC1 | MC1-UBC-022 | 1200.00 | 2.400 | 60 min | 0 | - | Order Total: 8 units
2025-12-06 | 2025-12-06 | Saturday | W3 | UBC-051 | 2526203482 | Unknown | W7 | 4 | 1 | 2 | 2/4 (50%) | 2 | SP1 | KVCALPPSP001 | 369.00 | 0.738 | 12 min | 1 | 24 min | Order Total: 4 units
2025-12-08 | 2025-12-08 | Monday | W3 | UBC-051 | 2526203482 | Unknown | W7 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | SP1 | KVCALPPSP001 | 369.00 | 0.738 | 12 min | 1 | 24 min | Order Total: 4 units
2025-12-13 | 2025-11-22 | Saturday | W4 | UBC-021 | 2526203482 | Unknown | W7 | 2 | 1 | 1 | 1/2 (50%) | 1 | Grinding | KVCALHMGR001 | 3600.00 | 3.600 | 300 min | 1 | 300 min | Order Total: 2 units
2025-12-15 | 2025-11-24 | Monday | W4 | UBC-021 | 2526203482 | Unknown | W7 | 2 | 2 | 2 | 2/2 COMPLETE ✓ | 1 | Grinding | KVCALHMGR001 | 3600.00 | 3.600 | 300 min | 1 | 300 min | Order Total: 2 units
2025-12-13 | 2025-12-13 | Saturday | W4 | UBC-014 | 2526203484 | Unknown | W7 | 50 | 1 | 48 | 48/50 (96%) | 48 | Casting | CS1-UBC-014 | 460.00 | 22.080 | 20 min | 1 | 960 min | Order Total: 50 units
2025-12-14 | 2025-12-13 | Sunday | W4 | UBC-014 | 2526203484 | Unknown | W7 | 50 | 1 | 50 | 50/50 COMPLETE ✓ | 50 | Cooling/Shakeout | N/A | 460.00 | 23.000 | - | 1 | - | Order Total: 50 units
2025-12-15 | 2025-12-15 | Monday | W4 | UBC-014 | 2526203484 | Unknown | W7 | 50 | 2 | 50 | 50/50 COMPLETE ✓ | 2 | Casting | CS1-UBC-014 | 460.00 | 0.920 | 20 min | 1 | 40 min | Order Total: 50 units
2025-11-22 | 2025-11-22 | Saturday | W1 | UBC-021 | 2526203547 | Unknown | W8 | 2 | 1 | 1 | 1/2 (50%) | 1 | Casting | CS1-UBC-021 | 3600.00 | 3.600 | 20 min | 1 | 20 min | Order Total: 2 units
2025-11-22 | 2025-11-22 | Saturday | W1 | UBC-020 | 2526203547 | Unknown | W8 | 4 | 1 | 2 | 2/4 (50%) | 2 | SP1 | KVCALPPSP001 | 1667.00 | 3.334 | 12 min | 1 | 24 min | Order Total: 4 units
2025-11-23 | 2025-11-22 | Sunday | W1 | UBC-021 | 2526203547 | Unknown | W8 | 2 | 1 | 1 | 1/2 (50%) | 1 | Cooling/Shakeout | N/A | 3600.00 | 3.600 | - | 1 | - | Order Total: 2 units
2025-11-24 | 2025-11-24 | Monday | W1 | UBC-021 | 2526203547 | Unknown | W8 | 2 | 2 | 2 | 2/2 COMPLETE ✓ | 1 | Casting | CS1-UBC-021 | 3600.00 | 3.600 | 20 min | 1 | 20 min | Order Total: 2 units
2025-11-24 | 2025-11-24 | Monday | W1 | UBC-020 | 2526203547 | Unknown | W8 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | SP1 | KVCALPPSP001 | 1667.00 | 3.334 | 12 min | 1 | 24 min | Order Total: 4 units
2025-11-25 | 2025-11-24 | Tuesday | W1 | UBC-021 | 2526203547 | Unknown | W8 | 2 | 2 | 2 | 2/2 COMPLETE ✓ | 1 | Cooling/Shakeout | N/A | 3600.00 | 3.600 | - | 1 | - | Order Total: 2 units
2025-12-13 | 2025-12-13 | Saturday | W4 | UBC-050 | 2526203547 | Unknown | W8 | 12 | 1 | 3 | 3/12 (25%) | 3 | SP1 | KVCALPPSP001 | 369.00 | 1.107 | 12 min | 1 | 36 min | Order Total: 12 units
2025-12-15 | 2025-12-15 | Monday | W4 | UBC-050 | 2526203547 | Unknown | W8 | 12 | 2 | 6 | 6/12 (50%) | 3 | SP1 | KVCALPPSP001 | 369.00 | 1.107 | 12 min | 1 | 36 min | Order Total: 12 units
2025-12-16 | 2025-12-16 | Tuesday | W4 | UBC-050 | 2526203547 | Unknown | W8 | 12 | 3 | 9 | 9/12 (75%) | 3 | SP1 | KVCALPPSP001 | 369.00 | 1.107 | 12 min | 1 | 36 min | Order Total: 12 units
2025-12-17 | 2025-12-17 | Wednesday | W4 | UBC-050 | 2526203547 | Unknown | W8 | 12 | 4 | 12 | 12/12 COMPLETE ✓ | 3 | SP1 | KVCALPPSP001 | 369.00 | 1.107 | 12 min | 1 | 36 min | Order Total: 12 units
2025-12-20 | 2025-12-20 | Saturday | W5 | UBC-051 | 2526203547 | Unknown | W8 | 12 | 1 | 3 | 3/12 (25%) | 3 | Grinding | KVCALHMGR001 | 369.00 | 1.107 | 120 min | 1 | 360 min | Order Total: 12 units
2025-12-20 | 2025-12-20 | Saturday | W5 | UBC-051 | 2526203547 | Unknown | W8 | 12 | 1 | 3 | 3/12 (25%) | 3 | SP1 | KVCALPPSP001 | 369.00 | 1.107 | 12 min | 1 | 36 min | Order Total: 12 units
2025-12-20 | 2025-11-22 | Saturday | W5 | UBC-021 | 2526203547 | Unknown | W8 | 2 | 1 | 1 | 1/2 (50%) | 1 | SP1 | KVCALPPSP001 | 3600.00 | 3.600 | 12 min | 1 | 12 min | Order Total: 2 units
2025-12-22 | 2025-12-22 | Monday | W5 | UBC-051 | 2526203547 | Unknown | W8 | 12 | 2 | 6 | 6/12 (50%) | 3 | Grinding | KVCALHMGR001 | 369.00 | 1.107 | 120 min | 1 | 360 min | Order Total: 12 units
2025-12-22 | 2025-12-22 | Monday | W5 | UBC-051 | 2526203547 | Unknown | W8 | 12 | 2 | 6 | 6/12 (50%) | 3 | SP1 | KVCALPPSP001 | 369.00 | 1.107 | 12 min | 1 | 36 min | Order Total: 12 units
2025-12-22 | 2025-11-24 | Monday | W5 | UBC-021 | 2526203547 | Unknown | W8 | 2 | 2 | 2 | 2/2 COMPLETE ✓ | 1 | SP1 | KVCALPPSP001 | 3600.00 | 3.600 | 12 min | 1 | 12 min | Order Total: 2 units
2025-12-23 | 2025-12-23 | Tuesday | W5 | UBC-051 | 2526203547 | Unknown | W8 | 12 | 3 | 9 | 9/12 (75%) | 3 | Grinding | KVCALHMGR001 | 369.00 | 1.107 | 120 min | 1 | 360 min | Order Total: 12 units
2025-12-23 | 2025-12-23 | Tuesday | W5 | UBC-051 | 2526203547 | Unknown | W8 | 12 | 3 | 9 | 9/12 (75%) | 3 | SP1 | KVCALPPSP001 | 369.00 | 1.107 | 12 min | 1 | 36 min | Order Total: 12 units
2025-12-24 | 2025-12-24 | Wednesday | W5 | UBC-051 | 2526203547 | Unknown | W8 | 12 | 4 | 12 | 12/12 COMPLETE ✓ | 3 | Grinding | KVCALHMGR001 | 369.00 | 1.107 | 120 min | 1 | 360 min | Order Total: 12 units
2025-12-24 | 2025-12-24 | Wednesday | W5 | UBC-051 | 2526203547 | Unknown | W8 | 12 | 4 | 12 | 12/12 COMPLETE ✓ | 3 | SP1 | KVCALPPSP001 | 369.00 | 1.107 | 12 min | 1 | 36 min | Order Total: 12 units
2025-12-20 | 2025-12-20 | Saturday | W5 | DGC-001 | 2526203549 | Unknown | W7 | 56 | 1 | 50 | 50/56 (89%) | 50 | Casting | CS1-DGC-001 | 396.00 | 19.800 | 20 min | 1 | 1000 min | Order Total: 56 units
2025-12-21 | 2025-12-20 | Sunday | W5 | DGC-001 | 2526203549 | Unknown | W7 | 56 | 1 | 50 | 50/56 (89%) | 50 | Cooling/Shakeout | N/A | 396.00 | 19.800 | - | 1 | - | Order Total: 56 units
2025-12-22 | 2025-12-22 | Monday | W5 | DGC-001 | 2526203549 | Unknown | W7 | 56 | 2 | 56 | 56/56 COMPLETE ✓ | 6 | Casting | CS1-DGC-001 | 396.00 | 2.376 | 20 min | 1 | 120 min | Order Total: 56 units
2025-12-23 | 2025-12-22 | Tuesday | W5 | DGC-001 | 2526203549 | Unknown | W7 | 56 | 2 | 56 | 56/56 COMPLETE ✓ | 6 | Cooling/Shakeout | N/A | 396.00 | 2.376 | - | 1 | - | Order Total: 56 units
2025-12-13 | 2025-12-13 | Saturday | W4 | DGC-001 | 2526203550 | Unknown | W8 | 56 | 1 | 50 | 50/56 (89%) | 50 | SP1 | KVCALPPSP001 | 396.00 | 19.800 | 7 min | 1 | 350 min | Order Total: 56 units
2025-12-13 | 2025-12-13 | Saturday | W4 | DGC-001 | 2526203550 | Unknown | W8 | 56 | 1 | 50 | 50/56 (89%) | 50 | SP2 | KVCALPPSP002 | 396.00 | 19.800 | 7 min | 1 | 350 min | Order Total: 56 units
2025-12-13 | 2025-12-13 | Saturday | W4 | DGC-001 | 2526203550 | Unknown | W8 | 56 | 1 | 50 | 50/56 (89%) | 50 | SP3 | KVCALFPSP001 | 396.00 | 19.800 | 7 min | 1 | 350 min | Order Total: 56 units
2025-12-15 | 2025-12-15 | Monday | W4 | DGC-001 | 2526203550 | Unknown | W8 | 56 | 2 | 56 | 56/56 COMPLETE ✓ | 6 | SP1 | KVCALPPSP001 | 396.00 | 2.376 | 7 min | 1 | 42 min | Order Total: 56 units
2025-12-15 | 2025-12-15 | Monday | W4 | DGC-001 | 2526203550 | Unknown | W8 | 56 | 2 | 56 | 56/56 COMPLETE ✓ | 6 | SP2 | KVCALPPSP002 | 396.00 | 2.376 | 7 min | 1 | 42 min | Order Total: 56 units
2025-12-15 | 2025-12-15 | Monday | W4 | DGC-001 | 2526203550 | Unknown | W8 | 56 | 2 | 56 | 56/56 COMPLETE ✓ | 6 | SP3 | KVCALFPSP001 | 396.00 | 2.376 | 7 min | 1 | 42 min | Order Total: 56 units
2025-12-13 | 2025-12-13 | Saturday | W4 | DGC-001 | 2526203551 | Unknown | W8 | 56 | 1 | 50 | 50/56 (89%) | 50 | SP1 | KVCALPPSP001 | 396.00 | 19.800 | 7 min | 1 | 350 min | Order Total: 56 units
2025-12-13 | 2025-12-13 | Saturday | W4 | DGC-001 | 2526203551 | Unknown | W8 | 56 | 1 | 50 | 50/56 (89%) | 50 | SP2 | KVCALPPSP002 | 396.00 | 19.800 | 7 min | 1 | 350 min | Order Total: 56 units
2025-12-13 | 2025-12-13 | Saturday | W4 | DGC-001 | 2526203551 | Unknown | W8 | 56 | 1 | 50 | 50/56 (89%) | 50 | SP3 | KVCALFPSP001 | 396.00 | 19.800 | 7 min | 1 | 350 min | Order Total: 56 units
2025-12-15 | 2025-12-15 | Monday | W4 | DGC-001 | 2526203551 | Unknown | W8 | 56 | 2 | 56 | 56/56 COMPLETE ✓ | 6 | SP1 | KVCALPPSP001 | 396.00 | 2.376 | 7 min | 1 | 42 min | Order Total: 56 units
2025-12-15 | 2025-12-15 | Monday | W4 | DGC-001 | 2526203551 | Unknown | W8 | 56 | 2 | 56 | 56/56 COMPLETE ✓ | 6 | SP2 | KVCALPPSP002 | 396.00 | 2.376 | 7 min | 1 | 42 min | Order Total: 56 units
2025-12-15 | 2025-12-15 | Monday | W4 | DGC-001 | 2526203551 | Unknown | W8 | 56 | 2 | 56 | 56/56 COMPLETE ✓ | 6 | SP3 | KVCALFPSP001 | 396.00 | 2.376 | 7 min | 1 | 42 min | Order Total: 56 units
2025-12-06 | 2025-12-06 | Saturday | W3 | DGC-001 | 2526203553 | Unknown | W10 | 56 | 1 | 50 | 50/56 (89%) | 50 | Casting | CS1-DGC-001 | 396.00 | 19.800 | 20 min | 1 | 1000 min | Order Total: 56 units
2025-12-07 | 2025-12-06 | Sunday | W3 | DGC-001 | 2526203553 | Unknown | W10 | 56 | 1 | 50 | 50/56 (89%) | 50 | Cooling/Shakeout | N/A | 396.00 | 19.800 | - | 1 | - | Order Total: 56 units
2025-12-08 | 2025-12-08 | Monday | W3 | DGC-001 | 2526203553 | Unknown | W10 | 56 | 2 | 56 | 56/56 COMPLETE ✓ | 6 | Casting | CS1-DGC-001 | 396.00 | 2.376 | 20 min | 1 | 120 min | Order Total: 56 units
2025-12-09 | 2025-12-08 | Tuesday | W3 | DGC-001 | 2526203553 | Unknown | W10 | 56 | 2 | 56 | 56/56 COMPLETE ✓ | 6 | Cooling/Shakeout | N/A | 396.00 | 2.376 | - | 1 | - | Order Total: 56 units
2025-12-13 | 2025-12-06 | Saturday | W4 | DGC-001 | 2526203553 | Unknown | W10 | 56 | 1 | 50 | 50/56 (89%) | 50 | Grinding | KVCALHMGR001 | 396.00 | 19.800 | 120 min | 1 | 6000 min | Order Total: 56 units
2025-12-15 | 2025-12-08 | Monday | W4 | DGC-001 | 2526203553 | Unknown | W10 | 56 | 2 | 56 | 56/56 COMPLETE ✓ | 6 | Grinding | KVCALHMGR001 | 396.00 | 2.376 | 120 min | 1 | 720 min | Order Total: 56 units
2025-12-06 | 2025-12-06 | Saturday | W3 | DGC-012 | 2526203554 | Unknown | W7 | 40 | 1 | 40 | 40/40 COMPLETE ✓ | 40 | Casting | CS1-DGC-012 | 200.00 | 8.000 | 20 min | 1 | 800 min | Order Total: 40 units
2025-12-06 | 2025-12-06 | Saturday | W3 | DGC-011 | 2526203554 | Unknown | W7 | 6 | 1 | 4 | 4/6 (66%) | 4 | Casting | CS1-DGC-011 | 2200.00 | 8.800 | 20 min | 1 | 80 min | Order Total: 6 units
2025-12-07 | 2025-12-06 | Sunday | W3 | DGC-012 | 2526203554 | Unknown | W7 | 40 | 1 | 40 | 40/40 COMPLETE ✓ | 40 | Cooling/Shakeout | N/A | 200.00 | 8.000 | - | 1 | - | Order Total: 40 units
2025-12-07 | 2025-12-06 | Sunday | W3 | DGC-011 | 2526203554 | Unknown | W7 | 6 | 1 | 2 | 2/6 (33%) | 2 | Cooling/Shakeout | N/A | 2200.00 | 4.400 | - | 1 | - | Order Total: 6 units
2025-12-08 | 2025-12-08 | Monday | W3 | DGC-011 | 2526203554 | Unknown | W7 | 6 | 2 | 6 | 6/6 COMPLETE ✓ | 2 | Casting | CS1-DGC-011 | 2200.00 | 4.400 | 20 min | 1 | 40 min | Order Total: 6 units
2025-12-09 | 2025-12-08 | Tuesday | W3 | DGC-011 | 2526203554 | Unknown | W7 | 6 | 2 | 4 | 4/6 (66%) | 2 | Cooling/Shakeout | N/A | 2200.00 | 4.400 | - | 1 | - | Order Total: 6 units
2025-12-10 | 2025-12-06 | Wednesday | W3 | DGC-011 | 2526203554 | Unknown | W7 | 6 | 3 | 6 | 6/6 COMPLETE ✓ | 2 | Cooling/Shakeout | N/A | 2200.00 | 4.400 | - | 1 | - | Order Total: 6 units
2025-12-06 | 2025-12-06 | Saturday | W3 | DGC-011 | 2526203555 | Unknown | W8 | 6 | 1 | 4 | 4/6 (66%) | 4 | Casting | CS1-DGC-011 | 2200.00 | 8.800 | 20 min | 1 | 80 min | Order Total: 6 units
2025-12-06 | 2025-12-06 | Saturday | W3 | DGC-012 | 2526203555 | Unknown | W8 | 40 | 1 | 40 | 40/40 COMPLETE ✓ | 40 | SP1 | KVCALPPSP001 | 200.00 | 8.000 | 7 min | 1 | 280 min | Order Total: 40 units
2025-12-06 | 2025-12-06 | Saturday | W3 | DGC-012 | 2526203555 | Unknown | W8 | 40 | 1 | 40 | 40/40 COMPLETE ✓ | 40 | SP2 | KVCALPPSP002 | 200.00 | 8.000 | 7 min | 1 | 280 min | Order Total: 40 units
2025-12-06 | 2025-12-06 | Saturday | W3 | DGC-012 | 2526203555 | Unknown | W8 | 40 | 1 | 40 | 40/40 COMPLETE ✓ | 40 | SP3 | KVCALFPSP001 | 200.00 | 8.000 | 7 min | 1 | 280 min | Order Total: 40 units
2025-12-07 | 2025-12-06 | Sunday | W3 | DGC-011 | 2526203555 | Unknown | W8 | 6 | 1 | 2 | 2/6 (33%) | 2 | Cooling/Shakeout | N/A | 2200.00 | 4.400 | - | 1 | - | Order Total: 6 units
2025-12-08 | 2025-12-08 | Monday | W3 | DGC-011 | 2526203555 | Unknown | W8 | 6 | 2 | 6 | 6/6 COMPLETE ✓ | 2 | Casting | CS1-DGC-011 | 2200.00 | 4.400 | 20 min | 1 | 40 min | Order Total: 6 units
2025-12-09 | 2025-12-08 | Tuesday | W3 | DGC-011 | 2526203555 | Unknown | W8 | 6 | 2 | 4 | 4/6 (66%) | 2 | Cooling/Shakeout | N/A | 2200.00 | 4.400 | - | 1 | - | Order Total: 6 units
2025-12-10 | 2025-12-06 | Wednesday | W3 | DGC-011 | 2526203555 | Unknown | W8 | 6 | 3 | 6 | 6/6 COMPLETE ✓ | 2 | Cooling/Shakeout | N/A | 2200.00 | 4.400 | - | 1 | - | Order Total: 6 units
2025-11-29 | 2025-11-29 | Saturday | W2 | DGC-012 | 2526203556 | Unknown | W9 | 34 | 1 | 34 | 34/34 COMPLETE ✓ | 34 | Grinding | KVCALHMGR001 | 200.00 | 6.800 | 150 min | 1 | 5100 min | Order Total: 34 units
2025-12-06 | 2025-12-06 | Saturday | W3 | DGC-011 | 2526203556 | Unknown | W9 | 5 | 1 | 4 | 4/5 (80%) | 4 | Casting | CS1-DGC-011 | 2200.00 | 8.800 | 20 min | 1 | 80 min | Order Total: 5 units
2025-12-07 | 2025-12-06 | Sunday | W3 | DGC-011 | 2526203556 | Unknown | W9 | 5 | 1 | 2 | 2/5 (40%) | 2 | Cooling/Shakeout | N/A | 2200.00 | 4.400 | - | 1 | - | Order Total: 5 units
2025-12-08 | 2025-12-08 | Monday | W3 | DGC-011 | 2526203556 | Unknown | W9 | 5 | 2 | 5 | 5/5 COMPLETE ✓ | 1 | Casting | CS1-DGC-011 | 2200.00 | 2.200 | 20 min | 1 | 20 min | Order Total: 5 units
2025-12-09 | 2025-12-08 | Tuesday | W3 | DGC-011 | 2526203556 | Unknown | W9 | 5 | 2 | 5 | 5/5 COMPLETE ✓ | 3 | Cooling/Shakeout | N/A | 2200.00 | 6.600 | - | 1 | - | Order Total: 5 units
2025-11-22 | 2025-11-22 | Saturday | W1 | KBS-012 | 2526500083 | Unknown | W1 | 1 | 1 | 1 | 1/1 COMPLETE ✓ | 1 | Casting | CS1-KBS-012 | 888.50 | 0.888 | 25 min | 1 | 25 min | Order Total: 1 units
2025-11-22 | 2025-11-22 | Saturday | W1 | KBS-012 | 2526500083 | Unknown | W1 | 1 | 1 | 1 | 1/1 COMPLETE ✓ | 1 | MC1 | KVCAD50MC001 | 888.50 | 0.888 | 58 min | 1 | 58 min | Order Total: 1 units
2025-11-22 | 2025-11-22 | Saturday | W1 | KBS-012 | 2526500083 | Unknown | W1 | 1 | 1 | 1 | 1/1 COMPLETE ✓ | 1 | MC2 | KVCAD50MC001 | 888.50 | 0.888 | 30 min | 1 | 30 min | Order Total: 1 units
2025-11-22 | 2025-11-22 | Saturday | W1 | KBS-012 | 2526500083 | Unknown | W1 | 1 | 1 | 1 | 1/1 COMPLETE ✓ | 1 | MC3 | KVCAD50MC001 | 888.50 | 0.888 | 25 min | 1 | 25 min | Order Total: 1 units
2025-11-23 | 2025-11-22 | Sunday | W1 | KBS-012 | 2526500083 | Unknown | W1 | 1 | 1 | 1 | 1/1 COMPLETE ✓ | 1 | Cooling/Shakeout | N/A | 888.50 | 0.888 | - | 1 | - | Order Total: 1 units
2025-12-06 | 2025-11-22 | Saturday | W3 | KBS-012 | 2526500083 | Unknown | W1 | 1 | 1 | 1 | 1/1 COMPLETE ✓ | 1 | Grinding | KVCALHMGR001 | 888.50 | 0.888 | 210 min | 1 | 210 min | Order Total: 1 units
2025-12-06 | 2025-11-22 | Saturday | W3 | KBS-012 | 2526500083 | Unknown | W1 | 1 | 1 | 1 | 1/1 COMPLETE ✓ | 1 | SP1 | KVCALPPSP001 | 888.50 | 0.888 | 12 min | 1 | 12 min | Order Total: 1 units
2025-12-06 | 2025-11-22 | Saturday | W3 | KBS-012 | 2526500083 | Unknown | W1 | 1 | 1 | 1 | 1/1 COMPLETE ✓ | 1 | SP2 | KVCALPPSP002 | 888.50 | 0.888 | 12 min | 1 | 12 min | Order Total: 1 units
2025-12-06 | 2025-11-22 | Saturday | W3 | KBS-012 | 2526500083 | Unknown | W1 | 1 | 1 | 1 | 1/1 COMPLETE ✓ | 1 | SP3 | KVCALFPSP001 | 888.50 | 0.888 | 7 min | 1 | 7 min | Order Total: 1 units
2025-12-06 | 2025-12-06 | Saturday | W3 | KBS-016 | 2526500086 | Unknown | W1 | 19 | 1 | 4 | 4/19 (21%) | 4 | Grinding | KVCALHMGR001 | 875.00 | 3.500 | 360 min | 1 | 1440 min | Order Total: 19 units
2025-12-06 | 2025-12-06 | Saturday | W3 | KBS-016 | 2526500086 | Unknown | W1 | 19 | 1 | 4 | 4/19 (21%) | 4 | SP1 | KVCALPPSP001 | 875.00 | 3.500 | 12 min | 1 | 48 min | Order Total: 19 units
2025-12-06 | 2025-12-06 | Saturday | W3 | KBS-016 | 2526500086 | Unknown | W1 | 19 | 1 | 4 | 4/19 (21%) | 4 | SP2 | KVCALPPSP002 | 875.00 | 3.500 | 12 min | 1 | 48 min | Order Total: 19 units
2025-12-06 | 2025-12-06 | Saturday | W3 | KBS-016 | 2526500086 | Unknown | W1 | 19 | 1 | 4 | 4/19 (21%) | 4 | SP3 | KVCALFPSP001 | 875.00 | 3.500 | 12 min | 1 | 48 min | Order Total: 19 units
2025-12-08 | 2025-12-08 | Monday | W3 | KBS-016 | 2526500086 | Unknown | W1 | 19 | 2 | 9 | 9/19 (47%) | 5 | Grinding | KVCALHMGR001 | 875.00 | 4.375 | 360 min | 1 | 1800 min | Order Total: 19 units
2025-12-08 | 2025-12-08 | Monday | W3 | KBS-016 | 2526500086 | Unknown | W1 | 19 | 2 | 9 | 9/19 (47%) | 5 | SP1 | KVCALPPSP001 | 875.00 | 4.375 | 12 min | 1 | 60 min | Order Total: 19 units
2025-12-08 | 2025-12-08 | Monday | W3 | KBS-016 | 2526500086 | Unknown | W1 | 19 | 2 | 9 | 9/19 (47%) | 5 | SP2 | KVCALPPSP002 | 875.00 | 4.375 | 12 min | 1 | 60 min | Order Total: 19 units
2025-12-08 | 2025-12-08 | Monday | W3 | KBS-016 | 2526500086 | Unknown | W1 | 19 | 2 | 9 | 9/19 (47%) | 5 | SP3 | KVCALFPSP001 | 875.00 | 4.375 | 12 min | 1 | 60 min | Order Total: 19 units
2025-12-09 | 2025-12-09 | Tuesday | W3 | KBS-016 | 2526500086 | Unknown | W1 | 19 | 3 | 14 | 14/19 (73%) | 5 | Grinding | KVCALHMGR001 | 875.00 | 4.375 | 360 min | 1 | 1800 min | Order Total: 19 units
2025-12-09 | 2025-12-09 | Tuesday | W3 | KBS-016 | 2526500086 | Unknown | W1 | 19 | 3 | 14 | 14/19 (73%) | 5 | SP1 | KVCALPPSP001 | 875.00 | 4.375 | 12 min | 1 | 60 min | Order Total: 19 units
2025-12-09 | 2025-12-09 | Tuesday | W3 | KBS-016 | 2526500086 | Unknown | W1 | 19 | 3 | 14 | 14/19 (73%) | 5 | SP2 | KVCALPPSP002 | 875.00 | 4.375 | 12 min | 1 | 60 min | Order Total: 19 units
2025-12-09 | 2025-12-09 | Tuesday | W3 | KBS-016 | 2526500086 | Unknown | W1 | 19 | 3 | 14 | 14/19 (73%) | 5 | SP3 | KVCALFPSP001 | 875.00 | 4.375 | 12 min | 1 | 60 min | Order Total: 19 units
2025-12-10 | 2025-12-10 | Wednesday | W3 | KBS-016 | 2526500086 | Unknown | W1 | 19 | 4 | 19 | 19/19 COMPLETE ✓ | 5 | Grinding | KVCALHMGR001 | 875.00 | 4.375 | 360 min | 1 | 1800 min | Order Total: 19 units
2025-12-10 | 2025-12-10 | Wednesday | W3 | KBS-016 | 2526500086 | Unknown | W1 | 19 | 4 | 19 | 19/19 COMPLETE ✓ | 5 | SP1 | KVCALPPSP001 | 875.00 | 4.375 | 12 min | 1 | 60 min | Order Total: 19 units
2025-12-10 | 2025-12-10 | Wednesday | W3 | KBS-016 | 2526500086 | Unknown | W1 | 19 | 4 | 19 | 19/19 COMPLETE ✓ | 5 | SP2 | KVCALPPSP002 | 875.00 | 4.375 | 12 min | 1 | 60 min | Order Total: 19 units
2025-12-10 | 2025-12-10 | Wednesday | W3 | KBS-016 | 2526500086 | Unknown | W1 | 19 | 4 | 19 | 19/19 COMPLETE ✓ | 5 | SP3 | KVCALFPSP001 | 875.00 | 4.375 | 12 min | 1 | 60 min | Order Total: 19 units
2025-11-22 | 2025-11-22 | Saturday | W1 | KBS-017 | 2526500087 | Unknown | W1 | 5 | 1 | 2 | 2/5 (40%) | 2 | SP1 | KVCALPPSP001 | 1079.30 | 2.159 | 12 min | 1 | 24 min | Order Total: 5 units
2025-11-22 | 2025-11-22 | Saturday | W1 | KBS-017 | 2526500087 | Unknown | W1 | 5 | 1 | 2 | 2/5 (40%) | 2 | SP2 | KVCALPPSP002 | 1079.30 | 2.159 | 12 min | 1 | 24 min | Order Total: 5 units
2025-11-22 | 2025-11-22 | Saturday | W1 | KBS-017 | 2526500087 | Unknown | W1 | 5 | 1 | 2 | 2/5 (40%) | 2 | SP3 | KVCALFPSP001 | 1079.30 | 2.159 | 12 min | 1 | 24 min | Order Total: 5 units
2025-11-24 | 2025-11-24 | Monday | W1 | KBS-017 | 2526500087 | Unknown | W1 | 5 | 2 | 5 | 5/5 COMPLETE ✓ | 3 | SP1 | KVCALPPSP001 | 1079.30 | 3.238 | 12 min | 1 | 36 min | Order Total: 5 units
2025-11-24 | 2025-11-24 | Monday | W1 | KBS-017 | 2526500087 | Unknown | W1 | 5 | 2 | 5 | 5/5 COMPLETE ✓ | 3 | SP2 | KVCALPPSP002 | 1079.30 | 3.238 | 12 min | 1 | 36 min | Order Total: 5 units
2025-11-24 | 2025-11-24 | Monday | W1 | KBS-017 | 2526500087 | Unknown | W1 | 5 | 2 | 5 | 5/5 COMPLETE ✓ | 3 | SP3 | KVCALFPSP001 | 1079.30 | 3.238 | 12 min | 1 | 36 min | Order Total: 5 units
2025-11-29 | 2025-11-29 | Saturday | W2 | KBS-017 | 2526500087 | Unknown | W1 | 5 | 1 | 2 | 2/5 (40%) | 2 | Grinding | KVCALHMGR001 | 1079.30 | 2.159 | 360 min | 1 | 720 min | Order Total: 5 units
2025-12-01 | 2025-12-01 | Monday | W2 | KBS-017 | 2526500087 | Unknown | W1 | 5 | 2 | 5 | 5/5 COMPLETE ✓ | 3 | Grinding | KVCALHMGR001 | 1079.30 | 3.238 | 360 min | 1 | 1080 min | Order Total: 5 units
2025-11-22 | 2025-11-22 | Saturday | W1 | KBS-018 | 2526500091 | Unknown | W1 | 8 | 1 | 2 | 2/8 (25%) | 2 | MC1 | BVCAD30MC001 | 997.00 | 1.994 | 200 min | 1 | 400 min | Order Total: 8 units
2025-11-22 | 2025-11-22 | Saturday | W1 | KBS-018 | 2526500091 | Unknown | W1 | 8 | 1 | 2 | 2/8 (25%) | 2 | MC2 | BVCABM1MC001 | 997.00 | 1.994 | 120 min | 1 | 240 min | Order Total: 8 units
2025-11-22 | 2025-11-22 | Saturday | W1 | KBS-018 | 2526500091 | Unknown | W1 | 8 | 1 | 2 | 2/8 (25%) | 2 | MC3 | BVCAD30MC001 | 997.00 | 1.994 | 45 min | 1 | 90 min | Order Total: 8 units
2025-11-22 | 2025-11-22 | Saturday | W1 | KBS-018 | 2526500091 | Unknown | W1 | 8 | 1 | 2 | 2/8 (25%) | 2 | SP1 | KVCALPPSP001 | 997.00 | 1.994 | 12 min | 1 | 24 min | Order Total: 8 units
2025-11-22 | 2025-11-22 | Saturday | W1 | KBS-018 | 2526500091 | Unknown | W1 | 8 | 1 | 2 | 2/8 (25%) | 2 | SP2 | KVCALPPSP002 | 997.00 | 1.994 | 12 min | 1 | 24 min | Order Total: 8 units
2025-11-22 | 2025-11-22 | Saturday | W1 | KBS-018 | 2526500091 | Unknown | W1 | 8 | 1 | 2 | 2/8 (25%) | 2 | SP3 | KVCALFPSP001 | 997.00 | 1.994 | 12 min | 1 | 24 min | Order Total: 8 units
2025-11-24 | 2025-11-24 | Monday | W1 | KBS-018 | 2526500091 | Unknown | W1 | 8 | 2 | 4 | 4/8 (50%) | 2 | MC1 | BVCAD30MC001 | 997.00 | 1.994 | 200 min | 1 | 400 min | Order Total: 8 units
2025-11-24 | 2025-11-24 | Monday | W1 | KBS-018 | 2526500091 | Unknown | W1 | 8 | 2 | 4 | 4/8 (50%) | 2 | MC2 | BVCABM1MC001 | 997.00 | 1.994 | 120 min | 1 | 240 min | Order Total: 8 units
2025-11-24 | 2025-11-24 | Monday | W1 | KBS-018 | 2526500091 | Unknown | W1 | 8 | 2 | 4 | 4/8 (50%) | 2 | MC3 | BVCAD30MC001 | 997.00 | 1.994 | 45 min | 1 | 90 min | Order Total: 8 units
2025-11-24 | 2025-11-24 | Monday | W1 | KBS-018 | 2526500091 | Unknown | W1 | 8 | 2 | 4 | 4/8 (50%) | 2 | SP1 | KVCALPPSP001 | 997.00 | 1.994 | 12 min | 1 | 24 min | Order Total: 8 units
2025-11-24 | 2025-11-24 | Monday | W1 | KBS-018 | 2526500091 | Unknown | W1 | 8 | 2 | 4 | 4/8 (50%) | 2 | SP2 | KVCALPPSP002 | 997.00 | 1.994 | 12 min | 1 | 24 min | Order Total: 8 units
2025-11-24 | 2025-11-24 | Monday | W1 | KBS-018 | 2526500091 | Unknown | W1 | 8 | 2 | 4 | 4/8 (50%) | 2 | SP3 | KVCALFPSP001 | 997.00 | 1.994 | 12 min | 1 | 24 min | Order Total: 8 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | KBS-018 | 2526500091 | Unknown | W1 | 8 | 3 | 6 | 6/8 (75%) | 2 | MC1 | BVCAD30MC001 | 997.00 | 1.994 | 200 min | 1 | 400 min | Order Total: 8 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | KBS-018 | 2526500091 | Unknown | W1 | 8 | 3 | 6 | 6/8 (75%) | 2 | MC2 | BVCABM1MC001 | 997.00 | 1.994 | 120 min | 1 | 240 min | Order Total: 8 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | KBS-018 | 2526500091 | Unknown | W1 | 8 | 3 | 6 | 6/8 (75%) | 2 | MC3 | BVCAD30MC001 | 997.00 | 1.994 | 45 min | 1 | 90 min | Order Total: 8 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | KBS-018 | 2526500091 | Unknown | W1 | 8 | 3 | 6 | 6/8 (75%) | 2 | SP1 | KVCALPPSP001 | 997.00 | 1.994 | 12 min | 1 | 24 min | Order Total: 8 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | KBS-018 | 2526500091 | Unknown | W1 | 8 | 3 | 6 | 6/8 (75%) | 2 | SP2 | KVCALPPSP002 | 997.00 | 1.994 | 12 min | 1 | 24 min | Order Total: 8 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | KBS-018 | 2526500091 | Unknown | W1 | 8 | 3 | 6 | 6/8 (75%) | 2 | SP3 | KVCALFPSP001 | 997.00 | 1.994 | 12 min | 1 | 24 min | Order Total: 8 units
2025-11-26 | 2025-11-26 | Wednesday | W1 | KBS-018 | 2526500091 | Unknown | W1 | 8 | 4 | 8 | 8/8 COMPLETE ✓ | 2 | MC1 | BVCAD30MC001 | 997.00 | 1.994 | 200 min | 1 | 400 min | Order Total: 8 units
2025-11-26 | 2025-11-26 | Wednesday | W1 | KBS-018 | 2526500091 | Unknown | W1 | 8 | 4 | 8 | 8/8 COMPLETE ✓ | 2 | MC2 | BVCABM1MC001 | 997.00 | 1.994 | 120 min | 1 | 240 min | Order Total: 8 units
2025-11-26 | 2025-11-26 | Wednesday | W1 | KBS-018 | 2526500091 | Unknown | W1 | 8 | 4 | 8 | 8/8 COMPLETE ✓ | 2 | MC3 | BVCAD30MC001 | 997.00 | 1.994 | 45 min | 1 | 90 min | Order Total: 8 units
2025-11-26 | 2025-11-26 | Wednesday | W1 | KBS-018 | 2526500091 | Unknown | W1 | 8 | 4 | 8 | 8/8 COMPLETE ✓ | 2 | SP1 | KVCALPPSP001 | 997.00 | 1.994 | 12 min | 1 | 24 min | Order Total: 8 units
2025-11-26 | 2025-11-26 | Wednesday | W1 | KBS-018 | 2526500091 | Unknown | W1 | 8 | 4 | 8 | 8/8 COMPLETE ✓ | 2 | SP2 | KVCALPPSP002 | 997.00 | 1.994 | 12 min | 1 | 24 min | Order Total: 8 units
2025-11-26 | 2025-11-26 | Wednesday | W1 | KBS-018 | 2526500091 | Unknown | W1 | 8 | 4 | 8 | 8/8 COMPLETE ✓ | 2 | SP3 | KVCALFPSP001 | 997.00 | 1.994 | 12 min | 1 | 24 min | Order Total: 8 units
2025-11-22 | 2025-11-22 | Saturday | W1 | KBS-017 | 2526500092 | Unknown | W1 | 1 | 1 | 1 | 1/1 COMPLETE ✓ | 1 | SP1 | KVCALPPSP001 | 1079.30 | 1.079 | 12 min | 1 | 12 min | Order Total: 1 units
2025-11-22 | 2025-11-22 | Saturday | W1 | KBS-017 | 2526500092 | Unknown | W1 | 1 | 1 | 1 | 1/1 COMPLETE ✓ | 1 | SP2 | KVCALPPSP002 | 1079.30 | 1.079 | 12 min | 1 | 12 min | Order Total: 1 units
2025-11-22 | 2025-11-22 | Saturday | W1 | KBS-017 | 2526500092 | Unknown | W1 | 1 | 1 | 1 | 1/1 COMPLETE ✓ | 1 | SP3 | KVCALFPSP001 | 1079.30 | 1.079 | 12 min | 1 | 12 min | Order Total: 1 units
2025-11-29 | 2025-11-29 | Saturday | W2 | KBS-017 | 2526500092 | Unknown | W1 | 1 | 1 | 1 | 1/1 COMPLETE ✓ | 1 | Grinding | KVCALHMGR001 | 1079.30 | 1.079 | 360 min | 1 | 360 min | Order Total: 1 units
2025-11-22 | 2025-11-22 | Saturday | W1 | KBS-018 | 2526500093 | Unknown | W1 | 16 | 1 | 4 | 4/16 (25%) | 4 | MC1 | BVCAD30MC001 | 997.00 | 3.988 | 200 min | 1 | 800 min | Order Total: 16 units
2025-11-22 | 2025-11-22 | Saturday | W1 | KBS-018 | 2526500093 | Unknown | W1 | 16 | 1 | 4 | 4/16 (25%) | 4 | MC2 | BVCABM1MC001 | 997.00 | 3.988 | 120 min | 1 | 480 min | Order Total: 16 units
2025-11-22 | 2025-11-22 | Saturday | W1 | KBS-018 | 2526500093 | Unknown | W1 | 16 | 1 | 4 | 4/16 (25%) | 4 | MC3 | BVCAD30MC001 | 997.00 | 3.988 | 45 min | 1 | 180 min | Order Total: 16 units
2025-11-22 | 2025-11-22 | Saturday | W1 | KBS-018 | 2526500093 | Unknown | W1 | 16 | 1 | 4 | 4/16 (25%) | 4 | SP1 | KVCALPPSP001 | 997.00 | 3.988 | 12 min | 1 | 48 min | Order Total: 16 units
2025-11-22 | 2025-11-22 | Saturday | W1 | KBS-018 | 2526500093 | Unknown | W1 | 16 | 1 | 4 | 4/16 (25%) | 4 | SP2 | KVCALPPSP002 | 997.00 | 3.988 | 12 min | 1 | 48 min | Order Total: 16 units
2025-11-22 | 2025-11-22 | Saturday | W1 | KBS-018 | 2526500093 | Unknown | W1 | 16 | 1 | 4 | 4/16 (25%) | 4 | SP3 | KVCALFPSP001 | 997.00 | 3.988 | 12 min | 1 | 48 min | Order Total: 16 units
2025-11-24 | 2025-11-24 | Monday | W1 | KBS-018 | 2526500093 | Unknown | W1 | 16 | 2 | 8 | 8/16 (50%) | 4 | MC1 | BVCAD30MC001 | 997.00 | 3.988 | 200 min | 1 | 800 min | Order Total: 16 units
2025-11-24 | 2025-11-24 | Monday | W1 | KBS-018 | 2526500093 | Unknown | W1 | 16 | 2 | 8 | 8/16 (50%) | 4 | MC2 | BVCABM1MC001 | 997.00 | 3.988 | 120 min | 1 | 480 min | Order Total: 16 units
2025-11-24 | 2025-11-24 | Monday | W1 | KBS-018 | 2526500093 | Unknown | W1 | 16 | 2 | 8 | 8/16 (50%) | 4 | MC3 | BVCAD30MC001 | 997.00 | 3.988 | 45 min | 1 | 180 min | Order Total: 16 units
2025-11-24 | 2025-11-24 | Monday | W1 | KBS-018 | 2526500093 | Unknown | W1 | 16 | 2 | 8 | 8/16 (50%) | 4 | SP1 | KVCALPPSP001 | 997.00 | 3.988 | 12 min | 1 | 48 min | Order Total: 16 units
2025-11-24 | 2025-11-24 | Monday | W1 | KBS-018 | 2526500093 | Unknown | W1 | 16 | 2 | 8 | 8/16 (50%) | 4 | SP2 | KVCALPPSP002 | 997.00 | 3.988 | 12 min | 1 | 48 min | Order Total: 16 units
2025-11-24 | 2025-11-24 | Monday | W1 | KBS-018 | 2526500093 | Unknown | W1 | 16 | 2 | 8 | 8/16 (50%) | 4 | SP3 | KVCALFPSP001 | 997.00 | 3.988 | 12 min | 1 | 48 min | Order Total: 16 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | KBS-018 | 2526500093 | Unknown | W1 | 16 | 3 | 12 | 12/16 (75%) | 4 | MC1 | BVCAD30MC001 | 997.00 | 3.988 | 200 min | 1 | 800 min | Order Total: 16 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | KBS-018 | 2526500093 | Unknown | W1 | 16 | 3 | 12 | 12/16 (75%) | 4 | MC2 | BVCABM1MC001 | 997.00 | 3.988 | 120 min | 1 | 480 min | Order Total: 16 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | KBS-018 | 2526500093 | Unknown | W1 | 16 | 3 | 12 | 12/16 (75%) | 4 | MC3 | BVCAD30MC001 | 997.00 | 3.988 | 45 min | 1 | 180 min | Order Total: 16 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | KBS-018 | 2526500093 | Unknown | W1 | 16 | 3 | 12 | 12/16 (75%) | 4 | SP1 | KVCALPPSP001 | 997.00 | 3.988 | 12 min | 1 | 48 min | Order Total: 16 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | KBS-018 | 2526500093 | Unknown | W1 | 16 | 3 | 12 | 12/16 (75%) | 4 | SP2 | KVCALPPSP002 | 997.00 | 3.988 | 12 min | 1 | 48 min | Order Total: 16 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | KBS-018 | 2526500093 | Unknown | W1 | 16 | 3 | 12 | 12/16 (75%) | 4 | SP3 | KVCALFPSP001 | 997.00 | 3.988 | 12 min | 1 | 48 min | Order Total: 16 units
2025-11-26 | 2025-11-26 | Wednesday | W1 | KBS-018 | 2526500093 | Unknown | W1 | 16 | 4 | 16 | 16/16 COMPLETE ✓ | 4 | MC1 | BVCAD30MC001 | 997.00 | 3.988 | 200 min | 1 | 800 min | Order Total: 16 units
2025-11-26 | 2025-11-26 | Wednesday | W1 | KBS-018 | 2526500093 | Unknown | W1 | 16 | 4 | 16 | 16/16 COMPLETE ✓ | 4 | MC2 | BVCABM1MC001 | 997.00 | 3.988 | 120 min | 1 | 480 min | Order Total: 16 units
2025-11-26 | 2025-11-26 | Wednesday | W1 | KBS-018 | 2526500093 | Unknown | W1 | 16 | 4 | 16 | 16/16 COMPLETE ✓ | 4 | MC3 | BVCAD30MC001 | 997.00 | 3.988 | 45 min | 1 | 180 min | Order Total: 16 units
2025-11-26 | 2025-11-26 | Wednesday | W1 | KBS-018 | 2526500093 | Unknown | W1 | 16 | 4 | 16 | 16/16 COMPLETE ✓ | 4 | SP1 | KVCALPPSP001 | 997.00 | 3.988 | 12 min | 1 | 48 min | Order Total: 16 units
2025-11-26 | 2025-11-26 | Wednesday | W1 | KBS-018 | 2526500093 | Unknown | W1 | 16 | 4 | 16 | 16/16 COMPLETE ✓ | 4 | SP2 | KVCALPPSP002 | 997.00 | 3.988 | 12 min | 1 | 48 min | Order Total: 16 units
2025-11-26 | 2025-11-26 | Wednesday | W1 | KBS-018 | 2526500093 | Unknown | W1 | 16 | 4 | 16 | 16/16 COMPLETE ✓ | 4 | SP3 | KVCALFPSP001 | 997.00 | 3.988 | 12 min | 1 | 48 min | Order Total: 16 units
2025-11-22 | 2025-11-22 | Saturday | W1 | KBS-017 | 2526500094 | Unknown | W1 | 15 | 1 | 3 | 3/15 (20%) | 3 | SP1 | KVCALPPSP001 | 1079.30 | 3.238 | 12 min | 1 | 36 min | Order Total: 15 units
2025-11-22 | 2025-11-22 | Saturday | W1 | KBS-017 | 2526500094 | Unknown | W1 | 15 | 1 | 3 | 3/15 (20%) | 3 | SP2 | KVCALPPSP002 | 1079.30 | 3.238 | 12 min | 1 | 36 min | Order Total: 15 units
2025-11-22 | 2025-11-22 | Saturday | W1 | KBS-017 | 2526500094 | Unknown | W1 | 15 | 1 | 3 | 3/15 (20%) | 3 | SP3 | KVCALFPSP001 | 1079.30 | 3.238 | 12 min | 1 | 36 min | Order Total: 15 units
2025-11-24 | 2025-11-24 | Monday | W1 | KBS-017 | 2526500094 | Unknown | W1 | 15 | 2 | 7 | 7/15 (46%) | 4 | SP1 | KVCALPPSP001 | 1079.30 | 4.317 | 12 min | 1 | 48 min | Order Total: 15 units
2025-11-24 | 2025-11-24 | Monday | W1 | KBS-017 | 2526500094 | Unknown | W1 | 15 | 2 | 7 | 7/15 (46%) | 4 | SP2 | KVCALPPSP002 | 1079.30 | 4.317 | 12 min | 1 | 48 min | Order Total: 15 units
2025-11-24 | 2025-11-24 | Monday | W1 | KBS-017 | 2526500094 | Unknown | W1 | 15 | 2 | 7 | 7/15 (46%) | 4 | SP3 | KVCALFPSP001 | 1079.30 | 4.317 | 12 min | 1 | 48 min | Order Total: 15 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | KBS-017 | 2526500094 | Unknown | W1 | 15 | 3 | 11 | 11/15 (73%) | 4 | SP1 | KVCALPPSP001 | 1079.30 | 4.317 | 12 min | 1 | 48 min | Order Total: 15 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | KBS-017 | 2526500094 | Unknown | W1 | 15 | 3 | 11 | 11/15 (73%) | 4 | SP2 | KVCALPPSP002 | 1079.30 | 4.317 | 12 min | 1 | 48 min | Order Total: 15 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | KBS-017 | 2526500094 | Unknown | W1 | 15 | 3 | 11 | 11/15 (73%) | 4 | SP3 | KVCALFPSP001 | 1079.30 | 4.317 | 12 min | 1 | 48 min | Order Total: 15 units
2025-11-26 | 2025-11-26 | Wednesday | W1 | KBS-017 | 2526500094 | Unknown | W1 | 15 | 4 | 15 | 15/15 COMPLETE ✓ | 4 | SP1 | KVCALPPSP001 | 1079.30 | 4.317 | 12 min | 1 | 48 min | Order Total: 15 units
2025-11-26 | 2025-11-26 | Wednesday | W1 | KBS-017 | 2526500094 | Unknown | W1 | 15 | 4 | 15 | 15/15 COMPLETE ✓ | 4 | SP2 | KVCALPPSP002 | 1079.30 | 4.317 | 12 min | 1 | 48 min | Order Total: 15 units
2025-11-26 | 2025-11-26 | Wednesday | W1 | KBS-017 | 2526500094 | Unknown | W1 | 15 | 4 | 15 | 15/15 COMPLETE ✓ | 4 | SP3 | KVCALFPSP001 | 1079.30 | 4.317 | 12 min | 1 | 48 min | Order Total: 15 units
2025-11-29 | 2025-11-29 | Saturday | W2 | KBS-017 | 2526500094 | Unknown | W1 | 15 | 1 | 3 | 3/15 (20%) | 3 | Grinding | KVCALHMGR001 | 1079.30 | 3.238 | 360 min | 1 | 1080 min | Order Total: 15 units
2025-12-01 | 2025-12-01 | Monday | W2 | KBS-017 | 2526500094 | Unknown | W1 | 15 | 2 | 7 | 7/15 (46%) | 4 | Grinding | KVCALHMGR001 | 1079.30 | 4.317 | 360 min | 1 | 1440 min | Order Total: 15 units
2025-12-02 | 2025-12-02 | Tuesday | W2 | KBS-017 | 2526500094 | Unknown | W1 | 15 | 3 | 11 | 11/15 (73%) | 4 | Grinding | KVCALHMGR001 | 1079.30 | 4.317 | 360 min | 1 | 1440 min | Order Total: 15 units
2025-12-03 | 2025-12-03 | Wednesday | W2 | KBS-017 | 2526500094 | Unknown | W1 | 15 | 4 | 15 | 15/15 COMPLETE ✓ | 4 | Grinding | KVCALHMGR001 | 1079.30 | 4.317 | 360 min | 1 | 1440 min | Order Total: 15 units
2025-11-22 | 2025-11-22 | Saturday | W1 | KBS-017 | 2526500095 | Unknown | W1 | 17 | 1 | 4 | 4/17 (23%) | 4 | SP1 | KVCALPPSP001 | 1079.30 | 4.317 | 12 min | 1 | 48 min | Order Total: 17 units
2025-11-22 | 2025-11-22 | Saturday | W1 | KBS-017 | 2526500095 | Unknown | W1 | 17 | 1 | 4 | 4/17 (23%) | 4 | SP2 | KVCALPPSP002 | 1079.30 | 4.317 | 12 min | 1 | 48 min | Order Total: 17 units
2025-11-22 | 2025-11-22 | Saturday | W1 | KBS-017 | 2526500095 | Unknown | W1 | 17 | 1 | 4 | 4/17 (23%) | 4 | SP3 | KVCALFPSP001 | 1079.30 | 4.317 | 12 min | 1 | 48 min | Order Total: 17 units
2025-11-24 | 2025-11-24 | Monday | W1 | KBS-017 | 2526500095 | Unknown | W1 | 17 | 2 | 8 | 8/17 (47%) | 4 | SP1 | KVCALPPSP001 | 1079.30 | 4.317 | 12 min | 1 | 48 min | Order Total: 17 units
2025-11-24 | 2025-11-24 | Monday | W1 | KBS-017 | 2526500095 | Unknown | W1 | 17 | 2 | 8 | 8/17 (47%) | 4 | SP2 | KVCALPPSP002 | 1079.30 | 4.317 | 12 min | 1 | 48 min | Order Total: 17 units
2025-11-24 | 2025-11-24 | Monday | W1 | KBS-017 | 2526500095 | Unknown | W1 | 17 | 2 | 8 | 8/17 (47%) | 4 | SP3 | KVCALFPSP001 | 1079.30 | 4.317 | 12 min | 1 | 48 min | Order Total: 17 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | KBS-017 | 2526500095 | Unknown | W1 | 17 | 3 | 12 | 12/17 (70%) | 4 | SP1 | KVCALPPSP001 | 1079.30 | 4.317 | 12 min | 1 | 48 min | Order Total: 17 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | KBS-017 | 2526500095 | Unknown | W1 | 17 | 3 | 12 | 12/17 (70%) | 4 | SP2 | KVCALPPSP002 | 1079.30 | 4.317 | 12 min | 1 | 48 min | Order Total: 17 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | KBS-017 | 2526500095 | Unknown | W1 | 17 | 3 | 12 | 12/17 (70%) | 4 | SP3 | KVCALFPSP001 | 1079.30 | 4.317 | 12 min | 1 | 48 min | Order Total: 17 units
2025-11-26 | 2025-11-26 | Wednesday | W1 | KBS-017 | 2526500095 | Unknown | W1 | 17 | 4 | 17 | 17/17 COMPLETE ✓ | 5 | SP1 | KVCALPPSP001 | 1079.30 | 5.396 | 12 min | 1 | 60 min | Order Total: 17 units
2025-11-26 | 2025-11-26 | Wednesday | W1 | KBS-017 | 2526500095 | Unknown | W1 | 17 | 4 | 17 | 17/17 COMPLETE ✓ | 5 | SP2 | KVCALPPSP002 | 1079.30 | 5.396 | 12 min | 1 | 60 min | Order Total: 17 units
2025-11-26 | 2025-11-26 | Wednesday | W1 | KBS-017 | 2526500095 | Unknown | W1 | 17 | 4 | 17 | 17/17 COMPLETE ✓ | 5 | SP3 | KVCALFPSP001 | 1079.30 | 5.396 | 12 min | 1 | 60 min | Order Total: 17 units
2025-11-29 | 2025-11-29 | Saturday | W2 | KBS-017 | 2526500095 | Unknown | W1 | 17 | 1 | 4 | 4/17 (23%) | 4 | Grinding | KVCALHMGR001 | 1079.30 | 4.317 | 360 min | 1 | 1440 min | Order Total: 17 units
2025-12-01 | 2025-12-01 | Monday | W2 | KBS-017 | 2526500095 | Unknown | W1 | 17 | 2 | 8 | 8/17 (47%) | 4 | Grinding | KVCALHMGR001 | 1079.30 | 4.317 | 360 min | 1 | 1440 min | Order Total: 17 units
2025-12-02 | 2025-12-02 | Tuesday | W2 | KBS-017 | 2526500095 | Unknown | W1 | 17 | 3 | 12 | 12/17 (70%) | 4 | Grinding | KVCALHMGR001 | 1079.30 | 4.317 | 360 min | 1 | 1440 min | Order Total: 17 units
2025-12-03 | 2025-12-03 | Wednesday | W2 | KBS-017 | 2526500095 | Unknown | W1 | 17 | 4 | 17 | 17/17 COMPLETE ✓ | 5 | Grinding | KVCALHMGR001 | 1079.30 | 5.396 | 360 min | 1 | 1800 min | Order Total: 17 units
2025-11-22 | 2025-11-22 | Saturday | W1 | KBS-017 | 2526500096 | Unknown | W1 | 14 | 1 | 3 | 3/14 (21%) | 3 | SP1 | KVCALPPSP001 | 1079.30 | 3.238 | 12 min | 1 | 36 min | Order Total: 14 units
2025-11-22 | 2025-11-22 | Saturday | W1 | KBS-017 | 2526500096 | Unknown | W1 | 14 | 1 | 3 | 3/14 (21%) | 3 | SP2 | KVCALPPSP002 | 1079.30 | 3.238 | 12 min | 1 | 36 min | Order Total: 14 units
2025-11-22 | 2025-11-22 | Saturday | W1 | KBS-017 | 2526500096 | Unknown | W1 | 14 | 1 | 3 | 3/14 (21%) | 3 | SP3 | KVCALFPSP001 | 1079.30 | 3.238 | 12 min | 1 | 36 min | Order Total: 14 units
2025-11-24 | 2025-11-24 | Monday | W1 | KBS-017 | 2526500096 | Unknown | W1 | 14 | 2 | 6 | 6/14 (42%) | 3 | SP1 | KVCALPPSP001 | 1079.30 | 3.238 | 12 min | 1 | 36 min | Order Total: 14 units
2025-11-24 | 2025-11-24 | Monday | W1 | KBS-017 | 2526500096 | Unknown | W1 | 14 | 2 | 6 | 6/14 (42%) | 3 | SP2 | KVCALPPSP002 | 1079.30 | 3.238 | 12 min | 1 | 36 min | Order Total: 14 units
2025-11-24 | 2025-11-24 | Monday | W1 | KBS-017 | 2526500096 | Unknown | W1 | 14 | 2 | 6 | 6/14 (42%) | 3 | SP3 | KVCALFPSP001 | 1079.30 | 3.238 | 12 min | 1 | 36 min | Order Total: 14 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | KBS-017 | 2526500096 | Unknown | W1 | 14 | 3 | 10 | 10/14 (71%) | 4 | SP1 | KVCALPPSP001 | 1079.30 | 4.317 | 12 min | 1 | 48 min | Order Total: 14 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | KBS-017 | 2526500096 | Unknown | W1 | 14 | 3 | 10 | 10/14 (71%) | 4 | SP2 | KVCALPPSP002 | 1079.30 | 4.317 | 12 min | 1 | 48 min | Order Total: 14 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | KBS-017 | 2526500096 | Unknown | W1 | 14 | 3 | 10 | 10/14 (71%) | 4 | SP3 | KVCALFPSP001 | 1079.30 | 4.317 | 12 min | 1 | 48 min | Order Total: 14 units
2025-11-26 | 2025-11-26 | Wednesday | W1 | KBS-017 | 2526500096 | Unknown | W1 | 14 | 4 | 14 | 14/14 COMPLETE ✓ | 4 | SP1 | KVCALPPSP001 | 1079.30 | 4.317 | 12 min | 1 | 48 min | Order Total: 14 units
2025-11-26 | 2025-11-26 | Wednesday | W1 | KBS-017 | 2526500096 | Unknown | W1 | 14 | 4 | 14 | 14/14 COMPLETE ✓ | 4 | SP2 | KVCALPPSP002 | 1079.30 | 4.317 | 12 min | 1 | 48 min | Order Total: 14 units
2025-11-26 | 2025-11-26 | Wednesday | W1 | KBS-017 | 2526500096 | Unknown | W1 | 14 | 4 | 14 | 14/14 COMPLETE ✓ | 4 | SP3 | KVCALFPSP001 | 1079.30 | 4.317 | 12 min | 1 | 48 min | Order Total: 14 units
2025-11-29 | 2025-11-29 | Saturday | W2 | KBS-017 | 2526500096 | Unknown | W1 | 14 | 1 | 3 | 3/14 (21%) | 3 | Grinding | KVCALHMGR001 | 1079.30 | 3.238 | 360 min | 1 | 1080 min | Order Total: 14 units
2025-12-01 | 2025-12-01 | Monday | W2 | KBS-017 | 2526500096 | Unknown | W1 | 14 | 2 | 6 | 6/14 (42%) | 3 | Grinding | KVCALHMGR001 | 1079.30 | 3.238 | 360 min | 1 | 1080 min | Order Total: 14 units
2025-12-02 | 2025-12-02 | Tuesday | W2 | KBS-017 | 2526500096 | Unknown | W1 | 14 | 3 | 10 | 10/14 (71%) | 4 | Grinding | KVCALHMGR001 | 1079.30 | 4.317 | 360 min | 1 | 1440 min | Order Total: 14 units
2025-12-03 | 2025-12-03 | Wednesday | W2 | KBS-017 | 2526500096 | Unknown | W1 | 14 | 4 | 14 | 14/14 COMPLETE ✓ | 4 | Grinding | KVCALHMGR001 | 1079.30 | 4.317 | 360 min | 1 | 1440 min | Order Total: 14 units
2025-11-22 | 2025-11-22 | Saturday | W1 | KBS-017 | 2526500097 | Unknown | W1 | 3 | 1 | 1 | 1/3 (33%) | 1 | SP1 | KVCALPPSP001 | 1079.30 | 1.079 | 12 min | 1 | 12 min | Order Total: 3 units
2025-11-22 | 2025-11-22 | Saturday | W1 | KBS-017 | 2526500097 | Unknown | W1 | 3 | 1 | 1 | 1/3 (33%) | 1 | SP2 | KVCALPPSP002 | 1079.30 | 1.079 | 12 min | 1 | 12 min | Order Total: 3 units
2025-11-22 | 2025-11-22 | Saturday | W1 | KBS-017 | 2526500097 | Unknown | W1 | 3 | 1 | 1 | 1/3 (33%) | 1 | SP3 | KVCALFPSP001 | 1079.30 | 1.079 | 12 min | 1 | 12 min | Order Total: 3 units
2025-11-24 | 2025-11-24 | Monday | W1 | KBS-017 | 2526500097 | Unknown | W1 | 3 | 2 | 2 | 2/3 (66%) | 1 | SP1 | KVCALPPSP001 | 1079.30 | 1.079 | 12 min | 1 | 12 min | Order Total: 3 units
2025-11-24 | 2025-11-24 | Monday | W1 | KBS-017 | 2526500097 | Unknown | W1 | 3 | 2 | 2 | 2/3 (66%) | 1 | SP2 | KVCALPPSP002 | 1079.30 | 1.079 | 12 min | 1 | 12 min | Order Total: 3 units
2025-11-24 | 2025-11-24 | Monday | W1 | KBS-017 | 2526500097 | Unknown | W1 | 3 | 2 | 2 | 2/3 (66%) | 1 | SP3 | KVCALFPSP001 | 1079.30 | 1.079 | 12 min | 1 | 12 min | Order Total: 3 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | KBS-017 | 2526500097 | Unknown | W1 | 3 | 3 | 3 | 3/3 COMPLETE ✓ | 1 | SP1 | KVCALPPSP001 | 1079.30 | 1.079 | 12 min | 1 | 12 min | Order Total: 3 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | KBS-017 | 2526500097 | Unknown | W1 | 3 | 3 | 3 | 3/3 COMPLETE ✓ | 1 | SP2 | KVCALPPSP002 | 1079.30 | 1.079 | 12 min | 1 | 12 min | Order Total: 3 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | KBS-017 | 2526500097 | Unknown | W1 | 3 | 3 | 3 | 3/3 COMPLETE ✓ | 1 | SP3 | KVCALFPSP001 | 1079.30 | 1.079 | 12 min | 1 | 12 min | Order Total: 3 units
2025-11-29 | 2025-11-29 | Saturday | W2 | KBS-017 | 2526500097 | Unknown | W1 | 3 | 1 | 1 | 1/3 (33%) | 1 | Grinding | KVCALHMGR001 | 1079.30 | 1.079 | 360 min | 1 | 360 min | Order Total: 3 units
2025-12-01 | 2025-12-01 | Monday | W2 | KBS-017 | 2526500097 | Unknown | W1 | 3 | 2 | 2 | 2/3 (66%) | 1 | Grinding | KVCALHMGR001 | 1079.30 | 1.079 | 360 min | 1 | 360 min | Order Total: 3 units
2025-12-02 | 2025-12-02 | Tuesday | W2 | KBS-017 | 2526500097 | Unknown | W1 | 3 | 3 | 3 | 3/3 COMPLETE ✓ | 1 | Grinding | KVCALHMGR001 | 1079.30 | 1.079 | 360 min | 1 | 360 min | Order Total: 3 units
2025-11-29 | 2025-11-29 | Saturday | W2 | KBS-017 | 2526500098 | Unknown | W2 | 22 | 1 | 22 | 22/22 COMPLETE ✓ | 22 | Casting | CS-KBS-017 | 1079.30 | 23.745 | 30 min | 1 | 660 min | Order Total: 22 units
2025-11-30 | 2025-11-29 | Sunday | W2 | KBS-017 | 2526500098 | Unknown | W2 | 22 | 1 | 22 | 22/22 COMPLETE ✓ | 22 | Cooling/Shakeout | N/A | 1079.30 | 23.745 | - | 1 | - | Order Total: 22 units
2025-11-29 | 2025-11-29 | Saturday | W2 | KBS-017 | 2526500099 | Unknown | W3 | 22 | 1 | 22 | 22/22 COMPLETE ✓ | 22 | MC1 | BVCAD30MC001 | 1079.30 | 23.745 | 200 min | 1 | 4400 min | Order Total: 22 units
2025-11-29 | 2025-11-29 | Saturday | W2 | KBS-017 | 2526500099 | Unknown | W3 | 22 | 1 | 22 | 22/22 COMPLETE ✓ | 22 | MC2 | BVCABM1MC001 | 1079.30 | 23.745 | 120 min | 1 | 2640 min | Order Total: 22 units
2025-11-29 | 2025-11-29 | Saturday | W2 | KBS-017 | 2526500099 | Unknown | W3 | 22 | 1 | 22 | 22/22 COMPLETE ✓ | 22 | MC3 | BVCAD30MC001 | 1079.30 | 23.745 | 45 min | 1 | 990 min | Order Total: 22 units
2025-12-06 | 2025-12-06 | Saturday | W3 | KBS-017 | 2526500099 | Unknown | W3 | 22 | 1 | 22 | 22/22 COMPLETE ✓ | 22 | SP1 | KVCALPPSP001 | 1079.30 | 23.745 | 12 min | 1 | 264 min | Order Total: 22 units
2025-12-06 | 2025-12-06 | Saturday | W3 | KBS-017 | 2526500099 | Unknown | W3 | 22 | 1 | 22 | 22/22 COMPLETE ✓ | 22 | SP2 | KVCALPPSP002 | 1079.30 | 23.745 | 12 min | 1 | 264 min | Order Total: 22 units
2025-12-06 | 2025-12-06 | Saturday | W3 | KBS-017 | 2526500099 | Unknown | W3 | 22 | 1 | 22 | 22/22 COMPLETE ✓ | 22 | SP3 | KVCALFPSP001 | 1079.30 | 23.745 | 12 min | 1 | 264 min | Order Total: 22 units
2025-12-06 | 2025-12-06 | Saturday | W3 | KBS-016 | 2526500104 | Unknown | W1 | 19 | 1 | 4 | 4/19 (21%) | 4 | Grinding | KVCALHMGR001 | 875.00 | 3.500 | 360 min | 1 | 1440 min | Order Total: 19 units
2025-12-06 | 2025-12-06 | Saturday | W3 | KBS-016 | 2526500104 | Unknown | W1 | 19 | 1 | 4 | 4/19 (21%) | 4 | SP1 | KVCALPPSP001 | 875.00 | 3.500 | 12 min | 1 | 48 min | Order Total: 19 units
2025-12-06 | 2025-12-06 | Saturday | W3 | KBS-016 | 2526500104 | Unknown | W1 | 19 | 1 | 4 | 4/19 (21%) | 4 | SP2 | KVCALPPSP002 | 875.00 | 3.500 | 12 min | 1 | 48 min | Order Total: 19 units
2025-12-06 | 2025-12-06 | Saturday | W3 | KBS-016 | 2526500104 | Unknown | W1 | 19 | 1 | 4 | 4/19 (21%) | 4 | SP3 | KVCALFPSP001 | 875.00 | 3.500 | 12 min | 1 | 48 min | Order Total: 19 units
2025-12-08 | 2025-12-08 | Monday | W3 | KBS-016 | 2526500104 | Unknown | W1 | 19 | 2 | 9 | 9/19 (47%) | 5 | Grinding | KVCALHMGR001 | 875.00 | 4.375 | 360 min | 1 | 1800 min | Order Total: 19 units
2025-12-08 | 2025-12-08 | Monday | W3 | KBS-016 | 2526500104 | Unknown | W1 | 19 | 2 | 9 | 9/19 (47%) | 5 | SP1 | KVCALPPSP001 | 875.00 | 4.375 | 12 min | 1 | 60 min | Order Total: 19 units
2025-12-08 | 2025-12-08 | Monday | W3 | KBS-016 | 2526500104 | Unknown | W1 | 19 | 2 | 9 | 9/19 (47%) | 5 | SP2 | KVCALPPSP002 | 875.00 | 4.375 | 12 min | 1 | 60 min | Order Total: 19 units
2025-12-08 | 2025-12-08 | Monday | W3 | KBS-016 | 2526500104 | Unknown | W1 | 19 | 2 | 9 | 9/19 (47%) | 5 | SP3 | KVCALFPSP001 | 875.00 | 4.375 | 12 min | 1 | 60 min | Order Total: 19 units
2025-12-09 | 2025-12-09 | Tuesday | W3 | KBS-016 | 2526500104 | Unknown | W1 | 19 | 3 | 14 | 14/19 (73%) | 5 | Grinding | KVCALHMGR001 | 875.00 | 4.375 | 360 min | 1 | 1800 min | Order Total: 19 units
2025-12-09 | 2025-12-09 | Tuesday | W3 | KBS-016 | 2526500104 | Unknown | W1 | 19 | 3 | 14 | 14/19 (73%) | 5 | SP1 | KVCALPPSP001 | 875.00 | 4.375 | 12 min | 1 | 60 min | Order Total: 19 units
2025-12-09 | 2025-12-09 | Tuesday | W3 | KBS-016 | 2526500104 | Unknown | W1 | 19 | 3 | 14 | 14/19 (73%) | 5 | SP2 | KVCALPPSP002 | 875.00 | 4.375 | 12 min | 1 | 60 min | Order Total: 19 units
2025-12-09 | 2025-12-09 | Tuesday | W3 | KBS-016 | 2526500104 | Unknown | W1 | 19 | 3 | 14 | 14/19 (73%) | 5 | SP3 | KVCALFPSP001 | 875.00 | 4.375 | 12 min | 1 | 60 min | Order Total: 19 units
2025-12-10 | 2025-12-10 | Wednesday | W3 | KBS-016 | 2526500104 | Unknown | W1 | 19 | 4 | 19 | 19/19 COMPLETE ✓ | 5 | Grinding | KVCALHMGR001 | 875.00 | 4.375 | 360 min | 1 | 1800 min | Order Total: 19 units
2025-12-10 | 2025-12-10 | Wednesday | W3 | KBS-016 | 2526500104 | Unknown | W1 | 19 | 4 | 19 | 19/19 COMPLETE ✓ | 5 | SP1 | KVCALPPSP001 | 875.00 | 4.375 | 12 min | 1 | 60 min | Order Total: 19 units
2025-12-10 | 2025-12-10 | Wednesday | W3 | KBS-016 | 2526500104 | Unknown | W1 | 19 | 4 | 19 | 19/19 COMPLETE ✓ | 5 | SP2 | KVCALPPSP002 | 875.00 | 4.375 | 12 min | 1 | 60 min | Order Total: 19 units
2025-12-10 | 2025-12-10 | Wednesday | W3 | KBS-016 | 2526500104 | Unknown | W1 | 19 | 4 | 19 | 19/19 COMPLETE ✓ | 5 | SP3 | KVCALFPSP001 | 875.00 | 4.375 | 12 min | 1 | 60 min | Order Total: 19 units
2025-12-06 | 2025-12-06 | Saturday | W3 | KBS-016 | 2526500105 | Unknown | W1 | 19 | 1 | 4 | 4/19 (21%) | 4 | Grinding | KVCALHMGR001 | 875.00 | 3.500 | 360 min | 1 | 1440 min | Order Total: 19 units
2025-12-06 | 2025-12-06 | Saturday | W3 | KBS-016 | 2526500105 | Unknown | W1 | 19 | 1 | 4 | 4/19 (21%) | 4 | SP1 | KVCALPPSP001 | 875.00 | 3.500 | 12 min | 1 | 48 min | Order Total: 19 units
2025-12-06 | 2025-12-06 | Saturday | W3 | KBS-016 | 2526500105 | Unknown | W1 | 19 | 1 | 4 | 4/19 (21%) | 4 | SP2 | KVCALPPSP002 | 875.00 | 3.500 | 12 min | 1 | 48 min | Order Total: 19 units
2025-12-06 | 2025-12-06 | Saturday | W3 | KBS-016 | 2526500105 | Unknown | W1 | 19 | 1 | 4 | 4/19 (21%) | 4 | SP3 | KVCALFPSP001 | 875.00 | 3.500 | 12 min | 1 | 48 min | Order Total: 19 units
2025-12-08 | 2025-12-08 | Monday | W3 | KBS-016 | 2526500105 | Unknown | W1 | 19 | 2 | 9 | 9/19 (47%) | 5 | Grinding | KVCALHMGR001 | 875.00 | 4.375 | 360 min | 1 | 1800 min | Order Total: 19 units
2025-12-08 | 2025-12-08 | Monday | W3 | KBS-016 | 2526500105 | Unknown | W1 | 19 | 2 | 9 | 9/19 (47%) | 5 | SP1 | KVCALPPSP001 | 875.00 | 4.375 | 12 min | 1 | 60 min | Order Total: 19 units
2025-12-08 | 2025-12-08 | Monday | W3 | KBS-016 | 2526500105 | Unknown | W1 | 19 | 2 | 9 | 9/19 (47%) | 5 | SP2 | KVCALPPSP002 | 875.00 | 4.375 | 12 min | 1 | 60 min | Order Total: 19 units
2025-12-08 | 2025-12-08 | Monday | W3 | KBS-016 | 2526500105 | Unknown | W1 | 19 | 2 | 9 | 9/19 (47%) | 5 | SP3 | KVCALFPSP001 | 875.00 | 4.375 | 12 min | 1 | 60 min | Order Total: 19 units
2025-12-09 | 2025-12-09 | Tuesday | W3 | KBS-016 | 2526500105 | Unknown | W1 | 19 | 3 | 14 | 14/19 (73%) | 5 | Grinding | KVCALHMGR001 | 875.00 | 4.375 | 360 min | 1 | 1800 min | Order Total: 19 units
2025-12-09 | 2025-12-09 | Tuesday | W3 | KBS-016 | 2526500105 | Unknown | W1 | 19 | 3 | 14 | 14/19 (73%) | 5 | SP1 | KVCALPPSP001 | 875.00 | 4.375 | 12 min | 1 | 60 min | Order Total: 19 units
2025-12-09 | 2025-12-09 | Tuesday | W3 | KBS-016 | 2526500105 | Unknown | W1 | 19 | 3 | 14 | 14/19 (73%) | 5 | SP2 | KVCALPPSP002 | 875.00 | 4.375 | 12 min | 1 | 60 min | Order Total: 19 units
2025-12-09 | 2025-12-09 | Tuesday | W3 | KBS-016 | 2526500105 | Unknown | W1 | 19 | 3 | 14 | 14/19 (73%) | 5 | SP3 | KVCALFPSP001 | 875.00 | 4.375 | 12 min | 1 | 60 min | Order Total: 19 units
2025-12-10 | 2025-12-10 | Wednesday | W3 | KBS-016 | 2526500105 | Unknown | W1 | 19 | 4 | 19 | 19/19 COMPLETE ✓ | 5 | Grinding | KVCALHMGR001 | 875.00 | 4.375 | 360 min | 1 | 1800 min | Order Total: 19 units
2025-12-10 | 2025-12-10 | Wednesday | W3 | KBS-016 | 2526500105 | Unknown | W1 | 19 | 4 | 19 | 19/19 COMPLETE ✓ | 5 | SP1 | KVCALPPSP001 | 875.00 | 4.375 | 12 min | 1 | 60 min | Order Total: 19 units
2025-12-10 | 2025-12-10 | Wednesday | W3 | KBS-016 | 2526500105 | Unknown | W1 | 19 | 4 | 19 | 19/19 COMPLETE ✓ | 5 | SP2 | KVCALPPSP002 | 875.00 | 4.375 | 12 min | 1 | 60 min | Order Total: 19 units
2025-12-10 | 2025-12-10 | Wednesday | W3 | KBS-016 | 2526500105 | Unknown | W1 | 19 | 4 | 19 | 19/19 COMPLETE ✓ | 5 | SP3 | KVCALFPSP001 | 875.00 | 4.375 | 12 min | 1 | 60 min | Order Total: 19 units
2025-11-29 | 2025-11-29 | Saturday | W2 | KBS-017 | 2526500106 | Unknown | W2 | 12 | 1 | 6 | 6/12 (50%) | 6 | Casting | CS-KBS-017 | 1079.30 | 6.476 | 30 min | 1 | 180 min | Order Total: 12 units
2025-11-30 | 2025-11-29 | Sunday | W2 | KBS-017 | 2526500106 | Unknown | W2 | 12 | 1 | 3 | 3/12 (25%) | 3 | Cooling/Shakeout | N/A | 1079.30 | 3.238 | - | 1 | - | Order Total: 12 units
2025-12-01 | 2025-12-01 | Monday | W2 | KBS-017 | 2526500106 | Unknown | W2 | 12 | 2 | 12 | 12/12 COMPLETE ✓ | 6 | Casting | CS-KBS-017 | 1079.30 | 6.476 | 30 min | 1 | 180 min | Order Total: 12 units
2025-12-02 | 2025-12-01 | Tuesday | W2 | KBS-017 | 2526500106 | Unknown | W2 | 12 | 2 | 6 | 6/12 (50%) | 3 | Cooling/Shakeout | N/A | 1079.30 | 3.238 | - | 1 | - | Order Total: 12 units
2025-12-03 | 2025-11-29 | Wednesday | W2 | KBS-017 | 2526500106 | Unknown | W2 | 12 | 3 | 9 | 9/12 (75%) | 3 | Cooling/Shakeout | N/A | 1079.30 | 3.238 | - | 1 | - | Order Total: 12 units
2025-12-04 | 2025-11-29 | Thursday | W2 | KBS-017 | 2526500106 | Unknown | W2 | 12 | 4 | 12 | 12/12 COMPLETE ✓ | 3 | Cooling/Shakeout | N/A | 1079.30 | 3.238 | - | 1 | - | Order Total: 12 units
2025-11-22 | 2025-11-22 | Saturday | W1 | KBS-014 | 2526500107 | Unknown | W1 | 24 | 1 | 24 | 24/24 COMPLETE ✓ | 24 | Casting | CS1-KBS-014 | 0.00 | 0.000 | 2 min | 1 | 60 min | Order Total: 24 units
2025-11-22 | 2025-11-22 | Saturday | W1 | KBS-014 | 2526500107 | Unknown | W1 | 24 | 1 | 24 | 24/24 COMPLETE ✓ | 24 | Grinding | GR1-KBS-014 | 0.00 | 0.000 | 1 min | 20 | 2 min | Order Total: 24 units
2025-11-22 | 2025-11-22 | Saturday | W1 | KBS-014 | 2526500107 | Unknown | W1 | 24 | 1 | 24 | 24/24 COMPLETE ✓ | 24 | MC1 | MC1-KBS-014 | 0.00 | 0.000 | 20 min | 50 | 20 min | Order Total: 24 units
2025-11-23 | 2025-11-22 | Sunday | W1 | KBS-014 | 2526500107 | Unknown | W1 | 24 | 1 | 24 | 24/24 COMPLETE ✓ | 24 | Cooling/Shakeout | N/A | 0.00 | 0.000 | - | 1 | - | Order Total: 24 units
2025-12-06 | 2025-11-22 | Saturday | W3 | KBS-014 | 2526500107 | Unknown | W1 | 24 | 1 | 24 | 24/24 COMPLETE ✓ | 24 | SP1 | SP1-KBS-014 | 0.00 | 0.000 | - | 10 | - | Order Total: 24 units
2025-11-22 | 2025-11-22 | Saturday | W1 | KBS-008 | 2526500109 | Unknown | W1 | 20 | 1 | 5 | 5/20 (25%) | 5 | Grinding | GR1-KBS-008 | 1020.00 | 5.100 | 120 min | 1 | 600 min | Order Total: 20 units
2025-11-22 | 2025-11-22 | Saturday | W1 | KBS-008 | 2526500109 | Unknown | W1 | 20 | 1 | 5 | 5/20 (25%) | 5 | MC1 | MC1-KBS-008 | 1020.00 | 5.100 | 45 min | 1 | 225 min | Order Total: 20 units
2025-11-22 | 2025-11-22 | Saturday | W1 | KBS-008 | 2526500109 | Unknown | W1 | 20 | 1 | 5 | 5/20 (25%) | 5 | SP1 | SP1-KBS-008 | 1020.00 | 5.100 | - | 1 | - | Order Total: 20 units
2025-11-22 | 2025-11-22 | Saturday | W1 | KBS-008 | 2526500109 | Unknown | W1 | 20 | 1 | 5 | 5/20 (25%) | 5 | SP2 | KVCALPPSP002 | 1020.00 | 5.100 | - | 1 | - | Order Total: 20 units
2025-11-22 | 2025-11-22 | Saturday | W1 | KBS-008 | 2526500109 | Unknown | W1 | 20 | 1 | 5 | 5/20 (25%) | 5 | SP3 | KVCALFPSP001 | 1020.00 | 5.100 | - | 1 | - | Order Total: 20 units
2025-11-24 | 2025-11-24 | Monday | W1 | KBS-008 | 2526500109 | Unknown | W1 | 20 | 2 | 10 | 10/20 (50%) | 5 | Grinding | GR1-KBS-008 | 1020.00 | 5.100 | 120 min | 1 | 600 min | Order Total: 20 units
2025-11-24 | 2025-11-24 | Monday | W1 | KBS-008 | 2526500109 | Unknown | W1 | 20 | 2 | 10 | 10/20 (50%) | 5 | MC1 | MC1-KBS-008 | 1020.00 | 5.100 | 45 min | 1 | 225 min | Order Total: 20 units
2025-11-24 | 2025-11-24 | Monday | W1 | KBS-008 | 2526500109 | Unknown | W1 | 20 | 2 | 10 | 10/20 (50%) | 5 | SP1 | SP1-KBS-008 | 1020.00 | 5.100 | - | 1 | - | Order Total: 20 units
2025-11-24 | 2025-11-24 | Monday | W1 | KBS-008 | 2526500109 | Unknown | W1 | 20 | 2 | 10 | 10/20 (50%) | 5 | SP2 | KVCALPPSP002 | 1020.00 | 5.100 | - | 1 | - | Order Total: 20 units
2025-11-24 | 2025-11-24 | Monday | W1 | KBS-008 | 2526500109 | Unknown | W1 | 20 | 2 | 10 | 10/20 (50%) | 5 | SP3 | KVCALFPSP001 | 1020.00 | 5.100 | - | 1 | - | Order Total: 20 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | KBS-008 | 2526500109 | Unknown | W1 | 20 | 3 | 15 | 15/20 (75%) | 5 | Grinding | GR1-KBS-008 | 1020.00 | 5.100 | 120 min | 1 | 600 min | Order Total: 20 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | KBS-008 | 2526500109 | Unknown | W1 | 20 | 3 | 15 | 15/20 (75%) | 5 | MC1 | MC1-KBS-008 | 1020.00 | 5.100 | 45 min | 1 | 225 min | Order Total: 20 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | KBS-008 | 2526500109 | Unknown | W1 | 20 | 3 | 15 | 15/20 (75%) | 5 | SP1 | SP1-KBS-008 | 1020.00 | 5.100 | - | 1 | - | Order Total: 20 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | KBS-008 | 2526500109 | Unknown | W1 | 20 | 3 | 15 | 15/20 (75%) | 5 | SP2 | KVCALPPSP002 | 1020.00 | 5.100 | - | 1 | - | Order Total: 20 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | KBS-008 | 2526500109 | Unknown | W1 | 20 | 3 | 15 | 15/20 (75%) | 5 | SP3 | KVCALFPSP001 | 1020.00 | 5.100 | - | 1 | - | Order Total: 20 units
2025-11-26 | 2025-11-26 | Wednesday | W1 | KBS-008 | 2526500109 | Unknown | W1 | 20 | 4 | 20 | 20/20 COMPLETE ✓ | 5 | Grinding | GR1-KBS-008 | 1020.00 | 5.100 | 120 min | 1 | 600 min | Order Total: 20 units
2025-11-26 | 2025-11-26 | Wednesday | W1 | KBS-008 | 2526500109 | Unknown | W1 | 20 | 4 | 20 | 20/20 COMPLETE ✓ | 5 | MC1 | MC1-KBS-008 | 1020.00 | 5.100 | 45 min | 1 | 225 min | Order Total: 20 units
2025-11-26 | 2025-11-26 | Wednesday | W1 | KBS-008 | 2526500109 | Unknown | W1 | 20 | 4 | 20 | 20/20 COMPLETE ✓ | 5 | SP1 | SP1-KBS-008 | 1020.00 | 5.100 | - | 1 | - | Order Total: 20 units
2025-11-26 | 2025-11-26 | Wednesday | W1 | KBS-008 | 2526500109 | Unknown | W1 | 20 | 4 | 20 | 20/20 COMPLETE ✓ | 5 | SP2 | KVCALPPSP002 | 1020.00 | 5.100 | - | 1 | - | Order Total: 20 units
2025-11-26 | 2025-11-26 | Wednesday | W1 | KBS-008 | 2526500109 | Unknown | W1 | 20 | 4 | 20 | 20/20 COMPLETE ✓ | 5 | SP3 | KVCALFPSP001 | 1020.00 | 5.100 | - | 1 | - | Order Total: 20 units
2025-11-22 | 2025-11-22 | Saturday | W1 | KBS-016 | 2526500110 | Unknown | W3 | 24 | 1 | 24 | 24/24 COMPLETE ✓ | 24 | Grinding | KVCALHMGR001 | 875.00 | 21.000 | 360 min | 1 | 8640 min | Order Total: 24 units
2025-11-22 | 2025-11-22 | Saturday | W1 | KBS-016 | 2526500110 | Unknown | W3 | 24 | 1 | 24 | 24/24 COMPLETE ✓ | 24 | MC1 | BVCAD30MC001 | 875.00 | 21.000 | 200 min | 1 | 4800 min | Order Total: 24 units
2025-11-22 | 2025-11-22 | Saturday | W1 | KBS-016 | 2526500110 | Unknown | W3 | 24 | 1 | 24 | 24/24 COMPLETE ✓ | 24 | MC2 | BVCABM1MC001 | 875.00 | 21.000 | 120 min | 1 | 2880 min | Order Total: 24 units
2025-11-22 | 2025-11-22 | Saturday | W1 | KBS-016 | 2526500110 | Unknown | W3 | 24 | 1 | 24 | 24/24 COMPLETE ✓ | 24 | MC3 | BVCAD30MC001 | 875.00 | 21.000 | 45 min | 1 | 1080 min | Order Total: 24 units
2025-11-22 | 2025-11-22 | Saturday | W1 | KBS-016 | 2526500110 | Unknown | W3 | 24 | 1 | 24 | 24/24 COMPLETE ✓ | 24 | SP1 | KVCALPPSP001 | 875.00 | 21.000 | 12 min | 1 | 288 min | Order Total: 24 units
2025-11-22 | 2025-11-22 | Saturday | W1 | KBS-016 | 2526500110 | Unknown | W3 | 24 | 1 | 24 | 24/24 COMPLETE ✓ | 24 | SP2 | KVCALPPSP002 | 875.00 | 21.000 | 12 min | 1 | 288 min | Order Total: 24 units
2025-11-22 | 2025-11-22 | Saturday | W1 | KBS-016 | 2526500110 | Unknown | W3 | 24 | 1 | 24 | 24/24 COMPLETE ✓ | 24 | SP3 | KVCALFPSP001 | 875.00 | 21.000 | 12 min | 1 | 288 min | Order Total: 24 units
2025-12-06 | 2025-12-06 | Saturday | W3 | KBS-017 | 2526500111 | Unknown | W4 | 20 | 1 | 5 | 5/20 (25%) | 5 | MC1 | BVCAD30MC001 | 1079.30 | 5.396 | 200 min | 1 | 1000 min | Order Total: 20 units
2025-12-06 | 2025-12-06 | Saturday | W3 | KBS-017 | 2526500111 | Unknown | W4 | 20 | 1 | 5 | 5/20 (25%) | 5 | MC2 | BVCABM1MC001 | 1079.30 | 5.396 | 120 min | 1 | 600 min | Order Total: 20 units
2025-12-06 | 2025-12-06 | Saturday | W3 | KBS-017 | 2526500111 | Unknown | W4 | 20 | 1 | 5 | 5/20 (25%) | 5 | MC3 | BVCAD30MC001 | 1079.30 | 5.396 | 45 min | 1 | 225 min | Order Total: 20 units
2025-12-08 | 2025-12-08 | Monday | W3 | KBS-017 | 2526500111 | Unknown | W4 | 20 | 2 | 10 | 10/20 (50%) | 5 | MC1 | BVCAD30MC001 | 1079.30 | 5.396 | 200 min | 1 | 1000 min | Order Total: 20 units
2025-12-08 | 2025-12-08 | Monday | W3 | KBS-017 | 2526500111 | Unknown | W4 | 20 | 2 | 10 | 10/20 (50%) | 5 | MC2 | BVCABM1MC001 | 1079.30 | 5.396 | 120 min | 1 | 600 min | Order Total: 20 units
2025-12-08 | 2025-12-08 | Monday | W3 | KBS-017 | 2526500111 | Unknown | W4 | 20 | 2 | 10 | 10/20 (50%) | 5 | MC3 | BVCAD30MC001 | 1079.30 | 5.396 | 45 min | 1 | 225 min | Order Total: 20 units
2025-12-09 | 2025-12-09 | Tuesday | W3 | KBS-017 | 2526500111 | Unknown | W4 | 20 | 3 | 15 | 15/20 (75%) | 5 | MC1 | BVCAD30MC001 | 1079.30 | 5.396 | 200 min | 1 | 1000 min | Order Total: 20 units
2025-12-09 | 2025-12-09 | Tuesday | W3 | KBS-017 | 2526500111 | Unknown | W4 | 20 | 3 | 15 | 15/20 (75%) | 5 | MC2 | BVCABM1MC001 | 1079.30 | 5.396 | 120 min | 1 | 600 min | Order Total: 20 units
2025-12-09 | 2025-12-09 | Tuesday | W3 | KBS-017 | 2526500111 | Unknown | W4 | 20 | 3 | 15 | 15/20 (75%) | 5 | MC3 | BVCAD30MC001 | 1079.30 | 5.396 | 45 min | 1 | 225 min | Order Total: 20 units
2025-12-10 | 2025-12-10 | Wednesday | W3 | KBS-017 | 2526500111 | Unknown | W4 | 20 | 4 | 20 | 20/20 COMPLETE ✓ | 5 | MC1 | BVCAD30MC001 | 1079.30 | 5.396 | 200 min | 1 | 1000 min | Order Total: 20 units
2025-12-10 | 2025-12-10 | Wednesday | W3 | KBS-017 | 2526500111 | Unknown | W4 | 20 | 4 | 20 | 20/20 COMPLETE ✓ | 5 | MC2 | BVCABM1MC001 | 1079.30 | 5.396 | 120 min | 1 | 600 min | Order Total: 20 units
2025-12-10 | 2025-12-10 | Wednesday | W3 | KBS-017 | 2526500111 | Unknown | W4 | 20 | 4 | 20 | 20/20 COMPLETE ✓ | 5 | MC3 | BVCAD30MC001 | 1079.30 | 5.396 | 45 min | 1 | 225 min | Order Total: 20 units
2025-12-06 | 2025-12-06 | Saturday | W3 | KBS-017 | 2526500112 | Unknown | W4 | 20 | 1 | 5 | 5/20 (25%) | 5 | MC1 | BVCAD30MC001 | 1079.30 | 5.396 | 200 min | 1 | 1000 min | Order Total: 20 units
2025-12-06 | 2025-12-06 | Saturday | W3 | KBS-017 | 2526500112 | Unknown | W4 | 20 | 1 | 5 | 5/20 (25%) | 5 | MC2 | BVCABM1MC001 | 1079.30 | 5.396 | 120 min | 1 | 600 min | Order Total: 20 units
2025-12-06 | 2025-12-06 | Saturday | W3 | KBS-017 | 2526500112 | Unknown | W4 | 20 | 1 | 5 | 5/20 (25%) | 5 | MC3 | BVCAD30MC001 | 1079.30 | 5.396 | 45 min | 1 | 225 min | Order Total: 20 units
2025-12-08 | 2025-12-08 | Monday | W3 | KBS-017 | 2526500112 | Unknown | W4 | 20 | 2 | 10 | 10/20 (50%) | 5 | MC1 | BVCAD30MC001 | 1079.30 | 5.396 | 200 min | 1 | 1000 min | Order Total: 20 units
2025-12-08 | 2025-12-08 | Monday | W3 | KBS-017 | 2526500112 | Unknown | W4 | 20 | 2 | 10 | 10/20 (50%) | 5 | MC2 | BVCABM1MC001 | 1079.30 | 5.396 | 120 min | 1 | 600 min | Order Total: 20 units
2025-12-08 | 2025-12-08 | Monday | W3 | KBS-017 | 2526500112 | Unknown | W4 | 20 | 2 | 10 | 10/20 (50%) | 5 | MC3 | BVCAD30MC001 | 1079.30 | 5.396 | 45 min | 1 | 225 min | Order Total: 20 units
2025-12-09 | 2025-12-09 | Tuesday | W3 | KBS-017 | 2526500112 | Unknown | W4 | 20 | 3 | 15 | 15/20 (75%) | 5 | MC1 | BVCAD30MC001 | 1079.30 | 5.396 | 200 min | 1 | 1000 min | Order Total: 20 units
2025-12-09 | 2025-12-09 | Tuesday | W3 | KBS-017 | 2526500112 | Unknown | W4 | 20 | 3 | 15 | 15/20 (75%) | 5 | MC2 | BVCABM1MC001 | 1079.30 | 5.396 | 120 min | 1 | 600 min | Order Total: 20 units
2025-12-09 | 2025-12-09 | Tuesday | W3 | KBS-017 | 2526500112 | Unknown | W4 | 20 | 3 | 15 | 15/20 (75%) | 5 | MC3 | BVCAD30MC001 | 1079.30 | 5.396 | 45 min | 1 | 225 min | Order Total: 20 units
2025-12-10 | 2025-12-10 | Wednesday | W3 | KBS-017 | 2526500112 | Unknown | W4 | 20 | 4 | 20 | 20/20 COMPLETE ✓ | 5 | MC1 | BVCAD30MC001 | 1079.30 | 5.396 | 200 min | 1 | 1000 min | Order Total: 20 units
2025-12-10 | 2025-12-10 | Wednesday | W3 | KBS-017 | 2526500112 | Unknown | W4 | 20 | 4 | 20 | 20/20 COMPLETE ✓ | 5 | MC2 | BVCABM1MC001 | 1079.30 | 5.396 | 120 min | 1 | 600 min | Order Total: 20 units
2025-12-10 | 2025-12-10 | Wednesday | W3 | KBS-017 | 2526500112 | Unknown | W4 | 20 | 4 | 20 | 20/20 COMPLETE ✓ | 5 | MC3 | BVCAD30MC001 | 1079.30 | 5.396 | 45 min | 1 | 225 min | Order Total: 20 units
2025-11-22 | 2025-11-22 | Saturday | W1 | KBS-017 | 2526500113 | Unknown | W5 | 20 | 1 | 5 | 5/20 (25%) | 5 | Grinding | KVCALHMGR001 | 1079.30 | 5.396 | 360 min | 1 | 1800 min | Order Total: 20 units
2025-11-22 | 2025-11-22 | Saturday | W1 | KBS-017 | 2526500113 | Unknown | W5 | 20 | 1 | 5 | 5/20 (25%) | 5 | MC1 | BVCAD30MC001 | 1079.30 | 5.396 | 200 min | 1 | 1000 min | Order Total: 20 units
2025-11-22 | 2025-11-22 | Saturday | W1 | KBS-017 | 2526500113 | Unknown | W5 | 20 | 1 | 5 | 5/20 (25%) | 5 | MC2 | BVCABM1MC001 | 1079.30 | 5.396 | 120 min | 1 | 600 min | Order Total: 20 units
2025-11-22 | 2025-11-22 | Saturday | W1 | KBS-017 | 2526500113 | Unknown | W5 | 20 | 1 | 5 | 5/20 (25%) | 5 | MC3 | BVCAD30MC001 | 1079.30 | 5.396 | 45 min | 1 | 225 min | Order Total: 20 units
2025-11-24 | 2025-11-24 | Monday | W1 | KBS-017 | 2526500113 | Unknown | W5 | 20 | 2 | 10 | 10/20 (50%) | 5 | Grinding | KVCALHMGR001 | 1079.30 | 5.396 | 360 min | 1 | 1800 min | Order Total: 20 units
2025-11-24 | 2025-11-24 | Monday | W1 | KBS-017 | 2526500113 | Unknown | W5 | 20 | 2 | 10 | 10/20 (50%) | 5 | MC1 | BVCAD30MC001 | 1079.30 | 5.396 | 200 min | 1 | 1000 min | Order Total: 20 units
2025-11-24 | 2025-11-24 | Monday | W1 | KBS-017 | 2526500113 | Unknown | W5 | 20 | 2 | 10 | 10/20 (50%) | 5 | MC2 | BVCABM1MC001 | 1079.30 | 5.396 | 120 min | 1 | 600 min | Order Total: 20 units
2025-11-24 | 2025-11-24 | Monday | W1 | KBS-017 | 2526500113 | Unknown | W5 | 20 | 2 | 10 | 10/20 (50%) | 5 | MC3 | BVCAD30MC001 | 1079.30 | 5.396 | 45 min | 1 | 225 min | Order Total: 20 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | KBS-017 | 2526500113 | Unknown | W5 | 20 | 3 | 15 | 15/20 (75%) | 5 | Grinding | KVCALHMGR001 | 1079.30 | 5.396 | 360 min | 1 | 1800 min | Order Total: 20 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | KBS-017 | 2526500113 | Unknown | W5 | 20 | 3 | 15 | 15/20 (75%) | 5 | MC1 | BVCAD30MC001 | 1079.30 | 5.396 | 200 min | 1 | 1000 min | Order Total: 20 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | KBS-017 | 2526500113 | Unknown | W5 | 20 | 3 | 15 | 15/20 (75%) | 5 | MC2 | BVCABM1MC001 | 1079.30 | 5.396 | 120 min | 1 | 600 min | Order Total: 20 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | KBS-017 | 2526500113 | Unknown | W5 | 20 | 3 | 15 | 15/20 (75%) | 5 | MC3 | BVCAD30MC001 | 1079.30 | 5.396 | 45 min | 1 | 225 min | Order Total: 20 units
2025-11-26 | 2025-11-26 | Wednesday | W1 | KBS-017 | 2526500113 | Unknown | W5 | 20 | 4 | 20 | 20/20 COMPLETE ✓ | 5 | Grinding | KVCALHMGR001 | 1079.30 | 5.396 | 360 min | 1 | 1800 min | Order Total: 20 units
2025-11-26 | 2025-11-26 | Wednesday | W1 | KBS-017 | 2526500113 | Unknown | W5 | 20 | 4 | 20 | 20/20 COMPLETE ✓ | 5 | MC1 | BVCAD30MC001 | 1079.30 | 5.396 | 200 min | 1 | 1000 min | Order Total: 20 units
2025-11-26 | 2025-11-26 | Wednesday | W1 | KBS-017 | 2526500113 | Unknown | W5 | 20 | 4 | 20 | 20/20 COMPLETE ✓ | 5 | MC2 | BVCABM1MC001 | 1079.30 | 5.396 | 120 min | 1 | 600 min | Order Total: 20 units
2025-11-26 | 2025-11-26 | Wednesday | W1 | KBS-017 | 2526500113 | Unknown | W5 | 20 | 4 | 20 | 20/20 COMPLETE ✓ | 5 | MC3 | BVCAD30MC001 | 1079.30 | 5.396 | 45 min | 1 | 225 min | Order Total: 20 units
2025-11-29 | 2025-11-29 | Saturday | W2 | KBS-017 | 2526500113 | Unknown | W5 | 20 | 1 | 5 | 5/20 (25%) | 5 | SP1 | KVCALPPSP001 | 1079.30 | 5.396 | 12 min | 1 | 60 min | Order Total: 20 units
2025-11-29 | 2025-11-29 | Saturday | W2 | KBS-017 | 2526500113 | Unknown | W5 | 20 | 1 | 5 | 5/20 (25%) | 5 | SP2 | KVCALPPSP002 | 1079.30 | 5.396 | 12 min | 1 | 60 min | Order Total: 20 units
2025-11-29 | 2025-11-29 | Saturday | W2 | KBS-017 | 2526500113 | Unknown | W5 | 20 | 1 | 5 | 5/20 (25%) | 5 | SP3 | KVCALFPSP001 | 1079.30 | 5.396 | 12 min | 1 | 60 min | Order Total: 20 units
2025-12-01 | 2025-12-01 | Monday | W2 | KBS-017 | 2526500113 | Unknown | W5 | 20 | 2 | 10 | 10/20 (50%) | 5 | SP1 | KVCALPPSP001 | 1079.30 | 5.396 | 12 min | 1 | 60 min | Order Total: 20 units
2025-12-01 | 2025-12-01 | Monday | W2 | KBS-017 | 2526500113 | Unknown | W5 | 20 | 2 | 10 | 10/20 (50%) | 5 | SP2 | KVCALPPSP002 | 1079.30 | 5.396 | 12 min | 1 | 60 min | Order Total: 20 units
2025-12-01 | 2025-12-01 | Monday | W2 | KBS-017 | 2526500113 | Unknown | W5 | 20 | 2 | 10 | 10/20 (50%) | 5 | SP3 | KVCALFPSP001 | 1079.30 | 5.396 | 12 min | 1 | 60 min | Order Total: 20 units
2025-12-02 | 2025-12-02 | Tuesday | W2 | KBS-017 | 2526500113 | Unknown | W5 | 20 | 3 | 15 | 15/20 (75%) | 5 | SP1 | KVCALPPSP001 | 1079.30 | 5.396 | 12 min | 1 | 60 min | Order Total: 20 units
2025-12-02 | 2025-12-02 | Tuesday | W2 | KBS-017 | 2526500113 | Unknown | W5 | 20 | 3 | 15 | 15/20 (75%) | 5 | SP2 | KVCALPPSP002 | 1079.30 | 5.396 | 12 min | 1 | 60 min | Order Total: 20 units
2025-12-02 | 2025-12-02 | Tuesday | W2 | KBS-017 | 2526500113 | Unknown | W5 | 20 | 3 | 15 | 15/20 (75%) | 5 | SP3 | KVCALFPSP001 | 1079.30 | 5.396 | 12 min | 1 | 60 min | Order Total: 20 units
2025-12-03 | 2025-12-03 | Wednesday | W2 | KBS-017 | 2526500113 | Unknown | W5 | 20 | 4 | 20 | 20/20 COMPLETE ✓ | 5 | SP1 | KVCALPPSP001 | 1079.30 | 5.396 | 12 min | 1 | 60 min | Order Total: 20 units
2025-12-03 | 2025-12-03 | Wednesday | W2 | KBS-017 | 2526500113 | Unknown | W5 | 20 | 4 | 20 | 20/20 COMPLETE ✓ | 5 | SP2 | KVCALPPSP002 | 1079.30 | 5.396 | 12 min | 1 | 60 min | Order Total: 20 units
2025-12-03 | 2025-12-03 | Wednesday | W2 | KBS-017 | 2526500113 | Unknown | W5 | 20 | 4 | 20 | 20/20 COMPLETE ✓ | 5 | SP3 | KVCALFPSP001 | 1079.30 | 5.396 | 12 min | 1 | 60 min | Order Total: 20 units
2025-11-22 | 2025-11-22 | Saturday | W1 | KBS-009 | 2526500114 | Unknown | W1 | 18 | 1 | 4 | 4/18 (22%) | 4 | Grinding | GR1-KBS-009 | 1232.00 | 4.928 | 210 min | 1 | 840 min | Order Total: 18 units
2025-11-24 | 2025-11-24 | Monday | W1 | KBS-009 | 2526500114 | Unknown | W1 | 18 | 2 | 8 | 8/18 (44%) | 4 | Grinding | GR1-KBS-009 | 1232.00 | 4.928 | 210 min | 1 | 840 min | Order Total: 18 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | KBS-009 | 2526500114 | Unknown | W1 | 18 | 3 | 13 | 13/18 (72%) | 5 | Grinding | GR1-KBS-009 | 1232.00 | 6.160 | 210 min | 1 | 1050 min | Order Total: 18 units
2025-11-26 | 2025-11-26 | Wednesday | W1 | KBS-009 | 2526500114 | Unknown | W1 | 18 | 4 | 18 | 18/18 COMPLETE ✓ | 5 | Grinding | GR1-KBS-009 | 1232.00 | 6.160 | 210 min | 1 | 1050 min | Order Total: 18 units
2025-11-22 | 2025-12-20 | Saturday | W1 | KBS-010 | 2526500115 | Unknown | W1 | 8 | 1 | 2 | 2/8 (25%) | 2 | MC1 | MC1-KBS-010 | 1443.00 | 2.886 | 45 min | 1 | 90 min | Order Total: 8 units
2025-11-22 | 2025-12-20 | Saturday | W1 | KBS-010 | 2526500115 | Unknown | W1 | 8 | 1 | 2 | 2/8 (25%) | 2 | SP1 | SP1-KBS-010 | 1443.00 | 2.886 | - | 1 | - | Order Total: 8 units
2025-11-22 | 2025-12-20 | Saturday | W1 | KBS-010 | 2526500115 | Unknown | W1 | 8 | 1 | 2 | 2/8 (25%) | 2 | SP2 | KVCALPPSP002 | 1443.00 | 2.886 | - | 1 | - | Order Total: 8 units
2025-11-22 | 2025-12-20 | Saturday | W1 | KBS-010 | 2526500115 | Unknown | W1 | 8 | 1 | 2 | 2/8 (25%) | 2 | SP3 | KVCALFPSP001 | 1443.00 | 2.886 | - | 1 | - | Order Total: 8 units
2025-11-24 | 2025-12-22 | Monday | W1 | KBS-010 | 2526500115 | Unknown | W1 | 8 | 2 | 4 | 4/8 (50%) | 2 | MC1 | MC1-KBS-010 | 1443.00 | 2.886 | 45 min | 1 | 90 min | Order Total: 8 units
2025-11-24 | 2025-12-22 | Monday | W1 | KBS-010 | 2526500115 | Unknown | W1 | 8 | 2 | 4 | 4/8 (50%) | 2 | SP1 | SP1-KBS-010 | 1443.00 | 2.886 | - | 1 | - | Order Total: 8 units
2025-11-24 | 2025-12-22 | Monday | W1 | KBS-010 | 2526500115 | Unknown | W1 | 8 | 2 | 4 | 4/8 (50%) | 2 | SP2 | KVCALPPSP002 | 1443.00 | 2.886 | - | 1 | - | Order Total: 8 units
2025-11-24 | 2025-12-22 | Monday | W1 | KBS-010 | 2526500115 | Unknown | W1 | 8 | 2 | 4 | 4/8 (50%) | 2 | SP3 | KVCALFPSP001 | 1443.00 | 2.886 | - | 1 | - | Order Total: 8 units
2025-11-25 | 2025-12-20 | Tuesday | W1 | KBS-010 | 2526500115 | Unknown | W1 | 8 | 3 | 6 | 6/8 (75%) | 2 | MC1 | MC1-KBS-010 | 1443.00 | 2.886 | 45 min | 1 | 90 min | Order Total: 8 units
2025-11-25 | 2025-12-20 | Tuesday | W1 | KBS-010 | 2526500115 | Unknown | W1 | 8 | 3 | 6 | 6/8 (75%) | 2 | SP1 | SP1-KBS-010 | 1443.00 | 2.886 | - | 1 | - | Order Total: 8 units
2025-11-25 | 2025-12-20 | Tuesday | W1 | KBS-010 | 2526500115 | Unknown | W1 | 8 | 3 | 6 | 6/8 (75%) | 2 | SP2 | KVCALPPSP002 | 1443.00 | 2.886 | - | 1 | - | Order Total: 8 units
2025-11-25 | 2025-12-20 | Tuesday | W1 | KBS-010 | 2526500115 | Unknown | W1 | 8 | 3 | 6 | 6/8 (75%) | 2 | SP3 | KVCALFPSP001 | 1443.00 | 2.886 | - | 1 | - | Order Total: 8 units
2025-11-26 | 2025-12-20 | Wednesday | W1 | KBS-010 | 2526500115 | Unknown | W1 | 8 | 4 | 8 | 8/8 COMPLETE ✓ | 2 | MC1 | MC1-KBS-010 | 1443.00 | 2.886 | 45 min | 1 | 90 min | Order Total: 8 units
2025-11-26 | 2025-12-20 | Wednesday | W1 | KBS-010 | 2526500115 | Unknown | W1 | 8 | 4 | 8 | 8/8 COMPLETE ✓ | 2 | SP1 | SP1-KBS-010 | 1443.00 | 2.886 | - | 1 | - | Order Total: 8 units
2025-11-26 | 2025-12-20 | Wednesday | W1 | KBS-010 | 2526500115 | Unknown | W1 | 8 | 4 | 8 | 8/8 COMPLETE ✓ | 2 | SP2 | KVCALPPSP002 | 1443.00 | 2.886 | - | 1 | - | Order Total: 8 units
2025-11-26 | 2025-12-20 | Wednesday | W1 | KBS-010 | 2526500115 | Unknown | W1 | 8 | 4 | 8 | 8/8 COMPLETE ✓ | 2 | SP3 | KVCALFPSP001 | 1443.00 | 2.886 | - | 1 | - | Order Total: 8 units
2025-12-20 | 2025-12-20 | Saturday | W5 | KBS-010 | 2526500115 | Unknown | W1 | 8 | 1 | 4 | 4/8 (50%) | 4 | Casting | CS1-KBS-010 | 1443.00 | 5.772 | 25 min | 1 | 100 min | Order Total: 8 units
2025-12-21 | 2025-12-20 | Sunday | W5 | KBS-010 | 2526500115 | Unknown | W1 | 8 | 1 | 2 | 2/8 (25%) | 2 | Cooling/Shakeout | N/A | 1443.00 | 2.886 | - | 1 | - | Order Total: 8 units
2025-12-22 | 2025-12-22 | Monday | W5 | KBS-010 | 2526500115 | Unknown | W1 | 8 | 2 | 8 | 8/8 COMPLETE ✓ | 4 | Casting | CS1-KBS-010 | 1443.00 | 5.772 | 25 min | 1 | 100 min | Order Total: 8 units
2025-12-23 | 2025-12-22 | Tuesday | W5 | KBS-010 | 2526500115 | Unknown | W1 | 8 | 2 | 4 | 4/8 (50%) | 2 | Cooling/Shakeout | N/A | 1443.00 | 2.886 | - | 1 | - | Order Total: 8 units
2025-12-24 | 2025-12-20 | Wednesday | W5 | KBS-010 | 2526500115 | Unknown | W1 | 8 | 3 | 6 | 6/8 (75%) | 2 | Cooling/Shakeout | N/A | 1443.00 | 2.886 | - | 1 | - | Order Total: 8 units
2025-12-25 | 2025-12-20 | Thursday | W5 | KBS-010 | 2526500115 | Unknown | W1 | 8 | 4 | 8 | 8/8 COMPLETE ✓ | 2 | Cooling/Shakeout | N/A | 1443.00 | 2.886 | - | 1 | - | Order Total: 8 units
2025-11-22 | 2025-11-29 | Saturday | W1 | KBS-011 | 2526500116 | Unknown | W1 | 13 | 1 | 3 | 3/13 (23%) | 3 | SP1 | KVCALPPSP001 | 1652.00 | 4.956 | 12 min | 1 | 36 min | Order Total: 13 units
2025-11-22 | 2025-11-29 | Saturday | W1 | KBS-011 | 2526500116 | Unknown | W1 | 13 | 1 | 3 | 3/13 (23%) | 3 | SP2 | KVCALPPSP002 | 1652.00 | 4.956 | 12 min | 1 | 36 min | Order Total: 13 units
2025-11-22 | 2025-11-29 | Saturday | W1 | KBS-011 | 2526500116 | Unknown | W1 | 13 | 1 | 3 | 3/13 (23%) | 3 | SP3 | KVCALFPSP001 | 1652.00 | 4.956 | 12 min | 1 | 36 min | Order Total: 13 units
2025-11-24 | 2025-12-01 | Monday | W1 | KBS-011 | 2526500116 | Unknown | W1 | 13 | 2 | 6 | 6/13 (46%) | 3 | SP1 | KVCALPPSP001 | 1652.00 | 4.956 | 12 min | 1 | 36 min | Order Total: 13 units
2025-11-24 | 2025-12-01 | Monday | W1 | KBS-011 | 2526500116 | Unknown | W1 | 13 | 2 | 6 | 6/13 (46%) | 3 | SP2 | KVCALPPSP002 | 1652.00 | 4.956 | 12 min | 1 | 36 min | Order Total: 13 units
2025-11-24 | 2025-12-01 | Monday | W1 | KBS-011 | 2526500116 | Unknown | W1 | 13 | 2 | 6 | 6/13 (46%) | 3 | SP3 | KVCALFPSP001 | 1652.00 | 4.956 | 12 min | 1 | 36 min | Order Total: 13 units
2025-11-25 | 2025-12-02 | Tuesday | W1 | KBS-011 | 2526500116 | Unknown | W1 | 13 | 3 | 9 | 9/13 (69%) | 3 | SP1 | KVCALPPSP001 | 1652.00 | 4.956 | 12 min | 1 | 36 min | Order Total: 13 units
2025-11-25 | 2025-12-02 | Tuesday | W1 | KBS-011 | 2526500116 | Unknown | W1 | 13 | 3 | 9 | 9/13 (69%) | 3 | SP2 | KVCALPPSP002 | 1652.00 | 4.956 | 12 min | 1 | 36 min | Order Total: 13 units
2025-11-25 | 2025-12-02 | Tuesday | W1 | KBS-011 | 2526500116 | Unknown | W1 | 13 | 3 | 9 | 9/13 (69%) | 3 | SP3 | KVCALFPSP001 | 1652.00 | 4.956 | 12 min | 1 | 36 min | Order Total: 13 units
2025-11-26 | 2025-12-03 | Wednesday | W1 | KBS-011 | 2526500116 | Unknown | W1 | 13 | 4 | 13 | 13/13 COMPLETE ✓ | 4 | SP1 | KVCALPPSP001 | 1652.00 | 6.608 | 12 min | 1 | 48 min | Order Total: 13 units
2025-11-26 | 2025-12-03 | Wednesday | W1 | KBS-011 | 2526500116 | Unknown | W1 | 13 | 4 | 13 | 13/13 COMPLETE ✓ | 4 | SP2 | KVCALPPSP002 | 1652.00 | 6.608 | 12 min | 1 | 48 min | Order Total: 13 units
2025-11-26 | 2025-12-03 | Wednesday | W1 | KBS-011 | 2526500116 | Unknown | W1 | 13 | 4 | 13 | 13/13 COMPLETE ✓ | 4 | SP3 | KVCALFPSP001 | 1652.00 | 6.608 | 12 min | 1 | 48 min | Order Total: 13 units
2025-11-29 | 2025-11-29 | Saturday | W2 | KBS-011 | 2526500116 | Unknown | W1 | 13 | 1 | 3 | 3/13 (23%) | 3 | Casting | CS1-KBS-011 | 1652.00 | 4.956 | 25 min | 1 | 75 min | Order Total: 13 units
2025-11-29 | 2025-11-29 | Saturday | W2 | KBS-011 | 2526500116 | Unknown | W1 | 13 | 1 | 3 | 3/13 (23%) | 3 | MC1 | KVCAD40MC001 | 1652.00 | 4.956 | 90 min | 1 | 270 min | Order Total: 13 units
2025-11-30 | 2025-11-29 | Sunday | W2 | KBS-011 | 2526500116 | Unknown | W1 | 13 | 1 | 3 | 3/13 (23%) | 3 | Cooling/Shakeout | N/A | 1652.00 | 4.956 | - | 1 | - | Order Total: 13 units
2025-12-01 | 2025-12-01 | Monday | W2 | KBS-011 | 2526500116 | Unknown | W1 | 13 | 2 | 6 | 6/13 (46%) | 3 | Casting | CS1-KBS-011 | 1652.00 | 4.956 | 25 min | 1 | 75 min | Order Total: 13 units
2025-12-01 | 2025-12-01 | Monday | W2 | KBS-011 | 2526500116 | Unknown | W1 | 13 | 2 | 6 | 6/13 (46%) | 3 | MC1 | KVCAD40MC001 | 1652.00 | 4.956 | 90 min | 1 | 270 min | Order Total: 13 units
2025-12-02 | 2025-12-02 | Tuesday | W2 | KBS-011 | 2526500116 | Unknown | W1 | 13 | 3 | 9 | 9/13 (69%) | 3 | Casting | CS1-KBS-011 | 1652.00 | 4.956 | 25 min | 1 | 75 min | Order Total: 13 units
2025-12-02 | 2025-12-01 | Tuesday | W2 | KBS-011 | 2526500116 | Unknown | W1 | 13 | 2 | 6 | 6/13 (46%) | 3 | Cooling/Shakeout | N/A | 1652.00 | 4.956 | - | 1 | - | Order Total: 13 units
2025-12-02 | 2025-12-02 | Tuesday | W2 | KBS-011 | 2526500116 | Unknown | W1 | 13 | 3 | 9 | 9/13 (69%) | 3 | MC1 | KVCAD40MC001 | 1652.00 | 4.956 | 90 min | 1 | 270 min | Order Total: 13 units
2025-12-03 | 2025-12-03 | Wednesday | W2 | KBS-011 | 2526500116 | Unknown | W1 | 13 | 4 | 13 | 13/13 COMPLETE ✓ | 4 | Casting | CS1-KBS-011 | 1652.00 | 6.608 | 25 min | 1 | 100 min | Order Total: 13 units
2025-12-03 | 2025-12-02 | Wednesday | W2 | KBS-011 | 2526500116 | Unknown | W1 | 13 | 3 | 9 | 9/13 (69%) | 3 | Cooling/Shakeout | N/A | 1652.00 | 4.956 | - | 1 | - | Order Total: 13 units
2025-12-03 | 2025-12-03 | Wednesday | W2 | KBS-011 | 2526500116 | Unknown | W1 | 13 | 4 | 13 | 13/13 COMPLETE ✓ | 4 | MC1 | KVCAD40MC001 | 1652.00 | 6.608 | 90 min | 1 | 360 min | Order Total: 13 units
2025-12-04 | 2025-12-03 | Thursday | W2 | KBS-011 | 2526500116 | Unknown | W1 | 13 | 4 | 13 | 13/13 COMPLETE ✓ | 4 | Cooling/Shakeout | N/A | 1652.00 | 6.608 | - | 1 | - | Order Total: 13 units
2025-11-29 | 2025-11-29 | Saturday | W2 | KBS-009 | 2526500117 | Unknown | W5 | 2 | 1 | 1 | 1/2 (50%) | 1 | SP1 | SP1-KBS-009 | 1232.00 | 1.232 | - | 1 | - | Order Total: 2 units
2025-11-29 | 2025-11-29 | Saturday | W2 | KBS-009 | 2526500117 | Unknown | W5 | 2 | 1 | 1 | 1/2 (50%) | 1 | SP2 | KVCALPPSP002 | 1232.00 | 1.232 | - | 1 | - | Order Total: 2 units
2025-11-29 | 2025-11-29 | Saturday | W2 | KBS-009 | 2526500117 | Unknown | W5 | 2 | 1 | 1 | 1/2 (50%) | 1 | SP3 | KVCALFPSP001 | 1232.00 | 1.232 | - | 1 | - | Order Total: 2 units
2025-12-01 | 2025-12-01 | Monday | W2 | KBS-009 | 2526500117 | Unknown | W5 | 2 | 2 | 2 | 2/2 COMPLETE ✓ | 1 | SP1 | SP1-KBS-009 | 1232.00 | 1.232 | - | 1 | - | Order Total: 2 units
2025-12-01 | 2025-12-01 | Monday | W2 | KBS-009 | 2526500117 | Unknown | W5 | 2 | 2 | 2 | 2/2 COMPLETE ✓ | 1 | SP2 | KVCALPPSP002 | 1232.00 | 1.232 | - | 1 | - | Order Total: 2 units
2025-12-01 | 2025-12-01 | Monday | W2 | KBS-009 | 2526500117 | Unknown | W5 | 2 | 2 | 2 | 2/2 COMPLETE ✓ | 1 | SP3 | KVCALFPSP001 | 1232.00 | 1.232 | - | 1 | - | Order Total: 2 units
2025-12-13 | 2025-12-13 | Saturday | W4 | KBS-009 | 2526500117 | Unknown | W5 | 2 | 1 | 1 | 1/2 (50%) | 1 | Grinding | GR1-KBS-009 | 1232.00 | 1.232 | 210 min | 1 | 210 min | Order Total: 2 units
2025-12-15 | 2025-12-15 | Monday | W4 | KBS-009 | 2526500117 | Unknown | W5 | 2 | 2 | 2 | 2/2 COMPLETE ✓ | 1 | Grinding | GR1-KBS-009 | 1232.00 | 1.232 | 210 min | 1 | 210 min | Order Total: 2 units
2025-12-20 | 2025-12-20 | Saturday | W5 | KBS-010 | 2526500118 | Unknown | W5 | 4 | 1 | 2 | 2/4 (50%) | 2 | Casting | CS1-KBS-010 | 1443.00 | 2.886 | 25 min | 1 | 50 min | Order Total: 4 units
2025-12-20 | 2025-12-20 | Saturday | W5 | KBS-010 | 2526500118 | Unknown | W5 | 4 | 1 | 2 | 2/4 (50%) | 2 | Grinding | GR1-KBS-010 | 1443.00 | 2.886 | 210 min | 1 | 420 min | Order Total: 4 units
2025-12-20 | 2025-12-20 | Saturday | W5 | KBS-010 | 2526500118 | Unknown | W5 | 4 | 1 | 2 | 2/4 (50%) | 2 | MC1 | MC1-KBS-010 | 1443.00 | 2.886 | 45 min | 1 | 90 min | Order Total: 4 units
2025-12-20 | 2025-12-20 | Saturday | W5 | KBS-010 | 2526500118 | Unknown | W5 | 4 | 1 | 2 | 2/4 (50%) | 2 | SP1 | SP1-KBS-010 | 1443.00 | 2.886 | - | 1 | - | Order Total: 4 units
2025-12-20 | 2025-12-20 | Saturday | W5 | KBS-010 | 2526500118 | Unknown | W5 | 4 | 1 | 2 | 2/4 (50%) | 2 | SP2 | KVCALPPSP002 | 1443.00 | 2.886 | - | 1 | - | Order Total: 4 units
2025-12-20 | 2025-12-20 | Saturday | W5 | KBS-010 | 2526500118 | Unknown | W5 | 4 | 1 | 2 | 2/4 (50%) | 2 | SP3 | KVCALFPSP001 | 1443.00 | 2.886 | - | 1 | - | Order Total: 4 units
2025-12-21 | 2025-12-20 | Sunday | W5 | KBS-010 | 2526500118 | Unknown | W5 | 4 | 1 | 2 | 2/4 (50%) | 2 | Cooling/Shakeout | N/A | 1443.00 | 2.886 | - | 1 | - | Order Total: 4 units
2025-12-22 | 2025-12-22 | Monday | W5 | KBS-010 | 2526500118 | Unknown | W5 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | Casting | CS1-KBS-010 | 1443.00 | 2.886 | 25 min | 1 | 50 min | Order Total: 4 units
2025-12-22 | 2025-12-22 | Monday | W5 | KBS-010 | 2526500118 | Unknown | W5 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | Grinding | GR1-KBS-010 | 1443.00 | 2.886 | 210 min | 1 | 420 min | Order Total: 4 units
2025-12-22 | 2025-12-22 | Monday | W5 | KBS-010 | 2526500118 | Unknown | W5 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | MC1 | MC1-KBS-010 | 1443.00 | 2.886 | 45 min | 1 | 90 min | Order Total: 4 units
2025-12-22 | 2025-12-22 | Monday | W5 | KBS-010 | 2526500118 | Unknown | W5 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | SP1 | SP1-KBS-010 | 1443.00 | 2.886 | - | 1 | - | Order Total: 4 units
2025-12-22 | 2025-12-22 | Monday | W5 | KBS-010 | 2526500118 | Unknown | W5 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | SP2 | KVCALPPSP002 | 1443.00 | 2.886 | - | 1 | - | Order Total: 4 units
2025-12-22 | 2025-12-22 | Monday | W5 | KBS-010 | 2526500118 | Unknown | W5 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | SP3 | KVCALFPSP001 | 1443.00 | 2.886 | - | 1 | - | Order Total: 4 units
2025-12-23 | 2025-12-22 | Tuesday | W5 | KBS-010 | 2526500118 | Unknown | W5 | 4 | 2 | 4 | 4/4 COMPLETE ✓ | 2 | Cooling/Shakeout | N/A | 1443.00 | 2.886 | - | 1 | - | Order Total: 4 units
2025-11-29 | 2025-11-29 | Saturday | W2 | KBS-011 | 2526500119 | Unknown | W5 | 1 | 1 | 1 | 1/1 COMPLETE ✓ | 1 | SP1 | KVCALPPSP001 | 1652.00 | 1.652 | 12 min | 1 | 12 min | Order Total: 1 units
2025-11-29 | 2025-11-29 | Saturday | W2 | KBS-011 | 2526500119 | Unknown | W5 | 1 | 1 | 1 | 1/1 COMPLETE ✓ | 1 | SP2 | KVCALPPSP002 | 1652.00 | 1.652 | 12 min | 1 | 12 min | Order Total: 1 units
2025-11-29 | 2025-11-29 | Saturday | W2 | KBS-011 | 2526500119 | Unknown | W5 | 1 | 1 | 1 | 1/1 COMPLETE ✓ | 1 | SP3 | KVCALFPSP001 | 1652.00 | 1.652 | 12 min | 1 | 12 min | Order Total: 1 units
2025-11-22 | 2025-11-22 | Saturday | W1 | KBS-009 | 2526500120 | Unknown | W2 | 20 | 1 | 5 | 5/20 (25%) | 5 | MC1 | MC1-KBS-009 | 1232.00 | 6.160 | 45 min | 1 | 225 min | Order Total: 20 units
2025-11-22 | 2025-11-22 | Saturday | W1 | KBS-009 | 2526500120 | Unknown | W2 | 20 | 1 | 5 | 5/20 (25%) | 5 | SP1 | SP1-KBS-009 | 1232.00 | 6.160 | - | 1 | - | Order Total: 20 units
2025-11-22 | 2025-11-22 | Saturday | W1 | KBS-009 | 2526500120 | Unknown | W2 | 20 | 1 | 5 | 5/20 (25%) | 5 | SP2 | KVCALPPSP002 | 1232.00 | 6.160 | - | 1 | - | Order Total: 20 units
2025-11-22 | 2025-11-22 | Saturday | W1 | KBS-009 | 2526500120 | Unknown | W2 | 20 | 1 | 5 | 5/20 (25%) | 5 | SP3 | KVCALFPSP001 | 1232.00 | 6.160 | - | 1 | - | Order Total: 20 units
2025-11-24 | 2025-11-24 | Monday | W1 | KBS-009 | 2526500120 | Unknown | W2 | 20 | 2 | 10 | 10/20 (50%) | 5 | MC1 | MC1-KBS-009 | 1232.00 | 6.160 | 45 min | 1 | 225 min | Order Total: 20 units
2025-11-24 | 2025-11-24 | Monday | W1 | KBS-009 | 2526500120 | Unknown | W2 | 20 | 2 | 10 | 10/20 (50%) | 5 | SP1 | SP1-KBS-009 | 1232.00 | 6.160 | - | 1 | - | Order Total: 20 units
2025-11-24 | 2025-11-24 | Monday | W1 | KBS-009 | 2526500120 | Unknown | W2 | 20 | 2 | 10 | 10/20 (50%) | 5 | SP2 | KVCALPPSP002 | 1232.00 | 6.160 | - | 1 | - | Order Total: 20 units
2025-11-24 | 2025-11-24 | Monday | W1 | KBS-009 | 2526500120 | Unknown | W2 | 20 | 2 | 10 | 10/20 (50%) | 5 | SP3 | KVCALFPSP001 | 1232.00 | 6.160 | - | 1 | - | Order Total: 20 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | KBS-009 | 2526500120 | Unknown | W2 | 20 | 3 | 15 | 15/20 (75%) | 5 | MC1 | MC1-KBS-009 | 1232.00 | 6.160 | 45 min | 1 | 225 min | Order Total: 20 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | KBS-009 | 2526500120 | Unknown | W2 | 20 | 3 | 15 | 15/20 (75%) | 5 | SP1 | SP1-KBS-009 | 1232.00 | 6.160 | - | 1 | - | Order Total: 20 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | KBS-009 | 2526500120 | Unknown | W2 | 20 | 3 | 15 | 15/20 (75%) | 5 | SP2 | KVCALPPSP002 | 1232.00 | 6.160 | - | 1 | - | Order Total: 20 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | KBS-009 | 2526500120 | Unknown | W2 | 20 | 3 | 15 | 15/20 (75%) | 5 | SP3 | KVCALFPSP001 | 1232.00 | 6.160 | - | 1 | - | Order Total: 20 units
2025-11-26 | 2025-11-26 | Wednesday | W1 | KBS-009 | 2526500120 | Unknown | W2 | 20 | 4 | 20 | 20/20 COMPLETE ✓ | 5 | MC1 | MC1-KBS-009 | 1232.00 | 6.160 | 45 min | 1 | 225 min | Order Total: 20 units
2025-11-26 | 2025-11-26 | Wednesday | W1 | KBS-009 | 2526500120 | Unknown | W2 | 20 | 4 | 20 | 20/20 COMPLETE ✓ | 5 | SP1 | SP1-KBS-009 | 1232.00 | 6.160 | - | 1 | - | Order Total: 20 units
2025-11-26 | 2025-11-26 | Wednesday | W1 | KBS-009 | 2526500120 | Unknown | W2 | 20 | 4 | 20 | 20/20 COMPLETE ✓ | 5 | SP2 | KVCALPPSP002 | 1232.00 | 6.160 | - | 1 | - | Order Total: 20 units
2025-11-26 | 2025-11-26 | Wednesday | W1 | KBS-009 | 2526500120 | Unknown | W2 | 20 | 4 | 20 | 20/20 COMPLETE ✓ | 5 | SP3 | KVCALFPSP001 | 1232.00 | 6.160 | - | 1 | - | Order Total: 20 units
2025-11-29 | 2025-11-29 | Saturday | W2 | KBS-009 | 2526500121 | Unknown | W5 | 2 | 1 | 1 | 1/2 (50%) | 1 | SP1 | SP1-KBS-009 | 1232.00 | 1.232 | - | 1 | - | Order Total: 2 units
2025-11-29 | 2025-11-29 | Saturday | W2 | KBS-009 | 2526500121 | Unknown | W5 | 2 | 1 | 1 | 1/2 (50%) | 1 | SP2 | KVCALPPSP002 | 1232.00 | 1.232 | - | 1 | - | Order Total: 2 units
2025-11-29 | 2025-11-29 | Saturday | W2 | KBS-009 | 2526500121 | Unknown | W5 | 2 | 1 | 1 | 1/2 (50%) | 1 | SP3 | KVCALFPSP001 | 1232.00 | 1.232 | - | 1 | - | Order Total: 2 units
2025-12-01 | 2025-12-01 | Monday | W2 | KBS-009 | 2526500121 | Unknown | W5 | 2 | 2 | 2 | 2/2 COMPLETE ✓ | 1 | SP1 | SP1-KBS-009 | 1232.00 | 1.232 | - | 1 | - | Order Total: 2 units
2025-12-01 | 2025-12-01 | Monday | W2 | KBS-009 | 2526500121 | Unknown | W5 | 2 | 2 | 2 | 2/2 COMPLETE ✓ | 1 | SP2 | KVCALPPSP002 | 1232.00 | 1.232 | - | 1 | - | Order Total: 2 units
2025-12-01 | 2025-12-01 | Monday | W2 | KBS-009 | 2526500121 | Unknown | W5 | 2 | 2 | 2 | 2/2 COMPLETE ✓ | 1 | SP3 | KVCALFPSP001 | 1232.00 | 1.232 | - | 1 | - | Order Total: 2 units
2025-12-13 | 2025-12-13 | Saturday | W4 | KBS-009 | 2526500121 | Unknown | W5 | 2 | 1 | 1 | 1/2 (50%) | 1 | Grinding | GR1-KBS-009 | 1232.00 | 1.232 | 210 min | 1 | 210 min | Order Total: 2 units
2025-12-15 | 2025-12-15 | Monday | W4 | KBS-009 | 2526500121 | Unknown | W5 | 2 | 2 | 2 | 2/2 COMPLETE ✓ | 1 | Grinding | GR1-KBS-009 | 1232.00 | 1.232 | 210 min | 1 | 210 min | Order Total: 2 units
2025-11-22 | 2025-11-22 | Saturday | W1 | KBS-011 | 2526500122 | Unknown | W2 | 15 | 1 | 3 | 3/15 (20%) | 3 | MC1 | KVCAD40MC001 | 1652.00 | 4.956 | 90 min | 1 | 270 min | Order Total: 15 units
2025-11-24 | 2025-11-24 | Monday | W1 | KBS-011 | 2526500122 | Unknown | W2 | 15 | 2 | 7 | 7/15 (46%) | 4 | MC1 | KVCAD40MC001 | 1652.00 | 6.608 | 90 min | 1 | 360 min | Order Total: 15 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | KBS-011 | 2526500122 | Unknown | W2 | 15 | 3 | 11 | 11/15 (73%) | 4 | MC1 | KVCAD40MC001 | 1652.00 | 6.608 | 90 min | 1 | 360 min | Order Total: 15 units
2025-11-26 | 2025-11-26 | Wednesday | W1 | KBS-011 | 2526500122 | Unknown | W2 | 15 | 4 | 15 | 15/15 COMPLETE ✓ | 4 | MC1 | KVCAD40MC001 | 1652.00 | 6.608 | 90 min | 1 | 360 min | Order Total: 15 units
2025-11-29 | 2025-11-29 | Saturday | W2 | KBS-011 | 2526500122 | Unknown | W2 | 15 | 1 | 3 | 3/15 (20%) | 3 | Grinding | KVCALHMGR001 | 1652.00 | 4.956 | 210 min | 1 | 630 min | Order Total: 15 units
2025-12-01 | 2025-12-01 | Monday | W2 | KBS-011 | 2526500122 | Unknown | W2 | 15 | 2 | 7 | 7/15 (46%) | 4 | Grinding | KVCALHMGR001 | 1652.00 | 6.608 | 210 min | 1 | 840 min | Order Total: 15 units
2025-12-02 | 2025-12-02 | Tuesday | W2 | KBS-011 | 2526500122 | Unknown | W2 | 15 | 3 | 11 | 11/15 (73%) | 4 | Grinding | KVCALHMGR001 | 1652.00 | 6.608 | 210 min | 1 | 840 min | Order Total: 15 units
2025-12-03 | 2025-12-03 | Wednesday | W2 | KBS-011 | 2526500122 | Unknown | W2 | 15 | 4 | 15 | 15/15 COMPLETE ✓ | 4 | Grinding | KVCALHMGR001 | 1652.00 | 6.608 | 210 min | 1 | 840 min | Order Total: 15 units
2025-11-29 | 2025-11-29 | Saturday | W2 | KBS-011 | 2526500123 | Unknown | W5 | 1 | 1 | 1 | 1/1 COMPLETE ✓ | 1 | SP1 | KVCALPPSP001 | 1652.00 | 1.652 | 12 min | 1 | 12 min | Order Total: 1 units
2025-11-29 | 2025-11-29 | Saturday | W2 | KBS-011 | 2526500123 | Unknown | W5 | 1 | 1 | 1 | 1/1 COMPLETE ✓ | 1 | SP2 | KVCALPPSP002 | 1652.00 | 1.652 | 12 min | 1 | 12 min | Order Total: 1 units
2025-11-29 | 2025-11-29 | Saturday | W2 | KBS-011 | 2526500123 | Unknown | W5 | 1 | 1 | 1 | 1/1 COMPLETE ✓ | 1 | SP3 | KVCALFPSP001 | 1652.00 | 1.652 | 12 min | 1 | 12 min | Order Total: 1 units
2025-11-22 | 2025-11-22 | Saturday | W1 | KBS-009 | 2526500124 | Unknown | W1 | 18 | 1 | 4 | 4/18 (22%) | 4 | Grinding | GR1-KBS-009 | 1232.00 | 4.928 | 210 min | 1 | 840 min | Order Total: 18 units
2025-11-24 | 2025-11-24 | Monday | W1 | KBS-009 | 2526500124 | Unknown | W1 | 18 | 2 | 8 | 8/18 (44%) | 4 | Grinding | GR1-KBS-009 | 1232.00 | 4.928 | 210 min | 1 | 840 min | Order Total: 18 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | KBS-009 | 2526500124 | Unknown | W1 | 18 | 3 | 13 | 13/18 (72%) | 5 | Grinding | GR1-KBS-009 | 1232.00 | 6.160 | 210 min | 1 | 1050 min | Order Total: 18 units
2025-11-26 | 2025-11-26 | Wednesday | W1 | KBS-009 | 2526500124 | Unknown | W1 | 18 | 4 | 18 | 18/18 COMPLETE ✓ | 5 | Grinding | GR1-KBS-009 | 1232.00 | 6.160 | 210 min | 1 | 1050 min | Order Total: 18 units
2025-11-22 | 2025-11-22 | Saturday | W1 | KBS-011 | 2526500125 | Unknown | W2 | 15 | 1 | 3 | 3/15 (20%) | 3 | MC1 | KVCAD40MC001 | 1652.00 | 4.956 | 90 min | 1 | 270 min | Order Total: 15 units
2025-11-24 | 2025-11-24 | Monday | W1 | KBS-011 | 2526500125 | Unknown | W2 | 15 | 2 | 7 | 7/15 (46%) | 4 | MC1 | KVCAD40MC001 | 1652.00 | 6.608 | 90 min | 1 | 360 min | Order Total: 15 units
2025-11-25 | 2025-11-25 | Tuesday | W1 | KBS-011 | 2526500125 | Unknown | W2 | 15 | 3 | 11 | 11/15 (73%) | 4 | MC1 | KVCAD40MC001 | 1652.00 | 6.608 | 90 min | 1 | 360 min | Order Total: 15 units
2025-11-26 | 2025-11-26 | Wednesday | W1 | KBS-011 | 2526500125 | Unknown | W2 | 15 | 4 | 15 | 15/15 COMPLETE ✓ | 4 | MC1 | KVCAD40MC001 | 1652.00 | 6.608 | 90 min | 1 | 360 min | Order Total: 15 units
2025-11-29 | 2025-11-29 | Saturday | W2 | KBS-011 | 2526500125 | Unknown | W2 | 15 | 1 | 3 | 3/15 (20%) | 3 | Grinding | KVCALHMGR001 | 1652.00 | 4.956 | 210 min | 1 | 630 min | Order Total: 15 units
2025-12-01 | 2025-12-01 | Monday | W2 | KBS-011 | 2526500125 | Unknown | W2 | 15 | 2 | 7 | 7/15 (46%) | 4 | Grinding | KVCALHMGR001 | 1652.00 | 6.608 | 210 min | 1 | 840 min | Order Total: 15 units
2025-12-02 | 2025-12-02 | Tuesday | W2 | KBS-011 | 2526500125 | Unknown | W2 | 15 | 3 | 11 | 11/15 (73%) | 4 | Grinding | KVCALHMGR001 | 1652.00 | 6.608 | 210 min | 1 | 840 min | Order Total: 15 units
2025-12-03 | 2025-12-03 | Wednesday | W2 | KBS-011 | 2526500125 | Unknown | W2 | 15 | 4 | 15 | 15/15 COMPLETE ✓ | 4 | Grinding | KVCALHMGR001 | 1652.00 | 6.608 | 210 min | 1 | 840 min | Order Total: 15 units
2025-11-22 | 2025-11-22 | Saturday | W1 | KBS-012 | 2526500126 | Unknown | W2 | 11 | 1 | 6 | 6/25 (24%) | 6 | Casting | CS1-KBS-012 | 888.50 | 5.331 | 25 min | 1 | 150 min | Order Total: 11 units
2025-11-22 | 2025-11-22 | Saturday | W1 | KBS-012 | 2526500126 | Unknown | W2 | 14 | 2 | 11 | 11/25 (44%) | 5 | Casting | CS1-KBS-012 | 888.50 | 4.442 | 25 min | 1 | 125 min | Order Total: 14 units
2025-11-22 | 2025-11-22 | Saturday | W1 | KBS-012 | 2526500126 | Unknown | W2 | 11 | 1 | 2 | 2/25 (8%) | 2 | Grinding | KVCALHMGR001 | 888.50 | 1.777 | 210 min | 1 | 420 min | Order Total: 11 units
2025-11-22 | 2025-11-22 | Saturday | W1 | KBS-012 | 2526500126 | Unknown | W2 | 14 | 2 | 5 | 5/25 (20%) | 3 | Grinding | KVCALHMGR001 | 888.50 | 2.666 | 210 min | 1 | 630 min | Order Total: 14 units
2025-11-22 | 2025-11-22 | Saturday | W1 | KBS-012 | 2526500126 | Unknown | W2 | 11 | 1 | 2 | 2/25 (8%) | 2 | SP1 | KVCALPPSP001 | 888.50 | 1.777 | 12 min | 1 | 24 min | Order Total: 11 units
2025-11-22 | 2025-11-22 | Saturday | W1 | KBS-012 | 2526500126 | Unknown | W2 | 14 | 2 | 5 | 5/25 (20%) | 3 | SP1 | KVCALPPSP001 | 888.50 | 2.666 | 12 min | 1 | 36 min | Order Total: 14 units
2025-11-22 | 2025-11-22 | Saturday | W1 | KBS-012 | 2526500126 | Unknown | W2 | 11 | 1 | 2 | 2/25 (8%) | 2 | SP2 | KVCALPPSP002 | 888.50 | 1.777 | 12 min | 1 | 24 min | Order Total: 11 units
2025-11-22 | 2025-11-22 | Saturday | W1 | KBS-012 | 2526500126 | Unknown | W2 | 14 | 2 | 5 | 5/25 (20%) | 3 | SP2 | KVCALPPSP002 | 888.50 | 2.666 | 12 min | 1 | 36 min | Order Total: 14 units
2025-11-22 | 2025-11-22 | Saturday | W1 | KBS-012 | 2526500126 | Unknown | W2 | 11 | 1 | 2 | 2/25 (8%) | 2 | SP3 | KVCALFPSP001 | 888.50 | 1.777 | 7 min | 1 | 14 min | Order Total: 11 units
2025-11-22 | 2025-11-22 | Saturday | W1 | KBS-012 | 2526500126 | Unknown | W2 | 14 | 2 | 5 | 5/25 (20%) | 3 | SP3 | KVCALFPSP001 | 888.50 | 2.666 | 7 min | 1 | 21 min | Order Total: 14 units
2025-11-23 | 2025-11-22 | Sunday | W1 | KBS-012 | 2526500126 | Unknown | W2 | 11 | 1 | 2 | 2/25 (8%) | 2 | Cooling/Shakeout | N/A | 888.50 | 1.777 | - | 1 | - | Order Total: 11 units
2025-11-23 | 2025-11-22 | Sunday | W1 | KBS-012 | 2526500126 | Unknown | W2 | 14 | 2 | 5 | 5/25 (20%) | 3 | Cooling/Shakeout | N/A | 888.50 | 2.666 | - | 1 | - | Order Total: 14 units
2025-11-24 | 2025-11-24 | Monday | W1 | KBS-012 | 2526500126 | Unknown | W2 | 11 | 3 | 16 | 16/25 (64%) | 5 | Casting | CS1-KBS-012 | 888.50 | 4.442 | 25 min | 1 | 125 min | Order Total: 11 units
2025-11-24 | 2025-11-24 | Monday | W1 | KBS-012 | 2526500126 | Unknown | W2 | 14 | 4 | 25 | 25/25 COMPLETE ✓ | 9 | Casting | CS1-KBS-012 | 888.50 | 7.997 | 25 min | 1 | 225 min | Order Total: 14 units
2025-11-24 | 2025-11-24 | Monday | W1 | KBS-012 | 2526500126 | Unknown | W2 | 11 | 3 | 8 | 8/25 (32%) | 3 | Grinding | KVCALHMGR001 | 888.50 | 2.666 | 210 min | 1 | 630 min | Order Total: 11 units
2025-11-24 | 2025-11-24 | Monday | W1 | KBS-012 | 2526500126 | Unknown | W2 | 14 | 4 | 11 | 11/25 (44%) | 3 | Grinding | KVCALHMGR001 | 888.50 | 2.666 | 210 min | 1 | 630 min | Order Total: 14 units
2025-11-24 | 2025-11-24 | Monday | W1 | KBS-012 | 2526500126 | Unknown | W2 | 11 | 3 | 8 | 8/25 (32%) | 3 | SP1 | KVCALPPSP001 | 888.50 | 2.666 | 12 min | 1 | 36 min | Order Total: 11 units
2025-11-24 | 2025-11-24 | Monday | W1 | KBS-012 | 2526500126 | Unknown | W2 | 14 | 4 | 11 | 11/25 (44%) | 3 | SP1 | KVCALPPSP001 | 888.50 | 2.666 | 12 min | 1 | 36 min | Order Total: 14 units
2025-11-24 | 2025-11-24 | Monday | W1 | KBS-012 | 2526500126 | Unknown | W2 | 11 | 3 | 8 | 8/25 (32%) | 3 | SP2 | KVCALPPSP002 | 888.50 | 2.666 | 12 min | 1 | 36 min | Order Total: 11 units
2025-11-24 | 2025-11-24 | Monday | W1 | KBS-012 | 2526500126 | Unknown | W2 | 14 | 4 | 11 | 11/25 (44%) | 3 | SP2 | KVCALPPSP002 | 888.50 | 2.666 | 12 min | 1 | 36 min | Order Total: 14 units
2025-11-24 | 2025-11-24 | Monday | W1 | KBS-012 | 2526500126 | Unknown | W2 | 11 | 3 | 8 | 8/25 (32%) | 3 | SP3 | KVCALFPSP001 | 888.50 | 2.666 | 7 min | 1 | 21 min | Order Total: 11 units
2025-11-24 | 2025-11-24 | Monday | W1 | KBS-012 | 2526500126 | Unknown | W2 | 14 | 4 | 11 | 11/25 (44%) | 3 | SP3 | KVCALFPSP001 | 888.50 | 2.666 | 7 min | 1 | 21 min | Order Total: 14 units
2025-11-25 | 2025-11-24 | Tuesday | W1 | KBS-012 | 2526500126 | Unknown | W2 | 11 | 3 | 8 | 8/25 (32%) | 3 | Cooling/Shakeout | N/A | 888.50 | 2.666 | - | 1 | - | Order Total: 11 units
2025-11-25 | 2025-11-24 | Tuesday | W1 | KBS-012 | 2526500126 | Unknown | W2 | 14 | 4 | 11 | 11/25 (44%) | 3 | Cooling/Shakeout | N/A | 888.50 | 2.666 | - | 1 | - | Order Total: 14 units
2025-11-25 | 2025-11-22 | Tuesday | W1 | KBS-012 | 2526500126 | Unknown | W2 | 11 | 5 | 14 | 14/25 (56%) | 3 | Grinding | KVCALHMGR001 | 888.50 | 2.666 | 210 min | 1 | 630 min | Order Total: 11 units
2025-11-25 | 2025-11-22 | Tuesday | W1 | KBS-012 | 2526500126 | Unknown | W2 | 14 | 6 | 18 | 18/25 (72%) | 4 | Grinding | KVCALHMGR001 | 888.50 | 3.554 | 210 min | 1 | 840 min | Order Total: 14 units
2025-11-25 | 2025-11-22 | Tuesday | W1 | KBS-012 | 2526500126 | Unknown | W2 | 11 | 5 | 14 | 14/25 (56%) | 3 | SP1 | KVCALPPSP001 | 888.50 | 2.666 | 12 min | 1 | 36 min | Order Total: 11 units
2025-11-25 | 2025-11-22 | Tuesday | W1 | KBS-012 | 2526500126 | Unknown | W2 | 14 | 6 | 18 | 18/25 (72%) | 4 | SP1 | KVCALPPSP001 | 888.50 | 3.554 | 12 min | 1 | 48 min | Order Total: 14 units
2025-11-25 | 2025-11-22 | Tuesday | W1 | KBS-012 | 2526500126 | Unknown | W2 | 11 | 5 | 14 | 14/25 (56%) | 3 | SP2 | KVCALPPSP002 | 888.50 | 2.666 | 12 min | 1 | 36 min | Order Total: 11 units
2025-11-25 | 2025-11-22 | Tuesday | W1 | KBS-012 | 2526500126 | Unknown | W2 | 14 | 6 | 18 | 18/25 (72%) | 4 | SP2 | KVCALPPSP002 | 888.50 | 3.554 | 12 min | 1 | 48 min | Order Total: 14 units
2025-11-25 | 2025-11-22 | Tuesday | W1 | KBS-012 | 2526500126 | Unknown | W2 | 11 | 5 | 14 | 14/25 (56%) | 3 | SP3 | KVCALFPSP001 | 888.50 | 2.666 | 7 min | 1 | 21 min | Order Total: 11 units
2025-11-25 | 2025-11-22 | Tuesday | W1 | KBS-012 | 2526500126 | Unknown | W2 | 14 | 6 | 18 | 18/25 (72%) | 4 | SP3 | KVCALFPSP001 | 888.50 | 3.554 | 7 min | 1 | 28 min | Order Total: 14 units
2025-11-26 | 2025-11-22 | Wednesday | W1 | KBS-012 | 2526500126 | Unknown | W2 | 11 | 5 | 14 | 14/25 (56%) | 3 | Cooling/Shakeout | N/A | 888.50 | 2.666 | - | 1 | - | Order Total: 11 units
2025-11-26 | 2025-11-22 | Wednesday | W1 | KBS-012 | 2526500126 | Unknown | W2 | 14 | 6 | 18 | 18/25 (72%) | 4 | Cooling/Shakeout | N/A | 888.50 | 3.554 | - | 1 | - | Order Total: 14 units
2025-11-26 | 2025-11-22 | Wednesday | W1 | KBS-012 | 2526500126 | Unknown | W2 | 11 | 7 | 21 | 21/25 (84%) | 3 | Grinding | KVCALHMGR001 | 888.50 | 2.666 | 210 min | 1 | 630 min | Order Total: 11 units
2025-11-26 | 2025-11-24 | Wednesday | W1 | KBS-012 | 2526500126 | Unknown | W2 | 14 | 8 | 25 | 25/25 COMPLETE ✓ | 4 | Grinding | KVCALHMGR001 | 888.50 | 3.554 | 210 min | 1 | 840 min | Order Total: 14 units
2025-11-26 | 2025-11-22 | Wednesday | W1 | KBS-012 | 2526500126 | Unknown | W2 | 11 | 7 | 21 | 21/25 (84%) | 3 | SP1 | KVCALPPSP001 | 888.50 | 2.666 | 12 min | 1 | 36 min | Order Total: 11 units
2025-11-26 | 2025-11-24 | Wednesday | W1 | KBS-012 | 2526500126 | Unknown | W2 | 14 | 8 | 25 | 25/25 COMPLETE ✓ | 4 | SP1 | KVCALPPSP001 | 888.50 | 3.554 | 12 min | 1 | 48 min | Order Total: 14 units
2025-11-26 | 2025-11-22 | Wednesday | W1 | KBS-012 | 2526500126 | Unknown | W2 | 11 | 7 | 21 | 21/25 (84%) | 3 | SP2 | KVCALPPSP002 | 888.50 | 2.666 | 12 min | 1 | 36 min | Order Total: 11 units
2025-11-26 | 2025-11-24 | Wednesday | W1 | KBS-012 | 2526500126 | Unknown | W2 | 14 | 8 | 25 | 25/25 COMPLETE ✓ | 4 | SP2 | KVCALPPSP002 | 888.50 | 3.554 | 12 min | 1 | 48 min | Order Total: 14 units
2025-11-26 | 2025-11-22 | Wednesday | W1 | KBS-012 | 2526500126 | Unknown | W2 | 11 | 7 | 21 | 21/25 (84%) | 3 | SP3 | KVCALFPSP001 | 888.50 | 2.666 | 7 min | 1 | 21 min | Order Total: 11 units
2025-11-26 | 2025-11-24 | Wednesday | W1 | KBS-012 | 2526500126 | Unknown | W2 | 14 | 8 | 25 | 25/25 COMPLETE ✓ | 4 | SP3 | KVCALFPSP001 | 888.50 | 3.554 | 7 min | 1 | 28 min | Order Total: 14 units
2025-11-27 | 2025-11-22 | Thursday | W1 | KBS-012 | 2526500126 | Unknown | W2 | 11 | 7 | 21 | 21/25 (84%) | 3 | Cooling/Shakeout | N/A | 888.50 | 2.666 | - | 1 | - | Order Total: 11 units
2025-11-27 | 2025-11-24 | Thursday | W1 | KBS-012 | 2526500126 | Unknown | W2 | 14 | 8 | 25 | 25/25 COMPLETE ✓ | 4 | Cooling/Shakeout | N/A | 888.50 | 3.554 | - | 1 | - | Order Total: 14 units
2025-11-22 | 2025-11-22 | Saturday | W1 | KBS-012 | 2526500127 | Unknown | W2 | 10 | 1 | 5 | 5/23 (21%) | 5 | Casting | CS1-KBS-012 | 888.50 | 4.442 | 25 min | 1 | 125 min | Order Total: 10 units
2025-11-22 | 2025-11-22 | Saturday | W1 | KBS-012 | 2526500127 | Unknown | W2 | 13 | 2 | 10 | 10/23 (43%) | 5 | Casting | CS1-KBS-012 | 888.50 | 4.442 | 25 min | 1 | 125 min | Order Total: 13 units
2025-11-22 | 2025-11-22 | Saturday | W1 | KBS-012 | 2526500127 | Unknown | W2 | 10 | 1 | 2 | 2/23 (8%) | 2 | Grinding | KVCALHMGR001 | 888.50 | 1.777 | 210 min | 1 | 420 min | Order Total: 10 units
2025-11-22 | 2025-11-22 | Saturday | W1 | KBS-012 | 2526500127 | Unknown | W2 | 13 | 2 | 5 | 5/23 (21%) | 3 | Grinding | KVCALHMGR001 | 888.50 | 2.666 | 210 min | 1 | 630 min | Order Total: 13 units
2025-11-22 | 2025-11-22 | Saturday | W1 | KBS-012 | 2526500127 | Unknown | W2 | 10 | 1 | 2 | 2/23 (8%) | 2 | SP1 | KVCALPPSP001 | 888.50 | 1.777 | 12 min | 1 | 24 min | Order Total: 10 units
2025-11-22 | 2025-11-22 | Saturday | W1 | KBS-012 | 2526500127 | Unknown | W2 | 13 | 2 | 5 | 5/23 (21%) | 3 | SP1 | KVCALPPSP001 | 888.50 | 2.666 | 12 min | 1 | 36 min | Order Total: 13 units
2025-11-22 | 2025-11-22 | Saturday | W1 | KBS-012 | 2526500127 | Unknown | W2 | 10 | 1 | 2 | 2/23 (8%) | 2 | SP2 | KVCALPPSP002 | 888.50 | 1.777 | 12 min | 1 | 24 min | Order Total: 10 units
2025-11-22 | 2025-11-22 | Saturday | W1 | KBS-012 | 2526500127 | Unknown | W2 | 13 | 2 | 5 | 5/23 (21%) | 3 | SP2 | KVCALPPSP002 | 888.50 | 2.666 | 12 min | 1 | 36 min | Order Total: 13 units
2025-11-22 | 2025-11-22 | Saturday | W1 | KBS-012 | 2526500127 | Unknown | W2 | 10 | 1 | 2 | 2/23 (8%) | 2 | SP3 | KVCALFPSP001 | 888.50 | 1.777 | 7 min | 1 | 14 min | Order Total: 10 units
2025-11-22 | 2025-11-22 | Saturday | W1 | KBS-012 | 2526500127 | Unknown | W2 | 13 | 2 | 5 | 5/23 (21%) | 3 | SP3 | KVCALFPSP001 | 888.50 | 2.666 | 7 min | 1 | 21 min | Order Total: 13 units
2025-11-23 | 2025-11-22 | Sunday | W1 | KBS-012 | 2526500127 | Unknown | W2 | 10 | 1 | 2 | 2/23 (8%) | 2 | Cooling/Shakeout | N/A | 888.50 | 1.777 | - | 1 | - | Order Total: 10 units
2025-11-23 | 2025-11-22 | Sunday | W1 | KBS-012 | 2526500127 | Unknown | W2 | 13 | 2 | 5 | 5/23 (21%) | 3 | Cooling/Shakeout | N/A | 888.50 | 2.666 | - | 1 | - | Order Total: 13 units
2025-11-24 | 2025-11-24 | Monday | W1 | KBS-012 | 2526500127 | Unknown | W2 | 10 | 3 | 15 | 15/23 (65%) | 5 | Casting | CS1-KBS-012 | 888.50 | 4.442 | 25 min | 1 | 125 min | Order Total: 10 units
2025-11-24 | 2025-11-24 | Monday | W1 | KBS-012 | 2526500127 | Unknown | W2 | 13 | 4 | 23 | 23/23 COMPLETE ✓ | 8 | Casting | CS1-KBS-012 | 888.50 | 7.108 | 25 min | 1 | 200 min | Order Total: 13 units
2025-11-24 | 2025-11-24 | Monday | W1 | KBS-012 | 2526500127 | Unknown | W2 | 10 | 3 | 7 | 7/23 (30%) | 2 | Grinding | KVCALHMGR001 | 888.50 | 1.777 | 210 min | 1 | 420 min | Order Total: 10 units
2025-11-24 | 2025-11-24 | Monday | W1 | KBS-012 | 2526500127 | Unknown | W2 | 13 | 4 | 10 | 10/23 (43%) | 3 | Grinding | KVCALHMGR001 | 888.50 | 2.666 | 210 min | 1 | 630 min | Order Total: 13 units
2025-11-24 | 2025-11-24 | Monday | W1 | KBS-012 | 2526500127 | Unknown | W2 | 10 | 3 | 7 | 7/23 (30%) | 2 | SP1 | KVCALPPSP001 | 888.50 | 1.777 | 12 min | 1 | 24 min | Order Total: 10 units
2025-11-24 | 2025-11-24 | Monday | W1 | KBS-012 | 2526500127 | Unknown | W2 | 13 | 4 | 10 | 10/23 (43%) | 3 | SP1 | KVCALPPSP001 | 888.50 | 2.666 | 12 min | 1 | 36 min | Order Total: 13 units
2025-11-24 | 2025-11-24 | Monday | W1 | KBS-012 | 2526500127 | Unknown | W2 | 10 | 3 | 7 | 7/23 (30%) | 2 | SP2 | KVCALPPSP002 | 888.50 | 1.777 | 12 min | 1 | 24 min | Order Total: 10 units
2025-11-24 | 2025-11-24 | Monday | W1 | KBS-012 | 2526500127 | Unknown | W2 | 13 | 4 | 10 | 10/23 (43%) | 3 | SP2 | KVCALPPSP002 | 888.50 | 2.666 | 12 min | 1 | 36 min | Order Total: 13 units
2025-11-24 | 2025-11-24 | Monday | W1 | KBS-012 | 2526500127 | Unknown | W2 | 10 | 3 | 7 | 7/23 (30%) | 2 | SP3 | KVCALFPSP001 | 888.50 | 1.777 | 7 min | 1 | 14 min | Order Total: 10 units
2025-11-24 | 2025-11-24 | Monday | W1 | KBS-012 | 2526500127 | Unknown | W2 | 13 | 4 | 10 | 10/23 (43%) | 3 | SP3 | KVCALFPSP001 | 888.50 | 2.666 | 7 min | 1 | 21 min | Order Total: 13 units
2025-11-25 | 2025-11-24 | Tuesday | W1 | KBS-012 | 2526500127 | Unknown | W2 | 10 | 3 | 7 | 7/23 (30%) | 2 | Cooling/Shakeout | N/A | 888.50 | 1.777 | - | 1 | - | Order Total: 10 units
2025-11-25 | 2025-11-24 | Tuesday | W1 | KBS-012 | 2526500127 | Unknown | W2 | 13 | 4 | 10 | 10/23 (43%) | 3 | Cooling/Shakeout | N/A | 888.50 | 2.666 | - | 1 | - | Order Total: 13 units
2025-11-25 | 2025-11-22 | Tuesday | W1 | KBS-012 | 2526500127 | Unknown | W2 | 10 | 5 | 13 | 13/23 (56%) | 3 | Grinding | KVCALHMGR001 | 888.50 | 2.666 | 210 min | 1 | 630 min | Order Total: 10 units
2025-11-25 | 2025-11-22 | Tuesday | W1 | KBS-012 | 2526500127 | Unknown | W2 | 13 | 6 | 16 | 16/23 (69%) | 3 | Grinding | KVCALHMGR001 | 888.50 | 2.666 | 210 min | 1 | 630 min | Order Total: 13 units
2025-11-25 | 2025-11-22 | Tuesday | W1 | KBS-012 | 2526500127 | Unknown | W2 | 10 | 5 | 13 | 13/23 (56%) | 3 | SP1 | KVCALPPSP001 | 888.50 | 2.666 | 12 min | 1 | 36 min | Order Total: 10 units
2025-11-25 | 2025-11-22 | Tuesday | W1 | KBS-012 | 2526500127 | Unknown | W2 | 13 | 6 | 16 | 16/23 (69%) | 3 | SP1 | KVCALPPSP001 | 888.50 | 2.666 | 12 min | 1 | 36 min | Order Total: 13 units
2025-11-25 | 2025-11-22 | Tuesday | W1 | KBS-012 | 2526500127 | Unknown | W2 | 10 | 5 | 13 | 13/23 (56%) | 3 | SP2 | KVCALPPSP002 | 888.50 | 2.666 | 12 min | 1 | 36 min | Order Total: 10 units
2025-11-25 | 2025-11-22 | Tuesday | W1 | KBS-012 | 2526500127 | Unknown | W2 | 13 | 6 | 16 | 16/23 (69%) | 3 | SP2 | KVCALPPSP002 | 888.50 | 2.666 | 12 min | 1 | 36 min | Order Total: 13 units
2025-11-25 | 2025-11-22 | Tuesday | W1 | KBS-012 | 2526500127 | Unknown | W2 | 10 | 5 | 13 | 13/23 (56%) | 3 | SP3 | KVCALFPSP001 | 888.50 | 2.666 | 7 min | 1 | 21 min | Order Total: 10 units
2025-11-25 | 2025-11-22 | Tuesday | W1 | KBS-012 | 2526500127 | Unknown | W2 | 13 | 6 | 16 | 16/23 (69%) | 3 | SP3 | KVCALFPSP001 | 888.50 | 2.666 | 7 min | 1 | 21 min | Order Total: 13 units
2025-11-26 | 2025-11-22 | Wednesday | W1 | KBS-012 | 2526500127 | Unknown | W2 | 10 | 5 | 13 | 13/23 (56%) | 3 | Cooling/Shakeout | N/A | 888.50 | 2.666 | - | 1 | - | Order Total: 10 units
2025-11-26 | 2025-11-22 | Wednesday | W1 | KBS-012 | 2526500127 | Unknown | W2 | 13 | 6 | 16 | 16/23 (69%) | 3 | Cooling/Shakeout | N/A | 888.50 | 2.666 | - | 1 | - | Order Total: 13 units
2025-11-26 | 2025-11-22 | Wednesday | W1 | KBS-012 | 2526500127 | Unknown | W2 | 10 | 7 | 19 | 19/23 (82%) | 3 | Grinding | KVCALHMGR001 | 888.50 | 2.666 | 210 min | 1 | 630 min | Order Total: 10 units
2025-11-26 | 2025-11-24 | Wednesday | W1 | KBS-012 | 2526500127 | Unknown | W2 | 13 | 8 | 23 | 23/23 COMPLETE ✓ | 4 | Grinding | KVCALHMGR001 | 888.50 | 3.554 | 210 min | 1 | 840 min | Order Total: 13 units
2025-11-26 | 2025-11-22 | Wednesday | W1 | KBS-012 | 2526500127 | Unknown | W2 | 10 | 7 | 19 | 19/23 (82%) | 3 | SP1 | KVCALPPSP001 | 888.50 | 2.666 | 12 min | 1 | 36 min | Order Total: 10 units
2025-11-26 | 2025-11-24 | Wednesday | W1 | KBS-012 | 2526500127 | Unknown | W2 | 13 | 8 | 23 | 23/23 COMPLETE ✓ | 4 | SP1 | KVCALPPSP001 | 888.50 | 3.554 | 12 min | 1 | 48 min | Order Total: 13 units
2025-11-26 | 2025-11-22 | Wednesday | W1 | KBS-012 | 2526500127 | Unknown | W2 | 10 | 7 | 19 | 19/23 (82%) | 3 | SP2 | KVCALPPSP002 | 888.50 | 2.666 | 12 min | 1 | 36 min | Order Total: 10 units
2025-11-26 | 2025-11-24 | Wednesday | W1 | KBS-012 | 2526500127 | Unknown | W2 | 13 | 8 | 23 | 23/23 COMPLETE ✓ | 4 | SP2 | KVCALPPSP002 | 888.50 | 3.554 | 12 min | 1 | 48 min | Order Total: 13 units
2025-11-26 | 2025-11-22 | Wednesday | W1 | KBS-012 | 2526500127 | Unknown | W2 | 10 | 7 | 19 | 19/23 (82%) | 3 | SP3 | KVCALFPSP001 | 888.50 | 2.666 | 7 min | 1 | 21 min | Order Total: 10 units
2025-11-26 | 2025-11-24 | Wednesday | W1 | KBS-012 | 2526500127 | Unknown | W2 | 13 | 8 | 23 | 23/23 COMPLETE ✓ | 4 | SP3 | KVCALFPSP001 | 888.50 | 3.554 | 7 min | 1 | 28 min | Order Total: 13 units
2025-11-27 | 2025-11-22 | Thursday | W1 | KBS-012 | 2526500127 | Unknown | W2 | 10 | 7 | 19 | 19/23 (82%) | 3 | Cooling/Shakeout | N/A | 888.50 | 2.666 | - | 1 | - | Order Total: 10 units
2025-11-27 | 2025-11-24 | Thursday | W1 | KBS-012 | 2526500127 | Unknown | W2 | 13 | 8 | 23 | 23/23 COMPLETE ✓ | 4 | Cooling/Shakeout | N/A | 888.50 | 3.554 | - | 1 | - | Order Total: 13 units
2025-11-22 | 2025-11-22 | Saturday | W1 | KBS-014 | 2526500130 | Unknown | W2 | 24 | 1 | 24 | 24/24 COMPLETE ✓ | 24 | SP1 | SP1-KBS-014 | 0.00 | 0.000 | - | 10 | - | Order Total: 24 units
2025-11-22 | 2025-11-22 | Saturday | W1 | KBS-014 | 2526500131 | Unknown | W3 | 24 | 1 | 24 | 24/24 COMPLETE ✓ | 24 | Casting | CS1-KBS-014 | 0.00 | 0.000 | 2 min | 1 | 60 min | Order Total: 24 units
2025-11-23 | 2025-11-22 | Sunday | W1 | KBS-014 | 2526500131 | Unknown | W3 | 24 | 1 | 24 | 24/24 COMPLETE ✓ | 24 | Cooling/Shakeout | N/A | 0.00 | 0.000 | - | 1 | - | Order Total: 24 units
OPERATION-WISE SUMMARY (All Days)
Operation | Total Entries | Total Units | Unique Parts | Avg Units/Day
Casting | 323 | 1145 | 48 | 3.5
Cooling/Shakeout | 403 | 1145 | 48 | 2.8
Grinding | 459 | 1227 | 65 | 2.7
MC1 | 406 | 1025 | 62 | 2.5
MC2 | 39 | 177 | 7 | 4.5
MC3 | 39 | 177 | 7 | 4.5
SP1 | 534 | 1648 | 75 | 3.1
SP2 | 222 | 956 | 32 | 4.3
SP3 | 222 | 956 | 32 | 4.3
MACHINE UTILIZATION SUMMARY (Top Machines)
Machine/Resource | Operations | Total Units | Total Production Time (hrs)
KVCALHMGR001 | 409 | 1088 | 4545.3
BVCAD30MC001 | 45 | 306 | 530.8
BVCABM1MC001 | 22 | 130 | 260.0
KVCALPPSP001 | 478 | 1476 | 230.7
GR1-KBS-009 | 12 | 40 | 140.0
KVCALPPSP002 | 222 | 956 | 134.4
KVCALFPSP001 | 200 | 897 | 116.2
KVCAD40MC001 | 24 | 73 | 101.2
MC1ARM-007 | 14 | 22 | 88.0
KVCAD50MC001 | 287 | 571 | 80.6
KVCAD30MC001 | 32 | 89 | 66.3
GR1ARM-007 | 10 | 14 | 56.0
CS1-DGC-001 | 14 | 154 | 51.3
GR1-UBC-022 | 6 | 12 | 48.0
KVCAD20MC001 | 10 | 15 | 42.5
KEY INSIGHTS - HOW TO DETERMINE ACTUAL DELIVERY DATE:
1. PRODUCTION FLOW: | A part must go through all 8 stages sequentially:
Casting (Week X) → Grinding (Week X+1) → MC1 (Week X+2) → MC2 (Week X+3) → MC3 (Week X+4) → SP1 (Week X+5) → SP2 (Week X+6) → SP3 (Week X+7)
2. DELIVERY DATE: | A part can only be delivered AFTER completing SP3 (final painting stage)
Example: | If SP3 completes on 2025-12-15, earliest delivery is 2025-12-15
3. WIP PARTS: | Parts already in WIP (Finished Goods, SP, MC, GR stages) skip earlier stages
Example: | Part in MC stage skips Casting & Grinding, goes directly to MC1→MC2→MC3→SP1→SP2→SP3
NOTES:
• This schedule shows EXACTLY which parts to produce each day on which machines
• Units are distributed evenly across working days (Mon-Sat, excluding holidays)
• Working days exclude Sundays and Indian national holidays
• Use this as the daily work order for the production floor
• Track each part through all 8 stages to determine real delivery capability

## 9_DAILY_PRODUCTION
Date | Week | ARM-004-N |  |  |  | ARM-007 |  |  |  | ATT-001 |  |  |  | ATT-002 |  |  |  | DGC-001 |  |  |  | DGC-006 |  |  |  | DGC-009 |  |  |  | DGC-011 |  |  |  | DGC-012 |  |  |  | KBS-008 |  |  |  | KBS-009 |  |  |  | KBS-010 |  |  |  | KBS-011 |  |  |  | KBS-012 |  |  |  | KBS-014 |  |  |  | KBS-016 |  |  |  | KBS-017 |  |  |  | KBS-018 |  |  |  | LKK-01 |  |  |  | LKK-02 |  |  |  | LKK-03 |  |  |  | LKK-030 |  |  |  | LKK-031 |  |  |  | LKK-032 |  |  |  | LKK-033 |  |  |  | LKK-034 |  |  |  | LKK-035 |  |  |  | LKK-04 |  |  |  | LKK-05 |  |  |  | LKK-06 |  |  |  | LKK-10 |  |  |  | LKK-11 |  |  |  | LKK-12 |  |  |  | LKK-16 |  |  |  | LKK-17 |  |  |  | MCB-007 |  |  |  | MCB-008 |  |  |  | MCB-009 |  |  |  | MCB-010 |  |  |  | MCB-HYG-015 |  |  |  | MCB-HYG-016 |  |  |  | MCB-HYG-023 |  |  |  | MCB-HYG-026 |  |  |  | MCB-JLG-019 |  |  |  | MCB-JLG-020 |  |  |  | MCB-JLG-032 |  |  |  | MCB-JLG-033 |  |  |  | MCB-JLG-046 |  |  |  | MCB-JLG-047 |  |  |  | NMS-H-001 |  |  |  | NMS-V-003 |  |  |  | NMS-V-004 |  |  |  | TAS-GN-004 |  |  |  | TAS-GN-006 |  |  |  | TAS-GN-007 |  |  |  | TAS-GN-008 |  |  |  | TAS-GN-009 |  |  |  | TAS-GN-010 |  |  |  | TAS-GN-011 |  |  |  | TAS-GN-012 |  |  |  | TAS-GN-014 |  |  |  | TAS-GN-021 |  |  |  | TAS-GN-029 |  |  |  | UBC-014 |  |  |  | UBC-018 |  |  |  | UBC-019 |  |  |  | UBC-020 |  |  |  | UBC-021 |  |  |  | UBC-022 |  |  |  | UBC-035 |  |  |  | UBC-046 |  |  |  | UBC-050 |  |  |  | UBC-051 |  |  |  | UBC-062 |  |  |  | UBC-063 |  |  |  | UBC-064 |  |  |  | Total
|  | CS | GR | MC | SP | CS | GR | MC | SP | CS | GR | MC | SP | CS | GR | MC | SP | CS | GR | MC | SP | CS | GR | MC | SP | CS | GR | MC | SP | CS | GR | MC | SP | CS | GR | MC | SP | CS | GR | MC | SP | CS | GR | MC | SP | CS | GR | MC | SP | CS | GR | MC | SP | CS | GR | MC | SP | CS | GR | MC | SP | CS | GR | MC | SP | CS | GR | MC | SP | CS | GR | MC | SP | CS | GR | MC | SP | CS | GR | MC | SP | CS | GR | MC | SP | CS | GR | MC | SP | CS | GR | MC | SP | CS | GR | MC | SP | CS | GR | MC | SP | CS | GR | MC | SP | CS | GR | MC | SP | CS | GR | MC | SP | CS | GR | MC | SP | CS | GR | MC | SP | CS | GR | MC | SP | CS | GR | MC | SP | CS | GR | MC | SP | CS | GR | MC | SP | CS | GR | MC | SP | CS | GR | MC | SP | CS | GR | MC | SP | CS | GR | MC | SP | CS | GR | MC | SP | CS | GR | MC | SP | CS | GR | MC | SP | CS | GR | MC | SP | CS | GR | MC | SP | CS | GR | MC | SP | CS | GR | MC | SP | CS | GR | MC | SP | CS | GR | MC | SP | CS | GR | MC | SP | CS | GR | MC | SP | CS | GR | MC | SP | CS | GR | MC | SP | CS | GR | MC | SP | CS | GR | MC | SP | CS | GR | MC | SP | CS | GR | MC | SP | CS | GR | MC | SP | CS | GR | MC | SP | CS | GR | MC | SP | CS | GR | MC | SP | CS | GR | MC | SP | CS | GR | MC | SP | CS | GR | MC | SP | CS | GR | MC | SP | CS | GR | MC | SP | CS | GR | MC | SP | CS | GR | MC | SP | CS | GR | MC | SP | CS | GR | MC | SP | CS | GR | MC | SP | CS | GR | MC | SP | CS | GR | MC | SP | CS | GR | MC | SP | CS | GR | MC | SP | CS | GR | MC | SP | CS | GR | MC | SP | CS | GR | MC | SP
2025-11-24 | W1 | 0 | 7 | 0 | 7 | 0 | 6 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 6 | 4 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 5 | 0 | 8 | 0 | 5 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 3 | 27 | 11 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 15 | 0 | 0 | 6 | 6 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 1 | 1 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 2 | 2 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 6 | 6 | 6 | 0 | 2 | 2 | 2 | 0 | 7 | 6 | 6 | 6 | 0 | 0 | 3 | 6 | 0 | 0 | 2 | 13 | 5 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 3 | 0 | 3 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 443
2025-11-25 | W1 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 5 | 0 | 10 | 0 | 5 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 3 | 0 | 13 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 13 | 0 | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 6 | 6 | 6 | 0 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 3 | 2 | 0 | 0 | 2 | 0 | 5 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 232
2025-11-26 | W1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 5 | 0 | 10 | 0 | 5 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 4 | 0 | 14 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 13 | 0 | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 8 | 8 | 8 | 0 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 172
2025-11-27 | W1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-11-28 | W1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-11-29 | W2 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 3 | 6 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 14 | 22 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 5 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 3 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 325
2025-12-01 | W2 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 3 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 15 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 5 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 4 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 194
2025-12-02 | W2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 94
2025-12-03 | W2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73
2025-12-04 | W2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-05 | W2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-06 | W3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 16 | 0 | 0 | 0 | 40 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 12 | 0 | 0 | 10 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 6 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 288
2025-12-08 | W3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 15 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 6 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 134
2025-12-09 | W3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 15 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 6 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 98
2025-12-10 | W3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 15 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75
2025-12-11 | W3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-12 | W3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-13 | W4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 50 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 1 | 0 | 0 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 277
2025-12-15 | W4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 6 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 1 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 93
2025-12-16 | W4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18
2025-12-17 | W4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10
2025-12-18 | W4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-19 | W4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-20 | W5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 4 | 0 | 0 | 0 | 6 | 0 | 0 | 50 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 154
2025-12-22 | W5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 4 | 0 | 0 | 0 | 7 | 0 | 0 | 6 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68
2025-12-23 | W5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23
2025-12-24 | W5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19
2025-12-26 | W5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-27 | W6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-29 | W6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-30 | W6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-31 | W6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-01 | W6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-02 | W6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-03 | W7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-05 | W7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-06 | W7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-07 | W7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-08 | W7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-09 | W7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-10 | W8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-12 | W8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-13 | W8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-14 | W8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-15 | W8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-16 | W8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-17 | W9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-19 | W9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-20 | W9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-21 | W9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-22 | W9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-23 | W9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-24 | W10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-27 | W10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-28 | W10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-29 | W10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-30 | W10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-31 | W11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-02 | W11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-03 | W11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-04 | W11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-05 | W11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-06 | W11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-07 | W12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-09 | W12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-10 | W12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-11 | W12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-12 | W12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-13 | W12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-14 | W13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-16 | W13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-17 | W13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-18 | W13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-19 | W13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-20 | W13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-21 | W14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-23 | W14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-24 | W14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-25 | W14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-26 | W14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-27 | W14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-28 | W15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-02 | W15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-03 | W15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-04 | W15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-05 | W15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-06 | W15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-07 | W16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-09 | W16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-10 | W16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-11 | W16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-12 | W16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-13 | W16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-14 | W17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-16 | W17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-17 | W17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-18 | W17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-19 | W17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-20 | W17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-23 | W18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-24 | W18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-25 | W18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-26 | W18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-27 | W18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-28 | W19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-30 | W19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-04-01 | W19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-04-02 | W19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## 10_DAILY_INVENTORY
Date | Week | ARM-004-N |  |  |  |  | ARM-007 |  |  |  |  | ATT-001 |  |  |  |  | ATT-002 |  |  |  |  | DGC-001 |  |  |  |  | DGC-006 |  |  |  |  | DGC-009 |  |  |  |  | DGC-011 |  |  |  |  | DGC-012 |  |  |  |  | KBS-008 |  |  |  |  | KBS-009 |  |  |  |  | KBS-010 |  |  |  |  | KBS-011 |  |  |  |  | KBS-012 |  |  |  |  | KBS-014 |  |  |  |  | KBS-016 |  |  |  |  | KBS-017 |  |  |  |  | KBS-018 |  |  |  |  | LKK-01 |  |  |  |  | LKK-02 |  |  |  |  | LKK-03 |  |  |  |  | LKK-030 |  |  |  |  | LKK-031 |  |  |  |  | LKK-032 |  |  |  |  | LKK-033 |  |  |  |  | LKK-034 |  |  |  |  | LKK-035 |  |  |  |  | LKK-04 |  |  |  |  | LKK-05 |  |  |  |  | LKK-06 |  |  |  |  | LKK-10 |  |  |  |  | LKK-11 |  |  |  |  | LKK-12 |  |  |  |  | LKK-16 |  |  |  |  | LKK-17 |  |  |  |  | MCB-007 |  |  |  |  | MCB-008 |  |  |  |  | MCB-009 |  |  |  |  | MCB-010 |  |  |  |  | MCB-HYG-015 |  |  |  |  | MCB-HYG-016 |  |  |  |  | MCB-HYG-023 |  |  |  |  | MCB-HYG-026 |  |  |  |  | MCB-JLG-019 |  |  |  |  | MCB-JLG-020 |  |  |  |  | MCB-JLG-032 |  |  |  |  | MCB-JLG-033 |  |  |  |  | MCB-JLG-046 |  |  |  |  | MCB-JLG-047 |  |  |  |  | NMS-H-001 |  |  |  |  | NMS-V-003 |  |  |  |  | NMS-V-004 |  |  |  |  | TAS-GN-004 |  |  |  |  | TAS-GN-006 |  |  |  |  | TAS-GN-007 |  |  |  |  | TAS-GN-008 |  |  |  |  | TAS-GN-009 |  |  |  |  | TAS-GN-010 |  |  |  |  | TAS-GN-011 |  |  |  |  | TAS-GN-012 |  |  |  |  | TAS-GN-014 |  |  |  |  | TAS-GN-021 |  |  |  |  | TAS-GN-029 |  |  |  |  | UBC-014 |  |  |  |  | UBC-018 |  |  |  |  | UBC-019 |  |  |  |  | UBC-020 |  |  |  |  | UBC-021 |  |  |  |  | UBC-022 |  |  |  |  | UBC-035 |  |  |  |  | UBC-046 |  |  |  |  | UBC-050 |  |  |  |  | UBC-051 |  |  |  |  | UBC-062 |  |  |  |  | UBC-063 |  |  |  |  | UBC-064
|  | FG | SP | MC | GR | CS | FG | SP | MC | GR | CS | FG | SP | MC | GR | CS | FG | SP | MC | GR | CS | FG | SP | MC | GR | CS | FG | SP | MC | GR | CS | FG | SP | MC | GR | CS | FG | SP | MC | GR | CS | FG | SP | MC | GR | CS | FG | SP | MC | GR | CS | FG | SP | MC | GR | CS | FG | SP | MC | GR | CS | FG | SP | MC | GR | CS | FG | SP | MC | GR | CS | FG | SP | MC | GR | CS | FG | SP | MC | GR | CS | FG | SP | MC | GR | CS | FG | SP | MC | GR | CS | FG | SP | MC | GR | CS | FG | SP | MC | GR | CS | FG | SP | MC | GR | CS | FG | SP | MC | GR | CS | FG | SP | MC | GR | CS | FG | SP | MC | GR | CS | FG | SP | MC | GR | CS | FG | SP | MC | GR | CS | FG | SP | MC | GR | CS | FG | SP | MC | GR | CS | FG | SP | MC | GR | CS | FG | SP | MC | GR | CS | FG | SP | MC | GR | CS | FG | SP | MC | GR | CS | FG | SP | MC | GR | CS | FG | SP | MC | GR | CS | FG | SP | MC | GR | CS | FG | SP | MC | GR | CS | FG | SP | MC | GR | CS | FG | SP | MC | GR | CS | FG | SP | MC | GR | CS | FG | SP | MC | GR | CS | FG | SP | MC | GR | CS | FG | SP | MC | GR | CS | FG | SP | MC | GR | CS | FG | SP | MC | GR | CS | FG | SP | MC | GR | CS | FG | SP | MC | GR | CS | FG | SP | MC | GR | CS | FG | SP | MC | GR | CS | FG | SP | MC | GR | CS | FG | SP | MC | GR | CS | FG | SP | MC | GR | CS | FG | SP | MC | GR | CS | FG | SP | MC | GR | CS | FG | SP | MC | GR | CS | FG | SP | MC | GR | CS | FG | SP | MC | GR | CS | FG | SP | MC | GR | CS | FG | SP | MC | GR | CS | FG | SP | MC | GR | CS | FG | SP | MC | GR | CS | FG | SP | MC | GR | CS | FG | SP | MC | GR | CS | FG | SP | MC | GR | CS | FG | SP | MC | GR | CS | FG | SP | MC | GR | CS | FG | SP | MC | GR | CS | FG | SP | MC | GR | CS | FG | SP | MC | GR | CS | FG | SP | MC | GR | CS | FG | SP | MC | GR | CS | FG | SP | MC | GR | CS | FG | SP | MC | GR | CS | FG | SP | MC | GR | CS | FG | SP | MC | GR | CS | FG | SP | MC | GR | CS | FG | SP | MC | GR | CS
2025-11-24 | W1 | 14 | 0 | 0 | 15 | 0 | 18 | 0 | 0 | 19 | 0 | 13 | 2 | 1 | 1 | 12 | 8 | 3 | 3 | 3 | 3 | 166 | 84 | 0 | 174 | 17 | 0 | 0 | 0 | 8 | 6 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 0 | 12 | 6 | 12 | 0 | 6 | 11 | 0 | 10 | 4 | 0 | 21 | 31 | 4 | 1 | 0 | 6 | 0 | 6 | 2 | 0 | 11 | 27 | 21 | 0 | 0 | 35 | 28 | 24 | 0 | 0 | 24 | 24 | 38 | 1 | 18 | 9 | 19 | 43 | 3 | 0 | 10 | 36 | 19 | 5 | 11 | 0 | 1 | 0 | 2 | 4 | 4 | 12 | 4 | 0 | 0 | 0 | 17 | 1 | 0 | 2 | 12 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 6 | 2 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 1 | 3 | 4 | 0 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 4 | 8 | 0 | 2 | 0 | 0 | 9 | 0 | 5 | 2 | 0 | 11 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 0 | 5 | 7 | 7 | 3 | 1 | 0 | 51 | 10 | 0 | 9 | 1 | 1 | 11 | 0 | 20 | 6 | 10 | 7 | 4 | 1 | 0 | 64 | 0 | 0 | 1 | 5 | 2 | 4 | 0 | 4 | 19 | 0 | 0 | 2 | 13 | 8 | 4 | 3 | 0 | 1 | 11 | 0 | 0 | 0 | 2 | 0 | 36 | 0 | 0 | 0 | 13 | 0 | 0 | 0 | 0 | 4 | 0 | 1 | 0 | 0 | 2 | 0 | 0 | 0 | 2 | 4 | 0 | 4 | 0 | 9 | 15 | 16 | 12 | 0 | 2 | 13 | 0 | 4 | 0 | 4 | 0 | 2 | 10 | 0 | 8 | 7 | 0 | 6 | 0 | 0 | 2 | 12 | 4 | 1 | 0 | 2 | 13 | 0 | 0 | 0 | 10 | 14 | 1 | 0 | 0 | 13 | 0 | 10 | 0 | 0 | 11 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 3 | 2 | 15 | 0 | 0 | 0 | 0 | 10 | 6 | 0 | 0 | 6 | 22 | 0 | 0 | 0 | 0 | 35 | 30 | 0 | 22 | 4 | 8 | 30 | 0 | 9 | 31 | 0 | 0 | 0 | 0 | 0 | 19 | 6 | 0 | 0 | 24 | 0 | 1 | 0 | 0 | 0 | 8 | 4 | 2 | 5 | 6 | 10 | 54 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 7 | 0 | 4 | 0 | 0 | 41 | 28 | 4 | 0 | 0 | 17 | 31 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 0
2025-11-25 | W1 | 17 | 0 | 0 | 18 | 0 | 18 | 0 | 0 | 19 | 0 | 13 | 2 | 1 | 1 | 12 | 8 | 3 | 3 | 3 | 3 | 166 | 84 | 0 | 174 | 17 | 0 | 0 | 0 | 10 | 4 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 0 | 12 | 6 | 17 | 0 | 1 | 16 | 0 | 15 | 4 | 0 | 31 | 21 | 6 | 1 | 0 | 6 | 0 | 9 | 2 | 0 | 11 | 27 | 34 | 0 | 0 | 48 | 15 | 24 | 0 | 0 | 24 | 24 | 38 | 1 | 18 | 9 | 19 | 56 | 3 | 0 | 10 | 31 | 25 | 5 | 11 | 0 | 1 | 0 | 2 | 4 | 4 | 12 | 4 | 0 | 0 | 0 | 17 | 1 | 0 | 2 | 12 | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 6 | 2 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 1 | 3 | 4 | 0 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 4 | 8 | 0 | 2 | 0 | 0 | 9 | 0 | 5 | 2 | 0 | 11 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 0 | 5 | 7 | 7 | 3 | 1 | 0 | 51 | 10 | 0 | 9 | 1 | 1 | 11 | 0 | 20 | 6 | 10 | 7 | 4 | 1 | 0 | 76 | 0 | 0 | 1 | 7 | 0 | 4 | 0 | 4 | 19 | 0 | 0 | 2 | 13 | 8 | 4 | 3 | 0 | 1 | 11 | 0 | 0 | 0 | 2 | 0 | 60 | 0 | 0 | 0 | 13 | 0 | 0 | 0 | 0 | 4 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 2 | 5 | 0 | 4 | 0 | 9 | 21 | 10 | 18 | 0 | 2 | 13 | 0 | 7 | 0 | 4 | 0 | 0 | 10 | 0 | 8 | 7 | 0 | 9 | 0 | 0 | 2 | 17 | 6 | 1 | 0 | 2 | 15 | 0 | 0 | 0 | 15 | 9 | 1 | 0 | 0 | 17 | 0 | 15 | 0 | 0 | 16 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 3 | 2 | 21 | 0 | 0 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 18 | 0 | 0 | 0 | 0 | 36 | 30 | 0 | 22 | 4 | 8 | 30 | 0 | 9 | 34 | 0 | 0 | 0 | 0 | 0 | 19 | 6 | 0 | 0 | 24 | 0 | 1 | 0 | 0 | 0 | 8 | 4 | 2 | 5 | 6 | 12 | 54 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 7 | 0 | 4 | 0 | 0 | 42 | 27 | 4 | 0 | 0 | 17 | 31 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 0
2025-11-26 | W1 | 17 | 0 | 0 | 18 | 0 | 18 | 0 | 0 | 19 | 0 | 13 | 2 | 1 | 1 | 12 | 8 | 3 | 3 | 3 | 3 | 166 | 84 | 0 | 174 | 17 | 0 | 0 | 0 | 10 | 4 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 0 | 12 | 6 | 22 | 0 | 0 | 21 | 0 | 20 | 4 | 0 | 41 | 11 | 8 | 1 | 0 | 6 | 0 | 13 | 2 | 0 | 11 | 27 | 48 | 0 | 0 | 62 | 1 | 24 | 0 | 0 | 24 | 24 | 38 | 1 | 18 | 9 | 19 | 69 | 3 | 0 | 10 | 26 | 31 | 5 | 11 | 0 | 1 | 0 | 2 | 4 | 4 | 12 | 4 | 0 | 0 | 0 | 17 | 1 | 0 | 2 | 12 | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 6 | 2 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 1 | 3 | 4 | 0 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 4 | 8 | 0 | 2 | 0 | 0 | 9 | 0 | 5 | 2 | 0 | 11 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 0 | 5 | 7 | 7 | 3 | 1 | 0 | 51 | 10 | 0 | 9 | 1 | 1 | 11 | 0 | 20 | 6 | 10 | 7 | 4 | 1 | 0 | 76 | 0 | 0 | 1 | 9 | 0 | 4 | 0 | 4 | 19 | 0 | 0 | 2 | 13 | 8 | 4 | 3 | 0 | 1 | 11 | 0 | 0 | 0 | 2 | 0 | 60 | 0 | 0 | 0 | 13 | 0 | 0 | 0 | 0 | 4 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 2 | 5 | 0 | 4 | 0 | 9 | 27 | 4 | 26 | 0 | 2 | 13 | 0 | 10 | 0 | 4 | 0 | 0 | 10 | 0 | 8 | 7 | 0 | 9 | 0 | 0 | 2 | 17 | 6 | 1 | 0 | 2 | 15 | 0 | 0 | 0 | 20 | 4 | 1 | 0 | 0 | 17 | 0 | 20 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 3 | 2 | 27 | 0 | 0 | 0 | 0 | 10 | 14 | 0 | 0 | 14 | 14 | 0 | 0 | 0 | 0 | 36 | 30 | 0 | 22 | 4 | 8 | 30 | 0 | 9 | 37 | 0 | 0 | 0 | 0 | 0 | 19 | 6 | 0 | 0 | 24 | 0 | 1 | 0 | 0 | 0 | 8 | 4 | 2 | 5 | 6 | 14 | 54 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 7 | 0 | 4 | 0 | 0 | 42 | 27 | 4 | 0 | 0 | 17 | 31 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 0
2025-11-27 | W1 | 17 | 0 | 0 | 18 | 0 | 18 | 0 | 0 | 19 | 0 | 13 | 2 | 1 | 1 | 12 | 8 | 3 | 3 | 3 | 3 | 166 | 84 | 0 | 174 | 17 | 0 | 0 | 0 | 10 | 4 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 0 | 12 | 6 | 22 | 0 | 0 | 21 | 0 | 20 | 4 | 0 | 41 | 11 | 8 | 1 | 0 | 6 | 0 | 13 | 2 | 0 | 11 | 27 | 48 | 0 | 0 | 62 | 1 | 24 | 0 | 0 | 24 | 24 | 38 | 1 | 18 | 9 | 19 | 69 | 3 | 0 | 10 | 26 | 31 | 5 | 11 | 0 | 1 | 0 | 2 | 4 | 4 | 12 | 4 | 0 | 0 | 0 | 17 | 1 | 0 | 2 | 12 | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 6 | 2 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 1 | 3 | 4 | 0 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 4 | 8 | 0 | 2 | 0 | 0 | 9 | 0 | 5 | 2 | 0 | 11 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 0 | 5 | 7 | 7 | 3 | 1 | 0 | 51 | 10 | 0 | 9 | 1 | 1 | 11 | 0 | 20 | 6 | 10 | 7 | 4 | 1 | 0 | 76 | 0 | 0 | 1 | 9 | 0 | 4 | 0 | 4 | 19 | 0 | 0 | 2 | 13 | 8 | 4 | 3 | 0 | 1 | 11 | 0 | 0 | 0 | 2 | 0 | 60 | 0 | 0 | 0 | 13 | 0 | 0 | 0 | 0 | 4 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 2 | 5 | 0 | 4 | 0 | 9 | 27 | 4 | 26 | 0 | 2 | 13 | 0 | 10 | 0 | 4 | 0 | 0 | 10 | 0 | 8 | 7 | 0 | 9 | 0 | 0 | 2 | 17 | 6 | 1 | 0 | 2 | 15 | 0 | 0 | 0 | 20 | 4 | 1 | 0 | 0 | 17 | 0 | 20 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 3 | 2 | 27 | 0 | 0 | 0 | 0 | 10 | 14 | 0 | 0 | 14 | 14 | 0 | 0 | 0 | 0 | 36 | 30 | 0 | 22 | 4 | 8 | 30 | 0 | 9 | 37 | 0 | 0 | 0 | 0 | 0 | 19 | 6 | 0 | 0 | 24 | 0 | 1 | 0 | 0 | 0 | 8 | 4 | 2 | 5 | 6 | 14 | 54 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 7 | 0 | 4 | 0 | 0 | 42 | 27 | 4 | 0 | 0 | 17 | 31 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 0
2025-11-28 | W1 | 17 | 0 | 0 | 18 | 0 | 18 | 0 | 0 | 19 | 0 | 13 | 2 | 1 | 1 | 12 | 8 | 3 | 3 | 3 | 3 | 166 | 84 | 0 | 174 | 17 | 0 | 0 | 0 | 10 | 4 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 0 | 12 | 6 | 22 | 0 | 0 | 21 | 0 | 20 | 4 | 0 | 41 | 11 | 8 | 1 | 0 | 6 | 0 | 13 | 2 | 0 | 11 | 27 | 48 | 0 | 0 | 62 | 1 | 24 | 0 | 0 | 24 | 24 | 38 | 1 | 18 | 9 | 19 | 69 | 3 | 0 | 10 | 26 | 31 | 5 | 11 | 0 | 1 | 0 | 2 | 4 | 4 | 12 | 4 | 0 | 0 | 0 | 17 | 1 | 0 | 2 | 12 | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 6 | 2 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 1 | 3 | 4 | 0 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 4 | 8 | 0 | 2 | 0 | 0 | 9 | 0 | 5 | 2 | 0 | 11 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 0 | 5 | 7 | 7 | 3 | 1 | 0 | 51 | 10 | 0 | 9 | 1 | 1 | 11 | 0 | 20 | 6 | 10 | 7 | 4 | 1 | 0 | 76 | 0 | 0 | 1 | 9 | 0 | 4 | 0 | 4 | 19 | 0 | 0 | 2 | 13 | 8 | 4 | 3 | 0 | 1 | 11 | 0 | 0 | 0 | 2 | 0 | 60 | 0 | 0 | 0 | 13 | 0 | 0 | 0 | 0 | 4 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 2 | 5 | 0 | 4 | 0 | 9 | 27 | 4 | 26 | 0 | 2 | 13 | 0 | 10 | 0 | 4 | 0 | 0 | 10 | 0 | 8 | 7 | 0 | 9 | 0 | 0 | 2 | 17 | 6 | 1 | 0 | 2 | 15 | 0 | 0 | 0 | 20 | 4 | 1 | 0 | 0 | 17 | 0 | 20 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 3 | 2 | 27 | 0 | 0 | 0 | 0 | 10 | 14 | 0 | 0 | 14 | 14 | 0 | 0 | 0 | 0 | 36 | 30 | 0 | 22 | 4 | 8 | 30 | 0 | 9 | 37 | 0 | 0 | 0 | 0 | 0 | 19 | 6 | 0 | 0 | 24 | 0 | 1 | 0 | 0 | 0 | 8 | 4 | 2 | 5 | 6 | 14 | 54 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 7 | 0 | 4 | 0 | 0 | 42 | 27 | 4 | 0 | 0 | 17 | 31 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 0
2025-11-29 | W2 | 17 | 0 | 0 | 18 | 0 | 18 | 0 | 0 | 19 | 10 | 13 | 2 | 1 | 1 | 12 | 8 | 3 | 3 | 3 | 43 | 166 | 84 | 0 | 174 | 33 | 0 | 0 | 0 | 10 | 4 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 0 | 46 | 0 | 22 | 0 | 0 | 21 | 0 | 22 | 4 | 0 | 41 | 11 | 8 | 1 | 0 | 6 | 0 | 15 | 2 | 0 | 17 | 24 | 48 | 0 | 0 | 62 | 1 | 24 | 0 | 0 | 24 | 24 | 38 | 1 | 18 | 9 | 19 | 74 | 3 | 17 | 2 | 40 | 31 | 5 | 11 | 0 | 1 | 0 | 2 | 4 | 4 | 12 | 4 | 0 | 0 | 2 | 15 | 1 | 0 | 2 | 12 | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 1 | 3 | 0 | 0 | 0 | 6 | 2 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 1 | 3 | 4 | 0 | 2 | 2 | 0 | 2 | 8 | 2 | 2 | 0 | 2 | 2 | 8 | 0 | 2 | 0 | 5 | 9 | 0 | 5 | 2 | 14 | 11 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 10 | 0 | 0 | 0 | 9 | 3 | 7 | 3 | 1 | 22 | 29 | 10 | 0 | 9 | 1 | 1 | 11 | 0 | 20 | 6 | 10 | 7 | 4 | 1 | 21 | 55 | 0 | 0 | 1 | 9 | 0 | 4 | 0 | 4 | 23 | 0 | 0 | 2 | 13 | 8 | 4 | 3 | 0 | 1 | 11 | 0 | 0 | 0 | 2 | 11 | 49 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 4 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 2 | 5 | 0 | 4 | 0 | 9 | 27 | 4 | 26 | 0 | 2 | 13 | 0 | 10 | 0 | 4 | 0 | 0 | 10 | 0 | 8 | 7 | 0 | 11 | 0 | 0 | 2 | 17 | 6 | 1 | 0 | 2 | 15 | 5 | 0 | 0 | 20 | 4 | 1 | 0 | 0 | 20 | 2 | 20 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 4 | 0 | 1 | 5 | 24 | 0 | 0 | 0 | 2 | 8 | 14 | 0 | 0 | 14 | 14 | 0 | 0 | 0 | 0 | 36 | 30 | 0 | 22 | 4 | 8 | 34 | 0 | 5 | 37 | 0 | 0 | 0 | 0 | 5 | 14 | 6 | 0 | 0 | 24 | 0 | 1 | 0 | 0 | 0 | 8 | 4 | 2 | 5 | 8 | 12 | 54 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 7 | 0 | 4 | 0 | 0 | 42 | 27 | 4 | 0 | 0 | 17 | 31 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 0
2025-12-01 | W2 | 17 | 0 | 0 | 18 | 0 | 18 | 0 | 0 | 19 | 18 | 13 | 2 | 1 | 1 | 12 | 8 | 3 | 3 | 3 | 47 | 166 | 84 | 0 | 174 | 51 | 0 | 0 | 0 | 10 | 4 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 0 | 46 | 0 | 22 | 0 | 0 | 21 | 0 | 24 | 4 | 0 | 41 | 11 | 8 | 1 | 0 | 6 | 0 | 15 | 2 | 0 | 25 | 19 | 48 | 0 | 0 | 62 | 1 | 24 | 0 | 0 | 24 | 24 | 38 | 1 | 18 | 9 | 19 | 79 | 3 | 12 | 17 | 31 | 31 | 5 | 11 | 0 | 1 | 0 | 2 | 4 | 4 | 12 | 4 | 0 | 0 | 4 | 13 | 1 | 0 | 2 | 12 | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 6 | 2 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 1 | 3 | 4 | 0 | 2 | 2 | 0 | 4 | 6 | 2 | 2 | 0 | 4 | 0 | 8 | 0 | 2 | 0 | 10 | 9 | 0 | 5 | 2 | 24 | 11 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 7 | 0 | 0 | 0 | 14 | 0 | 7 | 3 | 1 | 44 | 7 | 10 | 0 | 9 | 1 | 1 | 11 | 0 | 20 | 6 | 10 | 7 | 4 | 1 | 35 | 41 | 0 | 0 | 1 | 9 | 0 | 4 | 0 | 4 | 29 | 0 | 0 | 2 | 13 | 8 | 4 | 3 | 0 | 1 | 11 | 0 | 0 | 0 | 2 | 21 | 39 | 0 | 0 | 0 | 17 | 0 | 0 | 0 | 0 | 4 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 2 | 5 | 0 | 4 | 0 | 9 | 27 | 4 | 26 | 0 | 2 | 13 | 0 | 10 | 0 | 4 | 0 | 0 | 10 | 0 | 8 | 7 | 0 | 13 | 0 | 0 | 2 | 17 | 6 | 1 | 0 | 2 | 15 | 10 | 0 | 0 | 20 | 4 | 1 | 0 | 0 | 22 | 4 | 20 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 2 | 0 | 6 | 0 | 0 | 9 | 20 | 0 | 0 | 0 | 4 | 6 | 14 | 0 | 0 | 14 | 14 | 0 | 0 | 0 | 0 | 36 | 30 | 0 | 22 | 4 | 8 | 38 | 0 | 1 | 37 | 0 | 0 | 0 | 0 | 8 | 11 | 6 | 0 | 0 | 24 | 0 | 1 | 0 | 0 | 0 | 8 | 4 | 2 | 5 | 10 | 10 | 54 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 7 | 0 | 4 | 0 | 0 | 42 | 27 | 4 | 0 | 0 | 17 | 31 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 0
2025-12-02 | W2 | 17 | 0 | 0 | 18 | 0 | 18 | 0 | 0 | 19 | 18 | 13 | 2 | 1 | 1 | 12 | 8 | 3 | 3 | 3 | 47 | 166 | 84 | 0 | 174 | 59 | 0 | 0 | 0 | 10 | 4 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 0 | 46 | 0 | 22 | 0 | 0 | 21 | 0 | 24 | 4 | 0 | 41 | 11 | 8 | 1 | 0 | 6 | 0 | 15 | 2 | 0 | 33 | 14 | 48 | 0 | 0 | 62 | 1 | 24 | 0 | 0 | 24 | 24 | 38 | 1 | 18 | 9 | 19 | 84 | 3 | 7 | 30 | 18 | 31 | 5 | 11 | 0 | 1 | 0 | 2 | 4 | 4 | 12 | 4 | 0 | 0 | 4 | 13 | 1 | 0 | 2 | 12 | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 6 | 2 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 1 | 3 | 4 | 0 | 2 | 2 | 0 | 4 | 6 | 2 | 2 | 0 | 4 | 0 | 8 | 0 | 2 | 0 | 16 | 9 | 0 | 5 | 2 | 24 | 11 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 4 | 0 | 0 | 0 | 17 | 0 | 7 | 3 | 1 | 44 | 7 | 10 | 0 | 9 | 1 | 1 | 11 | 0 | 20 | 6 | 10 | 7 | 4 | 1 | 38 | 38 | 0 | 0 | 1 | 9 | 0 | 4 | 0 | 4 | 29 | 0 | 0 | 2 | 13 | 8 | 4 | 3 | 0 | 1 | 11 | 0 | 0 | 0 | 2 | 33 | 27 | 0 | 0 | 0 | 17 | 0 | 0 | 0 | 0 | 4 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 2 | 5 | 0 | 4 | 0 | 9 | 27 | 4 | 26 | 0 | 2 | 13 | 0 | 10 | 0 | 4 | 0 | 0 | 10 | 0 | 8 | 7 | 0 | 15 | 0 | 0 | 2 | 17 | 6 | 1 | 0 | 2 | 15 | 15 | 0 | 0 | 20 | 4 | 1 | 0 | 0 | 23 | 7 | 20 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 2 | 0 | 9 | 0 | 0 | 9 | 20 | 0 | 0 | 0 | 7 | 3 | 14 | 0 | 0 | 14 | 14 | 0 | 0 | 0 | 0 | 36 | 30 | 0 | 22 | 4 | 8 | 43 | 0 | 0 | 37 | 0 | 0 | 0 | 0 | 12 | 7 | 6 | 0 | 0 | 24 | 0 | 1 | 0 | 0 | 0 | 8 | 4 | 2 | 5 | 12 | 8 | 54 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 7 | 0 | 4 | 0 | 0 | 42 | 27 | 4 | 0 | 0 | 17 | 31 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 0
2025-12-03 | W2 | 17 | 0 | 0 | 18 | 0 | 18 | 0 | 0 | 19 | 18 | 13 | 2 | 1 | 1 | 12 | 8 | 3 | 3 | 3 | 47 | 166 | 84 | 0 | 174 | 59 | 0 | 0 | 0 | 10 | 4 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 0 | 46 | 0 | 22 | 0 | 0 | 21 | 0 | 24 | 4 | 0 | 41 | 11 | 8 | 1 | 0 | 6 | 0 | 15 | 2 | 0 | 41 | 10 | 48 | 0 | 0 | 62 | 1 | 24 | 0 | 0 | 24 | 24 | 38 | 1 | 18 | 9 | 19 | 89 | 3 | 2 | 43 | 5 | 31 | 5 | 11 | 0 | 1 | 0 | 2 | 4 | 4 | 12 | 4 | 0 | 0 | 4 | 13 | 1 | 0 | 2 | 12 | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 6 | 2 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 1 | 3 | 4 | 0 | 2 | 2 | 0 | 4 | 6 | 2 | 2 | 0 | 4 | 0 | 8 | 0 | 2 | 0 | 22 | 9 | 0 | 5 | 2 | 24 | 11 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 1 | 0 | 0 | 0 | 17 | 0 | 7 | 3 | 1 | 44 | 7 | 10 | 0 | 9 | 1 | 1 | 11 | 0 | 20 | 6 | 10 | 7 | 4 | 1 | 38 | 38 | 0 | 0 | 1 | 9 | 0 | 4 | 0 | 4 | 29 | 0 | 0 | 2 | 13 | 8 | 4 | 3 | 0 | 1 | 11 | 0 | 0 | 0 | 2 | 45 | 15 | 0 | 0 | 0 | 17 | 0 | 0 | 0 | 0 | 4 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 2 | 5 | 0 | 4 | 0 | 9 | 27 | 4 | 26 | 0 | 2 | 13 | 0 | 10 | 0 | 4 | 0 | 0 | 10 | 0 | 8 | 7 | 0 | 15 | 0 | 0 | 2 | 17 | 6 | 1 | 0 | 2 | 15 | 20 | 0 | 0 | 20 | 4 | 1 | 0 | 0 | 23 | 7 | 20 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 2 | 0 | 12 | 0 | 0 | 9 | 20 | 0 | 0 | 0 | 10 | 0 | 14 | 0 | 0 | 14 | 14 | 0 | 0 | 0 | 0 | 36 | 30 | 0 | 22 | 4 | 8 | 48 | 0 | 0 | 37 | 0 | 0 | 0 | 0 | 16 | 3 | 6 | 0 | 0 | 24 | 0 | 1 | 0 | 0 | 0 | 8 | 4 | 2 | 5 | 14 | 6 | 54 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 7 | 0 | 4 | 0 | 0 | 42 | 27 | 4 | 0 | 0 | 17 | 31 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 0
2025-12-04 | W2 | 17 | 0 | 0 | 18 | 0 | 18 | 0 | 0 | 19 | 18 | 13 | 2 | 1 | 1 | 12 | 8 | 3 | 3 | 3 | 47 | 166 | 84 | 0 | 174 | 59 | 0 | 0 | 0 | 10 | 4 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 0 | 46 | 0 | 22 | 0 | 0 | 21 | 0 | 24 | 4 | 0 | 41 | 11 | 8 | 1 | 0 | 6 | 0 | 15 | 2 | 0 | 41 | 10 | 48 | 0 | 0 | 62 | 1 | 24 | 0 | 0 | 24 | 24 | 38 | 1 | 18 | 9 | 19 | 89 | 3 | 2 | 43 | 5 | 31 | 5 | 11 | 0 | 1 | 0 | 2 | 4 | 4 | 12 | 4 | 0 | 0 | 4 | 13 | 1 | 0 | 2 | 12 | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 6 | 2 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 1 | 3 | 4 | 0 | 2 | 2 | 0 | 4 | 6 | 2 | 2 | 0 | 4 | 0 | 8 | 0 | 2 | 0 | 22 | 9 | 0 | 5 | 2 | 24 | 11 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 1 | 0 | 0 | 0 | 17 | 0 | 7 | 3 | 1 | 44 | 7 | 10 | 0 | 9 | 1 | 1 | 11 | 0 | 20 | 6 | 10 | 7 | 4 | 1 | 38 | 38 | 0 | 0 | 1 | 9 | 0 | 4 | 0 | 4 | 29 | 0 | 0 | 2 | 13 | 8 | 4 | 3 | 0 | 1 | 11 | 0 | 0 | 0 | 2 | 45 | 15 | 0 | 0 | 0 | 17 | 0 | 0 | 0 | 0 | 4 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 2 | 5 | 0 | 4 | 0 | 9 | 27 | 4 | 26 | 0 | 2 | 13 | 0 | 10 | 0 | 4 | 0 | 0 | 10 | 0 | 8 | 7 | 0 | 15 | 0 | 0 | 2 | 17 | 6 | 1 | 0 | 2 | 15 | 20 | 0 | 0 | 20 | 4 | 1 | 0 | 0 | 23 | 7 | 20 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 2 | 0 | 12 | 0 | 0 | 9 | 20 | 0 | 0 | 0 | 10 | 0 | 14 | 0 | 0 | 14 | 14 | 0 | 0 | 0 | 0 | 36 | 30 | 0 | 22 | 4 | 8 | 48 | 0 | 0 | 37 | 0 | 0 | 0 | 0 | 16 | 3 | 6 | 0 | 0 | 24 | 0 | 1 | 0 | 0 | 0 | 8 | 4 | 2 | 5 | 14 | 6 | 54 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 7 | 0 | 4 | 0 | 0 | 42 | 27 | 4 | 0 | 0 | 17 | 31 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 0
2025-12-05 | W2 | 17 | 0 | 0 | 18 | 0 | 18 | 0 | 0 | 19 | 18 | 13 | 2 | 1 | 1 | 12 | 8 | 3 | 3 | 3 | 47 | 166 | 84 | 0 | 174 | 59 | 0 | 0 | 0 | 10 | 4 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 0 | 46 | 0 | 22 | 0 | 0 | 21 | 0 | 24 | 4 | 0 | 41 | 11 | 8 | 1 | 0 | 6 | 0 | 15 | 2 | 0 | 41 | 10 | 48 | 0 | 0 | 62 | 1 | 24 | 0 | 0 | 24 | 24 | 38 | 1 | 18 | 9 | 19 | 89 | 3 | 2 | 43 | 5 | 31 | 5 | 11 | 0 | 1 | 0 | 2 | 4 | 4 | 12 | 4 | 0 | 0 | 4 | 13 | 1 | 0 | 2 | 12 | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 6 | 2 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 1 | 3 | 4 | 0 | 2 | 2 | 0 | 4 | 6 | 2 | 2 | 0 | 4 | 0 | 8 | 0 | 2 | 0 | 22 | 9 | 0 | 5 | 2 | 24 | 11 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 1 | 0 | 0 | 0 | 17 | 0 | 7 | 3 | 1 | 44 | 7 | 10 | 0 | 9 | 1 | 1 | 11 | 0 | 20 | 6 | 10 | 7 | 4 | 1 | 38 | 38 | 0 | 0 | 1 | 9 | 0 | 4 | 0 | 4 | 29 | 0 | 0 | 2 | 13 | 8 | 4 | 3 | 0 | 1 | 11 | 0 | 0 | 0 | 2 | 45 | 15 | 0 | 0 | 0 | 17 | 0 | 0 | 0 | 0 | 4 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 2 | 5 | 0 | 4 | 0 | 9 | 27 | 4 | 26 | 0 | 2 | 13 | 0 | 10 | 0 | 4 | 0 | 0 | 10 | 0 | 8 | 7 | 0 | 15 | 0 | 0 | 2 | 17 | 6 | 1 | 0 | 2 | 15 | 20 | 0 | 0 | 20 | 4 | 1 | 0 | 0 | 23 | 7 | 20 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 2 | 0 | 12 | 0 | 0 | 9 | 20 | 0 | 0 | 0 | 10 | 0 | 14 | 0 | 0 | 14 | 14 | 0 | 0 | 0 | 0 | 36 | 30 | 0 | 22 | 4 | 8 | 48 | 0 | 0 | 37 | 0 | 0 | 0 | 0 | 16 | 3 | 6 | 0 | 0 | 24 | 0 | 1 | 0 | 0 | 0 | 8 | 4 | 2 | 5 | 14 | 6 | 54 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 7 | 0 | 4 | 0 | 0 | 42 | 27 | 4 | 0 | 0 | 17 | 31 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 0
2025-12-06 | W3 | 17 | 0 | 0 | 18 | 0 | 20 | 0 | 0 | 19 | 18 | 13 | 2 | 1 | 7 | 6 | 8 | 3 | 3 | 3 | 47 | 166 | 84 | 0 | 174 | 109 | 0 | 0 | 0 | 10 | 4 | 0 | 0 | 0 | 3 | 11 | 0 | 0 | 0 | 0 | 16 | 40 | 22 | 0 | 46 | 40 | 22 | 0 | 0 | 21 | 0 | 24 | 4 | 0 | 41 | 11 | 8 | 1 | 0 | 6 | 0 | 15 | 2 | 0 | 41 | 10 | 49 | 0 | 0 | 63 | 0 | 24 | 0 | 0 | 24 | 24 | 50 | 1 | 6 | 21 | 7 | 111 | 3 | 0 | 33 | 5 | 31 | 5 | 11 | 0 | 1 | 0 | 2 | 4 | 4 | 12 | 4 | 0 | 0 | 4 | 13 | 1 | 0 | 2 | 12 | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 6 | 2 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 2 | 7 | 0 | 1 | 3 | 4 | 0 | 2 | 2 | 0 | 4 | 6 | 2 | 2 | 0 | 4 | 0 | 8 | 0 | 2 | 0 | 22 | 9 | 0 | 5 | 2 | 24 | 11 | 0 | 1 | 2 | 12 | 0 | 0 | 0 | 12 | 1 | 0 | 0 | 0 | 17 | 0 | 7 | 3 | 1 | 44 | 7 | 10 | 0 | 9 | 1 | 1 | 11 | 0 | 20 | 12 | 12 | 7 | 4 | 1 | 44 | 32 | 0 | 0 | 1 | 9 | 0 | 4 | 0 | 4 | 29 | 0 | 0 | 2 | 13 | 8 | 4 | 3 | 0 | 1 | 11 | 0 | 0 | 0 | 2 | 45 | 15 | 0 | 0 | 0 | 17 | 0 | 0 | 0 | 0 | 4 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 2 | 5 | 0 | 4 | 0 | 9 | 29 | 2 | 26 | 0 | 2 | 13 | 0 | 10 | 0 | 4 | 0 | 0 | 10 | 0 | 8 | 7 | 10 | 15 | 0 | 0 | 2 | 17 | 6 | 1 | 0 | 6 | 11 | 20 | 0 | 0 | 20 | 4 | 1 | 0 | 0 | 23 | 7 | 20 | 0 | 0 | 21 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 2 | 0 | 12 | 0 | 0 | 9 | 20 | 2 | 0 | 0 | 10 | 0 | 14 | 0 | 0 | 14 | 14 | 8 | 0 | 0 | 1 | 35 | 30 | 0 | 22 | 4 | 8 | 48 | 0 | 0 | 37 | 0 | 5 | 0 | 0 | 16 | 3 | 6 | 0 | 0 | 24 | 0 | 1 | 0 | 0 | 0 | 8 | 4 | 2 | 5 | 14 | 6 | 54 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 7 | 0 | 4 | 0 | 0 | 42 | 27 | 4 | 0 | 0 | 17 | 31 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 0
2025-12-08 | W3 | 17 | 0 | 0 | 18 | 0 | 22 | 0 | 0 | 19 | 18 | 13 | 2 | 1 | 14 | 0 | 8 | 3 | 3 | 3 | 47 | 166 | 84 | 0 | 174 | 115 | 0 | 0 | 0 | 10 | 4 | 0 | 0 | 0 | 6 | 8 | 0 | 0 | 0 | 0 | 21 | 40 | 22 | 0 | 46 | 40 | 22 | 0 | 0 | 21 | 0 | 24 | 4 | 0 | 41 | 11 | 8 | 1 | 0 | 6 | 0 | 15 | 2 | 0 | 41 | 10 | 49 | 0 | 0 | 63 | 0 | 24 | 0 | 0 | 24 | 24 | 65 | 1 | 0 | 36 | 0 | 111 | 3 | 10 | 23 | 5 | 31 | 5 | 11 | 0 | 1 | 0 | 2 | 4 | 4 | 12 | 4 | 0 | 0 | 4 | 13 | 1 | 0 | 2 | 12 | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 6 | 2 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 4 | 5 | 0 | 1 | 3 | 4 | 0 | 2 | 2 | 0 | 4 | 6 | 2 | 2 | 0 | 4 | 0 | 8 | 0 | 2 | 0 | 22 | 9 | 0 | 5 | 2 | 24 | 11 | 0 | 1 | 4 | 20 | 0 | 0 | 0 | 12 | 1 | 0 | 0 | 0 | 17 | 0 | 7 | 3 | 1 | 44 | 7 | 10 | 0 | 9 | 1 | 1 | 11 | 0 | 20 | 18 | 14 | 7 | 4 | 1 | 50 | 26 | 0 | 0 | 1 | 9 | 0 | 4 | 0 | 4 | 29 | 0 | 0 | 2 | 13 | 8 | 4 | 3 | 0 | 1 | 11 | 0 | 0 | 0 | 2 | 45 | 15 | 0 | 0 | 0 | 17 | 0 | 0 | 0 | 0 | 4 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 2 | 5 | 0 | 4 | 0 | 9 | 32 | 0 | 26 | 0 | 2 | 13 | 0 | 10 | 0 | 4 | 0 | 0 | 10 | 0 | 8 | 7 | 23 | 15 | 0 | 0 | 2 | 17 | 6 | 1 | 0 | 10 | 7 | 20 | 0 | 0 | 20 | 4 | 1 | 0 | 0 | 23 | 7 | 20 | 0 | 0 | 21 | 0 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 2 | 0 | 12 | 0 | 0 | 9 | 20 | 4 | 0 | 0 | 10 | 0 | 14 | 0 | 0 | 14 | 14 | 16 | 0 | 0 | 2 | 34 | 30 | 0 | 22 | 4 | 8 | 48 | 0 | 0 | 37 | 0 | 8 | 0 | 0 | 16 | 3 | 6 | 0 | 0 | 24 | 0 | 1 | 0 | 0 | 0 | 8 | 4 | 2 | 5 | 14 | 6 | 54 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 7 | 0 | 4 | 0 | 0 | 42 | 27 | 4 | 0 | 0 | 17 | 31 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 0
2025-12-09 | W3 | 17 | 0 | 0 | 18 | 0 | 22 | 0 | 0 | 19 | 18 | 13 | 2 | 1 | 17 | 0 | 8 | 3 | 3 | 3 | 47 | 166 | 84 | 0 | 174 | 115 | 0 | 0 | 0 | 10 | 4 | 0 | 0 | 0 | 10 | 4 | 0 | 0 | 0 | 0 | 21 | 40 | 22 | 0 | 46 | 40 | 22 | 0 | 0 | 21 | 0 | 24 | 4 | 0 | 41 | 11 | 8 | 1 | 0 | 6 | 0 | 15 | 2 | 0 | 41 | 10 | 49 | 0 | 0 | 63 | 0 | 24 | 0 | 0 | 24 | 24 | 80 | 1 | 0 | 51 | 0 | 111 | 3 | 20 | 13 | 5 | 31 | 5 | 11 | 0 | 1 | 0 | 2 | 4 | 4 | 12 | 4 | 0 | 0 | 4 | 13 | 1 | 0 | 2 | 12 | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 6 | 2 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 6 | 3 | 0 | 1 | 3 | 4 | 0 | 2 | 2 | 0 | 4 | 6 | 2 | 2 | 0 | 4 | 0 | 8 | 0 | 2 | 0 | 22 | 9 | 0 | 5 | 2 | 24 | 11 | 0 | 1 | 7 | 17 | 0 | 0 | 0 | 12 | 1 | 0 | 0 | 0 | 17 | 0 | 7 | 3 | 1 | 44 | 7 | 10 | 0 | 9 | 1 | 1 | 11 | 0 | 20 | 24 | 16 | 7 | 4 | 1 | 59 | 17 | 0 | 0 | 1 | 9 | 0 | 4 | 0 | 4 | 29 | 0 | 0 | 2 | 13 | 8 | 4 | 3 | 0 | 1 | 11 | 0 | 0 | 0 | 2 | 45 | 15 | 0 | 0 | 0 | 17 | 0 | 0 | 0 | 0 | 4 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 2 | 5 | 0 | 4 | 0 | 9 | 35 | 0 | 26 | 0 | 2 | 13 | 0 | 10 | 0 | 4 | 0 | 0 | 10 | 0 | 8 | 7 | 23 | 15 | 0 | 0 | 2 | 17 | 6 | 1 | 0 | 14 | 3 | 20 | 0 | 0 | 20 | 4 | 1 | 0 | 0 | 23 | 7 | 20 | 0 | 0 | 21 | 0 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 2 | 0 | 12 | 0 | 0 | 9 | 20 | 7 | 0 | 0 | 10 | 0 | 14 | 0 | 0 | 14 | 14 | 24 | 0 | 0 | 3 | 33 | 30 | 0 | 22 | 4 | 8 | 48 | 0 | 0 | 37 | 0 | 12 | 0 | 0 | 16 | 3 | 6 | 0 | 0 | 24 | 0 | 1 | 0 | 0 | 0 | 8 | 4 | 2 | 5 | 14 | 6 | 54 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 7 | 0 | 4 | 0 | 0 | 42 | 27 | 4 | 0 | 0 | 17 | 31 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 0
2025-12-10 | W3 | 17 | 0 | 0 | 18 | 0 | 22 | 0 | 0 | 19 | 18 | 13 | 2 | 1 | 17 | 0 | 8 | 3 | 3 | 3 | 47 | 166 | 84 | 0 | 174 | 115 | 0 | 0 | 0 | 10 | 4 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 21 | 40 | 22 | 0 | 46 | 40 | 22 | 0 | 0 | 21 | 0 | 24 | 4 | 0 | 41 | 11 | 8 | 1 | 0 | 6 | 0 | 15 | 2 | 0 | 41 | 10 | 49 | 0 | 0 | 63 | 0 | 24 | 0 | 0 | 24 | 24 | 95 | 1 | 0 | 66 | 0 | 111 | 3 | 30 | 3 | 5 | 31 | 5 | 11 | 0 | 1 | 0 | 2 | 4 | 4 | 12 | 4 | 0 | 0 | 4 | 13 | 1 | 0 | 2 | 12 | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 6 | 2 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 3 | 4 | 0 | 2 | 2 | 0 | 4 | 6 | 2 | 2 | 0 | 4 | 0 | 8 | 0 | 2 | 0 | 22 | 9 | 0 | 5 | 2 | 24 | 11 | 0 | 1 | 10 | 14 | 0 | 0 | 0 | 12 | 1 | 0 | 0 | 0 | 17 | 0 | 7 | 3 | 1 | 44 | 7 | 10 | 0 | 9 | 1 | 1 | 11 | 0 | 20 | 30 | 10 | 7 | 4 | 1 | 59 | 17 | 0 | 0 | 1 | 9 | 0 | 4 | 0 | 4 | 29 | 0 | 0 | 2 | 13 | 8 | 4 | 3 | 0 | 1 | 11 | 0 | 0 | 0 | 2 | 45 | 15 | 0 | 0 | 0 | 17 | 0 | 0 | 0 | 0 | 4 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 2 | 5 | 0 | 4 | 0 | 9 | 38 | 0 | 26 | 0 | 2 | 13 | 0 | 10 | 0 | 4 | 0 | 0 | 10 | 0 | 8 | 7 | 23 | 15 | 0 | 0 | 2 | 17 | 6 | 1 | 0 | 17 | 0 | 20 | 0 | 0 | 20 | 4 | 1 | 0 | 0 | 23 | 7 | 20 | 0 | 0 | 21 | 0 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 2 | 0 | 12 | 0 | 0 | 9 | 20 | 10 | 0 | 0 | 10 | 0 | 14 | 0 | 0 | 14 | 14 | 30 | 0 | 0 | 3 | 33 | 30 | 0 | 22 | 4 | 8 | 48 | 0 | 0 | 37 | 0 | 16 | 0 | 0 | 16 | 3 | 6 | 0 | 0 | 24 | 0 | 1 | 0 | 0 | 0 | 8 | 4 | 2 | 5 | 14 | 6 | 54 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 7 | 0 | 4 | 0 | 0 | 42 | 27 | 4 | 0 | 0 | 17 | 31 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 0
2025-12-11 | W3 | 17 | 0 | 0 | 18 | 0 | 22 | 0 | 0 | 19 | 18 | 13 | 2 | 1 | 17 | 0 | 8 | 3 | 3 | 3 | 47 | 166 | 84 | 0 | 174 | 115 | 0 | 0 | 0 | 10 | 4 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 21 | 40 | 22 | 0 | 46 | 40 | 22 | 0 | 0 | 21 | 0 | 24 | 4 | 0 | 41 | 11 | 8 | 1 | 0 | 6 | 0 | 15 | 2 | 0 | 41 | 10 | 49 | 0 | 0 | 63 | 0 | 24 | 0 | 0 | 24 | 24 | 95 | 1 | 0 | 66 | 0 | 111 | 3 | 30 | 3 | 5 | 31 | 5 | 11 | 0 | 1 | 0 | 2 | 4 | 4 | 12 | 4 | 0 | 0 | 4 | 13 | 1 | 0 | 2 | 12 | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 6 | 2 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 3 | 4 | 0 | 2 | 2 | 0 | 4 | 6 | 2 | 2 | 0 | 4 | 0 | 8 | 0 | 2 | 0 | 22 | 9 | 0 | 5 | 2 | 24 | 11 | 0 | 1 | 10 | 14 | 0 | 0 | 0 | 12 | 1 | 0 | 0 | 0 | 17 | 0 | 7 | 3 | 1 | 44 | 7 | 10 | 0 | 9 | 1 | 1 | 11 | 0 | 20 | 30 | 10 | 7 | 4 | 1 | 59 | 17 | 0 | 0 | 1 | 9 | 0 | 4 | 0 | 4 | 29 | 0 | 0 | 2 | 13 | 8 | 4 | 3 | 0 | 1 | 11 | 0 | 0 | 0 | 2 | 45 | 15 | 0 | 0 | 0 | 17 | 0 | 0 | 0 | 0 | 4 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 2 | 5 | 0 | 4 | 0 | 9 | 38 | 0 | 26 | 0 | 2 | 13 | 0 | 10 | 0 | 4 | 0 | 0 | 10 | 0 | 8 | 7 | 23 | 15 | 0 | 0 | 2 | 17 | 6 | 1 | 0 | 17 | 0 | 20 | 0 | 0 | 20 | 4 | 1 | 0 | 0 | 23 | 7 | 20 | 0 | 0 | 21 | 0 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 2 | 0 | 12 | 0 | 0 | 9 | 20 | 10 | 0 | 0 | 10 | 0 | 14 | 0 | 0 | 14 | 14 | 30 | 0 | 0 | 3 | 33 | 30 | 0 | 22 | 4 | 8 | 48 | 0 | 0 | 37 | 0 | 16 | 0 | 0 | 16 | 3 | 6 | 0 | 0 | 24 | 0 | 1 | 0 | 0 | 0 | 8 | 4 | 2 | 5 | 14 | 6 | 54 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 7 | 0 | 4 | 0 | 0 | 42 | 27 | 4 | 0 | 0 | 17 | 31 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 0
2025-12-12 | W3 | 17 | 0 | 0 | 18 | 0 | 22 | 0 | 0 | 19 | 18 | 13 | 2 | 1 | 17 | 0 | 8 | 3 | 3 | 3 | 47 | 166 | 84 | 0 | 174 | 115 | 0 | 0 | 0 | 10 | 4 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 21 | 40 | 22 | 0 | 46 | 40 | 22 | 0 | 0 | 21 | 0 | 24 | 4 | 0 | 41 | 11 | 8 | 1 | 0 | 6 | 0 | 15 | 2 | 0 | 41 | 10 | 49 | 0 | 0 | 63 | 0 | 24 | 0 | 0 | 24 | 24 | 95 | 1 | 0 | 66 | 0 | 111 | 3 | 30 | 3 | 5 | 31 | 5 | 11 | 0 | 1 | 0 | 2 | 4 | 4 | 12 | 4 | 0 | 0 | 4 | 13 | 1 | 0 | 2 | 12 | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 6 | 2 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 3 | 4 | 0 | 2 | 2 | 0 | 4 | 6 | 2 | 2 | 0 | 4 | 0 | 8 | 0 | 2 | 0 | 22 | 9 | 0 | 5 | 2 | 24 | 11 | 0 | 1 | 10 | 14 | 0 | 0 | 0 | 12 | 1 | 0 | 0 | 0 | 17 | 0 | 7 | 3 | 1 | 44 | 7 | 10 | 0 | 9 | 1 | 1 | 11 | 0 | 20 | 30 | 10 | 7 | 4 | 1 | 59 | 17 | 0 | 0 | 1 | 9 | 0 | 4 | 0 | 4 | 29 | 0 | 0 | 2 | 13 | 8 | 4 | 3 | 0 | 1 | 11 | 0 | 0 | 0 | 2 | 45 | 15 | 0 | 0 | 0 | 17 | 0 | 0 | 0 | 0 | 4 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 2 | 5 | 0 | 4 | 0 | 9 | 38 | 0 | 26 | 0 | 2 | 13 | 0 | 10 | 0 | 4 | 0 | 0 | 10 | 0 | 8 | 7 | 23 | 15 | 0 | 0 | 2 | 17 | 6 | 1 | 0 | 17 | 0 | 20 | 0 | 0 | 20 | 4 | 1 | 0 | 0 | 23 | 7 | 20 | 0 | 0 | 21 | 0 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 2 | 0 | 12 | 0 | 0 | 9 | 20 | 10 | 0 | 0 | 10 | 0 | 14 | 0 | 0 | 14 | 14 | 30 | 0 | 0 | 3 | 33 | 30 | 0 | 22 | 4 | 8 | 48 | 0 | 0 | 37 | 0 | 16 | 0 | 0 | 16 | 3 | 6 | 0 | 0 | 24 | 0 | 1 | 0 | 0 | 0 | 8 | 4 | 2 | 5 | 14 | 6 | 54 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 7 | 0 | 4 | 0 | 0 | 42 | 27 | 4 | 0 | 0 | 17 | 31 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 0
2025-12-13 | W4 | 17 | 0 | 0 | 18 | 0 | 22 | 0 | 0 | 19 | 18 | 13 | 2 | 1 | 17 | 0 | 8 | 3 | 3 | 7 | 43 | 266 | 84 | 0 | 224 | 65 | 0 | 0 | 0 | 10 | 4 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 21 | 40 | 22 | 0 | 46 | 40 | 22 | 0 | 0 | 21 | 0 | 24 | 4 | 0 | 43 | 9 | 8 | 1 | 0 | 6 | 0 | 15 | 2 | 0 | 41 | 10 | 49 | 0 | 0 | 63 | 0 | 24 | 0 | 0 | 24 | 24 | 95 | 1 | 0 | 66 | 0 | 111 | 3 | 30 | 3 | 5 | 31 | 5 | 11 | 0 | 1 | 0 | 2 | 4 | 5 | 25 | 4 | 0 | 0 | 6 | 15 | 1 | 0 | 2 | 12 | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 6 | 2 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 3 | 4 | 0 | 2 | 2 | 0 | 4 | 6 | 2 | 2 | 0 | 4 | 0 | 8 | 0 | 2 | 2 | 20 | 9 | 0 | 5 | 6 | 20 | 11 | 0 | 1 | 10 | 14 | 0 | 0 | 0 | 12 | 1 | 0 | 0 | 0 | 17 | 0 | 7 | 3 | 1 | 50 | 1 | 10 | 0 | 9 | 1 | 1 | 11 | 0 | 20 | 30 | 10 | 7 | 4 | 1 | 59 | 17 | 0 | 0 | 1 | 9 | 0 | 4 | 0 | 4 | 29 | 0 | 0 | 2 | 13 | 8 | 4 | 3 | 0 | 1 | 11 | 0 | 0 | 0 | 2 | 45 | 15 | 0 | 0 | 0 | 19 | 0 | 0 | 0 | 0 | 4 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 2 | 5 | 0 | 4 | 0 | 9 | 38 | 25 | 26 | 0 | 2 | 13 | 0 | 10 | 0 | 4 | 0 | 0 | 10 | 0 | 8 | 7 | 23 | 15 | 0 | 0 | 4 | 15 | 6 | 1 | 0 | 17 | 0 | 20 | 0 | 0 | 20 | 4 | 1 | 0 | 0 | 23 | 7 | 20 | 0 | 0 | 21 | 0 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 2 | 0 | 15 | 0 | 0 | 9 | 20 | 10 | 0 | 0 | 10 | 0 | 14 | 0 | 0 | 14 | 14 | 30 | 0 | 0 | 3 | 33 | 30 | 0 | 22 | 4 | 63 | 48 | 0 | 0 | 37 | 0 | 16 | 0 | 0 | 16 | 3 | 6 | 0 | 0 | 24 | 0 | 1 | 0 | 0 | 1 | 7 | 4 | 2 | 5 | 14 | 6 | 54 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 7 | 0 | 4 | 0 | 0 | 42 | 27 | 4 | 0 | 0 | 17 | 31 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 0
2025-12-15 | W4 | 17 | 0 | 0 | 18 | 0 | 22 | 0 | 0 | 19 | 18 | 13 | 2 | 1 | 17 | 0 | 8 | 3 | 3 | 11 | 39 | 278 | 84 | 0 | 230 | 59 | 0 | 0 | 0 | 10 | 4 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 21 | 40 | 22 | 0 | 46 | 40 | 22 | 0 | 0 | 21 | 0 | 24 | 4 | 0 | 45 | 7 | 8 | 1 | 0 | 6 | 0 | 15 | 2 | 0 | 41 | 10 | 49 | 0 | 0 | 63 | 0 | 24 | 0 | 0 | 24 | 24 | 95 | 1 | 0 | 66 | 0 | 111 | 3 | 30 | 3 | 5 | 31 | 5 | 11 | 0 | 1 | 0 | 2 | 4 | 6 | 34 | 4 | 0 | 0 | 8 | 13 | 1 | 0 | 2 | 12 | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 6 | 2 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 3 | 4 | 0 | 2 | 2 | 0 | 4 | 6 | 2 | 2 | 0 | 4 | 0 | 8 | 0 | 2 | 4 | 18 | 9 | 0 | 5 | 10 | 16 | 11 | 0 | 1 | 10 | 14 | 0 | 0 | 0 | 12 | 1 | 0 | 0 | 0 | 17 | 0 | 7 | 3 | 1 | 56 | 0 | 10 | 0 | 9 | 1 | 1 | 11 | 0 | 20 | 30 | 10 | 7 | 4 | 1 | 59 | 17 | 0 | 0 | 1 | 9 | 0 | 4 | 0 | 4 | 29 | 0 | 0 | 2 | 13 | 8 | 4 | 3 | 0 | 1 | 11 | 0 | 0 | 0 | 2 | 45 | 15 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 4 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 2 | 5 | 0 | 4 | 0 | 9 | 38 | 51 | 26 | 0 | 2 | 13 | 0 | 10 | 0 | 4 | 0 | 0 | 10 | 0 | 8 | 7 | 23 | 15 | 0 | 0 | 6 | 13 | 6 | 1 | 0 | 17 | 0 | 20 | 0 | 0 | 20 | 4 | 1 | 0 | 0 | 23 | 7 | 20 | 0 | 0 | 21 | 0 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 2 | 0 | 19 | 0 | 0 | 9 | 20 | 10 | 0 | 0 | 10 | 0 | 14 | 0 | 0 | 14 | 14 | 30 | 0 | 0 | 3 | 33 | 30 | 0 | 22 | 4 | 72 | 48 | 0 | 0 | 37 | 0 | 16 | 0 | 0 | 16 | 3 | 6 | 0 | 0 | 24 | 0 | 1 | 0 | 0 | 2 | 6 | 4 | 2 | 5 | 14 | 6 | 54 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 7 | 0 | 4 | 0 | 0 | 42 | 27 | 4 | 0 | 0 | 17 | 31 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 0
2025-12-16 | W4 | 17 | 0 | 0 | 18 | 0 | 22 | 0 | 0 | 19 | 18 | 13 | 2 | 1 | 17 | 0 | 8 | 3 | 3 | 15 | 35 | 278 | 84 | 0 | 230 | 59 | 0 | 0 | 0 | 10 | 4 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 21 | 40 | 22 | 0 | 46 | 40 | 22 | 0 | 0 | 21 | 0 | 24 | 4 | 0 | 45 | 7 | 8 | 1 | 0 | 6 | 0 | 15 | 2 | 0 | 41 | 10 | 49 | 0 | 0 | 63 | 0 | 24 | 0 | 0 | 24 | 24 | 95 | 1 | 0 | 66 | 0 | 111 | 3 | 30 | 3 | 5 | 31 | 5 | 11 | 0 | 1 | 0 | 2 | 4 | 6 | 34 | 4 | 0 | 0 | 8 | 13 | 1 | 0 | 2 | 12 | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 6 | 2 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 3 | 4 | 0 | 2 | 2 | 0 | 4 | 6 | 2 | 2 | 0 | 4 | 0 | 8 | 0 | 2 | 4 | 18 | 9 | 0 | 5 | 16 | 10 | 11 | 0 | 1 | 10 | 14 | 0 | 0 | 0 | 12 | 1 | 0 | 0 | 0 | 17 | 0 | 7 | 3 | 1 | 56 | 0 | 10 | 0 | 9 | 1 | 1 | 11 | 0 | 20 | 30 | 10 | 7 | 4 | 1 | 59 | 17 | 0 | 0 | 1 | 9 | 0 | 4 | 0 | 4 | 29 | 0 | 0 | 2 | 13 | 8 | 4 | 3 | 0 | 1 | 11 | 0 | 0 | 0 | 2 | 45 | 15 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 4 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 2 | 5 | 0 | 4 | 0 | 9 | 38 | 51 | 26 | 0 | 2 | 13 | 0 | 10 | 0 | 4 | 0 | 0 | 10 | 0 | 8 | 7 | 23 | 15 | 0 | 0 | 8 | 11 | 6 | 1 | 0 | 17 | 0 | 20 | 0 | 0 | 20 | 4 | 1 | 0 | 0 | 23 | 7 | 20 | 0 | 0 | 21 | 0 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 2 | 0 | 19 | 0 | 0 | 9 | 20 | 10 | 0 | 0 | 10 | 0 | 14 | 0 | 0 | 14 | 14 | 30 | 0 | 0 | 3 | 33 | 30 | 0 | 22 | 4 | 78 | 48 | 0 | 0 | 37 | 0 | 16 | 0 | 0 | 16 | 3 | 6 | 0 | 0 | 24 | 0 | 1 | 0 | 0 | 2 | 6 | 4 | 2 | 5 | 14 | 6 | 54 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 7 | 0 | 4 | 0 | 0 | 42 | 27 | 4 | 0 | 0 | 17 | 31 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 0
2025-12-17 | W4 | 17 | 0 | 0 | 18 | 0 | 22 | 0 | 0 | 19 | 18 | 13 | 2 | 1 | 17 | 0 | 8 | 3 | 3 | 19 | 31 | 278 | 84 | 0 | 230 | 59 | 0 | 0 | 0 | 10 | 4 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 21 | 40 | 22 | 0 | 46 | 40 | 22 | 0 | 0 | 21 | 0 | 24 | 4 | 0 | 45 | 7 | 8 | 1 | 0 | 6 | 0 | 15 | 2 | 0 | 41 | 10 | 49 | 0 | 0 | 63 | 0 | 24 | 0 | 0 | 24 | 24 | 95 | 1 | 0 | 66 | 0 | 111 | 3 | 30 | 3 | 5 | 31 | 5 | 11 | 0 | 1 | 0 | 2 | 4 | 6 | 34 | 4 | 0 | 0 | 8 | 13 | 1 | 0 | 2 | 12 | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 6 | 2 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 3 | 4 | 0 | 2 | 2 | 0 | 4 | 6 | 2 | 2 | 0 | 4 | 0 | 8 | 0 | 2 | 4 | 18 | 9 | 0 | 5 | 22 | 4 | 11 | 0 | 1 | 10 | 14 | 0 | 0 | 0 | 12 | 1 | 0 | 0 | 0 | 17 | 0 | 7 | 3 | 1 | 56 | 0 | 10 | 0 | 9 | 1 | 1 | 11 | 0 | 20 | 30 | 10 | 7 | 4 | 1 | 59 | 17 | 0 | 0 | 1 | 9 | 0 | 4 | 0 | 4 | 29 | 0 | 0 | 2 | 13 | 8 | 4 | 3 | 0 | 1 | 11 | 0 | 0 | 0 | 2 | 45 | 15 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 4 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 2 | 5 | 0 | 4 | 0 | 9 | 38 | 51 | 26 | 0 | 2 | 13 | 0 | 10 | 0 | 4 | 0 | 0 | 10 | 0 | 8 | 7 | 23 | 15 | 0 | 0 | 8 | 11 | 6 | 1 | 0 | 17 | 0 | 20 | 0 | 0 | 20 | 4 | 1 | 0 | 0 | 23 | 7 | 20 | 0 | 0 | 21 | 0 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 2 | 0 | 19 | 0 | 0 | 9 | 20 | 10 | 0 | 0 | 10 | 0 | 14 | 0 | 0 | 14 | 14 | 30 | 0 | 0 | 3 | 33 | 30 | 0 | 22 | 4 | 78 | 48 | 0 | 0 | 37 | 0 | 16 | 0 | 0 | 16 | 3 | 6 | 0 | 0 | 24 | 0 | 1 | 0 | 0 | 2 | 6 | 4 | 2 | 5 | 14 | 6 | 54 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 7 | 0 | 4 | 0 | 0 | 42 | 27 | 4 | 0 | 0 | 17 | 31 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 0
2025-12-18 | W4 | 17 | 0 | 0 | 18 | 0 | 22 | 0 | 0 | 19 | 18 | 13 | 2 | 1 | 17 | 0 | 8 | 3 | 3 | 19 | 31 | 278 | 84 | 0 | 230 | 59 | 0 | 0 | 0 | 10 | 4 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 21 | 40 | 22 | 0 | 46 | 40 | 22 | 0 | 0 | 21 | 0 | 24 | 4 | 0 | 45 | 7 | 8 | 1 | 0 | 6 | 0 | 15 | 2 | 0 | 41 | 10 | 49 | 0 | 0 | 63 | 0 | 24 | 0 | 0 | 24 | 24 | 95 | 1 | 0 | 66 | 0 | 111 | 3 | 30 | 3 | 5 | 31 | 5 | 11 | 0 | 1 | 0 | 2 | 4 | 6 | 34 | 4 | 0 | 0 | 8 | 13 | 1 | 0 | 2 | 12 | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 6 | 2 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 3 | 4 | 0 | 2 | 2 | 0 | 4 | 6 | 2 | 2 | 0 | 4 | 0 | 8 | 0 | 2 | 4 | 18 | 9 | 0 | 5 | 22 | 4 | 11 | 0 | 1 | 10 | 14 | 0 | 0 | 0 | 12 | 1 | 0 | 0 | 0 | 17 | 0 | 7 | 3 | 1 | 56 | 0 | 10 | 0 | 9 | 1 | 1 | 11 | 0 | 20 | 30 | 10 | 7 | 4 | 1 | 59 | 17 | 0 | 0 | 1 | 9 | 0 | 4 | 0 | 4 | 29 | 0 | 0 | 2 | 13 | 8 | 4 | 3 | 0 | 1 | 11 | 0 | 0 | 0 | 2 | 45 | 15 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 4 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 2 | 5 | 0 | 4 | 0 | 9 | 38 | 51 | 26 | 0 | 2 | 13 | 0 | 10 | 0 | 4 | 0 | 0 | 10 | 0 | 8 | 7 | 23 | 15 | 0 | 0 | 8 | 11 | 6 | 1 | 0 | 17 | 0 | 20 | 0 | 0 | 20 | 4 | 1 | 0 | 0 | 23 | 7 | 20 | 0 | 0 | 21 | 0 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 2 | 0 | 19 | 0 | 0 | 9 | 20 | 10 | 0 | 0 | 10 | 0 | 14 | 0 | 0 | 14 | 14 | 30 | 0 | 0 | 3 | 33 | 30 | 0 | 22 | 4 | 78 | 48 | 0 | 0 | 37 | 0 | 16 | 0 | 0 | 16 | 3 | 6 | 0 | 0 | 24 | 0 | 1 | 0 | 0 | 2 | 6 | 4 | 2 | 5 | 14 | 6 | 54 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 7 | 0 | 4 | 0 | 0 | 42 | 27 | 4 | 0 | 0 | 17 | 31 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 0
2025-12-19 | W4 | 17 | 0 | 0 | 18 | 0 | 22 | 0 | 0 | 19 | 18 | 13 | 2 | 1 | 17 | 0 | 8 | 3 | 3 | 19 | 31 | 278 | 84 | 0 | 230 | 59 | 0 | 0 | 0 | 10 | 4 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 21 | 40 | 22 | 0 | 46 | 40 | 22 | 0 | 0 | 21 | 0 | 24 | 4 | 0 | 45 | 7 | 8 | 1 | 0 | 6 | 0 | 15 | 2 | 0 | 41 | 10 | 49 | 0 | 0 | 63 | 0 | 24 | 0 | 0 | 24 | 24 | 95 | 1 | 0 | 66 | 0 | 111 | 3 | 30 | 3 | 5 | 31 | 5 | 11 | 0 | 1 | 0 | 2 | 4 | 6 | 34 | 4 | 0 | 0 | 8 | 13 | 1 | 0 | 2 | 12 | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 6 | 2 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 3 | 4 | 0 | 2 | 2 | 0 | 4 | 6 | 2 | 2 | 0 | 4 | 0 | 8 | 0 | 2 | 4 | 18 | 9 | 0 | 5 | 22 | 4 | 11 | 0 | 1 | 10 | 14 | 0 | 0 | 0 | 12 | 1 | 0 | 0 | 0 | 17 | 0 | 7 | 3 | 1 | 56 | 0 | 10 | 0 | 9 | 1 | 1 | 11 | 0 | 20 | 30 | 10 | 7 | 4 | 1 | 59 | 17 | 0 | 0 | 1 | 9 | 0 | 4 | 0 | 4 | 29 | 0 | 0 | 2 | 13 | 8 | 4 | 3 | 0 | 1 | 11 | 0 | 0 | 0 | 2 | 45 | 15 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 4 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 2 | 5 | 0 | 4 | 0 | 9 | 38 | 51 | 26 | 0 | 2 | 13 | 0 | 10 | 0 | 4 | 0 | 0 | 10 | 0 | 8 | 7 | 23 | 15 | 0 | 0 | 8 | 11 | 6 | 1 | 0 | 17 | 0 | 20 | 0 | 0 | 20 | 4 | 1 | 0 | 0 | 23 | 7 | 20 | 0 | 0 | 21 | 0 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 2 | 0 | 19 | 0 | 0 | 9 | 20 | 10 | 0 | 0 | 10 | 0 | 14 | 0 | 0 | 14 | 14 | 30 | 0 | 0 | 3 | 33 | 30 | 0 | 22 | 4 | 78 | 48 | 0 | 0 | 37 | 0 | 16 | 0 | 0 | 16 | 3 | 6 | 0 | 0 | 24 | 0 | 1 | 0 | 0 | 2 | 6 | 4 | 2 | 5 | 14 | 6 | 54 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 7 | 0 | 4 | 0 | 0 | 42 | 27 | 4 | 0 | 0 | 17 | 31 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 0
2025-12-20 | W5 | 17 | 0 | 0 | 18 | 0 | 22 | 0 | 0 | 19 | 18 | 13 | 2 | 1 | 21 | 4 | 8 | 3 | 3 | 25 | 25 | 328 | 84 | 0 | 230 | 109 | 0 | 0 | 0 | 10 | 4 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 21 | 40 | 22 | 0 | 49 | 37 | 22 | 0 | 0 | 21 | 0 | 24 | 4 | 0 | 45 | 7 | 10 | 1 | 0 | 8 | 4 | 15 | 2 | 0 | 41 | 10 | 49 | 0 | 0 | 63 | 0 | 24 | 0 | 0 | 24 | 24 | 95 | 1 | 0 | 66 | 0 | 111 | 3 | 30 | 3 | 5 | 31 | 5 | 11 | 0 | 1 | 0 | 2 | 4 | 6 | 34 | 4 | 0 | 0 | 8 | 13 | 1 | 0 | 2 | 12 | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 6 | 2 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 3 | 4 | 0 | 2 | 2 | 0 | 4 | 6 | 2 | 2 | 0 | 4 | 0 | 8 | 0 | 2 | 4 | 18 | 9 | 0 | 5 | 22 | 4 | 11 | 0 | 1 | 12 | 12 | 0 | 0 | 0 | 12 | 1 | 0 | 0 | 0 | 17 | 0 | 7 | 3 | 1 | 56 | 0 | 10 | 0 | 9 | 1 | 1 | 11 | 0 | 20 | 30 | 10 | 7 | 4 | 1 | 59 | 17 | 0 | 0 | 1 | 9 | 0 | 4 | 0 | 4 | 29 | 0 | 0 | 2 | 13 | 8 | 4 | 3 | 0 | 1 | 11 | 0 | 0 | 0 | 2 | 45 | 15 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 4 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 2 | 5 | 0 | 4 | 0 | 9 | 38 | 51 | 26 | 0 | 2 | 13 | 0 | 10 | 0 | 4 | 0 | 0 | 16 | 0 | 2 | 7 | 23 | 16 | 0 | 0 | 8 | 11 | 6 | 1 | 0 | 17 | 0 | 20 | 0 | 0 | 20 | 4 | 5 | 0 | 0 | 23 | 7 | 20 | 0 | 0 | 21 | 0 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 2 | 0 | 19 | 0 | 0 | 9 | 20 | 10 | 0 | 0 | 10 | 0 | 14 | 0 | 0 | 14 | 14 | 30 | 0 | 0 | 3 | 33 | 30 | 0 | 22 | 9 | 73 | 48 | 0 | 0 | 37 | 0 | 16 | 0 | 0 | 16 | 3 | 6 | 0 | 0 | 24 | 0 | 1 | 0 | 0 | 2 | 6 | 4 | 2 | 5 | 16 | 4 | 54 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 7 | 0 | 4 | 0 | 0 | 42 | 27 | 4 | 0 | 0 | 20 | 28 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 0
2025-12-22 | W5 | 17 | 0 | 0 | 18 | 0 | 22 | 0 | 0 | 19 | 18 | 13 | 2 | 1 | 25 | 8 | 8 | 3 | 3 | 32 | 18 | 334 | 84 | 0 | 230 | 115 | 0 | 0 | 0 | 10 | 4 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 21 | 40 | 22 | 0 | 52 | 34 | 22 | 0 | 0 | 21 | 0 | 24 | 4 | 0 | 45 | 7 | 12 | 1 | 0 | 10 | 8 | 15 | 2 | 0 | 41 | 10 | 49 | 0 | 0 | 63 | 0 | 24 | 0 | 0 | 24 | 24 | 95 | 1 | 0 | 66 | 0 | 111 | 3 | 30 | 3 | 5 | 31 | 5 | 11 | 0 | 1 | 0 | 2 | 4 | 6 | 34 | 4 | 0 | 0 | 8 | 13 | 1 | 0 | 2 | 12 | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 6 | 2 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 3 | 4 | 0 | 2 | 2 | 0 | 4 | 6 | 2 | 2 | 0 | 4 | 0 | 8 | 0 | 2 | 4 | 18 | 9 | 0 | 5 | 22 | 4 | 11 | 0 | 1 | 14 | 10 | 0 | 0 | 0 | 12 | 1 | 0 | 0 | 0 | 17 | 0 | 7 | 3 | 1 | 56 | 0 | 10 | 0 | 9 | 1 | 1 | 11 | 0 | 20 | 30 | 10 | 7 | 4 | 1 | 59 | 17 | 0 | 0 | 1 | 9 | 0 | 4 | 0 | 4 | 29 | 0 | 0 | 2 | 13 | 8 | 4 | 3 | 0 | 1 | 11 | 0 | 0 | 0 | 2 | 45 | 15 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 4 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 2 | 5 | 0 | 4 | 0 | 9 | 38 | 51 | 26 | 0 | 2 | 13 | 0 | 10 | 0 | 4 | 0 | 0 | 23 | 0 | 0 | 7 | 23 | 17 | 0 | 0 | 8 | 11 | 6 | 1 | 0 | 17 | 0 | 20 | 0 | 0 | 20 | 4 | 9 | 0 | 0 | 23 | 7 | 20 | 0 | 0 | 21 | 0 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 2 | 0 | 19 | 0 | 0 | 9 | 20 | 10 | 0 | 0 | 10 | 0 | 14 | 0 | 0 | 14 | 14 | 30 | 0 | 0 | 3 | 33 | 30 | 0 | 22 | 14 | 68 | 48 | 0 | 0 | 37 | 0 | 16 | 0 | 0 | 16 | 3 | 6 | 0 | 0 | 24 | 0 | 1 | 0 | 0 | 2 | 6 | 4 | 2 | 5 | 18 | 2 | 54 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 7 | 0 | 4 | 0 | 0 | 42 | 27 | 4 | 0 | 0 | 23 | 25 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 0
2025-12-23 | W5 | 17 | 0 | 0 | 18 | 0 | 22 | 0 | 0 | 19 | 18 | 13 | 2 | 1 | 29 | 4 | 8 | 3 | 3 | 32 | 18 | 334 | 84 | 0 | 230 | 115 | 0 | 0 | 0 | 10 | 4 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 21 | 40 | 22 | 0 | 56 | 30 | 22 | 0 | 0 | 21 | 0 | 24 | 4 | 0 | 45 | 7 | 12 | 1 | 0 | 10 | 8 | 15 | 2 | 0 | 41 | 10 | 49 | 0 | 0 | 63 | 0 | 24 | 0 | 0 | 24 | 24 | 95 | 1 | 0 | 66 | 0 | 111 | 3 | 30 | 3 | 5 | 31 | 5 | 11 | 0 | 1 | 0 | 2 | 4 | 6 | 34 | 4 | 0 | 0 | 8 | 13 | 1 | 0 | 2 | 12 | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 6 | 2 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 3 | 4 | 0 | 2 | 2 | 0 | 4 | 6 | 2 | 2 | 0 | 4 | 0 | 8 | 0 | 2 | 4 | 18 | 9 | 0 | 5 | 22 | 4 | 11 | 0 | 1 | 17 | 7 | 0 | 0 | 0 | 12 | 1 | 0 | 0 | 0 | 17 | 0 | 7 | 3 | 1 | 56 | 0 | 10 | 0 | 9 | 1 | 1 | 11 | 0 | 20 | 30 | 10 | 7 | 4 | 1 | 59 | 17 | 0 | 0 | 1 | 9 | 0 | 4 | 0 | 4 | 29 | 0 | 0 | 2 | 13 | 8 | 4 | 3 | 0 | 1 | 11 | 0 | 0 | 0 | 2 | 45 | 15 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 4 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 2 | 5 | 0 | 4 | 0 | 9 | 38 | 51 | 26 | 0 | 2 | 13 | 0 | 10 | 0 | 4 | 0 | 0 | 23 | 0 | 0 | 7 | 23 | 17 | 0 | 0 | 8 | 11 | 6 | 1 | 0 | 17 | 0 | 20 | 0 | 0 | 20 | 4 | 13 | 0 | 0 | 23 | 7 | 20 | 0 | 0 | 21 | 0 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 2 | 0 | 19 | 0 | 0 | 9 | 20 | 10 | 0 | 0 | 10 | 0 | 14 | 0 | 0 | 14 | 14 | 30 | 0 | 0 | 3 | 33 | 30 | 0 | 22 | 19 | 63 | 48 | 0 | 0 | 37 | 0 | 16 | 0 | 0 | 16 | 3 | 6 | 0 | 0 | 24 | 0 | 1 | 0 | 0 | 2 | 6 | 4 | 2 | 5 | 18 | 2 | 54 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 7 | 0 | 4 | 0 | 0 | 42 | 27 | 4 | 0 | 0 | 26 | 22 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 0
2025-12-24 | W5 | 17 | 0 | 0 | 18 | 0 | 22 | 0 | 0 | 19 | 18 | 13 | 2 | 1 | 33 | 0 | 8 | 3 | 3 | 32 | 18 | 334 | 84 | 0 | 230 | 115 | 0 | 0 | 0 | 10 | 4 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 21 | 40 | 22 | 0 | 60 | 26 | 22 | 0 | 0 | 21 | 0 | 24 | 4 | 0 | 45 | 7 | 12 | 1 | 0 | 10 | 8 | 15 | 2 | 0 | 41 | 10 | 49 | 0 | 0 | 63 | 0 | 24 | 0 | 0 | 24 | 24 | 95 | 1 | 0 | 66 | 0 | 111 | 3 | 30 | 3 | 5 | 31 | 5 | 11 | 0 | 1 | 0 | 2 | 4 | 6 | 34 | 4 | 0 | 0 | 8 | 13 | 1 | 0 | 2 | 12 | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 6 | 2 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 3 | 4 | 0 | 2 | 2 | 0 | 4 | 6 | 2 | 2 | 0 | 4 | 0 | 8 | 0 | 2 | 4 | 18 | 9 | 0 | 5 | 22 | 4 | 11 | 0 | 1 | 20 | 4 | 0 | 0 | 0 | 12 | 1 | 0 | 0 | 0 | 17 | 0 | 7 | 3 | 1 | 56 | 0 | 10 | 0 | 9 | 1 | 1 | 11 | 0 | 20 | 30 | 10 | 7 | 4 | 1 | 59 | 17 | 0 | 0 | 1 | 9 | 0 | 4 | 0 | 4 | 29 | 0 | 0 | 2 | 13 | 8 | 4 | 3 | 0 | 1 | 11 | 0 | 0 | 0 | 2 | 45 | 15 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 4 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 2 | 5 | 0 | 4 | 0 | 9 | 38 | 51 | 26 | 0 | 2 | 13 | 0 | 10 | 0 | 4 | 0 | 0 | 23 | 0 | 0 | 7 | 23 | 17 | 0 | 0 | 8 | 11 | 6 | 1 | 0 | 17 | 0 | 20 | 0 | 0 | 20 | 4 | 13 | 0 | 0 | 23 | 7 | 20 | 0 | 0 | 21 | 0 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 2 | 0 | 19 | 0 | 0 | 9 | 20 | 10 | 0 | 0 | 10 | 0 | 14 | 0 | 0 | 14 | 14 | 30 | 0 | 0 | 3 | 33 | 30 | 0 | 22 | 24 | 58 | 48 | 0 | 0 | 37 | 0 | 16 | 0 | 0 | 16 | 3 | 6 | 0 | 0 | 24 | 0 | 1 | 0 | 0 | 2 | 6 | 4 | 2 | 5 | 18 | 2 | 54 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 7 | 0 | 4 | 0 | 0 | 42 | 27 | 4 | 0 | 0 | 29 | 19 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 0
2025-12-26 | W5 | 17 | 0 | 0 | 18 | 0 | 22 | 0 | 0 | 19 | 18 | 13 | 2 | 1 | 33 | 0 | 8 | 3 | 3 | 32 | 18 | 334 | 84 | 0 | 230 | 115 | 0 | 0 | 0 | 10 | 4 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 21 | 40 | 22 | 0 | 60 | 26 | 22 | 0 | 0 | 21 | 0 | 24 | 4 | 0 | 45 | 7 | 12 | 1 | 0 | 10 | 8 | 15 | 2 | 0 | 41 | 10 | 49 | 0 | 0 | 63 | 0 | 24 | 0 | 0 | 24 | 24 | 95 | 1 | 0 | 66 | 0 | 111 | 3 | 30 | 3 | 5 | 31 | 5 | 11 | 0 | 1 | 0 | 2 | 4 | 6 | 34 | 4 | 0 | 0 | 8 | 13 | 1 | 0 | 2 | 12 | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 6 | 2 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 3 | 4 | 0 | 2 | 2 | 0 | 4 | 6 | 2 | 2 | 0 | 4 | 0 | 8 | 0 | 2 | 4 | 18 | 9 | 0 | 5 | 22 | 4 | 11 | 0 | 1 | 20 | 4 | 0 | 0 | 0 | 12 | 1 | 0 | 0 | 0 | 17 | 0 | 7 | 3 | 1 | 56 | 0 | 10 | 0 | 9 | 1 | 1 | 11 | 0 | 20 | 30 | 10 | 7 | 4 | 1 | 59 | 17 | 0 | 0 | 1 | 9 | 0 | 4 | 0 | 4 | 29 | 0 | 0 | 2 | 13 | 8 | 4 | 3 | 0 | 1 | 11 | 0 | 0 | 0 | 2 | 45 | 15 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 4 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 2 | 5 | 0 | 4 | 0 | 9 | 38 | 51 | 26 | 0 | 2 | 13 | 0 | 10 | 0 | 4 | 0 | 0 | 23 | 0 | 0 | 7 | 23 | 17 | 0 | 0 | 8 | 11 | 6 | 1 | 0 | 17 | 0 | 20 | 0 | 0 | 20 | 4 | 13 | 0 | 0 | 23 | 7 | 20 | 0 | 0 | 21 | 0 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 2 | 0 | 19 | 0 | 0 | 9 | 20 | 10 | 0 | 0 | 10 | 0 | 14 | 0 | 0 | 14 | 14 | 30 | 0 | 0 | 3 | 33 | 30 | 0 | 22 | 24 | 58 | 48 | 0 | 0 | 37 | 0 | 16 | 0 | 0 | 16 | 3 | 6 | 0 | 0 | 24 | 0 | 1 | 0 | 0 | 2 | 6 | 4 | 2 | 5 | 18 | 2 | 54 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 7 | 0 | 4 | 0 | 0 | 42 | 27 | 4 | 0 | 0 | 29 | 19 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 0
2025-12-27 | W6 | 17 | 0 | 0 | 18 | 0 | 22 | 0 | 0 | 19 | 18 | 13 | 2 | 1 | 33 | 0 | 8 | 3 | 3 | 32 | 18 | 334 | 84 | 0 | 230 | 115 | 0 | 0 | 0 | 10 | 4 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 21 | 40 | 22 | 0 | 60 | 26 | 22 | 0 | 0 | 21 | 0 | 24 | 4 | 0 | 45 | 7 | 12 | 1 | 0 | 10 | 8 | 15 | 2 | 0 | 41 | 10 | 49 | 0 | 0 | 63 | 0 | 24 | 0 | 0 | 24 | 24 | 95 | 1 | 0 | 66 | 0 | 111 | 3 | 30 | 3 | 5 | 31 | 5 | 11 | 0 | 1 | 0 | 2 | 4 | 6 | 34 | 4 | 0 | 0 | 8 | 13 | 1 | 0 | 2 | 12 | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 6 | 2 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 3 | 4 | 0 | 2 | 2 | 0 | 4 | 6 | 2 | 2 | 0 | 4 | 0 | 8 | 0 | 2 | 4 | 18 | 9 | 0 | 5 | 22 | 4 | 11 | 0 | 1 | 20 | 4 | 0 | 0 | 0 | 12 | 1 | 0 | 0 | 0 | 17 | 0 | 7 | 3 | 1 | 56 | 0 | 10 | 0 | 9 | 1 | 1 | 11 | 0 | 20 | 30 | 10 | 7 | 4 | 1 | 59 | 17 | 0 | 0 | 1 | 9 | 0 | 4 | 0 | 4 | 29 | 0 | 0 | 2 | 13 | 8 | 4 | 3 | 0 | 1 | 11 | 0 | 0 | 0 | 2 | 45 | 15 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 4 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 2 | 5 | 0 | 4 | 0 | 9 | 38 | 51 | 26 | 0 | 2 | 13 | 0 | 10 | 0 | 4 | 0 | 0 | 23 | 0 | 0 | 7 | 23 | 17 | 0 | 0 | 8 | 11 | 6 | 1 | 0 | 17 | 0 | 20 | 0 | 0 | 20 | 4 | 13 | 0 | 0 | 23 | 7 | 20 | 0 | 0 | 21 | 0 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 2 | 0 | 19 | 0 | 0 | 9 | 20 | 10 | 0 | 0 | 10 | 0 | 14 | 0 | 0 | 14 | 14 | 30 | 0 | 0 | 3 | 33 | 30 | 0 | 22 | 24 | 58 | 48 | 0 | 0 | 37 | 0 | 16 | 0 | 0 | 16 | 3 | 6 | 0 | 0 | 24 | 0 | 1 | 0 | 0 | 2 | 6 | 4 | 2 | 5 | 18 | 2 | 54 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 7 | 0 | 4 | 0 | 0 | 42 | 27 | 4 | 0 | 0 | 29 | 19 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 0
2025-12-29 | W6 | 17 | 0 | 0 | 18 | 0 | 22 | 0 | 0 | 19 | 18 | 13 | 2 | 1 | 33 | 0 | 8 | 3 | 3 | 32 | 18 | 334 | 84 | 0 | 230 | 115 | 0 | 0 | 0 | 10 | 4 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 21 | 40 | 22 | 0 | 60 | 26 | 22 | 0 | 0 | 21 | 0 | 24 | 4 | 0 | 45 | 7 | 12 | 1 | 0 | 10 | 8 | 15 | 2 | 0 | 41 | 10 | 49 | 0 | 0 | 63 | 0 | 24 | 0 | 0 | 24 | 24 | 95 | 1 | 0 | 66 | 0 | 111 | 3 | 30 | 3 | 5 | 31 | 5 | 11 | 0 | 1 | 0 | 2 | 4 | 6 | 34 | 4 | 0 | 0 | 8 | 13 | 1 | 0 | 2 | 12 | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 6 | 2 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 3 | 4 | 0 | 2 | 2 | 0 | 4 | 6 | 2 | 2 | 0 | 4 | 0 | 8 | 0 | 2 | 4 | 18 | 9 | 0 | 5 | 22 | 4 | 11 | 0 | 1 | 20 | 4 | 0 | 0 | 0 | 12 | 1 | 0 | 0 | 0 | 17 | 0 | 7 | 3 | 1 | 56 | 0 | 10 | 0 | 9 | 1 | 1 | 11 | 0 | 20 | 30 | 10 | 7 | 4 | 1 | 59 | 17 | 0 | 0 | 1 | 9 | 0 | 4 | 0 | 4 | 29 | 0 | 0 | 2 | 13 | 8 | 4 | 3 | 0 | 1 | 11 | 0 | 0 | 0 | 2 | 45 | 15 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 4 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 2 | 5 | 0 | 4 | 0 | 9 | 38 | 51 | 26 | 0 | 2 | 13 | 0 | 10 | 0 | 4 | 0 | 0 | 23 | 0 | 0 | 7 | 23 | 17 | 0 | 0 | 8 | 11 | 6 | 1 | 0 | 17 | 0 | 20 | 0 | 0 | 20 | 4 | 13 | 0 | 0 | 23 | 7 | 20 | 0 | 0 | 21 | 0 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 2 | 0 | 19 | 0 | 0 | 9 | 20 | 10 | 0 | 0 | 10 | 0 | 14 | 0 | 0 | 14 | 14 | 30 | 0 | 0 | 3 | 33 | 30 | 0 | 22 | 24 | 58 | 48 | 0 | 0 | 37 | 0 | 16 | 0 | 0 | 16 | 3 | 6 | 0 | 0 | 24 | 0 | 1 | 0 | 0 | 2 | 6 | 4 | 2 | 5 | 18 | 2 | 54 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 7 | 0 | 4 | 0 | 0 | 42 | 27 | 4 | 0 | 0 | 29 | 19 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 0
2025-12-30 | W6 | 17 | 0 | 0 | 18 | 0 | 22 | 0 | 0 | 19 | 18 | 13 | 2 | 1 | 33 | 0 | 8 | 3 | 3 | 32 | 18 | 334 | 84 | 0 | 230 | 115 | 0 | 0 | 0 | 10 | 4 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 21 | 40 | 22 | 0 | 60 | 26 | 22 | 0 | 0 | 21 | 0 | 24 | 4 | 0 | 45 | 7 | 12 | 1 | 0 | 10 | 8 | 15 | 2 | 0 | 41 | 10 | 49 | 0 | 0 | 63 | 0 | 24 | 0 | 0 | 24 | 24 | 95 | 1 | 0 | 66 | 0 | 111 | 3 | 30 | 3 | 5 | 31 | 5 | 11 | 0 | 1 | 0 | 2 | 4 | 6 | 34 | 4 | 0 | 0 | 8 | 13 | 1 | 0 | 2 | 12 | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 6 | 2 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 3 | 4 | 0 | 2 | 2 | 0 | 4 | 6 | 2 | 2 | 0 | 4 | 0 | 8 | 0 | 2 | 4 | 18 | 9 | 0 | 5 | 22 | 4 | 11 | 0 | 1 | 20 | 4 | 0 | 0 | 0 | 12 | 1 | 0 | 0 | 0 | 17 | 0 | 7 | 3 | 1 | 56 | 0 | 10 | 0 | 9 | 1 | 1 | 11 | 0 | 20 | 30 | 10 | 7 | 4 | 1 | 59 | 17 | 0 | 0 | 1 | 9 | 0 | 4 | 0 | 4 | 29 | 0 | 0 | 2 | 13 | 8 | 4 | 3 | 0 | 1 | 11 | 0 | 0 | 0 | 2 | 45 | 15 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 4 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 2 | 5 | 0 | 4 | 0 | 9 | 38 | 51 | 26 | 0 | 2 | 13 | 0 | 10 | 0 | 4 | 0 | 0 | 23 | 0 | 0 | 7 | 23 | 17 | 0 | 0 | 8 | 11 | 6 | 1 | 0 | 17 | 0 | 20 | 0 | 0 | 20 | 4 | 13 | 0 | 0 | 23 | 7 | 20 | 0 | 0 | 21 | 0 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 2 | 0 | 19 | 0 | 0 | 9 | 20 | 10 | 0 | 0 | 10 | 0 | 14 | 0 | 0 | 14 | 14 | 30 | 0 | 0 | 3 | 33 | 30 | 0 | 22 | 24 | 58 | 48 | 0 | 0 | 37 | 0 | 16 | 0 | 0 | 16 | 3 | 6 | 0 | 0 | 24 | 0 | 1 | 0 | 0 | 2 | 6 | 4 | 2 | 5 | 18 | 2 | 54 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 7 | 0 | 4 | 0 | 0 | 42 | 27 | 4 | 0 | 0 | 29 | 19 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 0
2025-12-31 | W6 | 17 | 0 | 0 | 18 | 0 | 22 | 0 | 0 | 19 | 18 | 13 | 2 | 1 | 33 | 0 | 8 | 3 | 3 | 32 | 18 | 334 | 84 | 0 | 230 | 115 | 0 | 0 | 0 | 10 | 4 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 21 | 40 | 22 | 0 | 60 | 26 | 22 | 0 | 0 | 21 | 0 | 24 | 4 | 0 | 45 | 7 | 12 | 1 | 0 | 10 | 8 | 15 | 2 | 0 | 41 | 10 | 49 | 0 | 0 | 63 | 0 | 24 | 0 | 0 | 24 | 24 | 95 | 1 | 0 | 66 | 0 | 111 | 3 | 30 | 3 | 5 | 31 | 5 | 11 | 0 | 1 | 0 | 2 | 4 | 6 | 34 | 4 | 0 | 0 | 8 | 13 | 1 | 0 | 2 | 12 | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 6 | 2 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 3 | 4 | 0 | 2 | 2 | 0 | 4 | 6 | 2 | 2 | 0 | 4 | 0 | 8 | 0 | 2 | 4 | 18 | 9 | 0 | 5 | 22 | 4 | 11 | 0 | 1 | 20 | 4 | 0 | 0 | 0 | 12 | 1 | 0 | 0 | 0 | 17 | 0 | 7 | 3 | 1 | 56 | 0 | 10 | 0 | 9 | 1 | 1 | 11 | 0 | 20 | 30 | 10 | 7 | 4 | 1 | 59 | 17 | 0 | 0 | 1 | 9 | 0 | 4 | 0 | 4 | 29 | 0 | 0 | 2 | 13 | 8 | 4 | 3 | 0 | 1 | 11 | 0 | 0 | 0 | 2 | 45 | 15 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 4 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 2 | 5 | 0 | 4 | 0 | 9 | 38 | 51 | 26 | 0 | 2 | 13 | 0 | 10 | 0 | 4 | 0 | 0 | 23 | 0 | 0 | 7 | 23 | 17 | 0 | 0 | 8 | 11 | 6 | 1 | 0 | 17 | 0 | 20 | 0 | 0 | 20 | 4 | 13 | 0 | 0 | 23 | 7 | 20 | 0 | 0 | 21 | 0 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 2 | 0 | 19 | 0 | 0 | 9 | 20 | 10 | 0 | 0 | 10 | 0 | 14 | 0 | 0 | 14 | 14 | 30 | 0 | 0 | 3 | 33 | 30 | 0 | 22 | 24 | 58 | 48 | 0 | 0 | 37 | 0 | 16 | 0 | 0 | 16 | 3 | 6 | 0 | 0 | 24 | 0 | 1 | 0 | 0 | 2 | 6 | 4 | 2 | 5 | 18 | 2 | 54 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 7 | 0 | 4 | 0 | 0 | 42 | 27 | 4 | 0 | 0 | 29 | 19 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 0
2026-01-01 | W6 | 17 | 0 | 0 | 18 | 0 | 22 | 0 | 0 | 19 | 18 | 13 | 2 | 1 | 33 | 0 | 8 | 3 | 3 | 32 | 18 | 334 | 84 | 0 | 230 | 115 | 0 | 0 | 0 | 10 | 4 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 21 | 40 | 22 | 0 | 60 | 26 | 22 | 0 | 0 | 21 | 0 | 24 | 4 | 0 | 45 | 7 | 12 | 1 | 0 | 10 | 8 | 15 | 2 | 0 | 41 | 10 | 49 | 0 | 0 | 63 | 0 | 24 | 0 | 0 | 24 | 24 | 95 | 1 | 0 | 66 | 0 | 111 | 3 | 30 | 3 | 5 | 31 | 5 | 11 | 0 | 1 | 0 | 2 | 4 | 6 | 34 | 4 | 0 | 0 | 8 | 13 | 1 | 0 | 2 | 12 | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 6 | 2 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 3 | 4 | 0 | 2 | 2 | 0 | 4 | 6 | 2 | 2 | 0 | 4 | 0 | 8 | 0 | 2 | 4 | 18 | 9 | 0 | 5 | 22 | 4 | 11 | 0 | 1 | 20 | 4 | 0 | 0 | 0 | 12 | 1 | 0 | 0 | 0 | 17 | 0 | 7 | 3 | 1 | 56 | 0 | 10 | 0 | 9 | 1 | 1 | 11 | 0 | 20 | 30 | 10 | 7 | 4 | 1 | 59 | 17 | 0 | 0 | 1 | 9 | 0 | 4 | 0 | 4 | 29 | 0 | 0 | 2 | 13 | 8 | 4 | 3 | 0 | 1 | 11 | 0 | 0 | 0 | 2 | 45 | 15 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 4 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 2 | 5 | 0 | 4 | 0 | 9 | 38 | 51 | 26 | 0 | 2 | 13 | 0 | 10 | 0 | 4 | 0 | 0 | 23 | 0 | 0 | 7 | 23 | 17 | 0 | 0 | 8 | 11 | 6 | 1 | 0 | 17 | 0 | 20 | 0 | 0 | 20 | 4 | 13 | 0 | 0 | 23 | 7 | 20 | 0 | 0 | 21 | 0 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 2 | 0 | 19 | 0 | 0 | 9 | 20 | 10 | 0 | 0 | 10 | 0 | 14 | 0 | 0 | 14 | 14 | 30 | 0 | 0 | 3 | 33 | 30 | 0 | 22 | 24 | 58 | 48 | 0 | 0 | 37 | 0 | 16 | 0 | 0 | 16 | 3 | 6 | 0 | 0 | 24 | 0 | 1 | 0 | 0 | 2 | 6 | 4 | 2 | 5 | 18 | 2 | 54 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 7 | 0 | 4 | 0 | 0 | 42 | 27 | 4 | 0 | 0 | 29 | 19 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 0
2026-01-02 | W6 | 17 | 0 | 0 | 18 | 0 | 22 | 0 | 0 | 19 | 18 | 13 | 2 | 1 | 33 | 0 | 8 | 3 | 3 | 32 | 18 | 334 | 84 | 0 | 230 | 115 | 0 | 0 | 0 | 10 | 4 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 21 | 40 | 22 | 0 | 60 | 26 | 22 | 0 | 0 | 21 | 0 | 24 | 4 | 0 | 45 | 7 | 12 | 1 | 0 | 10 | 8 | 15 | 2 | 0 | 41 | 10 | 49 | 0 | 0 | 63 | 0 | 24 | 0 | 0 | 24 | 24 | 95 | 1 | 0 | 66 | 0 | 111 | 3 | 30 | 3 | 5 | 31 | 5 | 11 | 0 | 1 | 0 | 2 | 4 | 6 | 34 | 4 | 0 | 0 | 8 | 13 | 1 | 0 | 2 | 12 | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 6 | 2 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 3 | 4 | 0 | 2 | 2 | 0 | 4 | 6 | 2 | 2 | 0 | 4 | 0 | 8 | 0 | 2 | 4 | 18 | 9 | 0 | 5 | 22 | 4 | 11 | 0 | 1 | 20 | 4 | 0 | 0 | 0 | 12 | 1 | 0 | 0 | 0 | 17 | 0 | 7 | 3 | 1 | 56 | 0 | 10 | 0 | 9 | 1 | 1 | 11 | 0 | 20 | 30 | 10 | 7 | 4 | 1 | 59 | 17 | 0 | 0 | 1 | 9 | 0 | 4 | 0 | 4 | 29 | 0 | 0 | 2 | 13 | 8 | 4 | 3 | 0 | 1 | 11 | 0 | 0 | 0 | 2 | 45 | 15 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 4 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 2 | 5 | 0 | 4 | 0 | 9 | 38 | 51 | 26 | 0 | 2 | 13 | 0 | 10 | 0 | 4 | 0 | 0 | 23 | 0 | 0 | 7 | 23 | 17 | 0 | 0 | 8 | 11 | 6 | 1 | 0 | 17 | 0 | 20 | 0 | 0 | 20 | 4 | 13 | 0 | 0 | 23 | 7 | 20 | 0 | 0 | 21 | 0 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 2 | 0 | 19 | 0 | 0 | 9 | 20 | 10 | 0 | 0 | 10 | 0 | 14 | 0 | 0 | 14 | 14 | 30 | 0 | 0 | 3 | 33 | 30 | 0 | 22 | 24 | 58 | 48 | 0 | 0 | 37 | 0 | 16 | 0 | 0 | 16 | 3 | 6 | 0 | 0 | 24 | 0 | 1 | 0 | 0 | 2 | 6 | 4 | 2 | 5 | 18 | 2 | 54 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 7 | 0 | 4 | 0 | 0 | 42 | 27 | 4 | 0 | 0 | 29 | 19 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 0
2026-01-03 | W7 | 17 | 0 | 0 | 18 | 0 | 22 | 0 | 0 | 19 | 18 | 13 | 2 | 1 | 33 | 0 | 8 | 3 | 3 | 32 | 18 | 334 | 84 | 0 | 230 | 115 | 0 | 0 | 0 | 10 | 4 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 21 | 40 | 22 | 0 | 60 | 26 | 22 | 0 | 0 | 21 | 0 | 24 | 4 | 0 | 45 | 7 | 12 | 1 | 0 | 10 | 8 | 15 | 2 | 0 | 41 | 10 | 49 | 0 | 0 | 63 | 0 | 24 | 0 | 0 | 24 | 24 | 95 | 1 | 0 | 66 | 0 | 111 | 3 | 30 | 3 | 5 | 31 | 5 | 11 | 0 | 1 | 0 | 2 | 4 | 6 | 34 | 4 | 0 | 0 | 8 | 13 | 1 | 0 | 2 | 12 | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 6 | 2 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 3 | 4 | 0 | 2 | 2 | 0 | 4 | 6 | 2 | 2 | 0 | 4 | 0 | 8 | 0 | 2 | 4 | 18 | 9 | 0 | 5 | 22 | 4 | 11 | 0 | 1 | 20 | 4 | 0 | 0 | 0 | 12 | 1 | 0 | 0 | 0 | 17 | 0 | 7 | 3 | 1 | 56 | 0 | 10 | 0 | 9 | 1 | 1 | 11 | 0 | 20 | 30 | 10 | 7 | 4 | 1 | 59 | 17 | 0 | 0 | 1 | 9 | 0 | 4 | 0 | 4 | 29 | 0 | 0 | 2 | 13 | 8 | 4 | 3 | 0 | 1 | 11 | 0 | 0 | 0 | 2 | 45 | 15 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 4 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 2 | 5 | 0 | 4 | 0 | 9 | 38 | 51 | 26 | 0 | 2 | 13 | 0 | 10 | 0 | 4 | 0 | 0 | 23 | 0 | 0 | 7 | 23 | 17 | 0 | 0 | 8 | 11 | 6 | 1 | 0 | 17 | 0 | 20 | 0 | 0 | 20 | 4 | 13 | 0 | 0 | 23 | 7 | 20 | 0 | 0 | 21 | 0 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 2 | 0 | 19 | 0 | 0 | 9 | 20 | 10 | 0 | 0 | 10 | 0 | 14 | 0 | 0 | 14 | 14 | 30 | 0 | 0 | 3 | 33 | 30 | 0 | 22 | 24 | 58 | 48 | 0 | 0 | 37 | 0 | 16 | 0 | 0 | 16 | 3 | 6 | 0 | 0 | 24 | 0 | 1 | 0 | 0 | 2 | 6 | 4 | 2 | 5 | 18 | 2 | 54 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 7 | 0 | 4 | 0 | 0 | 42 | 27 | 4 | 0 | 0 | 29 | 19 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 0
2026-01-05 | W7 | 17 | 0 | 0 | 18 | 0 | 22 | 0 | 0 | 19 | 18 | 13 | 2 | 1 | 33 | 0 | 8 | 3 | 3 | 32 | 18 | 334 | 84 | 0 | 230 | 115 | 0 | 0 | 0 | 10 | 4 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 21 | 40 | 22 | 0 | 60 | 26 | 22 | 0 | 0 | 21 | 0 | 24 | 4 | 0 | 45 | 7 | 12 | 1 | 0 | 10 | 8 | 15 | 2 | 0 | 41 | 10 | 49 | 0 | 0 | 63 | 0 | 24 | 0 | 0 | 24 | 24 | 95 | 1 | 0 | 66 | 0 | 111 | 3 | 30 | 3 | 5 | 31 | 5 | 11 | 0 | 1 | 0 | 2 | 4 | 6 | 34 | 4 | 0 | 0 | 8 | 13 | 1 | 0 | 2 | 12 | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 6 | 2 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 3 | 4 | 0 | 2 | 2 | 0 | 4 | 6 | 2 | 2 | 0 | 4 | 0 | 8 | 0 | 2 | 4 | 18 | 9 | 0 | 5 | 22 | 4 | 11 | 0 | 1 | 20 | 4 | 0 | 0 | 0 | 12 | 1 | 0 | 0 | 0 | 17 | 0 | 7 | 3 | 1 | 56 | 0 | 10 | 0 | 9 | 1 | 1 | 11 | 0 | 20 | 30 | 10 | 7 | 4 | 1 | 59 | 17 | 0 | 0 | 1 | 9 | 0 | 4 | 0 | 4 | 29 | 0 | 0 | 2 | 13 | 8 | 4 | 3 | 0 | 1 | 11 | 0 | 0 | 0 | 2 | 45 | 15 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 4 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 2 | 5 | 0 | 4 | 0 | 9 | 38 | 51 | 26 | 0 | 2 | 13 | 0 | 10 | 0 | 4 | 0 | 0 | 23 | 0 | 0 | 7 | 23 | 17 | 0 | 0 | 8 | 11 | 6 | 1 | 0 | 17 | 0 | 20 | 0 | 0 | 20 | 4 | 13 | 0 | 0 | 23 | 7 | 20 | 0 | 0 | 21 | 0 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 2 | 0 | 19 | 0 | 0 | 9 | 20 | 10 | 0 | 0 | 10 | 0 | 14 | 0 | 0 | 14 | 14 | 30 | 0 | 0 | 3 | 33 | 30 | 0 | 22 | 24 | 58 | 48 | 0 | 0 | 37 | 0 | 16 | 0 | 0 | 16 | 3 | 6 | 0 | 0 | 24 | 0 | 1 | 0 | 0 | 2 | 6 | 4 | 2 | 5 | 18 | 2 | 54 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 7 | 0 | 4 | 0 | 0 | 42 | 27 | 4 | 0 | 0 | 29 | 19 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 0
2026-01-06 | W7 | 17 | 0 | 0 | 18 | 0 | 22 | 0 | 0 | 19 | 18 | 13 | 2 | 1 | 33 | 0 | 8 | 3 | 3 | 32 | 18 | 334 | 84 | 0 | 230 | 115 | 0 | 0 | 0 | 10 | 4 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 21 | 40 | 22 | 0 | 60 | 26 | 22 | 0 | 0 | 21 | 0 | 24 | 4 | 0 | 45 | 7 | 12 | 1 | 0 | 10 | 8 | 15 | 2 | 0 | 41 | 10 | 49 | 0 | 0 | 63 | 0 | 24 | 0 | 0 | 24 | 24 | 95 | 1 | 0 | 66 | 0 | 111 | 3 | 30 | 3 | 5 | 31 | 5 | 11 | 0 | 1 | 0 | 2 | 4 | 6 | 34 | 4 | 0 | 0 | 8 | 13 | 1 | 0 | 2 | 12 | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 6 | 2 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 3 | 4 | 0 | 2 | 2 | 0 | 4 | 6 | 2 | 2 | 0 | 4 | 0 | 8 | 0 | 2 | 4 | 18 | 9 | 0 | 5 | 22 | 4 | 11 | 0 | 1 | 20 | 4 | 0 | 0 | 0 | 12 | 1 | 0 | 0 | 0 | 17 | 0 | 7 | 3 | 1 | 56 | 0 | 10 | 0 | 9 | 1 | 1 | 11 | 0 | 20 | 30 | 10 | 7 | 4 | 1 | 59 | 17 | 0 | 0 | 1 | 9 | 0 | 4 | 0 | 4 | 29 | 0 | 0 | 2 | 13 | 8 | 4 | 3 | 0 | 1 | 11 | 0 | 0 | 0 | 2 | 45 | 15 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 4 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 2 | 5 | 0 | 4 | 0 | 9 | 38 | 51 | 26 | 0 | 2 | 13 | 0 | 10 | 0 | 4 | 0 | 0 | 23 | 0 | 0 | 7 | 23 | 17 | 0 | 0 | 8 | 11 | 6 | 1 | 0 | 17 | 0 | 20 | 0 | 0 | 20 | 4 | 13 | 0 | 0 | 23 | 7 | 20 | 0 | 0 | 21 | 0 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 2 | 0 | 19 | 0 | 0 | 9 | 20 | 10 | 0 | 0 | 10 | 0 | 14 | 0 | 0 | 14 | 14 | 30 | 0 | 0 | 3 | 33 | 30 | 0 | 22 | 24 | 58 | 48 | 0 | 0 | 37 | 0 | 16 | 0 | 0 | 16 | 3 | 6 | 0 | 0 | 24 | 0 | 1 | 0 | 0 | 2 | 6 | 4 | 2 | 5 | 18 | 2 | 54 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 7 | 0 | 4 | 0 | 0 | 42 | 27 | 4 | 0 | 0 | 29 | 19 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 0
2026-01-07 | W7 | 17 | 0 | 0 | 18 | 0 | 22 | 0 | 0 | 19 | 18 | 13 | 2 | 1 | 33 | 0 | 8 | 3 | 3 | 32 | 18 | 334 | 84 | 0 | 230 | 115 | 0 | 0 | 0 | 10 | 4 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 21 | 40 | 22 | 0 | 60 | 26 | 22 | 0 | 0 | 21 | 0 | 24 | 4 | 0 | 45 | 7 | 12 | 1 | 0 | 10 | 8 | 15 | 2 | 0 | 41 | 10 | 49 | 0 | 0 | 63 | 0 | 24 | 0 | 0 | 24 | 24 | 95 | 1 | 0 | 66 | 0 | 111 | 3 | 30 | 3 | 5 | 31 | 5 | 11 | 0 | 1 | 0 | 2 | 4 | 6 | 34 | 4 | 0 | 0 | 8 | 13 | 1 | 0 | 2 | 12 | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 6 | 2 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 3 | 4 | 0 | 2 | 2 | 0 | 4 | 6 | 2 | 2 | 0 | 4 | 0 | 8 | 0 | 2 | 4 | 18 | 9 | 0 | 5 | 22 | 4 | 11 | 0 | 1 | 20 | 4 | 0 | 0 | 0 | 12 | 1 | 0 | 0 | 0 | 17 | 0 | 7 | 3 | 1 | 56 | 0 | 10 | 0 | 9 | 1 | 1 | 11 | 0 | 20 | 30 | 10 | 7 | 4 | 1 | 59 | 17 | 0 | 0 | 1 | 9 | 0 | 4 | 0 | 4 | 29 | 0 | 0 | 2 | 13 | 8 | 4 | 3 | 0 | 1 | 11 | 0 | 0 | 0 | 2 | 45 | 15 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 4 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 2 | 5 | 0 | 4 | 0 | 9 | 38 | 51 | 26 | 0 | 2 | 13 | 0 | 10 | 0 | 4 | 0 | 0 | 23 | 0 | 0 | 7 | 23 | 17 | 0 | 0 | 8 | 11 | 6 | 1 | 0 | 17 | 0 | 20 | 0 | 0 | 20 | 4 | 13 | 0 | 0 | 23 | 7 | 20 | 0 | 0 | 21 | 0 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 2 | 0 | 19 | 0 | 0 | 9 | 20 | 10 | 0 | 0 | 10 | 0 | 14 | 0 | 0 | 14 | 14 | 30 | 0 | 0 | 3 | 33 | 30 | 0 | 22 | 24 | 58 | 48 | 0 | 0 | 37 | 0 | 16 | 0 | 0 | 16 | 3 | 6 | 0 | 0 | 24 | 0 | 1 | 0 | 0 | 2 | 6 | 4 | 2 | 5 | 18 | 2 | 54 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 7 | 0 | 4 | 0 | 0 | 42 | 27 | 4 | 0 | 0 | 29 | 19 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 0
2026-01-08 | W7 | 17 | 0 | 0 | 18 | 0 | 22 | 0 | 0 | 19 | 18 | 13 | 2 | 1 | 33 | 0 | 8 | 3 | 3 | 32 | 18 | 334 | 84 | 0 | 230 | 115 | 0 | 0 | 0 | 10 | 4 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 21 | 40 | 22 | 0 | 60 | 26 | 22 | 0 | 0 | 21 | 0 | 24 | 4 | 0 | 45 | 7 | 12 | 1 | 0 | 10 | 8 | 15 | 2 | 0 | 41 | 10 | 49 | 0 | 0 | 63 | 0 | 24 | 0 | 0 | 24 | 24 | 95 | 1 | 0 | 66 | 0 | 111 | 3 | 30 | 3 | 5 | 31 | 5 | 11 | 0 | 1 | 0 | 2 | 4 | 6 | 34 | 4 | 0 | 0 | 8 | 13 | 1 | 0 | 2 | 12 | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 6 | 2 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 3 | 4 | 0 | 2 | 2 | 0 | 4 | 6 | 2 | 2 | 0 | 4 | 0 | 8 | 0 | 2 | 4 | 18 | 9 | 0 | 5 | 22 | 4 | 11 | 0 | 1 | 20 | 4 | 0 | 0 | 0 | 12 | 1 | 0 | 0 | 0 | 17 | 0 | 7 | 3 | 1 | 56 | 0 | 10 | 0 | 9 | 1 | 1 | 11 | 0 | 20 | 30 | 10 | 7 | 4 | 1 | 59 | 17 | 0 | 0 | 1 | 9 | 0 | 4 | 0 | 4 | 29 | 0 | 0 | 2 | 13 | 8 | 4 | 3 | 0 | 1 | 11 | 0 | 0 | 0 | 2 | 45 | 15 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 4 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 2 | 5 | 0 | 4 | 0 | 9 | 38 | 51 | 26 | 0 | 2 | 13 | 0 | 10 | 0 | 4 | 0 | 0 | 23 | 0 | 0 | 7 | 23 | 17 | 0 | 0 | 8 | 11 | 6 | 1 | 0 | 17 | 0 | 20 | 0 | 0 | 20 | 4 | 13 | 0 | 0 | 23 | 7 | 20 | 0 | 0 | 21 | 0 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 2 | 0 | 19 | 0 | 0 | 9 | 20 | 10 | 0 | 0 | 10 | 0 | 14 | 0 | 0 | 14 | 14 | 30 | 0 | 0 | 3 | 33 | 30 | 0 | 22 | 24 | 58 | 48 | 0 | 0 | 37 | 0 | 16 | 0 | 0 | 16 | 3 | 6 | 0 | 0 | 24 | 0 | 1 | 0 | 0 | 2 | 6 | 4 | 2 | 5 | 18 | 2 | 54 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 7 | 0 | 4 | 0 | 0 | 42 | 27 | 4 | 0 | 0 | 29 | 19 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 0
2026-01-09 | W7 | 17 | 0 | 0 | 18 | 0 | 22 | 0 | 0 | 19 | 18 | 13 | 2 | 1 | 33 | 0 | 8 | 3 | 3 | 32 | 18 | 334 | 84 | 0 | 230 | 115 | 0 | 0 | 0 | 10 | 4 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 21 | 40 | 22 | 0 | 60 | 26 | 22 | 0 | 0 | 21 | 0 | 24 | 4 | 0 | 45 | 7 | 12 | 1 | 0 | 10 | 8 | 15 | 2 | 0 | 41 | 10 | 49 | 0 | 0 | 63 | 0 | 24 | 0 | 0 | 24 | 24 | 95 | 1 | 0 | 66 | 0 | 111 | 3 | 30 | 3 | 5 | 31 | 5 | 11 | 0 | 1 | 0 | 2 | 4 | 6 | 34 | 4 | 0 | 0 | 8 | 13 | 1 | 0 | 2 | 12 | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 6 | 2 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 3 | 4 | 0 | 2 | 2 | 0 | 4 | 6 | 2 | 2 | 0 | 4 | 0 | 8 | 0 | 2 | 4 | 18 | 9 | 0 | 5 | 22 | 4 | 11 | 0 | 1 | 20 | 4 | 0 | 0 | 0 | 12 | 1 | 0 | 0 | 0 | 17 | 0 | 7 | 3 | 1 | 56 | 0 | 10 | 0 | 9 | 1 | 1 | 11 | 0 | 20 | 30 | 10 | 7 | 4 | 1 | 59 | 17 | 0 | 0 | 1 | 9 | 0 | 4 | 0 | 4 | 29 | 0 | 0 | 2 | 13 | 8 | 4 | 3 | 0 | 1 | 11 | 0 | 0 | 0 | 2 | 45 | 15 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 4 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 2 | 5 | 0 | 4 | 0 | 9 | 38 | 51 | 26 | 0 | 2 | 13 | 0 | 10 | 0 | 4 | 0 | 0 | 23 | 0 | 0 | 7 | 23 | 17 | 0 | 0 | 8 | 11 | 6 | 1 | 0 | 17 | 0 | 20 | 0 | 0 | 20 | 4 | 13 | 0 | 0 | 23 | 7 | 20 | 0 | 0 | 21 | 0 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 2 | 0 | 19 | 0 | 0 | 9 | 20 | 10 | 0 | 0 | 10 | 0 | 14 | 0 | 0 | 14 | 14 | 30 | 0 | 0 | 3 | 33 | 30 | 0 | 22 | 24 | 58 | 48 | 0 | 0 | 37 | 0 | 16 | 0 | 0 | 16 | 3 | 6 | 0 | 0 | 24 | 0 | 1 | 0 | 0 | 2 | 6 | 4 | 2 | 5 | 18 | 2 | 54 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 7 | 0 | 4 | 0 | 0 | 42 | 27 | 4 | 0 | 0 | 29 | 19 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 0
2026-01-10 | W8 | 17 | 0 | 0 | 18 | 0 | 22 | 0 | 0 | 19 | 18 | 13 | 2 | 1 | 33 | 0 | 8 | 3 | 3 | 32 | 18 | 334 | 84 | 0 | 230 | 115 | 0 | 0 | 0 | 10 | 4 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 21 | 40 | 22 | 0 | 60 | 26 | 22 | 0 | 0 | 21 | 0 | 24 | 4 | 0 | 45 | 7 | 12 | 1 | 0 | 10 | 8 | 15 | 2 | 0 | 41 | 10 | 49 | 0 | 0 | 63 | 0 | 24 | 0 | 0 | 24 | 24 | 95 | 1 | 0 | 66 | 0 | 111 | 3 | 30 | 3 | 5 | 31 | 5 | 11 | 0 | 1 | 0 | 2 | 4 | 6 | 34 | 4 | 0 | 0 | 8 | 13 | 1 | 0 | 2 | 12 | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 6 | 2 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 3 | 4 | 0 | 2 | 2 | 0 | 4 | 6 | 2 | 2 | 0 | 4 | 0 | 8 | 0 | 2 | 4 | 18 | 9 | 0 | 5 | 22 | 4 | 11 | 0 | 1 | 20 | 4 | 0 | 0 | 0 | 12 | 1 | 0 | 0 | 0 | 17 | 0 | 7 | 3 | 1 | 56 | 0 | 10 | 0 | 9 | 1 | 1 | 11 | 0 | 20 | 30 | 10 | 7 | 4 | 1 | 59 | 17 | 0 | 0 | 1 | 9 | 0 | 4 | 0 | 4 | 29 | 0 | 0 | 2 | 13 | 8 | 4 | 3 | 0 | 1 | 11 | 0 | 0 | 0 | 2 | 45 | 15 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 4 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 2 | 5 | 0 | 4 | 0 | 9 | 38 | 51 | 26 | 0 | 2 | 13 | 0 | 10 | 0 | 4 | 0 | 0 | 23 | 0 | 0 | 7 | 23 | 17 | 0 | 0 | 8 | 11 | 6 | 1 | 0 | 17 | 0 | 20 | 0 | 0 | 20 | 4 | 13 | 0 | 0 | 23 | 7 | 20 | 0 | 0 | 21 | 0 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 2 | 0 | 19 | 0 | 0 | 9 | 20 | 10 | 0 | 0 | 10 | 0 | 14 | 0 | 0 | 14 | 14 | 30 | 0 | 0 | 3 | 33 | 30 | 0 | 22 | 24 | 58 | 48 | 0 | 0 | 37 | 0 | 16 | 0 | 0 | 16 | 3 | 6 | 0 | 0 | 24 | 0 | 1 | 0 | 0 | 2 | 6 | 4 | 2 | 5 | 18 | 2 | 54 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 7 | 0 | 4 | 0 | 0 | 42 | 27 | 4 | 0 | 0 | 29 | 19 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 0
2026-01-12 | W8 | 17 | 0 | 0 | 18 | 0 | 22 | 0 | 0 | 19 | 18 | 13 | 2 | 1 | 33 | 0 | 8 | 3 | 3 | 32 | 18 | 334 | 84 | 0 | 230 | 115 | 0 | 0 | 0 | 10 | 4 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 21 | 40 | 22 | 0 | 60 | 26 | 22 | 0 | 0 | 21 | 0 | 24 | 4 | 0 | 45 | 7 | 12 | 1 | 0 | 10 | 8 | 15 | 2 | 0 | 41 | 10 | 49 | 0 | 0 | 63 | 0 | 24 | 0 | 0 | 24 | 24 | 95 | 1 | 0 | 66 | 0 | 111 | 3 | 30 | 3 | 5 | 31 | 5 | 11 | 0 | 1 | 0 | 2 | 4 | 6 | 34 | 4 | 0 | 0 | 8 | 13 | 1 | 0 | 2 | 12 | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 6 | 2 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 3 | 4 | 0 | 2 | 2 | 0 | 4 | 6 | 2 | 2 | 0 | 4 | 0 | 8 | 0 | 2 | 4 | 18 | 9 | 0 | 5 | 22 | 4 | 11 | 0 | 1 | 20 | 4 | 0 | 0 | 0 | 12 | 1 | 0 | 0 | 0 | 17 | 0 | 7 | 3 | 1 | 56 | 0 | 10 | 0 | 9 | 1 | 1 | 11 | 0 | 20 | 30 | 10 | 7 | 4 | 1 | 59 | 17 | 0 | 0 | 1 | 9 | 0 | 4 | 0 | 4 | 29 | 0 | 0 | 2 | 13 | 8 | 4 | 3 | 0 | 1 | 11 | 0 | 0 | 0 | 2 | 45 | 15 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 4 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 2 | 5 | 0 | 4 | 0 | 9 | 38 | 51 | 26 | 0 | 2 | 13 | 0 | 10 | 0 | 4 | 0 | 0 | 23 | 0 | 0 | 7 | 23 | 17 | 0 | 0 | 8 | 11 | 6 | 1 | 0 | 17 | 0 | 20 | 0 | 0 | 20 | 4 | 13 | 0 | 0 | 23 | 7 | 20 | 0 | 0 | 21 | 0 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 2 | 0 | 19 | 0 | 0 | 9 | 20 | 10 | 0 | 0 | 10 | 0 | 14 | 0 | 0 | 14 | 14 | 30 | 0 | 0 | 3 | 33 | 30 | 0 | 22 | 24 | 58 | 48 | 0 | 0 | 37 | 0 | 16 | 0 | 0 | 16 | 3 | 6 | 0 | 0 | 24 | 0 | 1 | 0 | 0 | 2 | 6 | 4 | 2 | 5 | 18 | 2 | 54 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 7 | 0 | 4 | 0 | 0 | 42 | 27 | 4 | 0 | 0 | 29 | 19 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 0
2026-01-13 | W8 | 17 | 0 | 0 | 18 | 0 | 22 | 0 | 0 | 19 | 18 | 13 | 2 | 1 | 33 | 0 | 8 | 3 | 3 | 32 | 18 | 334 | 84 | 0 | 230 | 115 | 0 | 0 | 0 | 10 | 4 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 21 | 40 | 22 | 0 | 60 | 26 | 22 | 0 | 0 | 21 | 0 | 24 | 4 | 0 | 45 | 7 | 12 | 1 | 0 | 10 | 8 | 15 | 2 | 0 | 41 | 10 | 49 | 0 | 0 | 63 | 0 | 24 | 0 | 0 | 24 | 24 | 95 | 1 | 0 | 66 | 0 | 111 | 3 | 30 | 3 | 5 | 31 | 5 | 11 | 0 | 1 | 0 | 2 | 4 | 6 | 34 | 4 | 0 | 0 | 8 | 13 | 1 | 0 | 2 | 12 | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 6 | 2 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 3 | 4 | 0 | 2 | 2 | 0 | 4 | 6 | 2 | 2 | 0 | 4 | 0 | 8 | 0 | 2 | 4 | 18 | 9 | 0 | 5 | 22 | 4 | 11 | 0 | 1 | 20 | 4 | 0 | 0 | 0 | 12 | 1 | 0 | 0 | 0 | 17 | 0 | 7 | 3 | 1 | 56 | 0 | 10 | 0 | 9 | 1 | 1 | 11 | 0 | 20 | 30 | 10 | 7 | 4 | 1 | 59 | 17 | 0 | 0 | 1 | 9 | 0 | 4 | 0 | 4 | 29 | 0 | 0 | 2 | 13 | 8 | 4 | 3 | 0 | 1 | 11 | 0 | 0 | 0 | 2 | 45 | 15 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 4 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 2 | 5 | 0 | 4 | 0 | 9 | 38 | 51 | 26 | 0 | 2 | 13 | 0 | 10 | 0 | 4 | 0 | 0 | 23 | 0 | 0 | 7 | 23 | 17 | 0 | 0 | 8 | 11 | 6 | 1 | 0 | 17 | 0 | 20 | 0 | 0 | 20 | 4 | 13 | 0 | 0 | 23 | 7 | 20 | 0 | 0 | 21 | 0 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 2 | 0 | 19 | 0 | 0 | 9 | 20 | 10 | 0 | 0 | 10 | 0 | 14 | 0 | 0 | 14 | 14 | 30 | 0 | 0 | 3 | 33 | 30 | 0 | 22 | 24 | 58 | 48 | 0 | 0 | 37 | 0 | 16 | 0 | 0 | 16 | 3 | 6 | 0 | 0 | 24 | 0 | 1 | 0 | 0 | 2 | 6 | 4 | 2 | 5 | 18 | 2 | 54 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 7 | 0 | 4 | 0 | 0 | 42 | 27 | 4 | 0 | 0 | 29 | 19 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 0
2026-01-14 | W8 | 17 | 0 | 0 | 18 | 0 | 22 | 0 | 0 | 19 | 18 | 13 | 2 | 1 | 33 | 0 | 8 | 3 | 3 | 32 | 18 | 334 | 84 | 0 | 230 | 115 | 0 | 0 | 0 | 10 | 4 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 21 | 40 | 22 | 0 | 60 | 26 | 22 | 0 | 0 | 21 | 0 | 24 | 4 | 0 | 45 | 7 | 12 | 1 | 0 | 10 | 8 | 15 | 2 | 0 | 41 | 10 | 49 | 0 | 0 | 63 | 0 | 24 | 0 | 0 | 24 | 24 | 95 | 1 | 0 | 66 | 0 | 111 | 3 | 30 | 3 | 5 | 31 | 5 | 11 | 0 | 1 | 0 | 2 | 4 | 6 | 34 | 4 | 0 | 0 | 8 | 13 | 1 | 0 | 2 | 12 | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 6 | 2 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 3 | 4 | 0 | 2 | 2 | 0 | 4 | 6 | 2 | 2 | 0 | 4 | 0 | 8 | 0 | 2 | 4 | 18 | 9 | 0 | 5 | 22 | 4 | 11 | 0 | 1 | 20 | 4 | 0 | 0 | 0 | 12 | 1 | 0 | 0 | 0 | 17 | 0 | 7 | 3 | 1 | 56 | 0 | 10 | 0 | 9 | 1 | 1 | 11 | 0 | 20 | 30 | 10 | 7 | 4 | 1 | 59 | 17 | 0 | 0 | 1 | 9 | 0 | 4 | 0 | 4 | 29 | 0 | 0 | 2 | 13 | 8 | 4 | 3 | 0 | 1 | 11 | 0 | 0 | 0 | 2 | 45 | 15 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 4 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 2 | 5 | 0 | 4 | 0 | 9 | 38 | 51 | 26 | 0 | 2 | 13 | 0 | 10 | 0 | 4 | 0 | 0 | 23 | 0 | 0 | 7 | 23 | 17 | 0 | 0 | 8 | 11 | 6 | 1 | 0 | 17 | 0 | 20 | 0 | 0 | 20 | 4 | 13 | 0 | 0 | 23 | 7 | 20 | 0 | 0 | 21 | 0 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 2 | 0 | 19 | 0 | 0 | 9 | 20 | 10 | 0 | 0 | 10 | 0 | 14 | 0 | 0 | 14 | 14 | 30 | 0 | 0 | 3 | 33 | 30 | 0 | 22 | 24 | 58 | 48 | 0 | 0 | 37 | 0 | 16 | 0 | 0 | 16 | 3 | 6 | 0 | 0 | 24 | 0 | 1 | 0 | 0 | 2 | 6 | 4 | 2 | 5 | 18 | 2 | 54 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 7 | 0 | 4 | 0 | 0 | 42 | 27 | 4 | 0 | 0 | 29 | 19 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 0
2026-01-15 | W8 | 17 | 0 | 0 | 18 | 0 | 22 | 0 | 0 | 19 | 18 | 13 | 2 | 1 | 33 | 0 | 8 | 3 | 3 | 32 | 18 | 334 | 84 | 0 | 230 | 115 | 0 | 0 | 0 | 10 | 4 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 21 | 40 | 22 | 0 | 60 | 26 | 22 | 0 | 0 | 21 | 0 | 24 | 4 | 0 | 45 | 7 | 12 | 1 | 0 | 10 | 8 | 15 | 2 | 0 | 41 | 10 | 49 | 0 | 0 | 63 | 0 | 24 | 0 | 0 | 24 | 24 | 95 | 1 | 0 | 66 | 0 | 111 | 3 | 30 | 3 | 5 | 31 | 5 | 11 | 0 | 1 | 0 | 2 | 4 | 6 | 34 | 4 | 0 | 0 | 8 | 13 | 1 | 0 | 2 | 12 | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 6 | 2 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 3 | 4 | 0 | 2 | 2 | 0 | 4 | 6 | 2 | 2 | 0 | 4 | 0 | 8 | 0 | 2 | 4 | 18 | 9 | 0 | 5 | 22 | 4 | 11 | 0 | 1 | 20 | 4 | 0 | 0 | 0 | 12 | 1 | 0 | 0 | 0 | 17 | 0 | 7 | 3 | 1 | 56 | 0 | 10 | 0 | 9 | 1 | 1 | 11 | 0 | 20 | 30 | 10 | 7 | 4 | 1 | 59 | 17 | 0 | 0 | 1 | 9 | 0 | 4 | 0 | 4 | 29 | 0 | 0 | 2 | 13 | 8 | 4 | 3 | 0 | 1 | 11 | 0 | 0 | 0 | 2 | 45 | 15 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 4 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 2 | 5 | 0 | 4 | 0 | 9 | 38 | 51 | 26 | 0 | 2 | 13 | 0 | 10 | 0 | 4 | 0 | 0 | 23 | 0 | 0 | 7 | 23 | 17 | 0 | 0 | 8 | 11 | 6 | 1 | 0 | 17 | 0 | 20 | 0 | 0 | 20 | 4 | 13 | 0 | 0 | 23 | 7 | 20 | 0 | 0 | 21 | 0 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 2 | 0 | 19 | 0 | 0 | 9 | 20 | 10 | 0 | 0 | 10 | 0 | 14 | 0 | 0 | 14 | 14 | 30 | 0 | 0 | 3 | 33 | 30 | 0 | 22 | 24 | 58 | 48 | 0 | 0 | 37 | 0 | 16 | 0 | 0 | 16 | 3 | 6 | 0 | 0 | 24 | 0 | 1 | 0 | 0 | 2 | 6 | 4 | 2 | 5 | 18 | 2 | 54 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 7 | 0 | 4 | 0 | 0 | 42 | 27 | 4 | 0 | 0 | 29 | 19 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 0
2026-01-16 | W8 | 17 | 0 | 0 | 18 | 0 | 22 | 0 | 0 | 19 | 18 | 13 | 2 | 1 | 33 | 0 | 8 | 3 | 3 | 32 | 18 | 334 | 84 | 0 | 230 | 115 | 0 | 0 | 0 | 10 | 4 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 21 | 40 | 22 | 0 | 60 | 26 | 22 | 0 | 0 | 21 | 0 | 24 | 4 | 0 | 45 | 7 | 12 | 1 | 0 | 10 | 8 | 15 | 2 | 0 | 41 | 10 | 49 | 0 | 0 | 63 | 0 | 24 | 0 | 0 | 24 | 24 | 95 | 1 | 0 | 66 | 0 | 111 | 3 | 30 | 3 | 5 | 31 | 5 | 11 | 0 | 1 | 0 | 2 | 4 | 6 | 34 | 4 | 0 | 0 | 8 | 13 | 1 | 0 | 2 | 12 | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 6 | 2 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 3 | 4 | 0 | 2 | 2 | 0 | 4 | 6 | 2 | 2 | 0 | 4 | 0 | 8 | 0 | 2 | 4 | 18 | 9 | 0 | 5 | 22 | 4 | 11 | 0 | 1 | 20 | 4 | 0 | 0 | 0 | 12 | 1 | 0 | 0 | 0 | 17 | 0 | 7 | 3 | 1 | 56 | 0 | 10 | 0 | 9 | 1 | 1 | 11 | 0 | 20 | 30 | 10 | 7 | 4 | 1 | 59 | 17 | 0 | 0 | 1 | 9 | 0 | 4 | 0 | 4 | 29 | 0 | 0 | 2 | 13 | 8 | 4 | 3 | 0 | 1 | 11 | 0 | 0 | 0 | 2 | 45 | 15 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 4 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 2 | 5 | 0 | 4 | 0 | 9 | 38 | 51 | 26 | 0 | 2 | 13 | 0 | 10 | 0 | 4 | 0 | 0 | 23 | 0 | 0 | 7 | 23 | 17 | 0 | 0 | 8 | 11 | 6 | 1 | 0 | 17 | 0 | 20 | 0 | 0 | 20 | 4 | 13 | 0 | 0 | 23 | 7 | 20 | 0 | 0 | 21 | 0 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 2 | 0 | 19 | 0 | 0 | 9 | 20 | 10 | 0 | 0 | 10 | 0 | 14 | 0 | 0 | 14 | 14 | 30 | 0 | 0 | 3 | 33 | 30 | 0 | 22 | 24 | 58 | 48 | 0 | 0 | 37 | 0 | 16 | 0 | 0 | 16 | 3 | 6 | 0 | 0 | 24 | 0 | 1 | 0 | 0 | 2 | 6 | 4 | 2 | 5 | 18 | 2 | 54 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 7 | 0 | 4 | 0 | 0 | 42 | 27 | 4 | 0 | 0 | 29 | 19 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 0
2026-01-17 | W9 | 17 | 0 | 0 | 18 | 0 | 22 | 0 | 0 | 19 | 18 | 13 | 2 | 1 | 33 | 0 | 8 | 3 | 3 | 32 | 18 | 334 | 84 | 0 | 230 | 115 | 0 | 0 | 0 | 10 | 4 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 21 | 40 | 22 | 0 | 60 | 26 | 22 | 0 | 0 | 21 | 0 | 24 | 4 | 0 | 45 | 7 | 12 | 1 | 0 | 10 | 8 | 15 | 2 | 0 | 41 | 10 | 49 | 0 | 0 | 63 | 0 | 24 | 0 | 0 | 24 | 24 | 95 | 1 | 0 | 66 | 0 | 111 | 3 | 30 | 3 | 5 | 31 | 5 | 11 | 0 | 1 | 0 | 2 | 4 | 6 | 34 | 4 | 0 | 0 | 8 | 13 | 1 | 0 | 2 | 12 | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 6 | 2 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 3 | 4 | 0 | 2 | 2 | 0 | 4 | 6 | 2 | 2 | 0 | 4 | 0 | 8 | 0 | 2 | 4 | 18 | 9 | 0 | 5 | 22 | 4 | 11 | 0 | 1 | 20 | 4 | 0 | 0 | 0 | 12 | 1 | 0 | 0 | 0 | 17 | 0 | 7 | 3 | 1 | 56 | 0 | 10 | 0 | 9 | 1 | 1 | 11 | 0 | 20 | 30 | 10 | 7 | 4 | 1 | 59 | 17 | 0 | 0 | 1 | 9 | 0 | 4 | 0 | 4 | 29 | 0 | 0 | 2 | 13 | 8 | 4 | 3 | 0 | 1 | 11 | 0 | 0 | 0 | 2 | 45 | 15 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 4 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 2 | 5 | 0 | 4 | 0 | 9 | 38 | 51 | 26 | 0 | 2 | 13 | 0 | 10 | 0 | 4 | 0 | 0 | 23 | 0 | 0 | 7 | 23 | 17 | 0 | 0 | 8 | 11 | 6 | 1 | 0 | 17 | 0 | 20 | 0 | 0 | 20 | 4 | 13 | 0 | 0 | 23 | 7 | 20 | 0 | 0 | 21 | 0 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 2 | 0 | 19 | 0 | 0 | 9 | 20 | 10 | 0 | 0 | 10 | 0 | 14 | 0 | 0 | 14 | 14 | 30 | 0 | 0 | 3 | 33 | 30 | 0 | 22 | 24 | 58 | 48 | 0 | 0 | 37 | 0 | 16 | 0 | 0 | 16 | 3 | 6 | 0 | 0 | 24 | 0 | 1 | 0 | 0 | 2 | 6 | 4 | 2 | 5 | 18 | 2 | 54 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 7 | 0 | 4 | 0 | 0 | 42 | 27 | 4 | 0 | 0 | 29 | 19 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 0
2026-01-19 | W9 | 17 | 0 | 0 | 18 | 0 | 22 | 0 | 0 | 19 | 18 | 13 | 2 | 1 | 33 | 0 | 8 | 3 | 3 | 32 | 18 | 334 | 84 | 0 | 230 | 115 | 0 | 0 | 0 | 10 | 4 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 21 | 40 | 22 | 0 | 60 | 26 | 22 | 0 | 0 | 21 | 0 | 24 | 4 | 0 | 45 | 7 | 12 | 1 | 0 | 10 | 8 | 15 | 2 | 0 | 41 | 10 | 49 | 0 | 0 | 63 | 0 | 24 | 0 | 0 | 24 | 24 | 95 | 1 | 0 | 66 | 0 | 111 | 3 | 30 | 3 | 5 | 31 | 5 | 11 | 0 | 1 | 0 | 2 | 4 | 6 | 34 | 4 | 0 | 0 | 8 | 13 | 1 | 0 | 2 | 12 | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 6 | 2 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 3 | 4 | 0 | 2 | 2 | 0 | 4 | 6 | 2 | 2 | 0 | 4 | 0 | 8 | 0 | 2 | 4 | 18 | 9 | 0 | 5 | 22 | 4 | 11 | 0 | 1 | 20 | 4 | 0 | 0 | 0 | 12 | 1 | 0 | 0 | 0 | 17 | 0 | 7 | 3 | 1 | 56 | 0 | 10 | 0 | 9 | 1 | 1 | 11 | 0 | 20 | 30 | 10 | 7 | 4 | 1 | 59 | 17 | 0 | 0 | 1 | 9 | 0 | 4 | 0 | 4 | 29 | 0 | 0 | 2 | 13 | 8 | 4 | 3 | 0 | 1 | 11 | 0 | 0 | 0 | 2 | 45 | 15 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 4 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 2 | 5 | 0 | 4 | 0 | 9 | 38 | 51 | 26 | 0 | 2 | 13 | 0 | 10 | 0 | 4 | 0 | 0 | 23 | 0 | 0 | 7 | 23 | 17 | 0 | 0 | 8 | 11 | 6 | 1 | 0 | 17 | 0 | 20 | 0 | 0 | 20 | 4 | 13 | 0 | 0 | 23 | 7 | 20 | 0 | 0 | 21 | 0 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 2 | 0 | 19 | 0 | 0 | 9 | 20 | 10 | 0 | 0 | 10 | 0 | 14 | 0 | 0 | 14 | 14 | 30 | 0 | 0 | 3 | 33 | 30 | 0 | 22 | 24 | 58 | 48 | 0 | 0 | 37 | 0 | 16 | 0 | 0 | 16 | 3 | 6 | 0 | 0 | 24 | 0 | 1 | 0 | 0 | 2 | 6 | 4 | 2 | 5 | 18 | 2 | 54 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 7 | 0 | 4 | 0 | 0 | 42 | 27 | 4 | 0 | 0 | 29 | 19 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 0
2026-01-20 | W9 | 17 | 0 | 0 | 18 | 0 | 22 | 0 | 0 | 19 | 18 | 13 | 2 | 1 | 33 | 0 | 8 | 3 | 3 | 32 | 18 | 334 | 84 | 0 | 230 | 115 | 0 | 0 | 0 | 10 | 4 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 21 | 40 | 22 | 0 | 60 | 26 | 22 | 0 | 0 | 21 | 0 | 24 | 4 | 0 | 45 | 7 | 12 | 1 | 0 | 10 | 8 | 15 | 2 | 0 | 41 | 10 | 49 | 0 | 0 | 63 | 0 | 24 | 0 | 0 | 24 | 24 | 95 | 1 | 0 | 66 | 0 | 111 | 3 | 30 | 3 | 5 | 31 | 5 | 11 | 0 | 1 | 0 | 2 | 4 | 6 | 34 | 4 | 0 | 0 | 8 | 13 | 1 | 0 | 2 | 12 | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 6 | 2 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 3 | 4 | 0 | 2 | 2 | 0 | 4 | 6 | 2 | 2 | 0 | 4 | 0 | 8 | 0 | 2 | 4 | 18 | 9 | 0 | 5 | 22 | 4 | 11 | 0 | 1 | 20 | 4 | 0 | 0 | 0 | 12 | 1 | 0 | 0 | 0 | 17 | 0 | 7 | 3 | 1 | 56 | 0 | 10 | 0 | 9 | 1 | 1 | 11 | 0 | 20 | 30 | 10 | 7 | 4 | 1 | 59 | 17 | 0 | 0 | 1 | 9 | 0 | 4 | 0 | 4 | 29 | 0 | 0 | 2 | 13 | 8 | 4 | 3 | 0 | 1 | 11 | 0 | 0 | 0 | 2 | 45 | 15 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 4 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 2 | 5 | 0 | 4 | 0 | 9 | 38 | 51 | 26 | 0 | 2 | 13 | 0 | 10 | 0 | 4 | 0 | 0 | 23 | 0 | 0 | 7 | 23 | 17 | 0 | 0 | 8 | 11 | 6 | 1 | 0 | 17 | 0 | 20 | 0 | 0 | 20 | 4 | 13 | 0 | 0 | 23 | 7 | 20 | 0 | 0 | 21 | 0 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 2 | 0 | 19 | 0 | 0 | 9 | 20 | 10 | 0 | 0 | 10 | 0 | 14 | 0 | 0 | 14 | 14 | 30 | 0 | 0 | 3 | 33 | 30 | 0 | 22 | 24 | 58 | 48 | 0 | 0 | 37 | 0 | 16 | 0 | 0 | 16 | 3 | 6 | 0 | 0 | 24 | 0 | 1 | 0 | 0 | 2 | 6 | 4 | 2 | 5 | 18 | 2 | 54 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 7 | 0 | 4 | 0 | 0 | 42 | 27 | 4 | 0 | 0 | 29 | 19 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 0
2026-01-21 | W9 | 17 | 0 | 0 | 18 | 0 | 22 | 0 | 0 | 19 | 18 | 13 | 2 | 1 | 33 | 0 | 8 | 3 | 3 | 32 | 18 | 334 | 84 | 0 | 230 | 115 | 0 | 0 | 0 | 10 | 4 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 21 | 40 | 22 | 0 | 60 | 26 | 22 | 0 | 0 | 21 | 0 | 24 | 4 | 0 | 45 | 7 | 12 | 1 | 0 | 10 | 8 | 15 | 2 | 0 | 41 | 10 | 49 | 0 | 0 | 63 | 0 | 24 | 0 | 0 | 24 | 24 | 95 | 1 | 0 | 66 | 0 | 111 | 3 | 30 | 3 | 5 | 31 | 5 | 11 | 0 | 1 | 0 | 2 | 4 | 6 | 34 | 4 | 0 | 0 | 8 | 13 | 1 | 0 | 2 | 12 | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 6 | 2 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 3 | 4 | 0 | 2 | 2 | 0 | 4 | 6 | 2 | 2 | 0 | 4 | 0 | 8 | 0 | 2 | 4 | 18 | 9 | 0 | 5 | 22 | 4 | 11 | 0 | 1 | 20 | 4 | 0 | 0 | 0 | 12 | 1 | 0 | 0 | 0 | 17 | 0 | 7 | 3 | 1 | 56 | 0 | 10 | 0 | 9 | 1 | 1 | 11 | 0 | 20 | 30 | 10 | 7 | 4 | 1 | 59 | 17 | 0 | 0 | 1 | 9 | 0 | 4 | 0 | 4 | 29 | 0 | 0 | 2 | 13 | 8 | 4 | 3 | 0 | 1 | 11 | 0 | 0 | 0 | 2 | 45 | 15 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 4 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 2 | 5 | 0 | 4 | 0 | 9 | 38 | 51 | 26 | 0 | 2 | 13 | 0 | 10 | 0 | 4 | 0 | 0 | 23 | 0 | 0 | 7 | 23 | 17 | 0 | 0 | 8 | 11 | 6 | 1 | 0 | 17 | 0 | 20 | 0 | 0 | 20 | 4 | 13 | 0 | 0 | 23 | 7 | 20 | 0 | 0 | 21 | 0 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 2 | 0 | 19 | 0 | 0 | 9 | 20 | 10 | 0 | 0 | 10 | 0 | 14 | 0 | 0 | 14 | 14 | 30 | 0 | 0 | 3 | 33 | 30 | 0 | 22 | 24 | 58 | 48 | 0 | 0 | 37 | 0 | 16 | 0 | 0 | 16 | 3 | 6 | 0 | 0 | 24 | 0 | 1 | 0 | 0 | 2 | 6 | 4 | 2 | 5 | 18 | 2 | 54 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 7 | 0 | 4 | 0 | 0 | 42 | 27 | 4 | 0 | 0 | 29 | 19 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 0
2026-01-22 | W9 | 17 | 0 | 0 | 18 | 0 | 22 | 0 | 0 | 19 | 18 | 13 | 2 | 1 | 33 | 0 | 8 | 3 | 3 | 32 | 18 | 334 | 84 | 0 | 230 | 115 | 0 | 0 | 0 | 10 | 4 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 21 | 40 | 22 | 0 | 60 | 26 | 22 | 0 | 0 | 21 | 0 | 24 | 4 | 0 | 45 | 7 | 12 | 1 | 0 | 10 | 8 | 15 | 2 | 0 | 41 | 10 | 49 | 0 | 0 | 63 | 0 | 24 | 0 | 0 | 24 | 24 | 95 | 1 | 0 | 66 | 0 | 111 | 3 | 30 | 3 | 5 | 31 | 5 | 11 | 0 | 1 | 0 | 2 | 4 | 6 | 34 | 4 | 0 | 0 | 8 | 13 | 1 | 0 | 2 | 12 | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 6 | 2 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 3 | 4 | 0 | 2 | 2 | 0 | 4 | 6 | 2 | 2 | 0 | 4 | 0 | 8 | 0 | 2 | 4 | 18 | 9 | 0 | 5 | 22 | 4 | 11 | 0 | 1 | 20 | 4 | 0 | 0 | 0 | 12 | 1 | 0 | 0 | 0 | 17 | 0 | 7 | 3 | 1 | 56 | 0 | 10 | 0 | 9 | 1 | 1 | 11 | 0 | 20 | 30 | 10 | 7 | 4 | 1 | 59 | 17 | 0 | 0 | 1 | 9 | 0 | 4 | 0 | 4 | 29 | 0 | 0 | 2 | 13 | 8 | 4 | 3 | 0 | 1 | 11 | 0 | 0 | 0 | 2 | 45 | 15 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 4 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 2 | 5 | 0 | 4 | 0 | 9 | 38 | 51 | 26 | 0 | 2 | 13 | 0 | 10 | 0 | 4 | 0 | 0 | 23 | 0 | 0 | 7 | 23 | 17 | 0 | 0 | 8 | 11 | 6 | 1 | 0 | 17 | 0 | 20 | 0 | 0 | 20 | 4 | 13 | 0 | 0 | 23 | 7 | 20 | 0 | 0 | 21 | 0 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 2 | 0 | 19 | 0 | 0 | 9 | 20 | 10 | 0 | 0 | 10 | 0 | 14 | 0 | 0 | 14 | 14 | 30 | 0 | 0 | 3 | 33 | 30 | 0 | 22 | 24 | 58 | 48 | 0 | 0 | 37 | 0 | 16 | 0 | 0 | 16 | 3 | 6 | 0 | 0 | 24 | 0 | 1 | 0 | 0 | 2 | 6 | 4 | 2 | 5 | 18 | 2 | 54 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 7 | 0 | 4 | 0 | 0 | 42 | 27 | 4 | 0 | 0 | 29 | 19 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 0
2026-01-23 | W9 | 17 | 0 | 0 | 18 | 0 | 22 | 0 | 0 | 19 | 18 | 13 | 2 | 1 | 33 | 0 | 8 | 3 | 3 | 32 | 18 | 334 | 84 | 0 | 230 | 115 | 0 | 0 | 0 | 10 | 4 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 21 | 40 | 22 | 0 | 60 | 26 | 22 | 0 | 0 | 21 | 0 | 24 | 4 | 0 | 45 | 7 | 12 | 1 | 0 | 10 | 8 | 15 | 2 | 0 | 41 | 10 | 49 | 0 | 0 | 63 | 0 | 24 | 0 | 0 | 24 | 24 | 95 | 1 | 0 | 66 | 0 | 111 | 3 | 30 | 3 | 5 | 31 | 5 | 11 | 0 | 1 | 0 | 2 | 4 | 6 | 34 | 4 | 0 | 0 | 8 | 13 | 1 | 0 | 2 | 12 | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 6 | 2 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 3 | 4 | 0 | 2 | 2 | 0 | 4 | 6 | 2 | 2 | 0 | 4 | 0 | 8 | 0 | 2 | 4 | 18 | 9 | 0 | 5 | 22 | 4 | 11 | 0 | 1 | 20 | 4 | 0 | 0 | 0 | 12 | 1 | 0 | 0 | 0 | 17 | 0 | 7 | 3 | 1 | 56 | 0 | 10 | 0 | 9 | 1 | 1 | 11 | 0 | 20 | 30 | 10 | 7 | 4 | 1 | 59 | 17 | 0 | 0 | 1 | 9 | 0 | 4 | 0 | 4 | 29 | 0 | 0 | 2 | 13 | 8 | 4 | 3 | 0 | 1 | 11 | 0 | 0 | 0 | 2 | 45 | 15 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 4 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 2 | 5 | 0 | 4 | 0 | 9 | 38 | 51 | 26 | 0 | 2 | 13 | 0 | 10 | 0 | 4 | 0 | 0 | 23 | 0 | 0 | 7 | 23 | 17 | 0 | 0 | 8 | 11 | 6 | 1 | 0 | 17 | 0 | 20 | 0 | 0 | 20 | 4 | 13 | 0 | 0 | 23 | 7 | 20 | 0 | 0 | 21 | 0 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 2 | 0 | 19 | 0 | 0 | 9 | 20 | 10 | 0 | 0 | 10 | 0 | 14 | 0 | 0 | 14 | 14 | 30 | 0 | 0 | 3 | 33 | 30 | 0 | 22 | 24 | 58 | 48 | 0 | 0 | 37 | 0 | 16 | 0 | 0 | 16 | 3 | 6 | 0 | 0 | 24 | 0 | 1 | 0 | 0 | 2 | 6 | 4 | 2 | 5 | 18 | 2 | 54 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 7 | 0 | 4 | 0 | 0 | 42 | 27 | 4 | 0 | 0 | 29 | 19 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 0
2026-01-24 | W10 | 17 | 0 | 0 | 18 | 0 | 22 | 0 | 0 | 19 | 18 | 13 | 2 | 1 | 33 | 0 | 8 | 3 | 3 | 32 | 18 | 334 | 84 | 0 | 230 | 115 | 0 | 0 | 0 | 10 | 4 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 21 | 40 | 22 | 0 | 60 | 26 | 22 | 0 | 0 | 21 | 0 | 24 | 4 | 0 | 45 | 7 | 12 | 1 | 0 | 10 | 8 | 15 | 2 | 0 | 41 | 10 | 49 | 0 | 0 | 63 | 0 | 24 | 0 | 0 | 24 | 24 | 95 | 1 | 0 | 66 | 0 | 111 | 3 | 30 | 3 | 5 | 31 | 5 | 11 | 0 | 1 | 0 | 2 | 4 | 6 | 34 | 4 | 0 | 0 | 8 | 13 | 1 | 0 | 2 | 12 | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 6 | 2 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 3 | 4 | 0 | 2 | 2 | 0 | 4 | 6 | 2 | 2 | 0 | 4 | 0 | 8 | 0 | 2 | 4 | 18 | 9 | 0 | 5 | 22 | 4 | 11 | 0 | 1 | 20 | 4 | 0 | 0 | 0 | 12 | 1 | 0 | 0 | 0 | 17 | 0 | 7 | 3 | 1 | 56 | 0 | 10 | 0 | 9 | 1 | 1 | 11 | 0 | 20 | 30 | 10 | 7 | 4 | 1 | 59 | 17 | 0 | 0 | 1 | 9 | 0 | 4 | 0 | 4 | 29 | 0 | 0 | 2 | 13 | 8 | 4 | 3 | 0 | 1 | 11 | 0 | 0 | 0 | 2 | 45 | 15 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 4 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 2 | 5 | 0 | 4 | 0 | 9 | 38 | 51 | 26 | 0 | 2 | 13 | 0 | 10 | 0 | 4 | 0 | 0 | 23 | 0 | 0 | 7 | 23 | 17 | 0 | 0 | 8 | 11 | 6 | 1 | 0 | 17 | 0 | 20 | 0 | 0 | 20 | 4 | 13 | 0 | 0 | 23 | 7 | 20 | 0 | 0 | 21 | 0 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 2 | 0 | 19 | 0 | 0 | 9 | 20 | 10 | 0 | 0 | 10 | 0 | 14 | 0 | 0 | 14 | 14 | 30 | 0 | 0 | 3 | 33 | 30 | 0 | 22 | 24 | 58 | 48 | 0 | 0 | 37 | 0 | 16 | 0 | 0 | 16 | 3 | 6 | 0 | 0 | 24 | 0 | 1 | 0 | 0 | 2 | 6 | 4 | 2 | 5 | 18 | 2 | 54 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 7 | 0 | 4 | 0 | 0 | 42 | 27 | 4 | 0 | 0 | 29 | 19 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 0
2026-01-27 | W10 | 17 | 0 | 0 | 18 | 0 | 22 | 0 | 0 | 19 | 18 | 13 | 2 | 1 | 33 | 0 | 8 | 3 | 3 | 32 | 18 | 334 | 84 | 0 | 230 | 115 | 0 | 0 | 0 | 10 | 4 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 21 | 40 | 22 | 0 | 60 | 26 | 22 | 0 | 0 | 21 | 0 | 24 | 4 | 0 | 45 | 7 | 12 | 1 | 0 | 10 | 8 | 15 | 2 | 0 | 41 | 10 | 49 | 0 | 0 | 63 | 0 | 24 | 0 | 0 | 24 | 24 | 95 | 1 | 0 | 66 | 0 | 111 | 3 | 30 | 3 | 5 | 31 | 5 | 11 | 0 | 1 | 0 | 2 | 4 | 6 | 34 | 4 | 0 | 0 | 8 | 13 | 1 | 0 | 2 | 12 | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 6 | 2 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 3 | 4 | 0 | 2 | 2 | 0 | 4 | 6 | 2 | 2 | 0 | 4 | 0 | 8 | 0 | 2 | 4 | 18 | 9 | 0 | 5 | 22 | 4 | 11 | 0 | 1 | 20 | 4 | 0 | 0 | 0 | 12 | 1 | 0 | 0 | 0 | 17 | 0 | 7 | 3 | 1 | 56 | 0 | 10 | 0 | 9 | 1 | 1 | 11 | 0 | 20 | 30 | 10 | 7 | 4 | 1 | 59 | 17 | 0 | 0 | 1 | 9 | 0 | 4 | 0 | 4 | 29 | 0 | 0 | 2 | 13 | 8 | 4 | 3 | 0 | 1 | 11 | 0 | 0 | 0 | 2 | 45 | 15 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 4 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 2 | 5 | 0 | 4 | 0 | 9 | 38 | 51 | 26 | 0 | 2 | 13 | 0 | 10 | 0 | 4 | 0 | 0 | 23 | 0 | 0 | 7 | 23 | 17 | 0 | 0 | 8 | 11 | 6 | 1 | 0 | 17 | 0 | 20 | 0 | 0 | 20 | 4 | 13 | 0 | 0 | 23 | 7 | 20 | 0 | 0 | 21 | 0 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 2 | 0 | 19 | 0 | 0 | 9 | 20 | 10 | 0 | 0 | 10 | 0 | 14 | 0 | 0 | 14 | 14 | 30 | 0 | 0 | 3 | 33 | 30 | 0 | 22 | 24 | 58 | 48 | 0 | 0 | 37 | 0 | 16 | 0 | 0 | 16 | 3 | 6 | 0 | 0 | 24 | 0 | 1 | 0 | 0 | 2 | 6 | 4 | 2 | 5 | 18 | 2 | 54 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 7 | 0 | 4 | 0 | 0 | 42 | 27 | 4 | 0 | 0 | 29 | 19 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 0
2026-01-28 | W10 | 17 | 0 | 0 | 18 | 0 | 22 | 0 | 0 | 19 | 18 | 13 | 2 | 1 | 33 | 0 | 8 | 3 | 3 | 32 | 18 | 334 | 84 | 0 | 230 | 115 | 0 | 0 | 0 | 10 | 4 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 21 | 40 | 22 | 0 | 60 | 26 | 22 | 0 | 0 | 21 | 0 | 24 | 4 | 0 | 45 | 7 | 12 | 1 | 0 | 10 | 8 | 15 | 2 | 0 | 41 | 10 | 49 | 0 | 0 | 63 | 0 | 24 | 0 | 0 | 24 | 24 | 95 | 1 | 0 | 66 | 0 | 111 | 3 | 30 | 3 | 5 | 31 | 5 | 11 | 0 | 1 | 0 | 2 | 4 | 6 | 34 | 4 | 0 | 0 | 8 | 13 | 1 | 0 | 2 | 12 | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 6 | 2 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 3 | 4 | 0 | 2 | 2 | 0 | 4 | 6 | 2 | 2 | 0 | 4 | 0 | 8 | 0 | 2 | 4 | 18 | 9 | 0 | 5 | 22 | 4 | 11 | 0 | 1 | 20 | 4 | 0 | 0 | 0 | 12 | 1 | 0 | 0 | 0 | 17 | 0 | 7 | 3 | 1 | 56 | 0 | 10 | 0 | 9 | 1 | 1 | 11 | 0 | 20 | 30 | 10 | 7 | 4 | 1 | 59 | 17 | 0 | 0 | 1 | 9 | 0 | 4 | 0 | 4 | 29 | 0 | 0 | 2 | 13 | 8 | 4 | 3 | 0 | 1 | 11 | 0 | 0 | 0 | 2 | 45 | 15 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 4 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 2 | 5 | 0 | 4 | 0 | 9 | 38 | 51 | 26 | 0 | 2 | 13 | 0 | 10 | 0 | 4 | 0 | 0 | 23 | 0 | 0 | 7 | 23 | 17 | 0 | 0 | 8 | 11 | 6 | 1 | 0 | 17 | 0 | 20 | 0 | 0 | 20 | 4 | 13 | 0 | 0 | 23 | 7 | 20 | 0 | 0 | 21 | 0 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 2 | 0 | 19 | 0 | 0 | 9 | 20 | 10 | 0 | 0 | 10 | 0 | 14 | 0 | 0 | 14 | 14 | 30 | 0 | 0 | 3 | 33 | 30 | 0 | 22 | 24 | 58 | 48 | 0 | 0 | 37 | 0 | 16 | 0 | 0 | 16 | 3 | 6 | 0 | 0 | 24 | 0 | 1 | 0 | 0 | 2 | 6 | 4 | 2 | 5 | 18 | 2 | 54 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 7 | 0 | 4 | 0 | 0 | 42 | 27 | 4 | 0 | 0 | 29 | 19 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 0
2026-01-29 | W10 | 17 | 0 | 0 | 18 | 0 | 22 | 0 | 0 | 19 | 18 | 13 | 2 | 1 | 33 | 0 | 8 | 3 | 3 | 32 | 18 | 334 | 84 | 0 | 230 | 115 | 0 | 0 | 0 | 10 | 4 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 21 | 40 | 22 | 0 | 60 | 26 | 22 | 0 | 0 | 21 | 0 | 24 | 4 | 0 | 45 | 7 | 12 | 1 | 0 | 10 | 8 | 15 | 2 | 0 | 41 | 10 | 49 | 0 | 0 | 63 | 0 | 24 | 0 | 0 | 24 | 24 | 95 | 1 | 0 | 66 | 0 | 111 | 3 | 30 | 3 | 5 | 31 | 5 | 11 | 0 | 1 | 0 | 2 | 4 | 6 | 34 | 4 | 0 | 0 | 8 | 13 | 1 | 0 | 2 | 12 | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 6 | 2 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 3 | 4 | 0 | 2 | 2 | 0 | 4 | 6 | 2 | 2 | 0 | 4 | 0 | 8 | 0 | 2 | 4 | 18 | 9 | 0 | 5 | 22 | 4 | 11 | 0 | 1 | 20 | 4 | 0 | 0 | 0 | 12 | 1 | 0 | 0 | 0 | 17 | 0 | 7 | 3 | 1 | 56 | 0 | 10 | 0 | 9 | 1 | 1 | 11 | 0 | 20 | 30 | 10 | 7 | 4 | 1 | 59 | 17 | 0 | 0 | 1 | 9 | 0 | 4 | 0 | 4 | 29 | 0 | 0 | 2 | 13 | 8 | 4 | 3 | 0 | 1 | 11 | 0 | 0 | 0 | 2 | 45 | 15 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 4 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 2 | 5 | 0 | 4 | 0 | 9 | 38 | 51 | 26 | 0 | 2 | 13 | 0 | 10 | 0 | 4 | 0 | 0 | 23 | 0 | 0 | 7 | 23 | 17 | 0 | 0 | 8 | 11 | 6 | 1 | 0 | 17 | 0 | 20 | 0 | 0 | 20 | 4 | 13 | 0 | 0 | 23 | 7 | 20 | 0 | 0 | 21 | 0 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 2 | 0 | 19 | 0 | 0 | 9 | 20 | 10 | 0 | 0 | 10 | 0 | 14 | 0 | 0 | 14 | 14 | 30 | 0 | 0 | 3 | 33 | 30 | 0 | 22 | 24 | 58 | 48 | 0 | 0 | 37 | 0 | 16 | 0 | 0 | 16 | 3 | 6 | 0 | 0 | 24 | 0 | 1 | 0 | 0 | 2 | 6 | 4 | 2 | 5 | 18 | 2 | 54 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 7 | 0 | 4 | 0 | 0 | 42 | 27 | 4 | 0 | 0 | 29 | 19 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 0
2026-01-30 | W10 | 17 | 0 | 0 | 18 | 0 | 22 | 0 | 0 | 19 | 18 | 13 | 2 | 1 | 33 | 0 | 8 | 3 | 3 | 32 | 18 | 334 | 84 | 0 | 230 | 115 | 0 | 0 | 0 | 10 | 4 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 21 | 40 | 22 | 0 | 60 | 26 | 22 | 0 | 0 | 21 | 0 | 24 | 4 | 0 | 45 | 7 | 12 | 1 | 0 | 10 | 8 | 15 | 2 | 0 | 41 | 10 | 49 | 0 | 0 | 63 | 0 | 24 | 0 | 0 | 24 | 24 | 95 | 1 | 0 | 66 | 0 | 111 | 3 | 30 | 3 | 5 | 31 | 5 | 11 | 0 | 1 | 0 | 2 | 4 | 6 | 34 | 4 | 0 | 0 | 8 | 13 | 1 | 0 | 2 | 12 | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 6 | 2 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 3 | 4 | 0 | 2 | 2 | 0 | 4 | 6 | 2 | 2 | 0 | 4 | 0 | 8 | 0 | 2 | 4 | 18 | 9 | 0 | 5 | 22 | 4 | 11 | 0 | 1 | 20 | 4 | 0 | 0 | 0 | 12 | 1 | 0 | 0 | 0 | 17 | 0 | 7 | 3 | 1 | 56 | 0 | 10 | 0 | 9 | 1 | 1 | 11 | 0 | 20 | 30 | 10 | 7 | 4 | 1 | 59 | 17 | 0 | 0 | 1 | 9 | 0 | 4 | 0 | 4 | 29 | 0 | 0 | 2 | 13 | 8 | 4 | 3 | 0 | 1 | 11 | 0 | 0 | 0 | 2 | 45 | 15 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 4 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 2 | 5 | 0 | 4 | 0 | 9 | 38 | 51 | 26 | 0 | 2 | 13 | 0 | 10 | 0 | 4 | 0 | 0 | 23 | 0 | 0 | 7 | 23 | 17 | 0 | 0 | 8 | 11 | 6 | 1 | 0 | 17 | 0 | 20 | 0 | 0 | 20 | 4 | 13 | 0 | 0 | 23 | 7 | 20 | 0 | 0 | 21 | 0 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 2 | 0 | 19 | 0 | 0 | 9 | 20 | 10 | 0 | 0 | 10 | 0 | 14 | 0 | 0 | 14 | 14 | 30 | 0 | 0 | 3 | 33 | 30 | 0 | 22 | 24 | 58 | 48 | 0 | 0 | 37 | 0 | 16 | 0 | 0 | 16 | 3 | 6 | 0 | 0 | 24 | 0 | 1 | 0 | 0 | 2 | 6 | 4 | 2 | 5 | 18 | 2 | 54 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 7 | 0 | 4 | 0 | 0 | 42 | 27 | 4 | 0 | 0 | 29 | 19 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 0
2026-01-31 | W11 | 17 | 0 | 0 | 18 | 0 | 22 | 0 | 0 | 19 | 18 | 13 | 2 | 1 | 33 | 0 | 8 | 3 | 3 | 32 | 18 | 334 | 84 | 0 | 230 | 115 | 0 | 0 | 0 | 10 | 4 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 21 | 40 | 22 | 0 | 60 | 26 | 22 | 0 | 0 | 21 | 0 | 24 | 4 | 0 | 45 | 7 | 12 | 1 | 0 | 10 | 8 | 15 | 2 | 0 | 41 | 10 | 49 | 0 | 0 | 63 | 0 | 24 | 0 | 0 | 24 | 24 | 95 | 1 | 0 | 66 | 0 | 111 | 3 | 30 | 3 | 5 | 31 | 5 | 11 | 0 | 1 | 0 | 2 | 4 | 6 | 34 | 4 | 0 | 0 | 8 | 13 | 1 | 0 | 2 | 12 | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 6 | 2 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 3 | 4 | 0 | 2 | 2 | 0 | 4 | 6 | 2 | 2 | 0 | 4 | 0 | 8 | 0 | 2 | 4 | 18 | 9 | 0 | 5 | 22 | 4 | 11 | 0 | 1 | 20 | 4 | 0 | 0 | 0 | 12 | 1 | 0 | 0 | 0 | 17 | 0 | 7 | 3 | 1 | 56 | 0 | 10 | 0 | 9 | 1 | 1 | 11 | 0 | 20 | 30 | 10 | 7 | 4 | 1 | 59 | 17 | 0 | 0 | 1 | 9 | 0 | 4 | 0 | 4 | 29 | 0 | 0 | 2 | 13 | 8 | 4 | 3 | 0 | 1 | 11 | 0 | 0 | 0 | 2 | 45 | 15 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 4 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 2 | 5 | 0 | 4 | 0 | 9 | 38 | 51 | 26 | 0 | 2 | 13 | 0 | 10 | 0 | 4 | 0 | 0 | 23 | 0 | 0 | 7 | 23 | 17 | 0 | 0 | 8 | 11 | 6 | 1 | 0 | 17 | 0 | 20 | 0 | 0 | 20 | 4 | 13 | 0 | 0 | 23 | 7 | 20 | 0 | 0 | 21 | 0 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 2 | 0 | 19 | 0 | 0 | 9 | 20 | 10 | 0 | 0 | 10 | 0 | 14 | 0 | 0 | 14 | 14 | 30 | 0 | 0 | 3 | 33 | 30 | 0 | 22 | 24 | 58 | 48 | 0 | 0 | 37 | 0 | 16 | 0 | 0 | 16 | 3 | 6 | 0 | 0 | 24 | 0 | 1 | 0 | 0 | 2 | 6 | 4 | 2 | 5 | 18 | 2 | 54 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 7 | 0 | 4 | 0 | 0 | 42 | 27 | 4 | 0 | 0 | 29 | 19 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 0
2026-02-02 | W11 | 17 | 0 | 0 | 18 | 0 | 22 | 0 | 0 | 19 | 18 | 13 | 2 | 1 | 33 | 0 | 8 | 3 | 3 | 32 | 18 | 334 | 84 | 0 | 230 | 115 | 0 | 0 | 0 | 10 | 4 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 21 | 40 | 22 | 0 | 60 | 26 | 22 | 0 | 0 | 21 | 0 | 24 | 4 | 0 | 45 | 7 | 12 | 1 | 0 | 10 | 8 | 15 | 2 | 0 | 41 | 10 | 49 | 0 | 0 | 63 | 0 | 24 | 0 | 0 | 24 | 24 | 95 | 1 | 0 | 66 | 0 | 111 | 3 | 30 | 3 | 5 | 31 | 5 | 11 | 0 | 1 | 0 | 2 | 4 | 6 | 34 | 4 | 0 | 0 | 8 | 13 | 1 | 0 | 2 | 12 | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 6 | 2 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 3 | 4 | 0 | 2 | 2 | 0 | 4 | 6 | 2 | 2 | 0 | 4 | 0 | 8 | 0 | 2 | 4 | 18 | 9 | 0 | 5 | 22 | 4 | 11 | 0 | 1 | 20 | 4 | 0 | 0 | 0 | 12 | 1 | 0 | 0 | 0 | 17 | 0 | 7 | 3 | 1 | 56 | 0 | 10 | 0 | 9 | 1 | 1 | 11 | 0 | 20 | 30 | 10 | 7 | 4 | 1 | 59 | 17 | 0 | 0 | 1 | 9 | 0 | 4 | 0 | 4 | 29 | 0 | 0 | 2 | 13 | 8 | 4 | 3 | 0 | 1 | 11 | 0 | 0 | 0 | 2 | 45 | 15 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 4 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 2 | 5 | 0 | 4 | 0 | 9 | 38 | 51 | 26 | 0 | 2 | 13 | 0 | 10 | 0 | 4 | 0 | 0 | 23 | 0 | 0 | 7 | 23 | 17 | 0 | 0 | 8 | 11 | 6 | 1 | 0 | 17 | 0 | 20 | 0 | 0 | 20 | 4 | 13 | 0 | 0 | 23 | 7 | 20 | 0 | 0 | 21 | 0 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 2 | 0 | 19 | 0 | 0 | 9 | 20 | 10 | 0 | 0 | 10 | 0 | 14 | 0 | 0 | 14 | 14 | 30 | 0 | 0 | 3 | 33 | 30 | 0 | 22 | 24 | 58 | 48 | 0 | 0 | 37 | 0 | 16 | 0 | 0 | 16 | 3 | 6 | 0 | 0 | 24 | 0 | 1 | 0 | 0 | 2 | 6 | 4 | 2 | 5 | 18 | 2 | 54 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 7 | 0 | 4 | 0 | 0 | 42 | 27 | 4 | 0 | 0 | 29 | 19 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 0
2026-02-03 | W11 | 17 | 0 | 0 | 18 | 0 | 22 | 0 | 0 | 19 | 18 | 13 | 2 | 1 | 33 | 0 | 8 | 3 | 3 | 32 | 18 | 334 | 84 | 0 | 230 | 115 | 0 | 0 | 0 | 10 | 4 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 21 | 40 | 22 | 0 | 60 | 26 | 22 | 0 | 0 | 21 | 0 | 24 | 4 | 0 | 45 | 7 | 12 | 1 | 0 | 10 | 8 | 15 | 2 | 0 | 41 | 10 | 49 | 0 | 0 | 63 | 0 | 24 | 0 | 0 | 24 | 24 | 95 | 1 | 0 | 66 | 0 | 111 | 3 | 30 | 3 | 5 | 31 | 5 | 11 | 0 | 1 | 0 | 2 | 4 | 6 | 34 | 4 | 0 | 0 | 8 | 13 | 1 | 0 | 2 | 12 | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 6 | 2 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 3 | 4 | 0 | 2 | 2 | 0 | 4 | 6 | 2 | 2 | 0 | 4 | 0 | 8 | 0 | 2 | 4 | 18 | 9 | 0 | 5 | 22 | 4 | 11 | 0 | 1 | 20 | 4 | 0 | 0 | 0 | 12 | 1 | 0 | 0 | 0 | 17 | 0 | 7 | 3 | 1 | 56 | 0 | 10 | 0 | 9 | 1 | 1 | 11 | 0 | 20 | 30 | 10 | 7 | 4 | 1 | 59 | 17 | 0 | 0 | 1 | 9 | 0 | 4 | 0 | 4 | 29 | 0 | 0 | 2 | 13 | 8 | 4 | 3 | 0 | 1 | 11 | 0 | 0 | 0 | 2 | 45 | 15 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 4 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 2 | 5 | 0 | 4 | 0 | 9 | 38 | 51 | 26 | 0 | 2 | 13 | 0 | 10 | 0 | 4 | 0 | 0 | 23 | 0 | 0 | 7 | 23 | 17 | 0 | 0 | 8 | 11 | 6 | 1 | 0 | 17 | 0 | 20 | 0 | 0 | 20 | 4 | 13 | 0 | 0 | 23 | 7 | 20 | 0 | 0 | 21 | 0 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 2 | 0 | 19 | 0 | 0 | 9 | 20 | 10 | 0 | 0 | 10 | 0 | 14 | 0 | 0 | 14 | 14 | 30 | 0 | 0 | 3 | 33 | 30 | 0 | 22 | 24 | 58 | 48 | 0 | 0 | 37 | 0 | 16 | 0 | 0 | 16 | 3 | 6 | 0 | 0 | 24 | 0 | 1 | 0 | 0 | 2 | 6 | 4 | 2 | 5 | 18 | 2 | 54 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 7 | 0 | 4 | 0 | 0 | 42 | 27 | 4 | 0 | 0 | 29 | 19 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 0
2026-02-04 | W11 | 17 | 0 | 0 | 18 | 0 | 22 | 0 | 0 | 19 | 18 | 13 | 2 | 1 | 33 | 0 | 8 | 3 | 3 | 32 | 18 | 334 | 84 | 0 | 230 | 115 | 0 | 0 | 0 | 10 | 4 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 21 | 40 | 22 | 0 | 60 | 26 | 22 | 0 | 0 | 21 | 0 | 24 | 4 | 0 | 45 | 7 | 12 | 1 | 0 | 10 | 8 | 15 | 2 | 0 | 41 | 10 | 49 | 0 | 0 | 63 | 0 | 24 | 0 | 0 | 24 | 24 | 95 | 1 | 0 | 66 | 0 | 111 | 3 | 30 | 3 | 5 | 31 | 5 | 11 | 0 | 1 | 0 | 2 | 4 | 6 | 34 | 4 | 0 | 0 | 8 | 13 | 1 | 0 | 2 | 12 | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 6 | 2 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 3 | 4 | 0 | 2 | 2 | 0 | 4 | 6 | 2 | 2 | 0 | 4 | 0 | 8 | 0 | 2 | 4 | 18 | 9 | 0 | 5 | 22 | 4 | 11 | 0 | 1 | 20 | 4 | 0 | 0 | 0 | 12 | 1 | 0 | 0 | 0 | 17 | 0 | 7 | 3 | 1 | 56 | 0 | 10 | 0 | 9 | 1 | 1 | 11 | 0 | 20 | 30 | 10 | 7 | 4 | 1 | 59 | 17 | 0 | 0 | 1 | 9 | 0 | 4 | 0 | 4 | 29 | 0 | 0 | 2 | 13 | 8 | 4 | 3 | 0 | 1 | 11 | 0 | 0 | 0 | 2 | 45 | 15 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 4 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 2 | 5 | 0 | 4 | 0 | 9 | 38 | 51 | 26 | 0 | 2 | 13 | 0 | 10 | 0 | 4 | 0 | 0 | 23 | 0 | 0 | 7 | 23 | 17 | 0 | 0 | 8 | 11 | 6 | 1 | 0 | 17 | 0 | 20 | 0 | 0 | 20 | 4 | 13 | 0 | 0 | 23 | 7 | 20 | 0 | 0 | 21 | 0 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 2 | 0 | 19 | 0 | 0 | 9 | 20 | 10 | 0 | 0 | 10 | 0 | 14 | 0 | 0 | 14 | 14 | 30 | 0 | 0 | 3 | 33 | 30 | 0 | 22 | 24 | 58 | 48 | 0 | 0 | 37 | 0 | 16 | 0 | 0 | 16 | 3 | 6 | 0 | 0 | 24 | 0 | 1 | 0 | 0 | 2 | 6 | 4 | 2 | 5 | 18 | 2 | 54 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 7 | 0 | 4 | 0 | 0 | 42 | 27 | 4 | 0 | 0 | 29 | 19 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 0
2026-02-05 | W11 | 17 | 0 | 0 | 18 | 0 | 22 | 0 | 0 | 19 | 18 | 13 | 2 | 1 | 33 | 0 | 8 | 3 | 3 | 32 | 18 | 334 | 84 | 0 | 230 | 115 | 0 | 0 | 0 | 10 | 4 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 21 | 40 | 22 | 0 | 60 | 26 | 22 | 0 | 0 | 21 | 0 | 24 | 4 | 0 | 45 | 7 | 12 | 1 | 0 | 10 | 8 | 15 | 2 | 0 | 41 | 10 | 49 | 0 | 0 | 63 | 0 | 24 | 0 | 0 | 24 | 24 | 95 | 1 | 0 | 66 | 0 | 111 | 3 | 30 | 3 | 5 | 31 | 5 | 11 | 0 | 1 | 0 | 2 | 4 | 6 | 34 | 4 | 0 | 0 | 8 | 13 | 1 | 0 | 2 | 12 | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 6 | 2 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 3 | 4 | 0 | 2 | 2 | 0 | 4 | 6 | 2 | 2 | 0 | 4 | 0 | 8 | 0 | 2 | 4 | 18 | 9 | 0 | 5 | 22 | 4 | 11 | 0 | 1 | 20 | 4 | 0 | 0 | 0 | 12 | 1 | 0 | 0 | 0 | 17 | 0 | 7 | 3 | 1 | 56 | 0 | 10 | 0 | 9 | 1 | 1 | 11 | 0 | 20 | 30 | 10 | 7 | 4 | 1 | 59 | 17 | 0 | 0 | 1 | 9 | 0 | 4 | 0 | 4 | 29 | 0 | 0 | 2 | 13 | 8 | 4 | 3 | 0 | 1 | 11 | 0 | 0 | 0 | 2 | 45 | 15 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 4 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 2 | 5 | 0 | 4 | 0 | 9 | 38 | 51 | 26 | 0 | 2 | 13 | 0 | 10 | 0 | 4 | 0 | 0 | 23 | 0 | 0 | 7 | 23 | 17 | 0 | 0 | 8 | 11 | 6 | 1 | 0 | 17 | 0 | 20 | 0 | 0 | 20 | 4 | 13 | 0 | 0 | 23 | 7 | 20 | 0 | 0 | 21 | 0 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 2 | 0 | 19 | 0 | 0 | 9 | 20 | 10 | 0 | 0 | 10 | 0 | 14 | 0 | 0 | 14 | 14 | 30 | 0 | 0 | 3 | 33 | 30 | 0 | 22 | 24 | 58 | 48 | 0 | 0 | 37 | 0 | 16 | 0 | 0 | 16 | 3 | 6 | 0 | 0 | 24 | 0 | 1 | 0 | 0 | 2 | 6 | 4 | 2 | 5 | 18 | 2 | 54 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 7 | 0 | 4 | 0 | 0 | 42 | 27 | 4 | 0 | 0 | 29 | 19 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 0
2026-02-06 | W11 | 17 | 0 | 0 | 18 | 0 | 22 | 0 | 0 | 19 | 18 | 13 | 2 | 1 | 33 | 0 | 8 | 3 | 3 | 32 | 18 | 334 | 84 | 0 | 230 | 115 | 0 | 0 | 0 | 10 | 4 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 21 | 40 | 22 | 0 | 60 | 26 | 22 | 0 | 0 | 21 | 0 | 24 | 4 | 0 | 45 | 7 | 12 | 1 | 0 | 10 | 8 | 15 | 2 | 0 | 41 | 10 | 49 | 0 | 0 | 63 | 0 | 24 | 0 | 0 | 24 | 24 | 95 | 1 | 0 | 66 | 0 | 111 | 3 | 30 | 3 | 5 | 31 | 5 | 11 | 0 | 1 | 0 | 2 | 4 | 6 | 34 | 4 | 0 | 0 | 8 | 13 | 1 | 0 | 2 | 12 | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 6 | 2 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 3 | 4 | 0 | 2 | 2 | 0 | 4 | 6 | 2 | 2 | 0 | 4 | 0 | 8 | 0 | 2 | 4 | 18 | 9 | 0 | 5 | 22 | 4 | 11 | 0 | 1 | 20 | 4 | 0 | 0 | 0 | 12 | 1 | 0 | 0 | 0 | 17 | 0 | 7 | 3 | 1 | 56 | 0 | 10 | 0 | 9 | 1 | 1 | 11 | 0 | 20 | 30 | 10 | 7 | 4 | 1 | 59 | 17 | 0 | 0 | 1 | 9 | 0 | 4 | 0 | 4 | 29 | 0 | 0 | 2 | 13 | 8 | 4 | 3 | 0 | 1 | 11 | 0 | 0 | 0 | 2 | 45 | 15 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 4 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 2 | 5 | 0 | 4 | 0 | 9 | 38 | 51 | 26 | 0 | 2 | 13 | 0 | 10 | 0 | 4 | 0 | 0 | 23 | 0 | 0 | 7 | 23 | 17 | 0 | 0 | 8 | 11 | 6 | 1 | 0 | 17 | 0 | 20 | 0 | 0 | 20 | 4 | 13 | 0 | 0 | 23 | 7 | 20 | 0 | 0 | 21 | 0 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 2 | 0 | 19 | 0 | 0 | 9 | 20 | 10 | 0 | 0 | 10 | 0 | 14 | 0 | 0 | 14 | 14 | 30 | 0 | 0 | 3 | 33 | 30 | 0 | 22 | 24 | 58 | 48 | 0 | 0 | 37 | 0 | 16 | 0 | 0 | 16 | 3 | 6 | 0 | 0 | 24 | 0 | 1 | 0 | 0 | 2 | 6 | 4 | 2 | 5 | 18 | 2 | 54 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 7 | 0 | 4 | 0 | 0 | 42 | 27 | 4 | 0 | 0 | 29 | 19 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 0
2026-02-07 | W12 | 17 | 0 | 0 | 18 | 0 | 22 | 0 | 0 | 19 | 18 | 13 | 2 | 1 | 33 | 0 | 8 | 3 | 3 | 32 | 18 | 334 | 84 | 0 | 230 | 115 | 0 | 0 | 0 | 10 | 4 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 21 | 40 | 22 | 0 | 60 | 26 | 22 | 0 | 0 | 21 | 0 | 24 | 4 | 0 | 45 | 7 | 12 | 1 | 0 | 10 | 8 | 15 | 2 | 0 | 41 | 10 | 49 | 0 | 0 | 63 | 0 | 24 | 0 | 0 | 24 | 24 | 95 | 1 | 0 | 66 | 0 | 111 | 3 | 30 | 3 | 5 | 31 | 5 | 11 | 0 | 1 | 0 | 2 | 4 | 6 | 34 | 4 | 0 | 0 | 8 | 13 | 1 | 0 | 2 | 12 | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 6 | 2 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 3 | 4 | 0 | 2 | 2 | 0 | 4 | 6 | 2 | 2 | 0 | 4 | 0 | 8 | 0 | 2 | 4 | 18 | 9 | 0 | 5 | 22 | 4 | 11 | 0 | 1 | 20 | 4 | 0 | 0 | 0 | 12 | 1 | 0 | 0 | 0 | 17 | 0 | 7 | 3 | 1 | 56 | 0 | 10 | 0 | 9 | 1 | 1 | 11 | 0 | 20 | 30 | 10 | 7 | 4 | 1 | 59 | 17 | 0 | 0 | 1 | 9 | 0 | 4 | 0 | 4 | 29 | 0 | 0 | 2 | 13 | 8 | 4 | 3 | 0 | 1 | 11 | 0 | 0 | 0 | 2 | 45 | 15 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 4 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 2 | 5 | 0 | 4 | 0 | 9 | 38 | 51 | 26 | 0 | 2 | 13 | 0 | 10 | 0 | 4 | 0 | 0 | 23 | 0 | 0 | 7 | 23 | 17 | 0 | 0 | 8 | 11 | 6 | 1 | 0 | 17 | 0 | 20 | 0 | 0 | 20 | 4 | 13 | 0 | 0 | 23 | 7 | 20 | 0 | 0 | 21 | 0 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 2 | 0 | 19 | 0 | 0 | 9 | 20 | 10 | 0 | 0 | 10 | 0 | 14 | 0 | 0 | 14 | 14 | 30 | 0 | 0 | 3 | 33 | 30 | 0 | 22 | 24 | 58 | 48 | 0 | 0 | 37 | 0 | 16 | 0 | 0 | 16 | 3 | 6 | 0 | 0 | 24 | 0 | 1 | 0 | 0 | 2 | 6 | 4 | 2 | 5 | 18 | 2 | 54 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 7 | 0 | 4 | 0 | 0 | 42 | 27 | 4 | 0 | 0 | 29 | 19 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 0
2026-02-09 | W12 | 17 | 0 | 0 | 18 | 0 | 22 | 0 | 0 | 19 | 18 | 13 | 2 | 1 | 33 | 0 | 8 | 3 | 3 | 32 | 18 | 334 | 84 | 0 | 230 | 115 | 0 | 0 | 0 | 10 | 4 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 21 | 40 | 22 | 0 | 60 | 26 | 22 | 0 | 0 | 21 | 0 | 24 | 4 | 0 | 45 | 7 | 12 | 1 | 0 | 10 | 8 | 15 | 2 | 0 | 41 | 10 | 49 | 0 | 0 | 63 | 0 | 24 | 0 | 0 | 24 | 24 | 95 | 1 | 0 | 66 | 0 | 111 | 3 | 30 | 3 | 5 | 31 | 5 | 11 | 0 | 1 | 0 | 2 | 4 | 6 | 34 | 4 | 0 | 0 | 8 | 13 | 1 | 0 | 2 | 12 | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 6 | 2 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 3 | 4 | 0 | 2 | 2 | 0 | 4 | 6 | 2 | 2 | 0 | 4 | 0 | 8 | 0 | 2 | 4 | 18 | 9 | 0 | 5 | 22 | 4 | 11 | 0 | 1 | 20 | 4 | 0 | 0 | 0 | 12 | 1 | 0 | 0 | 0 | 17 | 0 | 7 | 3 | 1 | 56 | 0 | 10 | 0 | 9 | 1 | 1 | 11 | 0 | 20 | 30 | 10 | 7 | 4 | 1 | 59 | 17 | 0 | 0 | 1 | 9 | 0 | 4 | 0 | 4 | 29 | 0 | 0 | 2 | 13 | 8 | 4 | 3 | 0 | 1 | 11 | 0 | 0 | 0 | 2 | 45 | 15 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 4 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 2 | 5 | 0 | 4 | 0 | 9 | 38 | 51 | 26 | 0 | 2 | 13 | 0 | 10 | 0 | 4 | 0 | 0 | 23 | 0 | 0 | 7 | 23 | 17 | 0 | 0 | 8 | 11 | 6 | 1 | 0 | 17 | 0 | 20 | 0 | 0 | 20 | 4 | 13 | 0 | 0 | 23 | 7 | 20 | 0 | 0 | 21 | 0 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 2 | 0 | 19 | 0 | 0 | 9 | 20 | 10 | 0 | 0 | 10 | 0 | 14 | 0 | 0 | 14 | 14 | 30 | 0 | 0 | 3 | 33 | 30 | 0 | 22 | 24 | 58 | 48 | 0 | 0 | 37 | 0 | 16 | 0 | 0 | 16 | 3 | 6 | 0 | 0 | 24 | 0 | 1 | 0 | 0 | 2 | 6 | 4 | 2 | 5 | 18 | 2 | 54 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 7 | 0 | 4 | 0 | 0 | 42 | 27 | 4 | 0 | 0 | 29 | 19 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 0
2026-02-10 | W12 | 17 | 0 | 0 | 18 | 0 | 22 | 0 | 0 | 19 | 18 | 13 | 2 | 1 | 33 | 0 | 8 | 3 | 3 | 32 | 18 | 334 | 84 | 0 | 230 | 115 | 0 | 0 | 0 | 10 | 4 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 21 | 40 | 22 | 0 | 60 | 26 | 22 | 0 | 0 | 21 | 0 | 24 | 4 | 0 | 45 | 7 | 12 | 1 | 0 | 10 | 8 | 15 | 2 | 0 | 41 | 10 | 49 | 0 | 0 | 63 | 0 | 24 | 0 | 0 | 24 | 24 | 95 | 1 | 0 | 66 | 0 | 111 | 3 | 30 | 3 | 5 | 31 | 5 | 11 | 0 | 1 | 0 | 2 | 4 | 6 | 34 | 4 | 0 | 0 | 8 | 13 | 1 | 0 | 2 | 12 | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 6 | 2 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 3 | 4 | 0 | 2 | 2 | 0 | 4 | 6 | 2 | 2 | 0 | 4 | 0 | 8 | 0 | 2 | 4 | 18 | 9 | 0 | 5 | 22 | 4 | 11 | 0 | 1 | 20 | 4 | 0 | 0 | 0 | 12 | 1 | 0 | 0 | 0 | 17 | 0 | 7 | 3 | 1 | 56 | 0 | 10 | 0 | 9 | 1 | 1 | 11 | 0 | 20 | 30 | 10 | 7 | 4 | 1 | 59 | 17 | 0 | 0 | 1 | 9 | 0 | 4 | 0 | 4 | 29 | 0 | 0 | 2 | 13 | 8 | 4 | 3 | 0 | 1 | 11 | 0 | 0 | 0 | 2 | 45 | 15 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 4 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 2 | 5 | 0 | 4 | 0 | 9 | 38 | 51 | 26 | 0 | 2 | 13 | 0 | 10 | 0 | 4 | 0 | 0 | 23 | 0 | 0 | 7 | 23 | 17 | 0 | 0 | 8 | 11 | 6 | 1 | 0 | 17 | 0 | 20 | 0 | 0 | 20 | 4 | 13 | 0 | 0 | 23 | 7 | 20 | 0 | 0 | 21 | 0 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 2 | 0 | 19 | 0 | 0 | 9 | 20 | 10 | 0 | 0 | 10 | 0 | 14 | 0 | 0 | 14 | 14 | 30 | 0 | 0 | 3 | 33 | 30 | 0 | 22 | 24 | 58 | 48 | 0 | 0 | 37 | 0 | 16 | 0 | 0 | 16 | 3 | 6 | 0 | 0 | 24 | 0 | 1 | 0 | 0 | 2 | 6 | 4 | 2 | 5 | 18 | 2 | 54 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 7 | 0 | 4 | 0 | 0 | 42 | 27 | 4 | 0 | 0 | 29 | 19 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 0
2026-02-11 | W12 | 17 | 0 | 0 | 18 | 0 | 22 | 0 | 0 | 19 | 18 | 13 | 2 | 1 | 33 | 0 | 8 | 3 | 3 | 32 | 18 | 334 | 84 | 0 | 230 | 115 | 0 | 0 | 0 | 10 | 4 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 21 | 40 | 22 | 0 | 60 | 26 | 22 | 0 | 0 | 21 | 0 | 24 | 4 | 0 | 45 | 7 | 12 | 1 | 0 | 10 | 8 | 15 | 2 | 0 | 41 | 10 | 49 | 0 | 0 | 63 | 0 | 24 | 0 | 0 | 24 | 24 | 95 | 1 | 0 | 66 | 0 | 111 | 3 | 30 | 3 | 5 | 31 | 5 | 11 | 0 | 1 | 0 | 2 | 4 | 6 | 34 | 4 | 0 | 0 | 8 | 13 | 1 | 0 | 2 | 12 | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 6 | 2 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 3 | 4 | 0 | 2 | 2 | 0 | 4 | 6 | 2 | 2 | 0 | 4 | 0 | 8 | 0 | 2 | 4 | 18 | 9 | 0 | 5 | 22 | 4 | 11 | 0 | 1 | 20 | 4 | 0 | 0 | 0 | 12 | 1 | 0 | 0 | 0 | 17 | 0 | 7 | 3 | 1 | 56 | 0 | 10 | 0 | 9 | 1 | 1 | 11 | 0 | 20 | 30 | 10 | 7 | 4 | 1 | 59 | 17 | 0 | 0 | 1 | 9 | 0 | 4 | 0 | 4 | 29 | 0 | 0 | 2 | 13 | 8 | 4 | 3 | 0 | 1 | 11 | 0 | 0 | 0 | 2 | 45 | 15 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 4 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 2 | 5 | 0 | 4 | 0 | 9 | 38 | 51 | 26 | 0 | 2 | 13 | 0 | 10 | 0 | 4 | 0 | 0 | 23 | 0 | 0 | 7 | 23 | 17 | 0 | 0 | 8 | 11 | 6 | 1 | 0 | 17 | 0 | 20 | 0 | 0 | 20 | 4 | 13 | 0 | 0 | 23 | 7 | 20 | 0 | 0 | 21 | 0 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 2 | 0 | 19 | 0 | 0 | 9 | 20 | 10 | 0 | 0 | 10 | 0 | 14 | 0 | 0 | 14 | 14 | 30 | 0 | 0 | 3 | 33 | 30 | 0 | 22 | 24 | 58 | 48 | 0 | 0 | 37 | 0 | 16 | 0 | 0 | 16 | 3 | 6 | 0 | 0 | 24 | 0 | 1 | 0 | 0 | 2 | 6 | 4 | 2 | 5 | 18 | 2 | 54 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 7 | 0 | 4 | 0 | 0 | 42 | 27 | 4 | 0 | 0 | 29 | 19 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 0
2026-02-12 | W12 | 17 | 0 | 0 | 18 | 0 | 22 | 0 | 0 | 19 | 18 | 13 | 2 | 1 | 33 | 0 | 8 | 3 | 3 | 32 | 18 | 334 | 84 | 0 | 230 | 115 | 0 | 0 | 0 | 10 | 4 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 21 | 40 | 22 | 0 | 60 | 26 | 22 | 0 | 0 | 21 | 0 | 24 | 4 | 0 | 45 | 7 | 12 | 1 | 0 | 10 | 8 | 15 | 2 | 0 | 41 | 10 | 49 | 0 | 0 | 63 | 0 | 24 | 0 | 0 | 24 | 24 | 95 | 1 | 0 | 66 | 0 | 111 | 3 | 30 | 3 | 5 | 31 | 5 | 11 | 0 | 1 | 0 | 2 | 4 | 6 | 34 | 4 | 0 | 0 | 8 | 13 | 1 | 0 | 2 | 12 | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 6 | 2 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 3 | 4 | 0 | 2 | 2 | 0 | 4 | 6 | 2 | 2 | 0 | 4 | 0 | 8 | 0 | 2 | 4 | 18 | 9 | 0 | 5 | 22 | 4 | 11 | 0 | 1 | 20 | 4 | 0 | 0 | 0 | 12 | 1 | 0 | 0 | 0 | 17 | 0 | 7 | 3 | 1 | 56 | 0 | 10 | 0 | 9 | 1 | 1 | 11 | 0 | 20 | 30 | 10 | 7 | 4 | 1 | 59 | 17 | 0 | 0 | 1 | 9 | 0 | 4 | 0 | 4 | 29 | 0 | 0 | 2 | 13 | 8 | 4 | 3 | 0 | 1 | 11 | 0 | 0 | 0 | 2 | 45 | 15 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 4 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 2 | 5 | 0 | 4 | 0 | 9 | 38 | 51 | 26 | 0 | 2 | 13 | 0 | 10 | 0 | 4 | 0 | 0 | 23 | 0 | 0 | 7 | 23 | 17 | 0 | 0 | 8 | 11 | 6 | 1 | 0 | 17 | 0 | 20 | 0 | 0 | 20 | 4 | 13 | 0 | 0 | 23 | 7 | 20 | 0 | 0 | 21 | 0 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 2 | 0 | 19 | 0 | 0 | 9 | 20 | 10 | 0 | 0 | 10 | 0 | 14 | 0 | 0 | 14 | 14 | 30 | 0 | 0 | 3 | 33 | 30 | 0 | 22 | 24 | 58 | 48 | 0 | 0 | 37 | 0 | 16 | 0 | 0 | 16 | 3 | 6 | 0 | 0 | 24 | 0 | 1 | 0 | 0 | 2 | 6 | 4 | 2 | 5 | 18 | 2 | 54 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 7 | 0 | 4 | 0 | 0 | 42 | 27 | 4 | 0 | 0 | 29 | 19 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 0
2026-02-13 | W12 | 17 | 0 | 0 | 18 | 0 | 22 | 0 | 0 | 19 | 18 | 13 | 2 | 1 | 33 | 0 | 8 | 3 | 3 | 32 | 18 | 334 | 84 | 0 | 230 | 115 | 0 | 0 | 0 | 10 | 4 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 21 | 40 | 22 | 0 | 60 | 26 | 22 | 0 | 0 | 21 | 0 | 24 | 4 | 0 | 45 | 7 | 12 | 1 | 0 | 10 | 8 | 15 | 2 | 0 | 41 | 10 | 49 | 0 | 0 | 63 | 0 | 24 | 0 | 0 | 24 | 24 | 95 | 1 | 0 | 66 | 0 | 111 | 3 | 30 | 3 | 5 | 31 | 5 | 11 | 0 | 1 | 0 | 2 | 4 | 6 | 34 | 4 | 0 | 0 | 8 | 13 | 1 | 0 | 2 | 12 | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 6 | 2 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 3 | 4 | 0 | 2 | 2 | 0 | 4 | 6 | 2 | 2 | 0 | 4 | 0 | 8 | 0 | 2 | 4 | 18 | 9 | 0 | 5 | 22 | 4 | 11 | 0 | 1 | 20 | 4 | 0 | 0 | 0 | 12 | 1 | 0 | 0 | 0 | 17 | 0 | 7 | 3 | 1 | 56 | 0 | 10 | 0 | 9 | 1 | 1 | 11 | 0 | 20 | 30 | 10 | 7 | 4 | 1 | 59 | 17 | 0 | 0 | 1 | 9 | 0 | 4 | 0 | 4 | 29 | 0 | 0 | 2 | 13 | 8 | 4 | 3 | 0 | 1 | 11 | 0 | 0 | 0 | 2 | 45 | 15 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 4 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 2 | 5 | 0 | 4 | 0 | 9 | 38 | 51 | 26 | 0 | 2 | 13 | 0 | 10 | 0 | 4 | 0 | 0 | 23 | 0 | 0 | 7 | 23 | 17 | 0 | 0 | 8 | 11 | 6 | 1 | 0 | 17 | 0 | 20 | 0 | 0 | 20 | 4 | 13 | 0 | 0 | 23 | 7 | 20 | 0 | 0 | 21 | 0 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 2 | 0 | 19 | 0 | 0 | 9 | 20 | 10 | 0 | 0 | 10 | 0 | 14 | 0 | 0 | 14 | 14 | 30 | 0 | 0 | 3 | 33 | 30 | 0 | 22 | 24 | 58 | 48 | 0 | 0 | 37 | 0 | 16 | 0 | 0 | 16 | 3 | 6 | 0 | 0 | 24 | 0 | 1 | 0 | 0 | 2 | 6 | 4 | 2 | 5 | 18 | 2 | 54 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 7 | 0 | 4 | 0 | 0 | 42 | 27 | 4 | 0 | 0 | 29 | 19 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 0
2026-02-14 | W13 | 17 | 0 | 0 | 18 | 0 | 22 | 0 | 0 | 19 | 18 | 13 | 2 | 1 | 33 | 0 | 8 | 3 | 3 | 32 | 18 | 334 | 84 | 0 | 230 | 115 | 0 | 0 | 0 | 10 | 4 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 21 | 40 | 22 | 0 | 60 | 26 | 22 | 0 | 0 | 21 | 0 | 24 | 4 | 0 | 45 | 7 | 12 | 1 | 0 | 10 | 8 | 15 | 2 | 0 | 41 | 10 | 49 | 0 | 0 | 63 | 0 | 24 | 0 | 0 | 24 | 24 | 95 | 1 | 0 | 66 | 0 | 111 | 3 | 30 | 3 | 5 | 31 | 5 | 11 | 0 | 1 | 0 | 2 | 4 | 6 | 34 | 4 | 0 | 0 | 8 | 13 | 1 | 0 | 2 | 12 | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 6 | 2 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 3 | 4 | 0 | 2 | 2 | 0 | 4 | 6 | 2 | 2 | 0 | 4 | 0 | 8 | 0 | 2 | 4 | 18 | 9 | 0 | 5 | 22 | 4 | 11 | 0 | 1 | 20 | 4 | 0 | 0 | 0 | 12 | 1 | 0 | 0 | 0 | 17 | 0 | 7 | 3 | 1 | 56 | 0 | 10 | 0 | 9 | 1 | 1 | 11 | 0 | 20 | 30 | 10 | 7 | 4 | 1 | 59 | 17 | 0 | 0 | 1 | 9 | 0 | 4 | 0 | 4 | 29 | 0 | 0 | 2 | 13 | 8 | 4 | 3 | 0 | 1 | 11 | 0 | 0 | 0 | 2 | 45 | 15 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 4 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 2 | 5 | 0 | 4 | 0 | 9 | 38 | 51 | 26 | 0 | 2 | 13 | 0 | 10 | 0 | 4 | 0 | 0 | 23 | 0 | 0 | 7 | 23 | 17 | 0 | 0 | 8 | 11 | 6 | 1 | 0 | 17 | 0 | 20 | 0 | 0 | 20 | 4 | 13 | 0 | 0 | 23 | 7 | 20 | 0 | 0 | 21 | 0 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 2 | 0 | 19 | 0 | 0 | 9 | 20 | 10 | 0 | 0 | 10 | 0 | 14 | 0 | 0 | 14 | 14 | 30 | 0 | 0 | 3 | 33 | 30 | 0 | 22 | 24 | 58 | 48 | 0 | 0 | 37 | 0 | 16 | 0 | 0 | 16 | 3 | 6 | 0 | 0 | 24 | 0 | 1 | 0 | 0 | 2 | 6 | 4 | 2 | 5 | 18 | 2 | 54 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 7 | 0 | 4 | 0 | 0 | 42 | 27 | 4 | 0 | 0 | 29 | 19 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 0
2026-02-16 | W13 | 17 | 0 | 0 | 18 | 0 | 22 | 0 | 0 | 19 | 18 | 13 | 2 | 1 | 33 | 0 | 8 | 3 | 3 | 32 | 18 | 334 | 84 | 0 | 230 | 115 | 0 | 0 | 0 | 10 | 4 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 21 | 40 | 22 | 0 | 60 | 26 | 22 | 0 | 0 | 21 | 0 | 24 | 4 | 0 | 45 | 7 | 12 | 1 | 0 | 10 | 8 | 15 | 2 | 0 | 41 | 10 | 49 | 0 | 0 | 63 | 0 | 24 | 0 | 0 | 24 | 24 | 95 | 1 | 0 | 66 | 0 | 111 | 3 | 30 | 3 | 5 | 31 | 5 | 11 | 0 | 1 | 0 | 2 | 4 | 6 | 34 | 4 | 0 | 0 | 8 | 13 | 1 | 0 | 2 | 12 | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 6 | 2 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 3 | 4 | 0 | 2 | 2 | 0 | 4 | 6 | 2 | 2 | 0 | 4 | 0 | 8 | 0 | 2 | 4 | 18 | 9 | 0 | 5 | 22 | 4 | 11 | 0 | 1 | 20 | 4 | 0 | 0 | 0 | 12 | 1 | 0 | 0 | 0 | 17 | 0 | 7 | 3 | 1 | 56 | 0 | 10 | 0 | 9 | 1 | 1 | 11 | 0 | 20 | 30 | 10 | 7 | 4 | 1 | 59 | 17 | 0 | 0 | 1 | 9 | 0 | 4 | 0 | 4 | 29 | 0 | 0 | 2 | 13 | 8 | 4 | 3 | 0 | 1 | 11 | 0 | 0 | 0 | 2 | 45 | 15 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 4 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 2 | 5 | 0 | 4 | 0 | 9 | 38 | 51 | 26 | 0 | 2 | 13 | 0 | 10 | 0 | 4 | 0 | 0 | 23 | 0 | 0 | 7 | 23 | 17 | 0 | 0 | 8 | 11 | 6 | 1 | 0 | 17 | 0 | 20 | 0 | 0 | 20 | 4 | 13 | 0 | 0 | 23 | 7 | 20 | 0 | 0 | 21 | 0 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 2 | 0 | 19 | 0 | 0 | 9 | 20 | 10 | 0 | 0 | 10 | 0 | 14 | 0 | 0 | 14 | 14 | 30 | 0 | 0 | 3 | 33 | 30 | 0 | 22 | 24 | 58 | 48 | 0 | 0 | 37 | 0 | 16 | 0 | 0 | 16 | 3 | 6 | 0 | 0 | 24 | 0 | 1 | 0 | 0 | 2 | 6 | 4 | 2 | 5 | 18 | 2 | 54 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 7 | 0 | 4 | 0 | 0 | 42 | 27 | 4 | 0 | 0 | 29 | 19 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 0
2026-02-17 | W13 | 17 | 0 | 0 | 18 | 0 | 22 | 0 | 0 | 19 | 18 | 13 | 2 | 1 | 33 | 0 | 8 | 3 | 3 | 32 | 18 | 334 | 84 | 0 | 230 | 115 | 0 | 0 | 0 | 10 | 4 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 21 | 40 | 22 | 0 | 60 | 26 | 22 | 0 | 0 | 21 | 0 | 24 | 4 | 0 | 45 | 7 | 12 | 1 | 0 | 10 | 8 | 15 | 2 | 0 | 41 | 10 | 49 | 0 | 0 | 63 | 0 | 24 | 0 | 0 | 24 | 24 | 95 | 1 | 0 | 66 | 0 | 111 | 3 | 30 | 3 | 5 | 31 | 5 | 11 | 0 | 1 | 0 | 2 | 4 | 6 | 34 | 4 | 0 | 0 | 8 | 13 | 1 | 0 | 2 | 12 | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 6 | 2 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 3 | 4 | 0 | 2 | 2 | 0 | 4 | 6 | 2 | 2 | 0 | 4 | 0 | 8 | 0 | 2 | 4 | 18 | 9 | 0 | 5 | 22 | 4 | 11 | 0 | 1 | 20 | 4 | 0 | 0 | 0 | 12 | 1 | 0 | 0 | 0 | 17 | 0 | 7 | 3 | 1 | 56 | 0 | 10 | 0 | 9 | 1 | 1 | 11 | 0 | 20 | 30 | 10 | 7 | 4 | 1 | 59 | 17 | 0 | 0 | 1 | 9 | 0 | 4 | 0 | 4 | 29 | 0 | 0 | 2 | 13 | 8 | 4 | 3 | 0 | 1 | 11 | 0 | 0 | 0 | 2 | 45 | 15 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 4 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 2 | 5 | 0 | 4 | 0 | 9 | 38 | 51 | 26 | 0 | 2 | 13 | 0 | 10 | 0 | 4 | 0 | 0 | 23 | 0 | 0 | 7 | 23 | 17 | 0 | 0 | 8 | 11 | 6 | 1 | 0 | 17 | 0 | 20 | 0 | 0 | 20 | 4 | 13 | 0 | 0 | 23 | 7 | 20 | 0 | 0 | 21 | 0 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 2 | 0 | 19 | 0 | 0 | 9 | 20 | 10 | 0 | 0 | 10 | 0 | 14 | 0 | 0 | 14 | 14 | 30 | 0 | 0 | 3 | 33 | 30 | 0 | 22 | 24 | 58 | 48 | 0 | 0 | 37 | 0 | 16 | 0 | 0 | 16 | 3 | 6 | 0 | 0 | 24 | 0 | 1 | 0 | 0 | 2 | 6 | 4 | 2 | 5 | 18 | 2 | 54 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 7 | 0 | 4 | 0 | 0 | 42 | 27 | 4 | 0 | 0 | 29 | 19 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 0
2026-02-18 | W13 | 17 | 0 | 0 | 18 | 0 | 22 | 0 | 0 | 19 | 18 | 13 | 2 | 1 | 33 | 0 | 8 | 3 | 3 | 32 | 18 | 334 | 84 | 0 | 230 | 115 | 0 | 0 | 0 | 10 | 4 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 21 | 40 | 22 | 0 | 60 | 26 | 22 | 0 | 0 | 21 | 0 | 24 | 4 | 0 | 45 | 7 | 12 | 1 | 0 | 10 | 8 | 15 | 2 | 0 | 41 | 10 | 49 | 0 | 0 | 63 | 0 | 24 | 0 | 0 | 24 | 24 | 95 | 1 | 0 | 66 | 0 | 111 | 3 | 30 | 3 | 5 | 31 | 5 | 11 | 0 | 1 | 0 | 2 | 4 | 6 | 34 | 4 | 0 | 0 | 8 | 13 | 1 | 0 | 2 | 12 | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 6 | 2 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 3 | 4 | 0 | 2 | 2 | 0 | 4 | 6 | 2 | 2 | 0 | 4 | 0 | 8 | 0 | 2 | 4 | 18 | 9 | 0 | 5 | 22 | 4 | 11 | 0 | 1 | 20 | 4 | 0 | 0 | 0 | 12 | 1 | 0 | 0 | 0 | 17 | 0 | 7 | 3 | 1 | 56 | 0 | 10 | 0 | 9 | 1 | 1 | 11 | 0 | 20 | 30 | 10 | 7 | 4 | 1 | 59 | 17 | 0 | 0 | 1 | 9 | 0 | 4 | 0 | 4 | 29 | 0 | 0 | 2 | 13 | 8 | 4 | 3 | 0 | 1 | 11 | 0 | 0 | 0 | 2 | 45 | 15 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 4 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 2 | 5 | 0 | 4 | 0 | 9 | 38 | 51 | 26 | 0 | 2 | 13 | 0 | 10 | 0 | 4 | 0 | 0 | 23 | 0 | 0 | 7 | 23 | 17 | 0 | 0 | 8 | 11 | 6 | 1 | 0 | 17 | 0 | 20 | 0 | 0 | 20 | 4 | 13 | 0 | 0 | 23 | 7 | 20 | 0 | 0 | 21 | 0 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 2 | 0 | 19 | 0 | 0 | 9 | 20 | 10 | 0 | 0 | 10 | 0 | 14 | 0 | 0 | 14 | 14 | 30 | 0 | 0 | 3 | 33 | 30 | 0 | 22 | 24 | 58 | 48 | 0 | 0 | 37 | 0 | 16 | 0 | 0 | 16 | 3 | 6 | 0 | 0 | 24 | 0 | 1 | 0 | 0 | 2 | 6 | 4 | 2 | 5 | 18 | 2 | 54 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 7 | 0 | 4 | 0 | 0 | 42 | 27 | 4 | 0 | 0 | 29 | 19 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 0
2026-02-19 | W13 | 17 | 0 | 0 | 18 | 0 | 22 | 0 | 0 | 19 | 18 | 13 | 2 | 1 | 33 | 0 | 8 | 3 | 3 | 32 | 18 | 334 | 84 | 0 | 230 | 115 | 0 | 0 | 0 | 10 | 4 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 21 | 40 | 22 | 0 | 60 | 26 | 22 | 0 | 0 | 21 | 0 | 24 | 4 | 0 | 45 | 7 | 12 | 1 | 0 | 10 | 8 | 15 | 2 | 0 | 41 | 10 | 49 | 0 | 0 | 63 | 0 | 24 | 0 | 0 | 24 | 24 | 95 | 1 | 0 | 66 | 0 | 111 | 3 | 30 | 3 | 5 | 31 | 5 | 11 | 0 | 1 | 0 | 2 | 4 | 6 | 34 | 4 | 0 | 0 | 8 | 13 | 1 | 0 | 2 | 12 | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 6 | 2 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 3 | 4 | 0 | 2 | 2 | 0 | 4 | 6 | 2 | 2 | 0 | 4 | 0 | 8 | 0 | 2 | 4 | 18 | 9 | 0 | 5 | 22 | 4 | 11 | 0 | 1 | 20 | 4 | 0 | 0 | 0 | 12 | 1 | 0 | 0 | 0 | 17 | 0 | 7 | 3 | 1 | 56 | 0 | 10 | 0 | 9 | 1 | 1 | 11 | 0 | 20 | 30 | 10 | 7 | 4 | 1 | 59 | 17 | 0 | 0 | 1 | 9 | 0 | 4 | 0 | 4 | 29 | 0 | 0 | 2 | 13 | 8 | 4 | 3 | 0 | 1 | 11 | 0 | 0 | 0 | 2 | 45 | 15 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 4 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 2 | 5 | 0 | 4 | 0 | 9 | 38 | 51 | 26 | 0 | 2 | 13 | 0 | 10 | 0 | 4 | 0 | 0 | 23 | 0 | 0 | 7 | 23 | 17 | 0 | 0 | 8 | 11 | 6 | 1 | 0 | 17 | 0 | 20 | 0 | 0 | 20 | 4 | 13 | 0 | 0 | 23 | 7 | 20 | 0 | 0 | 21 | 0 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 2 | 0 | 19 | 0 | 0 | 9 | 20 | 10 | 0 | 0 | 10 | 0 | 14 | 0 | 0 | 14 | 14 | 30 | 0 | 0 | 3 | 33 | 30 | 0 | 22 | 24 | 58 | 48 | 0 | 0 | 37 | 0 | 16 | 0 | 0 | 16 | 3 | 6 | 0 | 0 | 24 | 0 | 1 | 0 | 0 | 2 | 6 | 4 | 2 | 5 | 18 | 2 | 54 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 7 | 0 | 4 | 0 | 0 | 42 | 27 | 4 | 0 | 0 | 29 | 19 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 0
2026-02-20 | W13 | 17 | 0 | 0 | 18 | 0 | 22 | 0 | 0 | 19 | 18 | 13 | 2 | 1 | 33 | 0 | 8 | 3 | 3 | 32 | 18 | 334 | 84 | 0 | 230 | 115 | 0 | 0 | 0 | 10 | 4 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 21 | 40 | 22 | 0 | 60 | 26 | 22 | 0 | 0 | 21 | 0 | 24 | 4 | 0 | 45 | 7 | 12 | 1 | 0 | 10 | 8 | 15 | 2 | 0 | 41 | 10 | 49 | 0 | 0 | 63 | 0 | 24 | 0 | 0 | 24 | 24 | 95 | 1 | 0 | 66 | 0 | 111 | 3 | 30 | 3 | 5 | 31 | 5 | 11 | 0 | 1 | 0 | 2 | 4 | 6 | 34 | 4 | 0 | 0 | 8 | 13 | 1 | 0 | 2 | 12 | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 6 | 2 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 3 | 4 | 0 | 2 | 2 | 0 | 4 | 6 | 2 | 2 | 0 | 4 | 0 | 8 | 0 | 2 | 4 | 18 | 9 | 0 | 5 | 22 | 4 | 11 | 0 | 1 | 20 | 4 | 0 | 0 | 0 | 12 | 1 | 0 | 0 | 0 | 17 | 0 | 7 | 3 | 1 | 56 | 0 | 10 | 0 | 9 | 1 | 1 | 11 | 0 | 20 | 30 | 10 | 7 | 4 | 1 | 59 | 17 | 0 | 0 | 1 | 9 | 0 | 4 | 0 | 4 | 29 | 0 | 0 | 2 | 13 | 8 | 4 | 3 | 0 | 1 | 11 | 0 | 0 | 0 | 2 | 45 | 15 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 4 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 2 | 5 | 0 | 4 | 0 | 9 | 38 | 51 | 26 | 0 | 2 | 13 | 0 | 10 | 0 | 4 | 0 | 0 | 23 | 0 | 0 | 7 | 23 | 17 | 0 | 0 | 8 | 11 | 6 | 1 | 0 | 17 | 0 | 20 | 0 | 0 | 20 | 4 | 13 | 0 | 0 | 23 | 7 | 20 | 0 | 0 | 21 | 0 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 2 | 0 | 19 | 0 | 0 | 9 | 20 | 10 | 0 | 0 | 10 | 0 | 14 | 0 | 0 | 14 | 14 | 30 | 0 | 0 | 3 | 33 | 30 | 0 | 22 | 24 | 58 | 48 | 0 | 0 | 37 | 0 | 16 | 0 | 0 | 16 | 3 | 6 | 0 | 0 | 24 | 0 | 1 | 0 | 0 | 2 | 6 | 4 | 2 | 5 | 18 | 2 | 54 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 7 | 0 | 4 | 0 | 0 | 42 | 27 | 4 | 0 | 0 | 29 | 19 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 0
2026-02-21 | W14 | 17 | 0 | 0 | 18 | 0 | 22 | 0 | 0 | 19 | 18 | 13 | 2 | 1 | 33 | 0 | 8 | 3 | 3 | 32 | 18 | 334 | 84 | 0 | 230 | 115 | 0 | 0 | 0 | 10 | 4 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 21 | 40 | 22 | 0 | 60 | 26 | 22 | 0 | 0 | 21 | 0 | 24 | 4 | 0 | 45 | 7 | 12 | 1 | 0 | 10 | 8 | 15 | 2 | 0 | 41 | 10 | 49 | 0 | 0 | 63 | 0 | 24 | 0 | 0 | 24 | 24 | 95 | 1 | 0 | 66 | 0 | 111 | 3 | 30 | 3 | 5 | 31 | 5 | 11 | 0 | 1 | 0 | 2 | 4 | 6 | 34 | 4 | 0 | 0 | 8 | 13 | 1 | 0 | 2 | 12 | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 6 | 2 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 3 | 4 | 0 | 2 | 2 | 0 | 4 | 6 | 2 | 2 | 0 | 4 | 0 | 8 | 0 | 2 | 4 | 18 | 9 | 0 | 5 | 22 | 4 | 11 | 0 | 1 | 20 | 4 | 0 | 0 | 0 | 12 | 1 | 0 | 0 | 0 | 17 | 0 | 7 | 3 | 1 | 56 | 0 | 10 | 0 | 9 | 1 | 1 | 11 | 0 | 20 | 30 | 10 | 7 | 4 | 1 | 59 | 17 | 0 | 0 | 1 | 9 | 0 | 4 | 0 | 4 | 29 | 0 | 0 | 2 | 13 | 8 | 4 | 3 | 0 | 1 | 11 | 0 | 0 | 0 | 2 | 45 | 15 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 4 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 2 | 5 | 0 | 4 | 0 | 9 | 38 | 51 | 26 | 0 | 2 | 13 | 0 | 10 | 0 | 4 | 0 | 0 | 23 | 0 | 0 | 7 | 23 | 17 | 0 | 0 | 8 | 11 | 6 | 1 | 0 | 17 | 0 | 20 | 0 | 0 | 20 | 4 | 13 | 0 | 0 | 23 | 7 | 20 | 0 | 0 | 21 | 0 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 2 | 0 | 19 | 0 | 0 | 9 | 20 | 10 | 0 | 0 | 10 | 0 | 14 | 0 | 0 | 14 | 14 | 30 | 0 | 0 | 3 | 33 | 30 | 0 | 22 | 24 | 58 | 48 | 0 | 0 | 37 | 0 | 16 | 0 | 0 | 16 | 3 | 6 | 0 | 0 | 24 | 0 | 1 | 0 | 0 | 2 | 6 | 4 | 2 | 5 | 18 | 2 | 54 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 7 | 0 | 4 | 0 | 0 | 42 | 27 | 4 | 0 | 0 | 29 | 19 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 0
2026-02-23 | W14 | 17 | 0 | 0 | 18 | 0 | 22 | 0 | 0 | 19 | 18 | 13 | 2 | 1 | 33 | 0 | 8 | 3 | 3 | 32 | 18 | 334 | 84 | 0 | 230 | 115 | 0 | 0 | 0 | 10 | 4 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 21 | 40 | 22 | 0 | 60 | 26 | 22 | 0 | 0 | 21 | 0 | 24 | 4 | 0 | 45 | 7 | 12 | 1 | 0 | 10 | 8 | 15 | 2 | 0 | 41 | 10 | 49 | 0 | 0 | 63 | 0 | 24 | 0 | 0 | 24 | 24 | 95 | 1 | 0 | 66 | 0 | 111 | 3 | 30 | 3 | 5 | 31 | 5 | 11 | 0 | 1 | 0 | 2 | 4 | 6 | 34 | 4 | 0 | 0 | 8 | 13 | 1 | 0 | 2 | 12 | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 6 | 2 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 3 | 4 | 0 | 2 | 2 | 0 | 4 | 6 | 2 | 2 | 0 | 4 | 0 | 8 | 0 | 2 | 4 | 18 | 9 | 0 | 5 | 22 | 4 | 11 | 0 | 1 | 20 | 4 | 0 | 0 | 0 | 12 | 1 | 0 | 0 | 0 | 17 | 0 | 7 | 3 | 1 | 56 | 0 | 10 | 0 | 9 | 1 | 1 | 11 | 0 | 20 | 30 | 10 | 7 | 4 | 1 | 59 | 17 | 0 | 0 | 1 | 9 | 0 | 4 | 0 | 4 | 29 | 0 | 0 | 2 | 13 | 8 | 4 | 3 | 0 | 1 | 11 | 0 | 0 | 0 | 2 | 45 | 15 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 4 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 2 | 5 | 0 | 4 | 0 | 9 | 38 | 51 | 26 | 0 | 2 | 13 | 0 | 10 | 0 | 4 | 0 | 0 | 23 | 0 | 0 | 7 | 23 | 17 | 0 | 0 | 8 | 11 | 6 | 1 | 0 | 17 | 0 | 20 | 0 | 0 | 20 | 4 | 13 | 0 | 0 | 23 | 7 | 20 | 0 | 0 | 21 | 0 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 2 | 0 | 19 | 0 | 0 | 9 | 20 | 10 | 0 | 0 | 10 | 0 | 14 | 0 | 0 | 14 | 14 | 30 | 0 | 0 | 3 | 33 | 30 | 0 | 22 | 24 | 58 | 48 | 0 | 0 | 37 | 0 | 16 | 0 | 0 | 16 | 3 | 6 | 0 | 0 | 24 | 0 | 1 | 0 | 0 | 2 | 6 | 4 | 2 | 5 | 18 | 2 | 54 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 7 | 0 | 4 | 0 | 0 | 42 | 27 | 4 | 0 | 0 | 29 | 19 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 0
2026-02-24 | W14 | 17 | 0 | 0 | 18 | 0 | 22 | 0 | 0 | 19 | 18 | 13 | 2 | 1 | 33 | 0 | 8 | 3 | 3 | 32 | 18 | 334 | 84 | 0 | 230 | 115 | 0 | 0 | 0 | 10 | 4 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 21 | 40 | 22 | 0 | 60 | 26 | 22 | 0 | 0 | 21 | 0 | 24 | 4 | 0 | 45 | 7 | 12 | 1 | 0 | 10 | 8 | 15 | 2 | 0 | 41 | 10 | 49 | 0 | 0 | 63 | 0 | 24 | 0 | 0 | 24 | 24 | 95 | 1 | 0 | 66 | 0 | 111 | 3 | 30 | 3 | 5 | 31 | 5 | 11 | 0 | 1 | 0 | 2 | 4 | 6 | 34 | 4 | 0 | 0 | 8 | 13 | 1 | 0 | 2 | 12 | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 6 | 2 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 3 | 4 | 0 | 2 | 2 | 0 | 4 | 6 | 2 | 2 | 0 | 4 | 0 | 8 | 0 | 2 | 4 | 18 | 9 | 0 | 5 | 22 | 4 | 11 | 0 | 1 | 20 | 4 | 0 | 0 | 0 | 12 | 1 | 0 | 0 | 0 | 17 | 0 | 7 | 3 | 1 | 56 | 0 | 10 | 0 | 9 | 1 | 1 | 11 | 0 | 20 | 30 | 10 | 7 | 4 | 1 | 59 | 17 | 0 | 0 | 1 | 9 | 0 | 4 | 0 | 4 | 29 | 0 | 0 | 2 | 13 | 8 | 4 | 3 | 0 | 1 | 11 | 0 | 0 | 0 | 2 | 45 | 15 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 4 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 2 | 5 | 0 | 4 | 0 | 9 | 38 | 51 | 26 | 0 | 2 | 13 | 0 | 10 | 0 | 4 | 0 | 0 | 23 | 0 | 0 | 7 | 23 | 17 | 0 | 0 | 8 | 11 | 6 | 1 | 0 | 17 | 0 | 20 | 0 | 0 | 20 | 4 | 13 | 0 | 0 | 23 | 7 | 20 | 0 | 0 | 21 | 0 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 2 | 0 | 19 | 0 | 0 | 9 | 20 | 10 | 0 | 0 | 10 | 0 | 14 | 0 | 0 | 14 | 14 | 30 | 0 | 0 | 3 | 33 | 30 | 0 | 22 | 24 | 58 | 48 | 0 | 0 | 37 | 0 | 16 | 0 | 0 | 16 | 3 | 6 | 0 | 0 | 24 | 0 | 1 | 0 | 0 | 2 | 6 | 4 | 2 | 5 | 18 | 2 | 54 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 7 | 0 | 4 | 0 | 0 | 42 | 27 | 4 | 0 | 0 | 29 | 19 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 0
2026-02-25 | W14 | 17 | 0 | 0 | 18 | 0 | 22 | 0 | 0 | 19 | 18 | 13 | 2 | 1 | 33 | 0 | 8 | 3 | 3 | 32 | 18 | 334 | 84 | 0 | 230 | 115 | 0 | 0 | 0 | 10 | 4 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 21 | 40 | 22 | 0 | 60 | 26 | 22 | 0 | 0 | 21 | 0 | 24 | 4 | 0 | 45 | 7 | 12 | 1 | 0 | 10 | 8 | 15 | 2 | 0 | 41 | 10 | 49 | 0 | 0 | 63 | 0 | 24 | 0 | 0 | 24 | 24 | 95 | 1 | 0 | 66 | 0 | 111 | 3 | 30 | 3 | 5 | 31 | 5 | 11 | 0 | 1 | 0 | 2 | 4 | 6 | 34 | 4 | 0 | 0 | 8 | 13 | 1 | 0 | 2 | 12 | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 6 | 2 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 3 | 4 | 0 | 2 | 2 | 0 | 4 | 6 | 2 | 2 | 0 | 4 | 0 | 8 | 0 | 2 | 4 | 18 | 9 | 0 | 5 | 22 | 4 | 11 | 0 | 1 | 20 | 4 | 0 | 0 | 0 | 12 | 1 | 0 | 0 | 0 | 17 | 0 | 7 | 3 | 1 | 56 | 0 | 10 | 0 | 9 | 1 | 1 | 11 | 0 | 20 | 30 | 10 | 7 | 4 | 1 | 59 | 17 | 0 | 0 | 1 | 9 | 0 | 4 | 0 | 4 | 29 | 0 | 0 | 2 | 13 | 8 | 4 | 3 | 0 | 1 | 11 | 0 | 0 | 0 | 2 | 45 | 15 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 4 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 2 | 5 | 0 | 4 | 0 | 9 | 38 | 51 | 26 | 0 | 2 | 13 | 0 | 10 | 0 | 4 | 0 | 0 | 23 | 0 | 0 | 7 | 23 | 17 | 0 | 0 | 8 | 11 | 6 | 1 | 0 | 17 | 0 | 20 | 0 | 0 | 20 | 4 | 13 | 0 | 0 | 23 | 7 | 20 | 0 | 0 | 21 | 0 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 2 | 0 | 19 | 0 | 0 | 9 | 20 | 10 | 0 | 0 | 10 | 0 | 14 | 0 | 0 | 14 | 14 | 30 | 0 | 0 | 3 | 33 | 30 | 0 | 22 | 24 | 58 | 48 | 0 | 0 | 37 | 0 | 16 | 0 | 0 | 16 | 3 | 6 | 0 | 0 | 24 | 0 | 1 | 0 | 0 | 2 | 6 | 4 | 2 | 5 | 18 | 2 | 54 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 7 | 0 | 4 | 0 | 0 | 42 | 27 | 4 | 0 | 0 | 29 | 19 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 0
2026-02-26 | W14 | 17 | 0 | 0 | 18 | 0 | 22 | 0 | 0 | 19 | 18 | 13 | 2 | 1 | 33 | 0 | 8 | 3 | 3 | 32 | 18 | 334 | 84 | 0 | 230 | 115 | 0 | 0 | 0 | 10 | 4 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 21 | 40 | 22 | 0 | 60 | 26 | 22 | 0 | 0 | 21 | 0 | 24 | 4 | 0 | 45 | 7 | 12 | 1 | 0 | 10 | 8 | 15 | 2 | 0 | 41 | 10 | 49 | 0 | 0 | 63 | 0 | 24 | 0 | 0 | 24 | 24 | 95 | 1 | 0 | 66 | 0 | 111 | 3 | 30 | 3 | 5 | 31 | 5 | 11 | 0 | 1 | 0 | 2 | 4 | 6 | 34 | 4 | 0 | 0 | 8 | 13 | 1 | 0 | 2 | 12 | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 6 | 2 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 3 | 4 | 0 | 2 | 2 | 0 | 4 | 6 | 2 | 2 | 0 | 4 | 0 | 8 | 0 | 2 | 4 | 18 | 9 | 0 | 5 | 22 | 4 | 11 | 0 | 1 | 20 | 4 | 0 | 0 | 0 | 12 | 1 | 0 | 0 | 0 | 17 | 0 | 7 | 3 | 1 | 56 | 0 | 10 | 0 | 9 | 1 | 1 | 11 | 0 | 20 | 30 | 10 | 7 | 4 | 1 | 59 | 17 | 0 | 0 | 1 | 9 | 0 | 4 | 0 | 4 | 29 | 0 | 0 | 2 | 13 | 8 | 4 | 3 | 0 | 1 | 11 | 0 | 0 | 0 | 2 | 45 | 15 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 4 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 2 | 5 | 0 | 4 | 0 | 9 | 38 | 51 | 26 | 0 | 2 | 13 | 0 | 10 | 0 | 4 | 0 | 0 | 23 | 0 | 0 | 7 | 23 | 17 | 0 | 0 | 8 | 11 | 6 | 1 | 0 | 17 | 0 | 20 | 0 | 0 | 20 | 4 | 13 | 0 | 0 | 23 | 7 | 20 | 0 | 0 | 21 | 0 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 2 | 0 | 19 | 0 | 0 | 9 | 20 | 10 | 0 | 0 | 10 | 0 | 14 | 0 | 0 | 14 | 14 | 30 | 0 | 0 | 3 | 33 | 30 | 0 | 22 | 24 | 58 | 48 | 0 | 0 | 37 | 0 | 16 | 0 | 0 | 16 | 3 | 6 | 0 | 0 | 24 | 0 | 1 | 0 | 0 | 2 | 6 | 4 | 2 | 5 | 18 | 2 | 54 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 7 | 0 | 4 | 0 | 0 | 42 | 27 | 4 | 0 | 0 | 29 | 19 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 0
2026-02-27 | W14 | 17 | 0 | 0 | 18 | 0 | 22 | 0 | 0 | 19 | 18 | 13 | 2 | 1 | 33 | 0 | 8 | 3 | 3 | 32 | 18 | 334 | 84 | 0 | 230 | 115 | 0 | 0 | 0 | 10 | 4 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 21 | 40 | 22 | 0 | 60 | 26 | 22 | 0 | 0 | 21 | 0 | 24 | 4 | 0 | 45 | 7 | 12 | 1 | 0 | 10 | 8 | 15 | 2 | 0 | 41 | 10 | 49 | 0 | 0 | 63 | 0 | 24 | 0 | 0 | 24 | 24 | 95 | 1 | 0 | 66 | 0 | 111 | 3 | 30 | 3 | 5 | 31 | 5 | 11 | 0 | 1 | 0 | 2 | 4 | 6 | 34 | 4 | 0 | 0 | 8 | 13 | 1 | 0 | 2 | 12 | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 6 | 2 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 3 | 4 | 0 | 2 | 2 | 0 | 4 | 6 | 2 | 2 | 0 | 4 | 0 | 8 | 0 | 2 | 4 | 18 | 9 | 0 | 5 | 22 | 4 | 11 | 0 | 1 | 20 | 4 | 0 | 0 | 0 | 12 | 1 | 0 | 0 | 0 | 17 | 0 | 7 | 3 | 1 | 56 | 0 | 10 | 0 | 9 | 1 | 1 | 11 | 0 | 20 | 30 | 10 | 7 | 4 | 1 | 59 | 17 | 0 | 0 | 1 | 9 | 0 | 4 | 0 | 4 | 29 | 0 | 0 | 2 | 13 | 8 | 4 | 3 | 0 | 1 | 11 | 0 | 0 | 0 | 2 | 45 | 15 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 4 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 2 | 5 | 0 | 4 | 0 | 9 | 38 | 51 | 26 | 0 | 2 | 13 | 0 | 10 | 0 | 4 | 0 | 0 | 23 | 0 | 0 | 7 | 23 | 17 | 0 | 0 | 8 | 11 | 6 | 1 | 0 | 17 | 0 | 20 | 0 | 0 | 20 | 4 | 13 | 0 | 0 | 23 | 7 | 20 | 0 | 0 | 21 | 0 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 2 | 0 | 19 | 0 | 0 | 9 | 20 | 10 | 0 | 0 | 10 | 0 | 14 | 0 | 0 | 14 | 14 | 30 | 0 | 0 | 3 | 33 | 30 | 0 | 22 | 24 | 58 | 48 | 0 | 0 | 37 | 0 | 16 | 0 | 0 | 16 | 3 | 6 | 0 | 0 | 24 | 0 | 1 | 0 | 0 | 2 | 6 | 4 | 2 | 5 | 18 | 2 | 54 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 7 | 0 | 4 | 0 | 0 | 42 | 27 | 4 | 0 | 0 | 29 | 19 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 0
2026-02-28 | W15 | 17 | 0 | 0 | 18 | 0 | 22 | 0 | 0 | 19 | 18 | 13 | 2 | 1 | 33 | 0 | 8 | 3 | 3 | 32 | 18 | 334 | 84 | 0 | 230 | 115 | 0 | 0 | 0 | 10 | 4 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 21 | 40 | 22 | 0 | 60 | 26 | 22 | 0 | 0 | 21 | 0 | 24 | 4 | 0 | 45 | 7 | 12 | 1 | 0 | 10 | 8 | 15 | 2 | 0 | 41 | 10 | 49 | 0 | 0 | 63 | 0 | 24 | 0 | 0 | 24 | 24 | 95 | 1 | 0 | 66 | 0 | 111 | 3 | 30 | 3 | 5 | 31 | 5 | 11 | 0 | 1 | 0 | 2 | 4 | 6 | 34 | 4 | 0 | 0 | 8 | 13 | 1 | 0 | 2 | 12 | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 6 | 2 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 3 | 4 | 0 | 2 | 2 | 0 | 4 | 6 | 2 | 2 | 0 | 4 | 0 | 8 | 0 | 2 | 4 | 18 | 9 | 0 | 5 | 22 | 4 | 11 | 0 | 1 | 20 | 4 | 0 | 0 | 0 | 12 | 1 | 0 | 0 | 0 | 17 | 0 | 7 | 3 | 1 | 56 | 0 | 10 | 0 | 9 | 1 | 1 | 11 | 0 | 20 | 30 | 10 | 7 | 4 | 1 | 59 | 17 | 0 | 0 | 1 | 9 | 0 | 4 | 0 | 4 | 29 | 0 | 0 | 2 | 13 | 8 | 4 | 3 | 0 | 1 | 11 | 0 | 0 | 0 | 2 | 45 | 15 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 4 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 2 | 5 | 0 | 4 | 0 | 9 | 38 | 51 | 26 | 0 | 2 | 13 | 0 | 10 | 0 | 4 | 0 | 0 | 23 | 0 | 0 | 7 | 23 | 17 | 0 | 0 | 8 | 11 | 6 | 1 | 0 | 17 | 0 | 20 | 0 | 0 | 20 | 4 | 13 | 0 | 0 | 23 | 7 | 20 | 0 | 0 | 21 | 0 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 2 | 0 | 19 | 0 | 0 | 9 | 20 | 10 | 0 | 0 | 10 | 0 | 14 | 0 | 0 | 14 | 14 | 30 | 0 | 0 | 3 | 33 | 30 | 0 | 22 | 24 | 58 | 48 | 0 | 0 | 37 | 0 | 16 | 0 | 0 | 16 | 3 | 6 | 0 | 0 | 24 | 0 | 1 | 0 | 0 | 2 | 6 | 4 | 2 | 5 | 18 | 2 | 54 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 7 | 0 | 4 | 0 | 0 | 42 | 27 | 4 | 0 | 0 | 29 | 19 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 0
2026-03-02 | W15 | 17 | 0 | 0 | 18 | 0 | 22 | 0 | 0 | 19 | 18 | 13 | 2 | 1 | 33 | 0 | 8 | 3 | 3 | 32 | 18 | 334 | 84 | 0 | 230 | 115 | 0 | 0 | 0 | 10 | 4 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 21 | 40 | 22 | 0 | 60 | 26 | 22 | 0 | 0 | 21 | 0 | 24 | 4 | 0 | 45 | 7 | 12 | 1 | 0 | 10 | 8 | 15 | 2 | 0 | 41 | 10 | 49 | 0 | 0 | 63 | 0 | 24 | 0 | 0 | 24 | 24 | 95 | 1 | 0 | 66 | 0 | 111 | 3 | 30 | 3 | 5 | 31 | 5 | 11 | 0 | 1 | 0 | 2 | 4 | 6 | 34 | 4 | 0 | 0 | 8 | 13 | 1 | 0 | 2 | 12 | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 6 | 2 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 3 | 4 | 0 | 2 | 2 | 0 | 4 | 6 | 2 | 2 | 0 | 4 | 0 | 8 | 0 | 2 | 4 | 18 | 9 | 0 | 5 | 22 | 4 | 11 | 0 | 1 | 20 | 4 | 0 | 0 | 0 | 12 | 1 | 0 | 0 | 0 | 17 | 0 | 7 | 3 | 1 | 56 | 0 | 10 | 0 | 9 | 1 | 1 | 11 | 0 | 20 | 30 | 10 | 7 | 4 | 1 | 59 | 17 | 0 | 0 | 1 | 9 | 0 | 4 | 0 | 4 | 29 | 0 | 0 | 2 | 13 | 8 | 4 | 3 | 0 | 1 | 11 | 0 | 0 | 0 | 2 | 45 | 15 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 4 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 2 | 5 | 0 | 4 | 0 | 9 | 38 | 51 | 26 | 0 | 2 | 13 | 0 | 10 | 0 | 4 | 0 | 0 | 23 | 0 | 0 | 7 | 23 | 17 | 0 | 0 | 8 | 11 | 6 | 1 | 0 | 17 | 0 | 20 | 0 | 0 | 20 | 4 | 13 | 0 | 0 | 23 | 7 | 20 | 0 | 0 | 21 | 0 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 2 | 0 | 19 | 0 | 0 | 9 | 20 | 10 | 0 | 0 | 10 | 0 | 14 | 0 | 0 | 14 | 14 | 30 | 0 | 0 | 3 | 33 | 30 | 0 | 22 | 24 | 58 | 48 | 0 | 0 | 37 | 0 | 16 | 0 | 0 | 16 | 3 | 6 | 0 | 0 | 24 | 0 | 1 | 0 | 0 | 2 | 6 | 4 | 2 | 5 | 18 | 2 | 54 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 7 | 0 | 4 | 0 | 0 | 42 | 27 | 4 | 0 | 0 | 29 | 19 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 0
2026-03-03 | W15 | 17 | 0 | 0 | 18 | 0 | 22 | 0 | 0 | 19 | 18 | 13 | 2 | 1 | 33 | 0 | 8 | 3 | 3 | 32 | 18 | 334 | 84 | 0 | 230 | 115 | 0 | 0 | 0 | 10 | 4 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 21 | 40 | 22 | 0 | 60 | 26 | 22 | 0 | 0 | 21 | 0 | 24 | 4 | 0 | 45 | 7 | 12 | 1 | 0 | 10 | 8 | 15 | 2 | 0 | 41 | 10 | 49 | 0 | 0 | 63 | 0 | 24 | 0 | 0 | 24 | 24 | 95 | 1 | 0 | 66 | 0 | 111 | 3 | 30 | 3 | 5 | 31 | 5 | 11 | 0 | 1 | 0 | 2 | 4 | 6 | 34 | 4 | 0 | 0 | 8 | 13 | 1 | 0 | 2 | 12 | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 6 | 2 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 3 | 4 | 0 | 2 | 2 | 0 | 4 | 6 | 2 | 2 | 0 | 4 | 0 | 8 | 0 | 2 | 4 | 18 | 9 | 0 | 5 | 22 | 4 | 11 | 0 | 1 | 20 | 4 | 0 | 0 | 0 | 12 | 1 | 0 | 0 | 0 | 17 | 0 | 7 | 3 | 1 | 56 | 0 | 10 | 0 | 9 | 1 | 1 | 11 | 0 | 20 | 30 | 10 | 7 | 4 | 1 | 59 | 17 | 0 | 0 | 1 | 9 | 0 | 4 | 0 | 4 | 29 | 0 | 0 | 2 | 13 | 8 | 4 | 3 | 0 | 1 | 11 | 0 | 0 | 0 | 2 | 45 | 15 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 4 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 2 | 5 | 0 | 4 | 0 | 9 | 38 | 51 | 26 | 0 | 2 | 13 | 0 | 10 | 0 | 4 | 0 | 0 | 23 | 0 | 0 | 7 | 23 | 17 | 0 | 0 | 8 | 11 | 6 | 1 | 0 | 17 | 0 | 20 | 0 | 0 | 20 | 4 | 13 | 0 | 0 | 23 | 7 | 20 | 0 | 0 | 21 | 0 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 2 | 0 | 19 | 0 | 0 | 9 | 20 | 10 | 0 | 0 | 10 | 0 | 14 | 0 | 0 | 14 | 14 | 30 | 0 | 0 | 3 | 33 | 30 | 0 | 22 | 24 | 58 | 48 | 0 | 0 | 37 | 0 | 16 | 0 | 0 | 16 | 3 | 6 | 0 | 0 | 24 | 0 | 1 | 0 | 0 | 2 | 6 | 4 | 2 | 5 | 18 | 2 | 54 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 7 | 0 | 4 | 0 | 0 | 42 | 27 | 4 | 0 | 0 | 29 | 19 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 0
2026-03-04 | W15 | 17 | 0 | 0 | 18 | 0 | 22 | 0 | 0 | 19 | 18 | 13 | 2 | 1 | 33 | 0 | 8 | 3 | 3 | 32 | 18 | 334 | 84 | 0 | 230 | 115 | 0 | 0 | 0 | 10 | 4 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 21 | 40 | 22 | 0 | 60 | 26 | 22 | 0 | 0 | 21 | 0 | 24 | 4 | 0 | 45 | 7 | 12 | 1 | 0 | 10 | 8 | 15 | 2 | 0 | 41 | 10 | 49 | 0 | 0 | 63 | 0 | 24 | 0 | 0 | 24 | 24 | 95 | 1 | 0 | 66 | 0 | 111 | 3 | 30 | 3 | 5 | 31 | 5 | 11 | 0 | 1 | 0 | 2 | 4 | 6 | 34 | 4 | 0 | 0 | 8 | 13 | 1 | 0 | 2 | 12 | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 6 | 2 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 3 | 4 | 0 | 2 | 2 | 0 | 4 | 6 | 2 | 2 | 0 | 4 | 0 | 8 | 0 | 2 | 4 | 18 | 9 | 0 | 5 | 22 | 4 | 11 | 0 | 1 | 20 | 4 | 0 | 0 | 0 | 12 | 1 | 0 | 0 | 0 | 17 | 0 | 7 | 3 | 1 | 56 | 0 | 10 | 0 | 9 | 1 | 1 | 11 | 0 | 20 | 30 | 10 | 7 | 4 | 1 | 59 | 17 | 0 | 0 | 1 | 9 | 0 | 4 | 0 | 4 | 29 | 0 | 0 | 2 | 13 | 8 | 4 | 3 | 0 | 1 | 11 | 0 | 0 | 0 | 2 | 45 | 15 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 4 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 2 | 5 | 0 | 4 | 0 | 9 | 38 | 51 | 26 | 0 | 2 | 13 | 0 | 10 | 0 | 4 | 0 | 0 | 23 | 0 | 0 | 7 | 23 | 17 | 0 | 0 | 8 | 11 | 6 | 1 | 0 | 17 | 0 | 20 | 0 | 0 | 20 | 4 | 13 | 0 | 0 | 23 | 7 | 20 | 0 | 0 | 21 | 0 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 2 | 0 | 19 | 0 | 0 | 9 | 20 | 10 | 0 | 0 | 10 | 0 | 14 | 0 | 0 | 14 | 14 | 30 | 0 | 0 | 3 | 33 | 30 | 0 | 22 | 24 | 58 | 48 | 0 | 0 | 37 | 0 | 16 | 0 | 0 | 16 | 3 | 6 | 0 | 0 | 24 | 0 | 1 | 0 | 0 | 2 | 6 | 4 | 2 | 5 | 18 | 2 | 54 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 7 | 0 | 4 | 0 | 0 | 42 | 27 | 4 | 0 | 0 | 29 | 19 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 0
2026-03-05 | W15 | 17 | 0 | 0 | 18 | 0 | 22 | 0 | 0 | 19 | 18 | 13 | 2 | 1 | 33 | 0 | 8 | 3 | 3 | 32 | 18 | 334 | 84 | 0 | 230 | 115 | 0 | 0 | 0 | 10 | 4 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 21 | 40 | 22 | 0 | 60 | 26 | 22 | 0 | 0 | 21 | 0 | 24 | 4 | 0 | 45 | 7 | 12 | 1 | 0 | 10 | 8 | 15 | 2 | 0 | 41 | 10 | 49 | 0 | 0 | 63 | 0 | 24 | 0 | 0 | 24 | 24 | 95 | 1 | 0 | 66 | 0 | 111 | 3 | 30 | 3 | 5 | 31 | 5 | 11 | 0 | 1 | 0 | 2 | 4 | 6 | 34 | 4 | 0 | 0 | 8 | 13 | 1 | 0 | 2 | 12 | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 6 | 2 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 3 | 4 | 0 | 2 | 2 | 0 | 4 | 6 | 2 | 2 | 0 | 4 | 0 | 8 | 0 | 2 | 4 | 18 | 9 | 0 | 5 | 22 | 4 | 11 | 0 | 1 | 20 | 4 | 0 | 0 | 0 | 12 | 1 | 0 | 0 | 0 | 17 | 0 | 7 | 3 | 1 | 56 | 0 | 10 | 0 | 9 | 1 | 1 | 11 | 0 | 20 | 30 | 10 | 7 | 4 | 1 | 59 | 17 | 0 | 0 | 1 | 9 | 0 | 4 | 0 | 4 | 29 | 0 | 0 | 2 | 13 | 8 | 4 | 3 | 0 | 1 | 11 | 0 | 0 | 0 | 2 | 45 | 15 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 4 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 2 | 5 | 0 | 4 | 0 | 9 | 38 | 51 | 26 | 0 | 2 | 13 | 0 | 10 | 0 | 4 | 0 | 0 | 23 | 0 | 0 | 7 | 23 | 17 | 0 | 0 | 8 | 11 | 6 | 1 | 0 | 17 | 0 | 20 | 0 | 0 | 20 | 4 | 13 | 0 | 0 | 23 | 7 | 20 | 0 | 0 | 21 | 0 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 2 | 0 | 19 | 0 | 0 | 9 | 20 | 10 | 0 | 0 | 10 | 0 | 14 | 0 | 0 | 14 | 14 | 30 | 0 | 0 | 3 | 33 | 30 | 0 | 22 | 24 | 58 | 48 | 0 | 0 | 37 | 0 | 16 | 0 | 0 | 16 | 3 | 6 | 0 | 0 | 24 | 0 | 1 | 0 | 0 | 2 | 6 | 4 | 2 | 5 | 18 | 2 | 54 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 7 | 0 | 4 | 0 | 0 | 42 | 27 | 4 | 0 | 0 | 29 | 19 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 0
2026-03-06 | W15 | 17 | 0 | 0 | 18 | 0 | 22 | 0 | 0 | 19 | 18 | 13 | 2 | 1 | 33 | 0 | 8 | 3 | 3 | 32 | 18 | 334 | 84 | 0 | 230 | 115 | 0 | 0 | 0 | 10 | 4 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 21 | 40 | 22 | 0 | 60 | 26 | 22 | 0 | 0 | 21 | 0 | 24 | 4 | 0 | 45 | 7 | 12 | 1 | 0 | 10 | 8 | 15 | 2 | 0 | 41 | 10 | 49 | 0 | 0 | 63 | 0 | 24 | 0 | 0 | 24 | 24 | 95 | 1 | 0 | 66 | 0 | 111 | 3 | 30 | 3 | 5 | 31 | 5 | 11 | 0 | 1 | 0 | 2 | 4 | 6 | 34 | 4 | 0 | 0 | 8 | 13 | 1 | 0 | 2 | 12 | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 6 | 2 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 3 | 4 | 0 | 2 | 2 | 0 | 4 | 6 | 2 | 2 | 0 | 4 | 0 | 8 | 0 | 2 | 4 | 18 | 9 | 0 | 5 | 22 | 4 | 11 | 0 | 1 | 20 | 4 | 0 | 0 | 0 | 12 | 1 | 0 | 0 | 0 | 17 | 0 | 7 | 3 | 1 | 56 | 0 | 10 | 0 | 9 | 1 | 1 | 11 | 0 | 20 | 30 | 10 | 7 | 4 | 1 | 59 | 17 | 0 | 0 | 1 | 9 | 0 | 4 | 0 | 4 | 29 | 0 | 0 | 2 | 13 | 8 | 4 | 3 | 0 | 1 | 11 | 0 | 0 | 0 | 2 | 45 | 15 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 4 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 2 | 5 | 0 | 4 | 0 | 9 | 38 | 51 | 26 | 0 | 2 | 13 | 0 | 10 | 0 | 4 | 0 | 0 | 23 | 0 | 0 | 7 | 23 | 17 | 0 | 0 | 8 | 11 | 6 | 1 | 0 | 17 | 0 | 20 | 0 | 0 | 20 | 4 | 13 | 0 | 0 | 23 | 7 | 20 | 0 | 0 | 21 | 0 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 2 | 0 | 19 | 0 | 0 | 9 | 20 | 10 | 0 | 0 | 10 | 0 | 14 | 0 | 0 | 14 | 14 | 30 | 0 | 0 | 3 | 33 | 30 | 0 | 22 | 24 | 58 | 48 | 0 | 0 | 37 | 0 | 16 | 0 | 0 | 16 | 3 | 6 | 0 | 0 | 24 | 0 | 1 | 0 | 0 | 2 | 6 | 4 | 2 | 5 | 18 | 2 | 54 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 7 | 0 | 4 | 0 | 0 | 42 | 27 | 4 | 0 | 0 | 29 | 19 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 0
2026-03-07 | W16 | 17 | 0 | 0 | 18 | 0 | 22 | 0 | 0 | 19 | 18 | 13 | 2 | 1 | 33 | 0 | 8 | 3 | 3 | 32 | 18 | 334 | 84 | 0 | 230 | 115 | 0 | 0 | 0 | 10 | 4 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 21 | 40 | 22 | 0 | 60 | 26 | 22 | 0 | 0 | 21 | 0 | 24 | 4 | 0 | 45 | 7 | 12 | 1 | 0 | 10 | 8 | 15 | 2 | 0 | 41 | 10 | 49 | 0 | 0 | 63 | 0 | 24 | 0 | 0 | 24 | 24 | 95 | 1 | 0 | 66 | 0 | 111 | 3 | 30 | 3 | 5 | 31 | 5 | 11 | 0 | 1 | 0 | 2 | 4 | 6 | 34 | 4 | 0 | 0 | 8 | 13 | 1 | 0 | 2 | 12 | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 6 | 2 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 3 | 4 | 0 | 2 | 2 | 0 | 4 | 6 | 2 | 2 | 0 | 4 | 0 | 8 | 0 | 2 | 4 | 18 | 9 | 0 | 5 | 22 | 4 | 11 | 0 | 1 | 20 | 4 | 0 | 0 | 0 | 12 | 1 | 0 | 0 | 0 | 17 | 0 | 7 | 3 | 1 | 56 | 0 | 10 | 0 | 9 | 1 | 1 | 11 | 0 | 20 | 30 | 10 | 7 | 4 | 1 | 59 | 17 | 0 | 0 | 1 | 9 | 0 | 4 | 0 | 4 | 29 | 0 | 0 | 2 | 13 | 8 | 4 | 3 | 0 | 1 | 11 | 0 | 0 | 0 | 2 | 45 | 15 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 4 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 2 | 5 | 0 | 4 | 0 | 9 | 38 | 51 | 26 | 0 | 2 | 13 | 0 | 10 | 0 | 4 | 0 | 0 | 23 | 0 | 0 | 7 | 23 | 17 | 0 | 0 | 8 | 11 | 6 | 1 | 0 | 17 | 0 | 20 | 0 | 0 | 20 | 4 | 13 | 0 | 0 | 23 | 7 | 20 | 0 | 0 | 21 | 0 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 2 | 0 | 19 | 0 | 0 | 9 | 20 | 10 | 0 | 0 | 10 | 0 | 14 | 0 | 0 | 14 | 14 | 30 | 0 | 0 | 3 | 33 | 30 | 0 | 22 | 24 | 58 | 48 | 0 | 0 | 37 | 0 | 16 | 0 | 0 | 16 | 3 | 6 | 0 | 0 | 24 | 0 | 1 | 0 | 0 | 2 | 6 | 4 | 2 | 5 | 18 | 2 | 54 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 7 | 0 | 4 | 0 | 0 | 42 | 27 | 4 | 0 | 0 | 29 | 19 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 0
2026-03-09 | W16 | 17 | 0 | 0 | 18 | 0 | 22 | 0 | 0 | 19 | 18 | 13 | 2 | 1 | 33 | 0 | 8 | 3 | 3 | 32 | 18 | 334 | 84 | 0 | 230 | 115 | 0 | 0 | 0 | 10 | 4 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 21 | 40 | 22 | 0 | 60 | 26 | 22 | 0 | 0 | 21 | 0 | 24 | 4 | 0 | 45 | 7 | 12 | 1 | 0 | 10 | 8 | 15 | 2 | 0 | 41 | 10 | 49 | 0 | 0 | 63 | 0 | 24 | 0 | 0 | 24 | 24 | 95 | 1 | 0 | 66 | 0 | 111 | 3 | 30 | 3 | 5 | 31 | 5 | 11 | 0 | 1 | 0 | 2 | 4 | 6 | 34 | 4 | 0 | 0 | 8 | 13 | 1 | 0 | 2 | 12 | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 6 | 2 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 3 | 4 | 0 | 2 | 2 | 0 | 4 | 6 | 2 | 2 | 0 | 4 | 0 | 8 | 0 | 2 | 4 | 18 | 9 | 0 | 5 | 22 | 4 | 11 | 0 | 1 | 20 | 4 | 0 | 0 | 0 | 12 | 1 | 0 | 0 | 0 | 17 | 0 | 7 | 3 | 1 | 56 | 0 | 10 | 0 | 9 | 1 | 1 | 11 | 0 | 20 | 30 | 10 | 7 | 4 | 1 | 59 | 17 | 0 | 0 | 1 | 9 | 0 | 4 | 0 | 4 | 29 | 0 | 0 | 2 | 13 | 8 | 4 | 3 | 0 | 1 | 11 | 0 | 0 | 0 | 2 | 45 | 15 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 4 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 2 | 5 | 0 | 4 | 0 | 9 | 38 | 51 | 26 | 0 | 2 | 13 | 0 | 10 | 0 | 4 | 0 | 0 | 23 | 0 | 0 | 7 | 23 | 17 | 0 | 0 | 8 | 11 | 6 | 1 | 0 | 17 | 0 | 20 | 0 | 0 | 20 | 4 | 13 | 0 | 0 | 23 | 7 | 20 | 0 | 0 | 21 | 0 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 2 | 0 | 19 | 0 | 0 | 9 | 20 | 10 | 0 | 0 | 10 | 0 | 14 | 0 | 0 | 14 | 14 | 30 | 0 | 0 | 3 | 33 | 30 | 0 | 22 | 24 | 58 | 48 | 0 | 0 | 37 | 0 | 16 | 0 | 0 | 16 | 3 | 6 | 0 | 0 | 24 | 0 | 1 | 0 | 0 | 2 | 6 | 4 | 2 | 5 | 18 | 2 | 54 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 7 | 0 | 4 | 0 | 0 | 42 | 27 | 4 | 0 | 0 | 29 | 19 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 0
2026-03-10 | W16 | 17 | 0 | 0 | 18 | 0 | 22 | 0 | 0 | 19 | 18 | 13 | 2 | 1 | 33 | 0 | 8 | 3 | 3 | 32 | 18 | 334 | 84 | 0 | 230 | 115 | 0 | 0 | 0 | 10 | 4 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 21 | 40 | 22 | 0 | 60 | 26 | 22 | 0 | 0 | 21 | 0 | 24 | 4 | 0 | 45 | 7 | 12 | 1 | 0 | 10 | 8 | 15 | 2 | 0 | 41 | 10 | 49 | 0 | 0 | 63 | 0 | 24 | 0 | 0 | 24 | 24 | 95 | 1 | 0 | 66 | 0 | 111 | 3 | 30 | 3 | 5 | 31 | 5 | 11 | 0 | 1 | 0 | 2 | 4 | 6 | 34 | 4 | 0 | 0 | 8 | 13 | 1 | 0 | 2 | 12 | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 6 | 2 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 3 | 4 | 0 | 2 | 2 | 0 | 4 | 6 | 2 | 2 | 0 | 4 | 0 | 8 | 0 | 2 | 4 | 18 | 9 | 0 | 5 | 22 | 4 | 11 | 0 | 1 | 20 | 4 | 0 | 0 | 0 | 12 | 1 | 0 | 0 | 0 | 17 | 0 | 7 | 3 | 1 | 56 | 0 | 10 | 0 | 9 | 1 | 1 | 11 | 0 | 20 | 30 | 10 | 7 | 4 | 1 | 59 | 17 | 0 | 0 | 1 | 9 | 0 | 4 | 0 | 4 | 29 | 0 | 0 | 2 | 13 | 8 | 4 | 3 | 0 | 1 | 11 | 0 | 0 | 0 | 2 | 45 | 15 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 4 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 2 | 5 | 0 | 4 | 0 | 9 | 38 | 51 | 26 | 0 | 2 | 13 | 0 | 10 | 0 | 4 | 0 | 0 | 23 | 0 | 0 | 7 | 23 | 17 | 0 | 0 | 8 | 11 | 6 | 1 | 0 | 17 | 0 | 20 | 0 | 0 | 20 | 4 | 13 | 0 | 0 | 23 | 7 | 20 | 0 | 0 | 21 | 0 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 2 | 0 | 19 | 0 | 0 | 9 | 20 | 10 | 0 | 0 | 10 | 0 | 14 | 0 | 0 | 14 | 14 | 30 | 0 | 0 | 3 | 33 | 30 | 0 | 22 | 24 | 58 | 48 | 0 | 0 | 37 | 0 | 16 | 0 | 0 | 16 | 3 | 6 | 0 | 0 | 24 | 0 | 1 | 0 | 0 | 2 | 6 | 4 | 2 | 5 | 18 | 2 | 54 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 7 | 0 | 4 | 0 | 0 | 42 | 27 | 4 | 0 | 0 | 29 | 19 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 0
2026-03-11 | W16 | 17 | 0 | 0 | 18 | 0 | 22 | 0 | 0 | 19 | 18 | 13 | 2 | 1 | 33 | 0 | 8 | 3 | 3 | 32 | 18 | 334 | 84 | 0 | 230 | 115 | 0 | 0 | 0 | 10 | 4 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 21 | 40 | 22 | 0 | 60 | 26 | 22 | 0 | 0 | 21 | 0 | 24 | 4 | 0 | 45 | 7 | 12 | 1 | 0 | 10 | 8 | 15 | 2 | 0 | 41 | 10 | 49 | 0 | 0 | 63 | 0 | 24 | 0 | 0 | 24 | 24 | 95 | 1 | 0 | 66 | 0 | 111 | 3 | 30 | 3 | 5 | 31 | 5 | 11 | 0 | 1 | 0 | 2 | 4 | 6 | 34 | 4 | 0 | 0 | 8 | 13 | 1 | 0 | 2 | 12 | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 6 | 2 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 3 | 4 | 0 | 2 | 2 | 0 | 4 | 6 | 2 | 2 | 0 | 4 | 0 | 8 | 0 | 2 | 4 | 18 | 9 | 0 | 5 | 22 | 4 | 11 | 0 | 1 | 20 | 4 | 0 | 0 | 0 | 12 | 1 | 0 | 0 | 0 | 17 | 0 | 7 | 3 | 1 | 56 | 0 | 10 | 0 | 9 | 1 | 1 | 11 | 0 | 20 | 30 | 10 | 7 | 4 | 1 | 59 | 17 | 0 | 0 | 1 | 9 | 0 | 4 | 0 | 4 | 29 | 0 | 0 | 2 | 13 | 8 | 4 | 3 | 0 | 1 | 11 | 0 | 0 | 0 | 2 | 45 | 15 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 4 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 2 | 5 | 0 | 4 | 0 | 9 | 38 | 51 | 26 | 0 | 2 | 13 | 0 | 10 | 0 | 4 | 0 | 0 | 23 | 0 | 0 | 7 | 23 | 17 | 0 | 0 | 8 | 11 | 6 | 1 | 0 | 17 | 0 | 20 | 0 | 0 | 20 | 4 | 13 | 0 | 0 | 23 | 7 | 20 | 0 | 0 | 21 | 0 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 2 | 0 | 19 | 0 | 0 | 9 | 20 | 10 | 0 | 0 | 10 | 0 | 14 | 0 | 0 | 14 | 14 | 30 | 0 | 0 | 3 | 33 | 30 | 0 | 22 | 24 | 58 | 48 | 0 | 0 | 37 | 0 | 16 | 0 | 0 | 16 | 3 | 6 | 0 | 0 | 24 | 0 | 1 | 0 | 0 | 2 | 6 | 4 | 2 | 5 | 18 | 2 | 54 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 7 | 0 | 4 | 0 | 0 | 42 | 27 | 4 | 0 | 0 | 29 | 19 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 0
2026-03-12 | W16 | 17 | 0 | 0 | 18 | 0 | 22 | 0 | 0 | 19 | 18 | 13 | 2 | 1 | 33 | 0 | 8 | 3 | 3 | 32 | 18 | 334 | 84 | 0 | 230 | 115 | 0 | 0 | 0 | 10 | 4 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 21 | 40 | 22 | 0 | 60 | 26 | 22 | 0 | 0 | 21 | 0 | 24 | 4 | 0 | 45 | 7 | 12 | 1 | 0 | 10 | 8 | 15 | 2 | 0 | 41 | 10 | 49 | 0 | 0 | 63 | 0 | 24 | 0 | 0 | 24 | 24 | 95 | 1 | 0 | 66 | 0 | 111 | 3 | 30 | 3 | 5 | 31 | 5 | 11 | 0 | 1 | 0 | 2 | 4 | 6 | 34 | 4 | 0 | 0 | 8 | 13 | 1 | 0 | 2 | 12 | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 6 | 2 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 3 | 4 | 0 | 2 | 2 | 0 | 4 | 6 | 2 | 2 | 0 | 4 | 0 | 8 | 0 | 2 | 4 | 18 | 9 | 0 | 5 | 22 | 4 | 11 | 0 | 1 | 20 | 4 | 0 | 0 | 0 | 12 | 1 | 0 | 0 | 0 | 17 | 0 | 7 | 3 | 1 | 56 | 0 | 10 | 0 | 9 | 1 | 1 | 11 | 0 | 20 | 30 | 10 | 7 | 4 | 1 | 59 | 17 | 0 | 0 | 1 | 9 | 0 | 4 | 0 | 4 | 29 | 0 | 0 | 2 | 13 | 8 | 4 | 3 | 0 | 1 | 11 | 0 | 0 | 0 | 2 | 45 | 15 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 4 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 2 | 5 | 0 | 4 | 0 | 9 | 38 | 51 | 26 | 0 | 2 | 13 | 0 | 10 | 0 | 4 | 0 | 0 | 23 | 0 | 0 | 7 | 23 | 17 | 0 | 0 | 8 | 11 | 6 | 1 | 0 | 17 | 0 | 20 | 0 | 0 | 20 | 4 | 13 | 0 | 0 | 23 | 7 | 20 | 0 | 0 | 21 | 0 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 2 | 0 | 19 | 0 | 0 | 9 | 20 | 10 | 0 | 0 | 10 | 0 | 14 | 0 | 0 | 14 | 14 | 30 | 0 | 0 | 3 | 33 | 30 | 0 | 22 | 24 | 58 | 48 | 0 | 0 | 37 | 0 | 16 | 0 | 0 | 16 | 3 | 6 | 0 | 0 | 24 | 0 | 1 | 0 | 0 | 2 | 6 | 4 | 2 | 5 | 18 | 2 | 54 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 7 | 0 | 4 | 0 | 0 | 42 | 27 | 4 | 0 | 0 | 29 | 19 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 0
2026-03-13 | W16 | 17 | 0 | 0 | 18 | 0 | 22 | 0 | 0 | 19 | 18 | 13 | 2 | 1 | 33 | 0 | 8 | 3 | 3 | 32 | 18 | 334 | 84 | 0 | 230 | 115 | 0 | 0 | 0 | 10 | 4 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 21 | 40 | 22 | 0 | 60 | 26 | 22 | 0 | 0 | 21 | 0 | 24 | 4 | 0 | 45 | 7 | 12 | 1 | 0 | 10 | 8 | 15 | 2 | 0 | 41 | 10 | 49 | 0 | 0 | 63 | 0 | 24 | 0 | 0 | 24 | 24 | 95 | 1 | 0 | 66 | 0 | 111 | 3 | 30 | 3 | 5 | 31 | 5 | 11 | 0 | 1 | 0 | 2 | 4 | 6 | 34 | 4 | 0 | 0 | 8 | 13 | 1 | 0 | 2 | 12 | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 6 | 2 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 3 | 4 | 0 | 2 | 2 | 0 | 4 | 6 | 2 | 2 | 0 | 4 | 0 | 8 | 0 | 2 | 4 | 18 | 9 | 0 | 5 | 22 | 4 | 11 | 0 | 1 | 20 | 4 | 0 | 0 | 0 | 12 | 1 | 0 | 0 | 0 | 17 | 0 | 7 | 3 | 1 | 56 | 0 | 10 | 0 | 9 | 1 | 1 | 11 | 0 | 20 | 30 | 10 | 7 | 4 | 1 | 59 | 17 | 0 | 0 | 1 | 9 | 0 | 4 | 0 | 4 | 29 | 0 | 0 | 2 | 13 | 8 | 4 | 3 | 0 | 1 | 11 | 0 | 0 | 0 | 2 | 45 | 15 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 4 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 2 | 5 | 0 | 4 | 0 | 9 | 38 | 51 | 26 | 0 | 2 | 13 | 0 | 10 | 0 | 4 | 0 | 0 | 23 | 0 | 0 | 7 | 23 | 17 | 0 | 0 | 8 | 11 | 6 | 1 | 0 | 17 | 0 | 20 | 0 | 0 | 20 | 4 | 13 | 0 | 0 | 23 | 7 | 20 | 0 | 0 | 21 | 0 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 2 | 0 | 19 | 0 | 0 | 9 | 20 | 10 | 0 | 0 | 10 | 0 | 14 | 0 | 0 | 14 | 14 | 30 | 0 | 0 | 3 | 33 | 30 | 0 | 22 | 24 | 58 | 48 | 0 | 0 | 37 | 0 | 16 | 0 | 0 | 16 | 3 | 6 | 0 | 0 | 24 | 0 | 1 | 0 | 0 | 2 | 6 | 4 | 2 | 5 | 18 | 2 | 54 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 7 | 0 | 4 | 0 | 0 | 42 | 27 | 4 | 0 | 0 | 29 | 19 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 0
2026-03-14 | W17 | 17 | 0 | 0 | 18 | 0 | 22 | 0 | 0 | 19 | 18 | 13 | 2 | 1 | 33 | 0 | 8 | 3 | 3 | 32 | 18 | 334 | 84 | 0 | 230 | 115 | 0 | 0 | 0 | 10 | 4 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 21 | 40 | 22 | 0 | 60 | 26 | 22 | 0 | 0 | 21 | 0 | 24 | 4 | 0 | 45 | 7 | 12 | 1 | 0 | 10 | 8 | 15 | 2 | 0 | 41 | 10 | 49 | 0 | 0 | 63 | 0 | 24 | 0 | 0 | 24 | 24 | 95 | 1 | 0 | 66 | 0 | 111 | 3 | 30 | 3 | 5 | 31 | 5 | 11 | 0 | 1 | 0 | 2 | 4 | 6 | 34 | 4 | 0 | 0 | 8 | 13 | 1 | 0 | 2 | 12 | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 6 | 2 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 3 | 4 | 0 | 2 | 2 | 0 | 4 | 6 | 2 | 2 | 0 | 4 | 0 | 8 | 0 | 2 | 4 | 18 | 9 | 0 | 5 | 22 | 4 | 11 | 0 | 1 | 20 | 4 | 0 | 0 | 0 | 12 | 1 | 0 | 0 | 0 | 17 | 0 | 7 | 3 | 1 | 56 | 0 | 10 | 0 | 9 | 1 | 1 | 11 | 0 | 20 | 30 | 10 | 7 | 4 | 1 | 59 | 17 | 0 | 0 | 1 | 9 | 0 | 4 | 0 | 4 | 29 | 0 | 0 | 2 | 13 | 8 | 4 | 3 | 0 | 1 | 11 | 0 | 0 | 0 | 2 | 45 | 15 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 4 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 2 | 5 | 0 | 4 | 0 | 9 | 38 | 51 | 26 | 0 | 2 | 13 | 0 | 10 | 0 | 4 | 0 | 0 | 23 | 0 | 0 | 7 | 23 | 17 | 0 | 0 | 8 | 11 | 6 | 1 | 0 | 17 | 0 | 20 | 0 | 0 | 20 | 4 | 13 | 0 | 0 | 23 | 7 | 20 | 0 | 0 | 21 | 0 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 2 | 0 | 19 | 0 | 0 | 9 | 20 | 10 | 0 | 0 | 10 | 0 | 14 | 0 | 0 | 14 | 14 | 30 | 0 | 0 | 3 | 33 | 30 | 0 | 22 | 24 | 58 | 48 | 0 | 0 | 37 | 0 | 16 | 0 | 0 | 16 | 3 | 6 | 0 | 0 | 24 | 0 | 1 | 0 | 0 | 2 | 6 | 4 | 2 | 5 | 18 | 2 | 54 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 7 | 0 | 4 | 0 | 0 | 42 | 27 | 4 | 0 | 0 | 29 | 19 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 0
2026-03-16 | W17 | 17 | 0 | 0 | 18 | 0 | 22 | 0 | 0 | 19 | 18 | 13 | 2 | 1 | 33 | 0 | 8 | 3 | 3 | 32 | 18 | 334 | 84 | 0 | 230 | 115 | 0 | 0 | 0 | 10 | 4 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 21 | 40 | 22 | 0 | 60 | 26 | 22 | 0 | 0 | 21 | 0 | 24 | 4 | 0 | 45 | 7 | 12 | 1 | 0 | 10 | 8 | 15 | 2 | 0 | 41 | 10 | 49 | 0 | 0 | 63 | 0 | 24 | 0 | 0 | 24 | 24 | 95 | 1 | 0 | 66 | 0 | 111 | 3 | 30 | 3 | 5 | 31 | 5 | 11 | 0 | 1 | 0 | 2 | 4 | 6 | 34 | 4 | 0 | 0 | 8 | 13 | 1 | 0 | 2 | 12 | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 6 | 2 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 3 | 4 | 0 | 2 | 2 | 0 | 4 | 6 | 2 | 2 | 0 | 4 | 0 | 8 | 0 | 2 | 4 | 18 | 9 | 0 | 5 | 22 | 4 | 11 | 0 | 1 | 20 | 4 | 0 | 0 | 0 | 12 | 1 | 0 | 0 | 0 | 17 | 0 | 7 | 3 | 1 | 56 | 0 | 10 | 0 | 9 | 1 | 1 | 11 | 0 | 20 | 30 | 10 | 7 | 4 | 1 | 59 | 17 | 0 | 0 | 1 | 9 | 0 | 4 | 0 | 4 | 29 | 0 | 0 | 2 | 13 | 8 | 4 | 3 | 0 | 1 | 11 | 0 | 0 | 0 | 2 | 45 | 15 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 4 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 2 | 5 | 0 | 4 | 0 | 9 | 38 | 51 | 26 | 0 | 2 | 13 | 0 | 10 | 0 | 4 | 0 | 0 | 23 | 0 | 0 | 7 | 23 | 17 | 0 | 0 | 8 | 11 | 6 | 1 | 0 | 17 | 0 | 20 | 0 | 0 | 20 | 4 | 13 | 0 | 0 | 23 | 7 | 20 | 0 | 0 | 21 | 0 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 2 | 0 | 19 | 0 | 0 | 9 | 20 | 10 | 0 | 0 | 10 | 0 | 14 | 0 | 0 | 14 | 14 | 30 | 0 | 0 | 3 | 33 | 30 | 0 | 22 | 24 | 58 | 48 | 0 | 0 | 37 | 0 | 16 | 0 | 0 | 16 | 3 | 6 | 0 | 0 | 24 | 0 | 1 | 0 | 0 | 2 | 6 | 4 | 2 | 5 | 18 | 2 | 54 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 7 | 0 | 4 | 0 | 0 | 42 | 27 | 4 | 0 | 0 | 29 | 19 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 0
2026-03-17 | W17 | 17 | 0 | 0 | 18 | 0 | 22 | 0 | 0 | 19 | 18 | 13 | 2 | 1 | 33 | 0 | 8 | 3 | 3 | 32 | 18 | 334 | 84 | 0 | 230 | 115 | 0 | 0 | 0 | 10 | 4 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 21 | 40 | 22 | 0 | 60 | 26 | 22 | 0 | 0 | 21 | 0 | 24 | 4 | 0 | 45 | 7 | 12 | 1 | 0 | 10 | 8 | 15 | 2 | 0 | 41 | 10 | 49 | 0 | 0 | 63 | 0 | 24 | 0 | 0 | 24 | 24 | 95 | 1 | 0 | 66 | 0 | 111 | 3 | 30 | 3 | 5 | 31 | 5 | 11 | 0 | 1 | 0 | 2 | 4 | 6 | 34 | 4 | 0 | 0 | 8 | 13 | 1 | 0 | 2 | 12 | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 6 | 2 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 3 | 4 | 0 | 2 | 2 | 0 | 4 | 6 | 2 | 2 | 0 | 4 | 0 | 8 | 0 | 2 | 4 | 18 | 9 | 0 | 5 | 22 | 4 | 11 | 0 | 1 | 20 | 4 | 0 | 0 | 0 | 12 | 1 | 0 | 0 | 0 | 17 | 0 | 7 | 3 | 1 | 56 | 0 | 10 | 0 | 9 | 1 | 1 | 11 | 0 | 20 | 30 | 10 | 7 | 4 | 1 | 59 | 17 | 0 | 0 | 1 | 9 | 0 | 4 | 0 | 4 | 29 | 0 | 0 | 2 | 13 | 8 | 4 | 3 | 0 | 1 | 11 | 0 | 0 | 0 | 2 | 45 | 15 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 4 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 2 | 5 | 0 | 4 | 0 | 9 | 38 | 51 | 26 | 0 | 2 | 13 | 0 | 10 | 0 | 4 | 0 | 0 | 23 | 0 | 0 | 7 | 23 | 17 | 0 | 0 | 8 | 11 | 6 | 1 | 0 | 17 | 0 | 20 | 0 | 0 | 20 | 4 | 13 | 0 | 0 | 23 | 7 | 20 | 0 | 0 | 21 | 0 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 2 | 0 | 19 | 0 | 0 | 9 | 20 | 10 | 0 | 0 | 10 | 0 | 14 | 0 | 0 | 14 | 14 | 30 | 0 | 0 | 3 | 33 | 30 | 0 | 22 | 24 | 58 | 48 | 0 | 0 | 37 | 0 | 16 | 0 | 0 | 16 | 3 | 6 | 0 | 0 | 24 | 0 | 1 | 0 | 0 | 2 | 6 | 4 | 2 | 5 | 18 | 2 | 54 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 7 | 0 | 4 | 0 | 0 | 42 | 27 | 4 | 0 | 0 | 29 | 19 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 0
2026-03-18 | W17 | 17 | 0 | 0 | 18 | 0 | 22 | 0 | 0 | 19 | 18 | 13 | 2 | 1 | 33 | 0 | 8 | 3 | 3 | 32 | 18 | 334 | 84 | 0 | 230 | 115 | 0 | 0 | 0 | 10 | 4 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 21 | 40 | 22 | 0 | 60 | 26 | 22 | 0 | 0 | 21 | 0 | 24 | 4 | 0 | 45 | 7 | 12 | 1 | 0 | 10 | 8 | 15 | 2 | 0 | 41 | 10 | 49 | 0 | 0 | 63 | 0 | 24 | 0 | 0 | 24 | 24 | 95 | 1 | 0 | 66 | 0 | 111 | 3 | 30 | 3 | 5 | 31 | 5 | 11 | 0 | 1 | 0 | 2 | 4 | 6 | 34 | 4 | 0 | 0 | 8 | 13 | 1 | 0 | 2 | 12 | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 6 | 2 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 3 | 4 | 0 | 2 | 2 | 0 | 4 | 6 | 2 | 2 | 0 | 4 | 0 | 8 | 0 | 2 | 4 | 18 | 9 | 0 | 5 | 22 | 4 | 11 | 0 | 1 | 20 | 4 | 0 | 0 | 0 | 12 | 1 | 0 | 0 | 0 | 17 | 0 | 7 | 3 | 1 | 56 | 0 | 10 | 0 | 9 | 1 | 1 | 11 | 0 | 20 | 30 | 10 | 7 | 4 | 1 | 59 | 17 | 0 | 0 | 1 | 9 | 0 | 4 | 0 | 4 | 29 | 0 | 0 | 2 | 13 | 8 | 4 | 3 | 0 | 1 | 11 | 0 | 0 | 0 | 2 | 45 | 15 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 4 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 2 | 5 | 0 | 4 | 0 | 9 | 38 | 51 | 26 | 0 | 2 | 13 | 0 | 10 | 0 | 4 | 0 | 0 | 23 | 0 | 0 | 7 | 23 | 17 | 0 | 0 | 8 | 11 | 6 | 1 | 0 | 17 | 0 | 20 | 0 | 0 | 20 | 4 | 13 | 0 | 0 | 23 | 7 | 20 | 0 | 0 | 21 | 0 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 2 | 0 | 19 | 0 | 0 | 9 | 20 | 10 | 0 | 0 | 10 | 0 | 14 | 0 | 0 | 14 | 14 | 30 | 0 | 0 | 3 | 33 | 30 | 0 | 22 | 24 | 58 | 48 | 0 | 0 | 37 | 0 | 16 | 0 | 0 | 16 | 3 | 6 | 0 | 0 | 24 | 0 | 1 | 0 | 0 | 2 | 6 | 4 | 2 | 5 | 18 | 2 | 54 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 7 | 0 | 4 | 0 | 0 | 42 | 27 | 4 | 0 | 0 | 29 | 19 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 0
2026-03-19 | W17 | 17 | 0 | 0 | 18 | 0 | 22 | 0 | 0 | 19 | 18 | 13 | 2 | 1 | 33 | 0 | 8 | 3 | 3 | 32 | 18 | 334 | 84 | 0 | 230 | 115 | 0 | 0 | 0 | 10 | 4 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 21 | 40 | 22 | 0 | 60 | 26 | 22 | 0 | 0 | 21 | 0 | 24 | 4 | 0 | 45 | 7 | 12 | 1 | 0 | 10 | 8 | 15 | 2 | 0 | 41 | 10 | 49 | 0 | 0 | 63 | 0 | 24 | 0 | 0 | 24 | 24 | 95 | 1 | 0 | 66 | 0 | 111 | 3 | 30 | 3 | 5 | 31 | 5 | 11 | 0 | 1 | 0 | 2 | 4 | 6 | 34 | 4 | 0 | 0 | 8 | 13 | 1 | 0 | 2 | 12 | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 6 | 2 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 3 | 4 | 0 | 2 | 2 | 0 | 4 | 6 | 2 | 2 | 0 | 4 | 0 | 8 | 0 | 2 | 4 | 18 | 9 | 0 | 5 | 22 | 4 | 11 | 0 | 1 | 20 | 4 | 0 | 0 | 0 | 12 | 1 | 0 | 0 | 0 | 17 | 0 | 7 | 3 | 1 | 56 | 0 | 10 | 0 | 9 | 1 | 1 | 11 | 0 | 20 | 30 | 10 | 7 | 4 | 1 | 59 | 17 | 0 | 0 | 1 | 9 | 0 | 4 | 0 | 4 | 29 | 0 | 0 | 2 | 13 | 8 | 4 | 3 | 0 | 1 | 11 | 0 | 0 | 0 | 2 | 45 | 15 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 4 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 2 | 5 | 0 | 4 | 0 | 9 | 38 | 51 | 26 | 0 | 2 | 13 | 0 | 10 | 0 | 4 | 0 | 0 | 23 | 0 | 0 | 7 | 23 | 17 | 0 | 0 | 8 | 11 | 6 | 1 | 0 | 17 | 0 | 20 | 0 | 0 | 20 | 4 | 13 | 0 | 0 | 23 | 7 | 20 | 0 | 0 | 21 | 0 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 2 | 0 | 19 | 0 | 0 | 9 | 20 | 10 | 0 | 0 | 10 | 0 | 14 | 0 | 0 | 14 | 14 | 30 | 0 | 0 | 3 | 33 | 30 | 0 | 22 | 24 | 58 | 48 | 0 | 0 | 37 | 0 | 16 | 0 | 0 | 16 | 3 | 6 | 0 | 0 | 24 | 0 | 1 | 0 | 0 | 2 | 6 | 4 | 2 | 5 | 18 | 2 | 54 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 7 | 0 | 4 | 0 | 0 | 42 | 27 | 4 | 0 | 0 | 29 | 19 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 0
2026-03-20 | W17 | 17 | 0 | 0 | 18 | 0 | 22 | 0 | 0 | 19 | 18 | 13 | 2 | 1 | 33 | 0 | 8 | 3 | 3 | 32 | 18 | 334 | 84 | 0 | 230 | 115 | 0 | 0 | 0 | 10 | 4 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 21 | 40 | 22 | 0 | 60 | 26 | 22 | 0 | 0 | 21 | 0 | 24 | 4 | 0 | 45 | 7 | 12 | 1 | 0 | 10 | 8 | 15 | 2 | 0 | 41 | 10 | 49 | 0 | 0 | 63 | 0 | 24 | 0 | 0 | 24 | 24 | 95 | 1 | 0 | 66 | 0 | 111 | 3 | 30 | 3 | 5 | 31 | 5 | 11 | 0 | 1 | 0 | 2 | 4 | 6 | 34 | 4 | 0 | 0 | 8 | 13 | 1 | 0 | 2 | 12 | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 6 | 2 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 3 | 4 | 0 | 2 | 2 | 0 | 4 | 6 | 2 | 2 | 0 | 4 | 0 | 8 | 0 | 2 | 4 | 18 | 9 | 0 | 5 | 22 | 4 | 11 | 0 | 1 | 20 | 4 | 0 | 0 | 0 | 12 | 1 | 0 | 0 | 0 | 17 | 0 | 7 | 3 | 1 | 56 | 0 | 10 | 0 | 9 | 1 | 1 | 11 | 0 | 20 | 30 | 10 | 7 | 4 | 1 | 59 | 17 | 0 | 0 | 1 | 9 | 0 | 4 | 0 | 4 | 29 | 0 | 0 | 2 | 13 | 8 | 4 | 3 | 0 | 1 | 11 | 0 | 0 | 0 | 2 | 45 | 15 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 4 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 2 | 5 | 0 | 4 | 0 | 9 | 38 | 51 | 26 | 0 | 2 | 13 | 0 | 10 | 0 | 4 | 0 | 0 | 23 | 0 | 0 | 7 | 23 | 17 | 0 | 0 | 8 | 11 | 6 | 1 | 0 | 17 | 0 | 20 | 0 | 0 | 20 | 4 | 13 | 0 | 0 | 23 | 7 | 20 | 0 | 0 | 21 | 0 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 2 | 0 | 19 | 0 | 0 | 9 | 20 | 10 | 0 | 0 | 10 | 0 | 14 | 0 | 0 | 14 | 14 | 30 | 0 | 0 | 3 | 33 | 30 | 0 | 22 | 24 | 58 | 48 | 0 | 0 | 37 | 0 | 16 | 0 | 0 | 16 | 3 | 6 | 0 | 0 | 24 | 0 | 1 | 0 | 0 | 2 | 6 | 4 | 2 | 5 | 18 | 2 | 54 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 7 | 0 | 4 | 0 | 0 | 42 | 27 | 4 | 0 | 0 | 29 | 19 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 0
2026-03-23 | W18 | 17 | 0 | 0 | 18 | 0 | 22 | 0 | 0 | 19 | 18 | 13 | 2 | 1 | 33 | 0 | 8 | 3 | 3 | 32 | 18 | 334 | 84 | 0 | 230 | 115 | 0 | 0 | 0 | 10 | 4 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 21 | 40 | 22 | 0 | 60 | 26 | 22 | 0 | 0 | 21 | 0 | 24 | 4 | 0 | 45 | 7 | 12 | 1 | 0 | 10 | 8 | 15 | 2 | 0 | 41 | 10 | 49 | 0 | 0 | 63 | 0 | 24 | 0 | 0 | 24 | 24 | 95 | 1 | 0 | 66 | 0 | 111 | 3 | 30 | 3 | 5 | 31 | 5 | 11 | 0 | 1 | 0 | 2 | 4 | 6 | 34 | 4 | 0 | 0 | 8 | 13 | 1 | 0 | 2 | 12 | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 6 | 2 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 3 | 4 | 0 | 2 | 2 | 0 | 4 | 6 | 2 | 2 | 0 | 4 | 0 | 8 | 0 | 2 | 4 | 18 | 9 | 0 | 5 | 22 | 4 | 11 | 0 | 1 | 20 | 4 | 0 | 0 | 0 | 12 | 1 | 0 | 0 | 0 | 17 | 0 | 7 | 3 | 1 | 56 | 0 | 10 | 0 | 9 | 1 | 1 | 11 | 0 | 20 | 30 | 10 | 7 | 4 | 1 | 59 | 17 | 0 | 0 | 1 | 9 | 0 | 4 | 0 | 4 | 29 | 0 | 0 | 2 | 13 | 8 | 4 | 3 | 0 | 1 | 11 | 0 | 0 | 0 | 2 | 45 | 15 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 4 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 2 | 5 | 0 | 4 | 0 | 9 | 38 | 51 | 26 | 0 | 2 | 13 | 0 | 10 | 0 | 4 | 0 | 0 | 23 | 0 | 0 | 7 | 23 | 17 | 0 | 0 | 8 | 11 | 6 | 1 | 0 | 17 | 0 | 20 | 0 | 0 | 20 | 4 | 13 | 0 | 0 | 23 | 7 | 20 | 0 | 0 | 21 | 0 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 2 | 0 | 19 | 0 | 0 | 9 | 20 | 10 | 0 | 0 | 10 | 0 | 14 | 0 | 0 | 14 | 14 | 30 | 0 | 0 | 3 | 33 | 30 | 0 | 22 | 24 | 58 | 48 | 0 | 0 | 37 | 0 | 16 | 0 | 0 | 16 | 3 | 6 | 0 | 0 | 24 | 0 | 1 | 0 | 0 | 2 | 6 | 4 | 2 | 5 | 18 | 2 | 54 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 7 | 0 | 4 | 0 | 0 | 42 | 27 | 4 | 0 | 0 | 29 | 19 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 0
2026-03-24 | W18 | 17 | 0 | 0 | 18 | 0 | 22 | 0 | 0 | 19 | 18 | 13 | 2 | 1 | 33 | 0 | 8 | 3 | 3 | 32 | 18 | 334 | 84 | 0 | 230 | 115 | 0 | 0 | 0 | 10 | 4 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 21 | 40 | 22 | 0 | 60 | 26 | 22 | 0 | 0 | 21 | 0 | 24 | 4 | 0 | 45 | 7 | 12 | 1 | 0 | 10 | 8 | 15 | 2 | 0 | 41 | 10 | 49 | 0 | 0 | 63 | 0 | 24 | 0 | 0 | 24 | 24 | 95 | 1 | 0 | 66 | 0 | 111 | 3 | 30 | 3 | 5 | 31 | 5 | 11 | 0 | 1 | 0 | 2 | 4 | 6 | 34 | 4 | 0 | 0 | 8 | 13 | 1 | 0 | 2 | 12 | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 6 | 2 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 3 | 4 | 0 | 2 | 2 | 0 | 4 | 6 | 2 | 2 | 0 | 4 | 0 | 8 | 0 | 2 | 4 | 18 | 9 | 0 | 5 | 22 | 4 | 11 | 0 | 1 | 20 | 4 | 0 | 0 | 0 | 12 | 1 | 0 | 0 | 0 | 17 | 0 | 7 | 3 | 1 | 56 | 0 | 10 | 0 | 9 | 1 | 1 | 11 | 0 | 20 | 30 | 10 | 7 | 4 | 1 | 59 | 17 | 0 | 0 | 1 | 9 | 0 | 4 | 0 | 4 | 29 | 0 | 0 | 2 | 13 | 8 | 4 | 3 | 0 | 1 | 11 | 0 | 0 | 0 | 2 | 45 | 15 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 4 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 2 | 5 | 0 | 4 | 0 | 9 | 38 | 51 | 26 | 0 | 2 | 13 | 0 | 10 | 0 | 4 | 0 | 0 | 23 | 0 | 0 | 7 | 23 | 17 | 0 | 0 | 8 | 11 | 6 | 1 | 0 | 17 | 0 | 20 | 0 | 0 | 20 | 4 | 13 | 0 | 0 | 23 | 7 | 20 | 0 | 0 | 21 | 0 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 2 | 0 | 19 | 0 | 0 | 9 | 20 | 10 | 0 | 0 | 10 | 0 | 14 | 0 | 0 | 14 | 14 | 30 | 0 | 0 | 3 | 33 | 30 | 0 | 22 | 24 | 58 | 48 | 0 | 0 | 37 | 0 | 16 | 0 | 0 | 16 | 3 | 6 | 0 | 0 | 24 | 0 | 1 | 0 | 0 | 2 | 6 | 4 | 2 | 5 | 18 | 2 | 54 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 7 | 0 | 4 | 0 | 0 | 42 | 27 | 4 | 0 | 0 | 29 | 19 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 0
2026-03-25 | W18 | 17 | 0 | 0 | 18 | 0 | 22 | 0 | 0 | 19 | 18 | 13 | 2 | 1 | 33 | 0 | 8 | 3 | 3 | 32 | 18 | 334 | 84 | 0 | 230 | 115 | 0 | 0 | 0 | 10 | 4 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 21 | 40 | 22 | 0 | 60 | 26 | 22 | 0 | 0 | 21 | 0 | 24 | 4 | 0 | 45 | 7 | 12 | 1 | 0 | 10 | 8 | 15 | 2 | 0 | 41 | 10 | 49 | 0 | 0 | 63 | 0 | 24 | 0 | 0 | 24 | 24 | 95 | 1 | 0 | 66 | 0 | 111 | 3 | 30 | 3 | 5 | 31 | 5 | 11 | 0 | 1 | 0 | 2 | 4 | 6 | 34 | 4 | 0 | 0 | 8 | 13 | 1 | 0 | 2 | 12 | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 6 | 2 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 3 | 4 | 0 | 2 | 2 | 0 | 4 | 6 | 2 | 2 | 0 | 4 | 0 | 8 | 0 | 2 | 4 | 18 | 9 | 0 | 5 | 22 | 4 | 11 | 0 | 1 | 20 | 4 | 0 | 0 | 0 | 12 | 1 | 0 | 0 | 0 | 17 | 0 | 7 | 3 | 1 | 56 | 0 | 10 | 0 | 9 | 1 | 1 | 11 | 0 | 20 | 30 | 10 | 7 | 4 | 1 | 59 | 17 | 0 | 0 | 1 | 9 | 0 | 4 | 0 | 4 | 29 | 0 | 0 | 2 | 13 | 8 | 4 | 3 | 0 | 1 | 11 | 0 | 0 | 0 | 2 | 45 | 15 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 4 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 2 | 5 | 0 | 4 | 0 | 9 | 38 | 51 | 26 | 0 | 2 | 13 | 0 | 10 | 0 | 4 | 0 | 0 | 23 | 0 | 0 | 7 | 23 | 17 | 0 | 0 | 8 | 11 | 6 | 1 | 0 | 17 | 0 | 20 | 0 | 0 | 20 | 4 | 13 | 0 | 0 | 23 | 7 | 20 | 0 | 0 | 21 | 0 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 2 | 0 | 19 | 0 | 0 | 9 | 20 | 10 | 0 | 0 | 10 | 0 | 14 | 0 | 0 | 14 | 14 | 30 | 0 | 0 | 3 | 33 | 30 | 0 | 22 | 24 | 58 | 48 | 0 | 0 | 37 | 0 | 16 | 0 | 0 | 16 | 3 | 6 | 0 | 0 | 24 | 0 | 1 | 0 | 0 | 2 | 6 | 4 | 2 | 5 | 18 | 2 | 54 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 7 | 0 | 4 | 0 | 0 | 42 | 27 | 4 | 0 | 0 | 29 | 19 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 0
2026-03-26 | W18 | 17 | 0 | 0 | 18 | 0 | 22 | 0 | 0 | 19 | 18 | 13 | 2 | 1 | 33 | 0 | 8 | 3 | 3 | 32 | 18 | 334 | 84 | 0 | 230 | 115 | 0 | 0 | 0 | 10 | 4 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 21 | 40 | 22 | 0 | 60 | 26 | 22 | 0 | 0 | 21 | 0 | 24 | 4 | 0 | 45 | 7 | 12 | 1 | 0 | 10 | 8 | 15 | 2 | 0 | 41 | 10 | 49 | 0 | 0 | 63 | 0 | 24 | 0 | 0 | 24 | 24 | 95 | 1 | 0 | 66 | 0 | 111 | 3 | 30 | 3 | 5 | 31 | 5 | 11 | 0 | 1 | 0 | 2 | 4 | 6 | 34 | 4 | 0 | 0 | 8 | 13 | 1 | 0 | 2 | 12 | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 6 | 2 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 3 | 4 | 0 | 2 | 2 | 0 | 4 | 6 | 2 | 2 | 0 | 4 | 0 | 8 | 0 | 2 | 4 | 18 | 9 | 0 | 5 | 22 | 4 | 11 | 0 | 1 | 20 | 4 | 0 | 0 | 0 | 12 | 1 | 0 | 0 | 0 | 17 | 0 | 7 | 3 | 1 | 56 | 0 | 10 | 0 | 9 | 1 | 1 | 11 | 0 | 20 | 30 | 10 | 7 | 4 | 1 | 59 | 17 | 0 | 0 | 1 | 9 | 0 | 4 | 0 | 4 | 29 | 0 | 0 | 2 | 13 | 8 | 4 | 3 | 0 | 1 | 11 | 0 | 0 | 0 | 2 | 45 | 15 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 4 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 2 | 5 | 0 | 4 | 0 | 9 | 38 | 51 | 26 | 0 | 2 | 13 | 0 | 10 | 0 | 4 | 0 | 0 | 23 | 0 | 0 | 7 | 23 | 17 | 0 | 0 | 8 | 11 | 6 | 1 | 0 | 17 | 0 | 20 | 0 | 0 | 20 | 4 | 13 | 0 | 0 | 23 | 7 | 20 | 0 | 0 | 21 | 0 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 2 | 0 | 19 | 0 | 0 | 9 | 20 | 10 | 0 | 0 | 10 | 0 | 14 | 0 | 0 | 14 | 14 | 30 | 0 | 0 | 3 | 33 | 30 | 0 | 22 | 24 | 58 | 48 | 0 | 0 | 37 | 0 | 16 | 0 | 0 | 16 | 3 | 6 | 0 | 0 | 24 | 0 | 1 | 0 | 0 | 2 | 6 | 4 | 2 | 5 | 18 | 2 | 54 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 7 | 0 | 4 | 0 | 0 | 42 | 27 | 4 | 0 | 0 | 29 | 19 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 0
2026-03-27 | W18 | 17 | 0 | 0 | 18 | 0 | 22 | 0 | 0 | 19 | 18 | 13 | 2 | 1 | 33 | 0 | 8 | 3 | 3 | 32 | 18 | 334 | 84 | 0 | 230 | 115 | 0 | 0 | 0 | 10 | 4 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 21 | 40 | 22 | 0 | 60 | 26 | 22 | 0 | 0 | 21 | 0 | 24 | 4 | 0 | 45 | 7 | 12 | 1 | 0 | 10 | 8 | 15 | 2 | 0 | 41 | 10 | 49 | 0 | 0 | 63 | 0 | 24 | 0 | 0 | 24 | 24 | 95 | 1 | 0 | 66 | 0 | 111 | 3 | 30 | 3 | 5 | 31 | 5 | 11 | 0 | 1 | 0 | 2 | 4 | 6 | 34 | 4 | 0 | 0 | 8 | 13 | 1 | 0 | 2 | 12 | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 6 | 2 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 3 | 4 | 0 | 2 | 2 | 0 | 4 | 6 | 2 | 2 | 0 | 4 | 0 | 8 | 0 | 2 | 4 | 18 | 9 | 0 | 5 | 22 | 4 | 11 | 0 | 1 | 20 | 4 | 0 | 0 | 0 | 12 | 1 | 0 | 0 | 0 | 17 | 0 | 7 | 3 | 1 | 56 | 0 | 10 | 0 | 9 | 1 | 1 | 11 | 0 | 20 | 30 | 10 | 7 | 4 | 1 | 59 | 17 | 0 | 0 | 1 | 9 | 0 | 4 | 0 | 4 | 29 | 0 | 0 | 2 | 13 | 8 | 4 | 3 | 0 | 1 | 11 | 0 | 0 | 0 | 2 | 45 | 15 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 4 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 2 | 5 | 0 | 4 | 0 | 9 | 38 | 51 | 26 | 0 | 2 | 13 | 0 | 10 | 0 | 4 | 0 | 0 | 23 | 0 | 0 | 7 | 23 | 17 | 0 | 0 | 8 | 11 | 6 | 1 | 0 | 17 | 0 | 20 | 0 | 0 | 20 | 4 | 13 | 0 | 0 | 23 | 7 | 20 | 0 | 0 | 21 | 0 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 2 | 0 | 19 | 0 | 0 | 9 | 20 | 10 | 0 | 0 | 10 | 0 | 14 | 0 | 0 | 14 | 14 | 30 | 0 | 0 | 3 | 33 | 30 | 0 | 22 | 24 | 58 | 48 | 0 | 0 | 37 | 0 | 16 | 0 | 0 | 16 | 3 | 6 | 0 | 0 | 24 | 0 | 1 | 0 | 0 | 2 | 6 | 4 | 2 | 5 | 18 | 2 | 54 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 7 | 0 | 4 | 0 | 0 | 42 | 27 | 4 | 0 | 0 | 29 | 19 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 0
2026-03-28 | W19 | 17 | 0 | 0 | 18 | 0 | 22 | 0 | 0 | 19 | 18 | 13 | 2 | 1 | 33 | 0 | 8 | 3 | 3 | 32 | 18 | 334 | 84 | 0 | 230 | 115 | 0 | 0 | 0 | 10 | 4 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 21 | 40 | 22 | 0 | 60 | 26 | 22 | 0 | 0 | 21 | 0 | 24 | 4 | 0 | 45 | 7 | 12 | 1 | 0 | 10 | 8 | 15 | 2 | 0 | 41 | 10 | 49 | 0 | 0 | 63 | 0 | 24 | 0 | 0 | 24 | 24 | 95 | 1 | 0 | 66 | 0 | 111 | 3 | 30 | 3 | 5 | 31 | 5 | 11 | 0 | 1 | 0 | 2 | 4 | 6 | 34 | 4 | 0 | 0 | 8 | 13 | 1 | 0 | 2 | 12 | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 6 | 2 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 3 | 4 | 0 | 2 | 2 | 0 | 4 | 6 | 2 | 2 | 0 | 4 | 0 | 8 | 0 | 2 | 4 | 18 | 9 | 0 | 5 | 22 | 4 | 11 | 0 | 1 | 20 | 4 | 0 | 0 | 0 | 12 | 1 | 0 | 0 | 0 | 17 | 0 | 7 | 3 | 1 | 56 | 0 | 10 | 0 | 9 | 1 | 1 | 11 | 0 | 20 | 30 | 10 | 7 | 4 | 1 | 59 | 17 | 0 | 0 | 1 | 9 | 0 | 4 | 0 | 4 | 29 | 0 | 0 | 2 | 13 | 8 | 4 | 3 | 0 | 1 | 11 | 0 | 0 | 0 | 2 | 45 | 15 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 4 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 2 | 5 | 0 | 4 | 0 | 9 | 38 | 51 | 26 | 0 | 2 | 13 | 0 | 10 | 0 | 4 | 0 | 0 | 23 | 0 | 0 | 7 | 23 | 17 | 0 | 0 | 8 | 11 | 6 | 1 | 0 | 17 | 0 | 20 | 0 | 0 | 20 | 4 | 13 | 0 | 0 | 23 | 7 | 20 | 0 | 0 | 21 | 0 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 2 | 0 | 19 | 0 | 0 | 9 | 20 | 10 | 0 | 0 | 10 | 0 | 14 | 0 | 0 | 14 | 14 | 30 | 0 | 0 | 3 | 33 | 30 | 0 | 22 | 24 | 58 | 48 | 0 | 0 | 37 | 0 | 16 | 0 | 0 | 16 | 3 | 6 | 0 | 0 | 24 | 0 | 1 | 0 | 0 | 2 | 6 | 4 | 2 | 5 | 18 | 2 | 54 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 7 | 0 | 4 | 0 | 0 | 42 | 27 | 4 | 0 | 0 | 29 | 19 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 0
2026-03-30 | W19 | 17 | 0 | 0 | 18 | 0 | 22 | 0 | 0 | 19 | 18 | 13 | 2 | 1 | 33 | 0 | 8 | 3 | 3 | 32 | 18 | 334 | 84 | 0 | 230 | 115 | 0 | 0 | 0 | 10 | 4 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 21 | 40 | 22 | 0 | 60 | 26 | 22 | 0 | 0 | 21 | 0 | 24 | 4 | 0 | 45 | 7 | 12 | 1 | 0 | 10 | 8 | 15 | 2 | 0 | 41 | 10 | 49 | 0 | 0 | 63 | 0 | 24 | 0 | 0 | 24 | 24 | 95 | 1 | 0 | 66 | 0 | 111 | 3 | 30 | 3 | 5 | 31 | 5 | 11 | 0 | 1 | 0 | 2 | 4 | 6 | 34 | 4 | 0 | 0 | 8 | 13 | 1 | 0 | 2 | 12 | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 6 | 2 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 3 | 4 | 0 | 2 | 2 | 0 | 4 | 6 | 2 | 2 | 0 | 4 | 0 | 8 | 0 | 2 | 4 | 18 | 9 | 0 | 5 | 22 | 4 | 11 | 0 | 1 | 20 | 4 | 0 | 0 | 0 | 12 | 1 | 0 | 0 | 0 | 17 | 0 | 7 | 3 | 1 | 56 | 0 | 10 | 0 | 9 | 1 | 1 | 11 | 0 | 20 | 30 | 10 | 7 | 4 | 1 | 59 | 17 | 0 | 0 | 1 | 9 | 0 | 4 | 0 | 4 | 29 | 0 | 0 | 2 | 13 | 8 | 4 | 3 | 0 | 1 | 11 | 0 | 0 | 0 | 2 | 45 | 15 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 4 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 2 | 5 | 0 | 4 | 0 | 9 | 38 | 51 | 26 | 0 | 2 | 13 | 0 | 10 | 0 | 4 | 0 | 0 | 23 | 0 | 0 | 7 | 23 | 17 | 0 | 0 | 8 | 11 | 6 | 1 | 0 | 17 | 0 | 20 | 0 | 0 | 20 | 4 | 13 | 0 | 0 | 23 | 7 | 20 | 0 | 0 | 21 | 0 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 2 | 0 | 19 | 0 | 0 | 9 | 20 | 10 | 0 | 0 | 10 | 0 | 14 | 0 | 0 | 14 | 14 | 30 | 0 | 0 | 3 | 33 | 30 | 0 | 22 | 24 | 58 | 48 | 0 | 0 | 37 | 0 | 16 | 0 | 0 | 16 | 3 | 6 | 0 | 0 | 24 | 0 | 1 | 0 | 0 | 2 | 6 | 4 | 2 | 5 | 18 | 2 | 54 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 7 | 0 | 4 | 0 | 0 | 42 | 27 | 4 | 0 | 0 | 29 | 19 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 0
2026-04-01 | W19 | 17 | 0 | 0 | 18 | 0 | 22 | 0 | 0 | 19 | 18 | 13 | 2 | 1 | 33 | 0 | 8 | 3 | 3 | 32 | 18 | 334 | 84 | 0 | 230 | 115 | 0 | 0 | 0 | 10 | 4 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 21 | 40 | 22 | 0 | 60 | 26 | 22 | 0 | 0 | 21 | 0 | 24 | 4 | 0 | 45 | 7 | 12 | 1 | 0 | 10 | 8 | 15 | 2 | 0 | 41 | 10 | 49 | 0 | 0 | 63 | 0 | 24 | 0 | 0 | 24 | 24 | 95 | 1 | 0 | 66 | 0 | 111 | 3 | 30 | 3 | 5 | 31 | 5 | 11 | 0 | 1 | 0 | 2 | 4 | 6 | 34 | 4 | 0 | 0 | 8 | 13 | 1 | 0 | 2 | 12 | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 6 | 2 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 3 | 4 | 0 | 2 | 2 | 0 | 4 | 6 | 2 | 2 | 0 | 4 | 0 | 8 | 0 | 2 | 4 | 18 | 9 | 0 | 5 | 22 | 4 | 11 | 0 | 1 | 20 | 4 | 0 | 0 | 0 | 12 | 1 | 0 | 0 | 0 | 17 | 0 | 7 | 3 | 1 | 56 | 0 | 10 | 0 | 9 | 1 | 1 | 11 | 0 | 20 | 30 | 10 | 7 | 4 | 1 | 59 | 17 | 0 | 0 | 1 | 9 | 0 | 4 | 0 | 4 | 29 | 0 | 0 | 2 | 13 | 8 | 4 | 3 | 0 | 1 | 11 | 0 | 0 | 0 | 2 | 45 | 15 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 4 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 2 | 5 | 0 | 4 | 0 | 9 | 38 | 51 | 26 | 0 | 2 | 13 | 0 | 10 | 0 | 4 | 0 | 0 | 23 | 0 | 0 | 7 | 23 | 17 | 0 | 0 | 8 | 11 | 6 | 1 | 0 | 17 | 0 | 20 | 0 | 0 | 20 | 4 | 13 | 0 | 0 | 23 | 7 | 20 | 0 | 0 | 21 | 0 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 2 | 0 | 19 | 0 | 0 | 9 | 20 | 10 | 0 | 0 | 10 | 0 | 14 | 0 | 0 | 14 | 14 | 30 | 0 | 0 | 3 | 33 | 30 | 0 | 22 | 24 | 58 | 48 | 0 | 0 | 37 | 0 | 16 | 0 | 0 | 16 | 3 | 6 | 0 | 0 | 24 | 0 | 1 | 0 | 0 | 2 | 6 | 4 | 2 | 5 | 18 | 2 | 54 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 7 | 0 | 4 | 0 | 0 | 42 | 27 | 4 | 0 | 0 | 29 | 19 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 0
2026-04-02 | W19 | 17 | 0 | 0 | 18 | 0 | 22 | 0 | 0 | 19 | 18 | 13 | 2 | 1 | 33 | 0 | 8 | 3 | 3 | 32 | 18 | 334 | 84 | 0 | 230 | 115 | 0 | 0 | 0 | 10 | 4 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 21 | 40 | 22 | 0 | 60 | 26 | 22 | 0 | 0 | 21 | 0 | 24 | 4 | 0 | 45 | 7 | 12 | 1 | 0 | 10 | 8 | 15 | 2 | 0 | 41 | 10 | 49 | 0 | 0 | 63 | 0 | 24 | 0 | 0 | 24 | 24 | 95 | 1 | 0 | 66 | 0 | 111 | 3 | 30 | 3 | 5 | 31 | 5 | 11 | 0 | 1 | 0 | 2 | 4 | 6 | 34 | 4 | 0 | 0 | 8 | 13 | 1 | 0 | 2 | 12 | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 6 | 2 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 3 | 4 | 0 | 2 | 2 | 0 | 4 | 6 | 2 | 2 | 0 | 4 | 0 | 8 | 0 | 2 | 4 | 18 | 9 | 0 | 5 | 22 | 4 | 11 | 0 | 1 | 20 | 4 | 0 | 0 | 0 | 12 | 1 | 0 | 0 | 0 | 17 | 0 | 7 | 3 | 1 | 56 | 0 | 10 | 0 | 9 | 1 | 1 | 11 | 0 | 20 | 30 | 10 | 7 | 4 | 1 | 59 | 17 | 0 | 0 | 1 | 9 | 0 | 4 | 0 | 4 | 29 | 0 | 0 | 2 | 13 | 8 | 4 | 3 | 0 | 1 | 11 | 0 | 0 | 0 | 2 | 45 | 15 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 4 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 2 | 5 | 0 | 4 | 0 | 9 | 38 | 51 | 26 | 0 | 2 | 13 | 0 | 10 | 0 | 4 | 0 | 0 | 23 | 0 | 0 | 7 | 23 | 17 | 0 | 0 | 8 | 11 | 6 | 1 | 0 | 17 | 0 | 20 | 0 | 0 | 20 | 4 | 13 | 0 | 0 | 23 | 7 | 20 | 0 | 0 | 21 | 0 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 2 | 0 | 19 | 0 | 0 | 9 | 20 | 10 | 0 | 0 | 10 | 0 | 14 | 0 | 0 | 14 | 14 | 30 | 0 | 0 | 3 | 33 | 30 | 0 | 22 | 24 | 58 | 48 | 0 | 0 | 37 | 0 | 16 | 0 | 0 | 16 | 3 | 6 | 0 | 0 | 24 | 0 | 1 | 0 | 0 | 2 | 6 | 4 | 2 | 5 | 18 | 2 | 54 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 7 | 0 | 4 | 0 | 0 | 42 | 27 | 4 | 0 | 0 | 29 | 19 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 0