## 1_EXECUTIVE_SUMMARY
Metric | Value | Status
PRODUCTION HEALTH
Total Bottlenecks Detected | 3 | 🟢 OK
Weeks with Bottlenecks | 2
Critical Path Resources | BIG_LINE, SMALL_LINE
ORDER FULFILLMENT
Total Orders | 303
Critical Risk Orders | 6 | 🔴 Action Required
High Risk Orders | 0 | 🟢 OK
Total At-Risk Quantity | 16
At-Risk Customers | 1
RECOMMENDATIONS
Critical Priority Actions | 1 | 🔴 Immediate
High Priority Actions | 3 | 🟡 This Week
Total Recommendations | 4

## 2_BOTTLENECK_ANALYSIS
Week | Resource | Operation | Utilization_% | Capacity | Used | Overflow | Unit | Severity | Parts_Affected
W1 | Big Line Casting | Casting | 96.8 | 129.6 | 125.5 | 0 | hours | High
W2 | Small Line Casting | Casting | 96.1 | 129.6 | 124.5 | 0 | hours | High
W1 | Small Line Casting | Casting | 90.9 | 129.6 | 117.8 | 0 | hours | Medium

## 3_BOTTLENECK_SUMMARY
Resource | Total_Overflow | Is_Critical
BIG_LINE | 0 | TRUE
SMALL_LINE | 0 | TRUE

## 4_ORDER_RISK
Order_ID | Part | Customer | Ordered_Qty | Delivered_Qty | Unmet_Qty | Due_Week | Weeks_Until_Due | Fulfillment_% | Risk_Level | Risk_Factors
2526100367 | UBC-035 | Unknown | 60 | 54 | 6 | W1 | 0 | 90 | Critical | Partial fulfillment (90%); Already past due
2526200576 | UBC-064 | Unknown | 3 | 2 | 1 | W1 | 0 | 66.7 | Critical | Partial fulfillment (67%); Already past due
2526201681 | UBC-046 | Unknown | 8 | 7 | 1 | W1 | 0 | 87.5 | Critical | Partial fulfillment (88%); Already past due
2526203270 | DGC-011 | Unknown | 4 | 3 | 1 | W1 | 0 | 75 | Critical | Partial fulfillment (75%); Already past due
2526203434 | UBC-064 | Unknown | 2 | 1 | 1 | W1 | 0 | 50 | Critical | Partial fulfillment (50%); Already past due
2526500115 | KBS-010 | Unknown | 16 | 10 | 6 | W1 | 0 | 62.5 | Critical | Partial fulfillment (62%); Already past due
2526203276 | DGC-011 | Unknown | 4 | 3 | 1 | W5 | 4 | 75 | Medium | Partial fulfillment (75%)
2526500118 | KBS-010 | Unknown | 4 | 3 | 1 | W5 | 4 | 75 | Medium | Partial fulfillment (75%)
2526203554 | DGC-011 | Unknown | 6 | 5 | 1 | W7 | 6 | 83.3 | Medium | Partial fulfillment (83%)
2526203555 | DGC-011 | Unknown | 6 | 5 | 1 | W8 | 7 | 83.3 | Medium | Partial fulfillment (83%)
2526203556 | DGC-011 | Unknown | 5 | 4 | 1 | W9 | 8 | 80 | Medium | Partial fulfillment (80%)
2526100558 | ARM-004-N | Unknown | 4 | 4 | 0 | W1 | 0 | 100 | Low | Fully fulfilled
2526100559 | ARM-007 | Unknown | 1 | 1 | 0 | W1 | 0 | 100 | Low | Fully fulfilled
2526100560 | ARM-007 | Unknown | 2 | 2 | 0 | W1 | 0 | 100 | Low | Fully fulfilled
2526100561 | ARM-004-N | Unknown | 1 | 1 | 0 | W1 | 0 | 100 | Low | Fully fulfilled
2526100562 | ARM-004-N | Unknown | 5 | 5 | 0 | W1 | 0 | 100 | Low | Fully fulfilled
2526100563 | ARM-004-N | Unknown | 7 | 7 | 0 | W1 | 0 | 100 | Low | Fully fulfilled
2526100564 | ARM-007 | Unknown | 2 | 2 | 0 | W1 | 0 | 100 | Low | Fully fulfilled
2526100565 | ARM-007 | Unknown | 4 | 4 | 0 | W1 | 0 | 100 | Low | Fully fulfilled
2526100566 | ARM-007 | Unknown | 4 | 4 | 0 | W1 | 0 | 100 | Low | Fully fulfilled
2526100569 | ARM-007 | Unknown | 1 | 1 | 0 | W1 | 0 | 100 | Low | Fully fulfilled
2526200576 | UBC-062 | Unknown | 2 | 2 | 0 | W1 | 0 | 100 | Low | Fully fulfilled
2526200576 | UBC-063 | Unknown | 2 | 2 | 0 | W1 | 0 | 100 | Low | Fully fulfilled
2526201015 | ATT-001 | Unknown | 8 | 8 | 0 | W1 | 0 | 100 | Low | Fully fulfilled
2526201015 | ATT-002 | Unknown | 8 | 8 | 0 | W1 | 0 | 100 | Low | Fully fulfilled
2526201611 | TAS-GN-008 | Unknown | 3 | 3 | 0 | W1 | 0 | 100 | Low | Fully fulfilled
2526201804 | TAS-GN-008 | Unknown | 2 | 2 | 0 | W1 | 0 | 100 | Low | Fully fulfilled
2526202458 | LKK-03 | Unknown | 4 | 4 | 0 | W1 | 0 | 100 | Low | Fully fulfilled
2526202458 | LKK-04 | Unknown | 4 | 4 | 0 | W1 | 0 | 100 | Low | Fully fulfilled
2526202458 | LKK-05 | Unknown | 4 | 4 | 0 | W1 | 0 | 100 | Low | Fully fulfilled
2526202458 | LKK-06 | Unknown | 4 | 4 | 0 | W1 | 0 | 100 | Low | Fully fulfilled
2526202458 | LKK-01 | Unknown | 4 | 4 | 0 | W1 | 0 | 100 | Low | Fully fulfilled
2526202458 | LKK-02 | Unknown | 4 | 4 | 0 | W1 | 0 | 100 | Low | Fully fulfilled
2526202459 | LKK-10 | Unknown | 10 | 10 | 0 | W1 | 0 | 100 | Low | Fully fulfilled
2526202459 | LKK-11 | Unknown | 10 | 10 | 0 | W1 | 0 | 100 | Low | Fully fulfilled
2526202459 | LKK-12 | Unknown | 10 | 10 | 0 | W1 | 0 | 100 | Low | Fully fulfilled
2526202474 | MCB-HYG-026 | Unknown | 6 | 6 | 0 | W1 | 0 | 100 | Low | Fully fulfilled
2526202705 | MCB-HYG-016 | Unknown | 5 | 5 | 0 | W1 | 0 | 100 | Low | Fully fulfilled
2526202706 | MCB-HYG-016 | Unknown | 5 | 5 | 0 | W1 | 0 | 100 | Low | Fully fulfilled
2526202707 | MCB-HYG-016 | Unknown | 5 | 5 | 0 | W1 | 0 | 100 | Low | Fully fulfilled
2526202708 | MCB-HYG-016 | Unknown | 5 | 5 | 0 | W1 | 0 | 100 | Low | Fully fulfilled
2526202709 | MCB-HYG-026 | Unknown | 6 | 6 | 0 | W1 | 0 | 100 | Low | Fully fulfilled
2526202713 | TAS-GN-004 | Unknown | 2 | 2 | 0 | W1 | 0 | 100 | Low | Fully fulfilled
2526202788 | MCB-HYG-023 | Unknown | 6 | 6 | 0 | W1 | 0 | 100 | Low | Fully fulfilled
2526202810 | MCB-JLG-046 | Unknown | 3 | 3 | 0 | W1 | 0 | 100 | Low | Fully fulfilled
2526202810 | MCB-JLG-046 | Unknown | 1 | 1 | 0 | W1 | 0 | 100 | Low | Fully fulfilled
2526202818 | MCB-HYG-023 | Unknown | 6 | 6 | 0 | W1 | 0 | 100 | Low | Fully fulfilled
2526202929 | TAS-GN-008 | Unknown | 1 | 1 | 0 | W1 | 0 | 100 | Low | Fully fulfilled
2526202939 | NMS-V-004 | Unknown | 5 | 5 | 0 | W1 | 0 | 100 | Low | Fully fulfilled
2526202941 | UBC-020 | Unknown | 2 | 2 | 0 | W1 | 0 | 100 | Low | Fully fulfilled
2526202943 | UBC-022 | Unknown | 4 | 4 | 0 | W1 | 0 | 100 | Low | Fully fulfilled
2526202943 | UBC-022 | Unknown | 4 | 4 | 0 | W1 | 0 | 100 | Low | Fully fulfilled
2526202947 | UBC-020 | Unknown | 4 | 4 | 0 | W1 | 0 | 100 | Low | Fully fulfilled
2526202947 | UBC-050 | Unknown | 8 | 8 | 0 | W1 | 0 | 100 | Low | Fully fulfilled
2526202947 | UBC-051 | Unknown | 8 | 8 | 0 | W1 | 0 | 100 | Low | Fully fulfilled
2526202952 | ATT-001 | Unknown | 8 | 8 | 0 | W1 | 0 | 100 | Low | Fully fulfilled
2526202952 | ATT-002 | Unknown | 8 | 8 | 0 | W1 | 0 | 100 | Low | Fully fulfilled
2526202953 | ATT-001 | Unknown | 8 | 8 | 0 | W1 | 0 | 100 | Low | Fully fulfilled
2526202953 | ATT-002 | Unknown | 8 | 8 | 0 | W1 | 0 | 100 | Low | Fully fulfilled
2526202970 | DGC-001 | Unknown | 56 | 56 | 0 | W1 | 0 | 100 | Low | Fully fulfilled
2526202971 | DGC-001 | Unknown | 56 | 56 | 0 | W1 | 0 | 100 | Low | Fully fulfilled
2526203022 | UBC-020 | Unknown | 8 | 8 | 0 | W1 | 0 | 100 | Low | Fully fulfilled
2526203022 | UBC-022 | Unknown | 4 | 4 | 0 | W1 | 0 | 100 | Low | Fully fulfilled
2526203022 | UBC-050 | Unknown | 4 | 4 | 0 | W1 | 0 | 100 | Low | Fully fulfilled
2526203022 | UBC-051 | Unknown | 4 | 4 | 0 | W1 | 0 | 100 | Low | Fully fulfilled
2526203022 | UBC-022 | Unknown | 4 | 4 | 0 | W1 | 0 | 100 | Low | Fully fulfilled
2526203022 | UBC-020 | Unknown | 8 | 8 | 0 | W1 | 0 | 100 | Low | Fully fulfilled
2526203023 | UBC-018 | Unknown | 48 | 48 | 0 | W1 | 0 | 100 | Low | Fully fulfilled
2526203038 | MCB-009 | Unknown | 12 | 12 | 0 | W1 | 0 | 100 | Low | Fully fulfilled
2526203039 | MCB-JLG-020 | Unknown | 4 | 4 | 0 | W1 | 0 | 100 | Low | Fully fulfilled
2526203057 | MCB-JLG-047 | Unknown | 11 | 11 | 0 | W1 | 0 | 100 | Low | Fully fulfilled
2526203090 | NMS-V-004 | Unknown | 5 | 5 | 0 | W1 | 0 | 100 | Low | Fully fulfilled
2526203091 | NMS-V-004 | Unknown | 5 | 5 | 0 | W1 | 0 | 100 | Low | Fully fulfilled
2526203092 | NMS-H-001 | Unknown | 13 | 13 | 0 | W1 | 0 | 100 | Low | Fully fulfilled
2526203093 | NMS-H-001 | Unknown | 13 | 13 | 0 | W1 | 0 | 100 | Low | Fully fulfilled
2526203094 | NMS-V-003 | Unknown | 10 | 10 | 0 | W1 | 0 | 100 | Low | Fully fulfilled
2526203139 | MCB-009 | Unknown | 12 | 12 | 0 | W1 | 0 | 100 | Low | Fully fulfilled
2526203141 | MCB-JLG-047 | Unknown | 11 | 11 | 0 | W1 | 0 | 100 | Low | Fully fulfilled
2526203143 | MCB-JLG-020 | Unknown | 4 | 4 | 0 | W1 | 0 | 100 | Low | Fully fulfilled
2526203269 | DGC-001 | Unknown | 56 | 56 | 0 | W1 | 0 | 100 | Low | Fully fulfilled
2526203270 | DGC-001 | Unknown | 34 | 34 | 0 | W1 | 0 | 100 | Low | Fully fulfilled
2526203279 | MCB-JLG-014 | Unknown | 6 | 6 | 0 | W1 | 0 | 100 | Low | Fully fulfilled
2526203284 | MCB-007 | Unknown | 4 | 4 | 0 | W1 | 0 | 100 | Low | Fully fulfilled
2526203285 | MCB-007 | Unknown | 4 | 4 | 0 | W1 | 0 | 100 | Low | Fully fulfilled
2526203286 | MCB-007 | Unknown | 4 | 4 | 0 | W1 | 0 | 100 | Low | Fully fulfilled
2526500083 | KBS-012 | Unknown | 1 | 1 | 0 | W1 | 0 | 100 | Low | Fully fulfilled
2526500086 | KBS-016 | Unknown | 24 | 24 | 0 | W1 | 0 | 100 | Low | Fully fulfilled
2526500087 | KBS-017 | Unknown | 6 | 6 | 0 | W1 | 0 | 100 | Low | Fully fulfilled
2526500091 | KBS-018 | Unknown | 12 | 12 | 0 | W1 | 0 | 100 | Low | Fully fulfilled
2526500092 | KBS-017 | Unknown | 2 | 2 | 0 | W1 | 0 | 100 | Low | Fully fulfilled
2526500093 | KBS-018 | Unknown | 24 | 24 | 0 | W1 | 0 | 100 | Low | Fully fulfilled
2526500094 | KBS-017 | Unknown | 20 | 20 | 0 | W1 | 0 | 100 | Low | Fully fulfilled
2526500095 | KBS-017 | Unknown | 22 | 22 | 0 | W1 | 0 | 100 | Low | Fully fulfilled
2526500096 | KBS-017 | Unknown | 18 | 18 | 0 | W1 | 0 | 100 | Low | Fully fulfilled
2526500097 | KBS-017 | Unknown | 4 | 4 | 0 | W1 | 0 | 100 | Low | Fully fulfilled
2526500104 | KBS-016 | Unknown | 24 | 24 | 0 | W1 | 0 | 100 | Low | Fully fulfilled
2526500105 | KBS-016 | Unknown | 24 | 24 | 0 | W1 | 0 | 100 | Low | Fully fulfilled
2526500107 | KBS-014 | Unknown | 24 | 24 | 0 | W1 | 0 | 100 | Low | Fully fulfilled
2526500109 | KBS-008 | Unknown | 22 | 22 | 0 | W1 | 0 | 100 | Low | Fully fulfilled
2526500114 | KBS-009 | Unknown | 20 | 20 | 0 | W1 | 0 | 100 | Low | Fully fulfilled
2526500116 | KBS-011 | Unknown | 15 | 15 | 0 | W1 | 0 | 100 | Low | Fully fulfilled
2526500124 | KBS-009 | Unknown | 20 | 20 | 0 | W1 | 0 | 100 | Low | Fully fulfilled
2526100567 | ARM-007 | Unknown | 4 | 4 | 0 | W2 | 1 | 100 | Low | Fully fulfilled
2526201160 | MCB-HYG-034 | Unknown | 20 | 20 | 0 | W2 | 1 | 100 | Low | Fully fulfilled
2526201341 | MCB-009 | Unknown | 7 | 7 | 0 | W2 | 1 | 100 | Low | Fully fulfilled
2526201341 | MCB-JLG-031 | Unknown | 1 | 1 | 0 | W2 | 1 | 100 | Low | Fully fulfilled
2526201561 | LKK-01 | Unknown | 2 | 2 | 0 | W2 | 1 | 100 | Low | Fully fulfilled
2526201561 | TAS-GN-006 | Unknown | 7 | 7 | 0 | W2 | 1 | 100 | Low | Fully fulfilled
2526201561 | ATT-001 | Unknown | 1 | 1 | 0 | W2 | 1 | 100 | Low | Fully fulfilled
2526202819 | MCB-HYG-016 | Unknown | 5 | 5 | 0 | W2 | 1 | 100 | Low | Fully fulfilled
2526202820 | MCB-HYG-016 | Unknown | 5 | 5 | 0 | W2 | 1 | 100 | Low | Fully fulfilled
2526202964 | LKK-01 | Unknown | 8 | 8 | 0 | W2 | 1 | 100 | Low | Fully fulfilled
2526202964 | LKK-02 | Unknown | 8 | 8 | 0 | W2 | 1 | 100 | Low | Fully fulfilled
2526202964 | LKK-03 | Unknown | 8 | 8 | 0 | W2 | 1 | 100 | Low | Fully fulfilled
2526203076 | UBC-020 | Unknown | 8 | 8 | 0 | W2 | 1 | 100 | Low | Fully fulfilled
2526203076 | UBC-022 | Unknown | 4 | 4 | 0 | W2 | 1 | 100 | Low | Fully fulfilled
2526203076 | UBC-050 | Unknown | 4 | 4 | 0 | W2 | 1 | 100 | Low | Fully fulfilled
2526203076 | UBC-051 | Unknown | 4 | 4 | 0 | W2 | 1 | 100 | Low | Fully fulfilled
2526203078 | UBC-014 | Unknown | 50 | 50 | 0 | W2 | 1 | 100 | Low | Fully fulfilled
2526203131 | MCB-JLG-014 | Unknown | 6 | 6 | 0 | W2 | 1 | 100 | Low | Fully fulfilled
2526203138 | MCB-009 | Unknown | 12 | 12 | 0 | W2 | 1 | 100 | Low | Fully fulfilled
2526203140 | MCB-JLG-047 | Unknown | 11 | 11 | 0 | W2 | 1 | 100 | Low | Fully fulfilled
2526203142 | MCB-JLG-020 | Unknown | 4 | 4 | 0 | W2 | 1 | 100 | Low | Fully fulfilled
2526203153 | MCB-008 | Unknown | 6 | 6 | 0 | W2 | 1 | 100 | Low | Fully fulfilled
2526203154 | MCB-008 | Unknown | 6 | 6 | 0 | W2 | 1 | 100 | Low | Fully fulfilled
2526203163 | MCB-JLG-014 | Unknown | 6 | 6 | 0 | W2 | 1 | 100 | Low | Fully fulfilled
2526203164 | MCB-008 | Unknown | 6 | 6 | 0 | W2 | 1 | 100 | Low | Fully fulfilled
2526203171 | MCB-010 | Unknown | 7 | 7 | 0 | W2 | 1 | 100 | Low | Fully fulfilled
2526203172 | MCB-010 | Unknown | 7 | 7 | 0 | W2 | 1 | 100 | Low | Fully fulfilled
2526203173 | MCB-010 | Unknown | 7 | 7 | 0 | W2 | 1 | 100 | Low | Fully fulfilled
2526203174 | MCB-010 | Unknown | 7 | 7 | 0 | W2 | 1 | 100 | Low | Fully fulfilled
2526203175 | MCB-010 | Unknown | 7 | 7 | 0 | W2 | 1 | 100 | Low | Fully fulfilled
2526203176 | MCB-010 | Unknown | 7 | 7 | 0 | W2 | 1 | 100 | Low | Fully fulfilled
2526203177 | MCB-010 | Unknown | 7 | 7 | 0 | W2 | 1 | 100 | Low | Fully fulfilled
2526203249 | MCB-JLG-019 | Unknown | 15 | 15 | 0 | W2 | 1 | 100 | Low | Fully fulfilled
2526203250 | MCB-JLG-019 | Unknown | 15 | 15 | 0 | W2 | 1 | 100 | Low | Fully fulfilled
2526203251 | MCB-JLG-019 | Unknown | 15 | 15 | 0 | W2 | 1 | 100 | Low | Fully fulfilled
2526203271 | DGC-001 | Unknown | 38 | 38 | 0 | W2 | 1 | 100 | Low | Fully fulfilled
2526203271 | DGC-012 | Unknown | 36 | 36 | 0 | W2 | 1 | 100 | Low | Fully fulfilled
2526203287 | MCB-JLG-014 | Unknown | 6 | 6 | 0 | W2 | 1 | 100 | Low | Fully fulfilled
2526203332 | DGC-006 | Unknown | 10 | 10 | 0 | W2 | 1 | 100 | Low | Fully fulfilled
2526203332 | DGC-009 | Unknown | 14 | 14 | 0 | W2 | 1 | 100 | Low | Fully fulfilled
2526203388 | MCB-JLG-032 | Unknown | 4 | 4 | 0 | W2 | 1 | 100 | Low | Fully fulfilled
2526203463 | LKK-04 | Unknown | 4 | 4 | 0 | W2 | 1 | 100 | Low | Fully fulfilled
2526203463 | LKK-05 | Unknown | 4 | 4 | 0 | W2 | 1 | 100 | Low | Fully fulfilled
2526203463 | LKK-06 | Unknown | 4 | 4 | 0 | W2 | 1 | 100 | Low | Fully fulfilled
2526203463 | LKK-16 | Unknown | 12 | 12 | 0 | W2 | 1 | 100 | Low | Fully fulfilled
2526203463 | LKK-17 | Unknown | 12 | 12 | 0 | W2 | 1 | 100 | Low | Fully fulfilled
2526500098 | KBS-017 | Unknown | 22 | 22 | 0 | W2 | 1 | 100 | Low | Fully fulfilled
2526500106 | KBS-017 | Unknown | 12 | 12 | 0 | W2 | 1 | 100 | Low | Fully fulfilled
2526500120 | KBS-009 | Unknown | 20 | 20 | 0 | W2 | 1 | 100 | Low | Fully fulfilled
2526500122 | KBS-011 | Unknown | 15 | 15 | 0 | W2 | 1 | 100 | Low | Fully fulfilled
2526500125 | KBS-011 | Unknown | 15 | 15 | 0 | W2 | 1 | 100 | Low | Fully fulfilled
2526500126 | KBS-012 | Unknown | 24 | 24 | 0 | W2 | 1 | 100 | Low | Fully fulfilled
2526500127 | KBS-012 | Unknown | 24 | 24 | 0 | W2 | 1 | 100 | Low | Fully fulfilled
2526500130 | KBS-014 | Unknown | 24 | 24 | 0 | W2 | 1 | 100 | Low | Fully fulfilled
2526100568 | ARM-007 | Unknown | 4 | 4 | 0 | W3 | 2 | 100 | Low | Fully fulfilled
2526202965 | LKK-01 | Unknown | 8 | 8 | 0 | W3 | 2 | 100 | Low | Fully fulfilled
2526202965 | LKK-02 | Unknown | 8 | 8 | 0 | W3 | 2 | 100 | Low | Fully fulfilled
2526202965 | LKK-03 | Unknown | 8 | 8 | 0 | W3 | 2 | 100 | Low | Fully fulfilled
2526203252 | MCB-HYG-023 | Unknown | 6 | 6 | 0 | W3 | 2 | 100 | Low | Fully fulfilled
2526203253 | MCB-HYG-015 | Unknown | 8 | 8 | 0 | W3 | 2 | 100 | Low | Fully fulfilled
2526203255 | MCB-008 | Unknown | 6 | 6 | 0 | W3 | 2 | 100 | Low | Fully fulfilled
2526203256 | MCB-007 | Unknown | 4 | 4 | 0 | W3 | 2 | 100 | Low | Fully fulfilled
2526203258 | MCB-JLG-033 | Unknown | 4 | 4 | 0 | W3 | 2 | 100 | Low | Fully fulfilled
2526203260 | MCB-010 | Unknown | 7 | 7 | 0 | W3 | 2 | 100 | Low | Fully fulfilled
2526203261 | MCB-JLG-014 | Unknown | 6 | 6 | 0 | W3 | 2 | 100 | Low | Fully fulfilled
2526203262 | MCB-JLG-014 | Unknown | 6 | 6 | 0 | W3 | 2 | 100 | Low | Fully fulfilled
2526203386 | MCB-007 | Unknown | 4 | 4 | 0 | W3 | 2 | 100 | Low | Fully fulfilled
2526203387 | MCB-007 | Unknown | 4 | 4 | 0 | W3 | 2 | 100 | Low | Fully fulfilled
2526203396 | MCB-010 | Unknown | 7 | 7 | 0 | W3 | 2 | 100 | Low | Fully fulfilled
2526203397 | MCB-010 | Unknown | 7 | 7 | 0 | W3 | 2 | 100 | Low | Fully fulfilled
2526203454 | TAS-GN-029 | Unknown | 6 | 6 | 0 | W3 | 2 | 100 | Low | Fully fulfilled
2526203454 | TAS-GN-029 | Unknown | 12 | 12 | 0 | W3 | 2 | 100 | Low | Fully fulfilled
2526203454 | TAS-GN-021 | Unknown | 12 | 12 | 0 | W3 | 2 | 100 | Low | Fully fulfilled
2526203454 | TAS-GN-029 | Unknown | 12 | 12 | 0 | W3 | 2 | 100 | Low | Fully fulfilled
2526203456 | TAS-GN-012 | Unknown | 9 | 9 | 0 | W3 | 2 | 100 | Low | Fully fulfilled
2526203456 | TAS-GN-008 | Unknown | 1 | 1 | 0 | W3 | 2 | 100 | Low | Fully fulfilled
2526203459 | TAS-GN-014 | Unknown | 10 | 10 | 0 | W3 | 2 | 100 | Low | Fully fulfilled
2526203459 | TAS-GN-007 | Unknown | 20 | 20 | 0 | W3 | 2 | 100 | Low | Fully fulfilled
2526203459 | TAS-GN-009 | Unknown | 20 | 20 | 0 | W3 | 2 | 100 | Low | Fully fulfilled
2526203459 | TAS-GN-006 | Unknown | 9 | 9 | 0 | W3 | 2 | 100 | Low | Fully fulfilled
2526203464 | LKK-033 | Unknown | 6 | 6 | 0 | W3 | 2 | 100 | Low | Fully fulfilled
2526203464 | LKK-034 | Unknown | 3 | 3 | 0 | W3 | 2 | 100 | Low | Fully fulfilled
2526203464 | LKK-030 | Unknown | 3 | 3 | 0 | W3 | 2 | 100 | Low | Fully fulfilled
2526203464 | LKK-031 | Unknown | 3 | 3 | 0 | W3 | 2 | 100 | Low | Fully fulfilled
2526203464 | LKK-032 | Unknown | 3 | 3 | 0 | W3 | 2 | 100 | Low | Fully fulfilled
2526500099 | KBS-017 | Unknown | 22 | 22 | 0 | W3 | 2 | 100 | Low | Fully fulfilled
2526500110 | KBS-016 | Unknown | 24 | 24 | 0 | W3 | 2 | 100 | Low | Fully fulfilled
2526500131 | KBS-014 | Unknown | 24 | 24 | 0 | W3 | 2 | 100 | Low | Fully fulfilled
2526202954 | ATT-001 | Unknown | 8 | 8 | 0 | W4 | 3 | 100 | Low | Fully fulfilled
2526202954 | ATT-002 | Unknown | 8 | 8 | 0 | W4 | 3 | 100 | Low | Fully fulfilled
2526202955 | ATT-001 | Unknown | 8 | 8 | 0 | W4 | 3 | 100 | Low | Fully fulfilled
2526202955 | ATT-002 | Unknown | 8 | 8 | 0 | W4 | 3 | 100 | Low | Fully fulfilled
2526203095 | LKK-10 | Unknown | 10 | 10 | 0 | W4 | 3 | 100 | Low | Fully fulfilled
2526203095 | LKK-11 | Unknown | 10 | 10 | 0 | W4 | 3 | 100 | Low | Fully fulfilled
2526203095 | LKK-12 | Unknown | 10 | 10 | 0 | W4 | 3 | 100 | Low | Fully fulfilled
2526203274 | DGC-001 | Unknown | 56 | 56 | 0 | W4 | 3 | 100 | Low | Fully fulfilled
2526203310 | UBC-022 | Unknown | 8 | 8 | 0 | W4 | 3 | 100 | Low | Fully fulfilled
2526203310 | UBC-050 | Unknown | 4 | 4 | 0 | W4 | 3 | 100 | Low | Fully fulfilled
2526203310 | UBC-051 | Unknown | 4 | 4 | 0 | W4 | 3 | 100 | Low | Fully fulfilled
2526203310 | UBC-021 | Unknown | 2 | 2 | 0 | W4 | 3 | 100 | Low | Fully fulfilled
2526203311 | UBC-019 | Unknown | 14 | 14 | 0 | W4 | 3 | 100 | Low | Fully fulfilled
2526203312 | UBC-018 | Unknown | 36 | 36 | 0 | W4 | 3 | 100 | Low | Fully fulfilled
2526203312 | UBC-019 | Unknown | 1 | 1 | 0 | W4 | 3 | 100 | Low | Fully fulfilled
2526203312 | UBC-019 | Unknown | 1 | 1 | 0 | W4 | 3 | 100 | Low | Fully fulfilled
2526203370 | MCB-JLG-047 | Unknown | 11 | 11 | 0 | W4 | 3 | 100 | Low | Fully fulfilled
2526203373 | MCB-JLG-019 | Unknown | 15 | 15 | 0 | W4 | 3 | 100 | Low | Fully fulfilled
2526203374 | MCB-JLG-020 | Unknown | 4 | 4 | 0 | W4 | 3 | 100 | Low | Fully fulfilled
2526203375 | MCB-007 | Unknown | 4 | 4 | 0 | W4 | 3 | 100 | Low | Fully fulfilled
2526203376 | MCB-007 | Unknown | 4 | 4 | 0 | W4 | 3 | 100 | Low | Fully fulfilled
2526203377 | MCB-007 | Unknown | 4 | 4 | 0 | W4 | 3 | 100 | Low | Fully fulfilled
2526203378 | MCB-007 | Unknown | 4 | 4 | 0 | W4 | 3 | 100 | Low | Fully fulfilled
2526203379 | MCB-007 | Unknown | 4 | 4 | 0 | W4 | 3 | 100 | Low | Fully fulfilled
2526203380 | MCB-007 | Unknown | 4 | 4 | 0 | W4 | 3 | 100 | Low | Fully fulfilled
2526203381 | MCB-007 | Unknown | 4 | 4 | 0 | W4 | 3 | 100 | Low | Fully fulfilled
2526203382 | MCB-007 | Unknown | 4 | 4 | 0 | W4 | 3 | 100 | Low | Fully fulfilled
2526203383 | MCB-007 | Unknown | 4 | 4 | 0 | W4 | 3 | 100 | Low | Fully fulfilled
2526203384 | MCB-007 | Unknown | 4 | 4 | 0 | W4 | 3 | 100 | Low | Fully fulfilled
2526203385 | MCB-007 | Unknown | 4 | 4 | 0 | W4 | 3 | 100 | Low | Fully fulfilled
2526203389 | MCB-JLG-047 | Unknown | 11 | 11 | 0 | W4 | 3 | 100 | Low | Fully fulfilled
2526203394 | MCB-008 | Unknown | 6 | 6 | 0 | W4 | 3 | 100 | Low | Fully fulfilled
2526203398 | MCB-HYG-023 | Unknown | 6 | 6 | 0 | W4 | 3 | 100 | Low | Fully fulfilled
2526203455 | TAS-GN-010 | Unknown | 2 | 2 | 0 | W4 | 3 | 100 | Low | Fully fulfilled
2526203455 | TAS-GN-011 | Unknown | 2 | 2 | 0 | W4 | 3 | 100 | Low | Fully fulfilled
2526203455 | TAS-GN-021 | Unknown | 14 | 14 | 0 | W4 | 3 | 100 | Low | Fully fulfilled
2526203455 | TAS-GN-029 | Unknown | 3 | 3 | 0 | W4 | 3 | 100 | Low | Fully fulfilled
2526203457 | TAS-GN-012 | Unknown | 10 | 10 | 0 | W4 | 3 | 100 | Low | Fully fulfilled
2526203460 | TAS-GN-004 | Unknown | 9 | 9 | 0 | W4 | 3 | 100 | Low | Fully fulfilled
2526203465 | LKK-035 | Unknown | 9 | 9 | 0 | W4 | 3 | 100 | Low | Fully fulfilled
2526500111 | KBS-017 | Unknown | 20 | 20 | 0 | W4 | 3 | 100 | Low | Fully fulfilled
2526500112 | KBS-017 | Unknown | 20 | 20 | 0 | W4 | 3 | 100 | Low | Fully fulfilled
2526203096 | LKK-10 | Unknown | 10 | 10 | 0 | W5 | 4 | 100 | Low | Fully fulfilled
2526203096 | LKK-11 | Unknown | 10 | 10 | 0 | W5 | 4 | 100 | Low | Fully fulfilled
2526203096 | LKK-12 | Unknown | 10 | 10 | 0 | W5 | 4 | 100 | Low | Fully fulfilled
2526203097 | LKK-10 | Unknown | 10 | 10 | 0 | W5 | 4 | 100 | Low | Fully fulfilled
2526203097 | LKK-11 | Unknown | 10 | 10 | 0 | W5 | 4 | 100 | Low | Fully fulfilled
2526203097 | LKK-12 | Unknown | 10 | 10 | 0 | W5 | 4 | 100 | Low | Fully fulfilled
2526203236 | ATT-002 | Unknown | 28 | 28 | 0 | W5 | 4 | 100 | Low | Fully fulfilled
2526203276 | DGC-001 | Unknown | 34 | 34 | 0 | W5 | 4 | 100 | Low | Fully fulfilled
2526203277 | DGC-001 | Unknown | 56 | 56 | 0 | W5 | 4 | 100 | Low | Fully fulfilled
2526203331 | UBC-022 | Unknown | 8 | 8 | 0 | W5 | 4 | 100 | Low | Fully fulfilled
2526203331 | UBC-050 | Unknown | 4 | 4 | 0 | W5 | 4 | 100 | Low | Fully fulfilled
2526203331 | UBC-051 | Unknown | 4 | 4 | 0 | W5 | 4 | 100 | Low | Fully fulfilled
2526203331 | UBC-021 | Unknown | 2 | 2 | 0 | W5 | 4 | 100 | Low | Fully fulfilled
2526203458 | TAS-GN-012 | Unknown | 10 | 10 | 0 | W5 | 4 | 100 | Low | Fully fulfilled
2526203461 | TAS-GN-004 | Unknown | 6 | 6 | 0 | W5 | 4 | 100 | Low | Fully fulfilled
2526203461 | TAS-GN-008 | Unknown | 3 | 3 | 0 | W5 | 4 | 100 | Low | Fully fulfilled
2526203462 | TAS-GN-008 | Unknown | 3 | 3 | 0 | W5 | 4 | 100 | Low | Fully fulfilled
2526203462 | TAS-GN-008 | Unknown | 6 | 6 | 0 | W5 | 4 | 100 | Low | Fully fulfilled
2526500113 | KBS-017 | Unknown | 20 | 20 | 0 | W5 | 4 | 100 | Low | Fully fulfilled
2526500117 | KBS-009 | Unknown | 2 | 2 | 0 | W5 | 4 | 100 | Low | Fully fulfilled
2526500119 | KBS-011 | Unknown | 1 | 1 | 0 | W5 | 4 | 100 | Low | Fully fulfilled
2526500121 | KBS-009 | Unknown | 2 | 2 | 0 | W5 | 4 | 100 | Low | Fully fulfilled
2526500123 | KBS-011 | Unknown | 1 | 1 | 0 | W5 | 4 | 100 | Low | Fully fulfilled
2526203098 | LKK-10 | Unknown | 10 | 10 | 0 | W6 | 5 | 100 | Low | Fully fulfilled
2526203098 | LKK-11 | Unknown | 10 | 10 | 0 | W6 | 5 | 100 | Low | Fully fulfilled
2526203098 | LKK-12 | Unknown | 10 | 10 | 0 | W6 | 5 | 100 | Low | Fully fulfilled
2526203103 | NMS-V-004 | Unknown | 5 | 5 | 0 | W6 | 5 | 100 | Low | Fully fulfilled
2526203148 | NMS-V-004 | Unknown | 5 | 5 | 0 | W6 | 5 | 100 | Low | Fully fulfilled
2526203259 | MCB-009 | Unknown | 12 | 12 | 0 | W6 | 5 | 100 | Low | Fully fulfilled
2526203280 | DGC-001 | Unknown | 56 | 56 | 0 | W6 | 5 | 100 | Low | Fully fulfilled
2526203390 | MCB-009 | Unknown | 12 | 12 | 0 | W6 | 5 | 100 | Low | Fully fulfilled
2526203427 | UBC-022 | Unknown | 8 | 8 | 0 | W6 | 5 | 100 | Low | Fully fulfilled
2526203427 | UBC-050 | Unknown | 4 | 4 | 0 | W6 | 5 | 100 | Low | Fully fulfilled
2526203427 | UBC-051 | Unknown | 4 | 4 | 0 | W6 | 5 | 100 | Low | Fully fulfilled
2526203427 | UBC-021 | Unknown | 2 | 2 | 0 | W6 | 5 | 100 | Low | Fully fulfilled
2526203099 | LKK-01 | Unknown | 4 | 4 | 0 | W7 | 6 | 100 | Low | Fully fulfilled
2526203099 | LKK-02 | Unknown | 4 | 4 | 0 | W7 | 6 | 100 | Low | Fully fulfilled
2526203099 | LKK-03 | Unknown | 4 | 4 | 0 | W7 | 6 | 100 | Low | Fully fulfilled
2526203099 | LKK-10 | Unknown | 4 | 4 | 0 | W7 | 6 | 100 | Low | Fully fulfilled
2526203099 | LKK-11 | Unknown | 4 | 4 | 0 | W7 | 6 | 100 | Low | Fully fulfilled
2526203099 | LKK-12 | Unknown | 4 | 4 | 0 | W7 | 6 | 100 | Low | Fully fulfilled
2526203482 | UBC-022 | Unknown | 8 | 8 | 0 | W7 | 6 | 100 | Low | Fully fulfilled
2526203482 | UBC-050 | Unknown | 4 | 4 | 0 | W7 | 6 | 100 | Low | Fully fulfilled
2526203482 | UBC-051 | Unknown | 4 | 4 | 0 | W7 | 6 | 100 | Low | Fully fulfilled
2526203482 | UBC-021 | Unknown | 2 | 2 | 0 | W7 | 6 | 100 | Low | Fully fulfilled
2526203484 | UBC-014 | Unknown | 50 | 50 | 0 | W7 | 6 | 100 | Low | Fully fulfilled
2526203549 | DGC-001 | Unknown | 56 | 56 | 0 | W7 | 6 | 100 | Low | Fully fulfilled
2526203554 | DGC-012 | Unknown | 40 | 40 | 0 | W7 | 6 | 100 | Low | Fully fulfilled
2526202956 | ATT-001 | Unknown | 8 | 8 | 0 | W8 | 7 | 100 | Low | Fully fulfilled
2526202956 | ATT-002 | Unknown | 8 | 8 | 0 | W8 | 7 | 100 | Low | Fully fulfilled
2526202957 | ATT-001 | Unknown | 8 | 8 | 0 | W8 | 7 | 100 | Low | Fully fulfilled
2526202957 | ATT-002 | Unknown | 8 | 8 | 0 | W8 | 7 | 100 | Low | Fully fulfilled
2526203547 | UBC-020 | Unknown | 4 | 4 | 0 | W8 | 7 | 100 | Low | Fully fulfilled
2526203547 | UBC-050 | Unknown | 12 | 12 | 0 | W8 | 7 | 100 | Low | Fully fulfilled
2526203547 | UBC-051 | Unknown | 12 | 12 | 0 | W8 | 7 | 100 | Low | Fully fulfilled
2526203547 | UBC-021 | Unknown | 2 | 2 | 0 | W8 | 7 | 100 | Low | Fully fulfilled
2526203550 | DGC-001 | Unknown | 56 | 56 | 0 | W8 | 7 | 100 | Low | Fully fulfilled
2526203551 | DGC-001 | Unknown | 56 | 56 | 0 | W8 | 7 | 100 | Low | Fully fulfilled
2526203555 | DGC-012 | Unknown | 40 | 40 | 0 | W8 | 7 | 100 | Low | Fully fulfilled
2526203552 | DGC-001 | Unknown | 56 | 56 | 0 | W9 | 8 | 100 | Low | Fully fulfilled
2526203556 | DGC-012 | Unknown | 34 | 34 | 0 | W9 | 8 | 100 | Low | Fully fulfilled
2526203556 | DGC-001 | Unknown | 12 | 12 | 0 | W9 | 8 | 100 | Low | Fully fulfilled
2526203553 | DGC-001 | Unknown | 56 | 56 | 0 | W10 | 9 | 100 | Low | Fully fulfilled
2526202958 | ATT-001 | Unknown | 8 | 8 | 0 | W13 | 12 | 100 | Low | Fully fulfilled
2526202958 | ATT-002 | Unknown | 8 | 8 | 0 | W13 | 12 | 100 | Low | Fully fulfilled
2526202959 | ATT-001 | Unknown | 8 | 8 | 0 | W13 | 12 | 100 | Low | Fully fulfilled
2526202959 | ATT-002 | Unknown | 8 | 8 | 0 | W13 | 12 | 100 | Low | Fully fulfilled
2526202960 | ATT-001 | Unknown | 8 | 8 | 0 | W17 | 16 | 100 | Low | Fully fulfilled
2526202960 | ATT-002 | Unknown | 8 | 8 | 0 | W17 | 16 | 100 | Low | Fully fulfilled
2526202961 | ATT-001 | Unknown | 8 | 8 | 0 | W17 | 16 | 100 | Low | Fully fulfilled
2526202961 | ATT-002 | Unknown | 8 | 8 | 0 | W17 | 16 | 100 | Low | Fully fulfilled

## 5_RISK_BY_CUSTOMER
Customer | Total_Orders | Critical_Orders | High_Risk_Orders | Total_Unmet_Qty | Priority
Unknown | 303 | 6 | 0 | 21 | High

## 6_RISK_BY_WEEK
Week | Total_Orders | Critical | High_Risk | Unmet_Qty
W1 | 97 | 6 | 0 | 16
W2 | 54 | 0 | 0 | 0
W3 | 34 | 0 | 0 | 0
W4 | 42 | 0 | 0 | 0
W5 | 25 | 0 | 0 | 2
W6 | 12 | 0 | 0 | 0
W7 | 14 | 0 | 0 | 1
W8 | 12 | 0 | 0 | 1
W9 | 4 | 0 | 0 | 1
W10 | 1 | 0 | 0 | 0
W13 | 4 | 0 | 0 | 0
W17 | 4 | 0 | 0 | 0

## 7_CAPACITY_FORECAST
Week | Avg_Utilization_% | Constrained_Resources | Status
W1 | 85.4 | 2 | Tight
W2 | 84.8 | 1 | Tight
W3 | 77.9 | 0 | OK
W4 | 76.2 | 0 | OK
W5 | 58.3 | 0 | OK
W6 | 0 | 0 | OK
W7 | 0 | 0 | OK
W8 | 0 | 0 | OK
W9 | 0 | 0 | OK
W10 | 0 | 0 | OK
W11 | 0 | 0 | OK
W12 | 0 | 0 | OK
W13 | 0 | 0 | OK
W14 | 0 | 0 | OK
W15 | 0 | 0 | OK
W16 | 0 | 0 | OK
W17 | 0 | 0 | OK
W18 | 0 | 0 | OK
W19 | 0 | 0 | OK

## 8_CAPACITY_BY_RESOURCE
Resource | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19
Big_Line | 4 (TIGHT) | 20 | 61 | 27 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130
Casting | 121 | 135 | 30 | 37 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000
Grinding | 58 | 63 | 77 | 55 | 92 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000
MC1 | 74 | 61 | 64 | 38 | 44 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000
MC2 | 48 | 51 | 44 | 46 | 37 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000
MC3 | 22 | 10 | 10 | 12 | 2 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000
SP1 | 109 | 76 | 84 | 55 | 155 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000
SP2 | 94 | 61 | 78 | 53 | 177 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000
SP3 | 62 | 29 | 34 | 19 | 121 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000
Small_Line | 12 (TIGHT) | 5 (TIGHT) | 52 | 108 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130

## 9_ATP_NEW_ORDERS
Part_Code | Requested_Qty | Requested_Week | Feasible | Earliest_Delivery | Delay_Weeks | Limiting_Resource | Confidence | Notes
PART-001 | 100 | W5 | No | W0 | 0 | Unknown | Low | Part PART-001 not found in Part_Parameters
PART-002 | 200 | W6 | No | W0 | 0 | Unknown | Low | Part PART-002 not found in Part_Parameters
PART-003 | 150 | W7 | No | W0 | 0 | Unknown | Low | Part PART-003 not found in Part_Parameters

## 10_RECOMMENDATIONS
Priority | Category | Recommendation | Description | Impact | Action_Items | Affected_Resources | Expected_Benefit
Critical | Scheduling | Address Critical Orders Immediately | 6 orders are at critical risk of missing delivery. | 16 units at risk | • Review critical order list with planning team • Expedite production for critical items • Communicate proactively with affected customers • Identify alternative supply options | - | Prevent customer escalations
High | Capacity | Increase Big Line Capacity | BIG_LINE is overloaded by 0.0 hours across the planning horizon. | Affects casting schedule and downstream operations | • Add overtime shifts (weekend/evening) • Consider outsourcing overflow castings • Evaluate equipment utilization improvements • Review pattern changeover times for optimization | BIG_LINE | Recover 0.0 hours capacity
High | Capacity | Increase Small Line Capacity | SMALL_LINE is overloaded by 0.0 hours across the planning horizon. | Affects casting schedule and downstream operations | • Add overtime shifts (weekend/evening) • Consider outsourcing overflow castings • Evaluate equipment utilization improvements • Review pattern changeover times for optimization | SMALL_LINE | Recover 0.0 hours capacity
High | Process | Customer Communication Plan | 1 customers have at-risk orders. | Customer relationships at stake | • Prepare status updates for affected customers • Propose recovery plans with revised dates • Consider compensation/goodwill gestures • Schedule follow-up calls | - | Maintain customer trust

## 11_ACTION_PLAN
Action_# | Priority | Action | Category | Recommendation
1 | Critical | Review critical order list with planning team | Scheduling | Address Critical Orders Immediately
2 | Critical | Expedite production for critical items | Scheduling | Address Critical Orders Immediately
3 | High | Add overtime shifts (weekend/evening) | Capacity | Increase Big Line Capacity
4 | High | Consider outsourcing overflow castings | Capacity | Increase Big Line Capacity
5 | High | Add overtime shifts (weekend/evening) | Capacity | Increase Small Line Capacity
6 | High | Consider outsourcing overflow castings | Capacity | Increase Small Line Capacity
7 | High | Prepare status updates for affected customers | Process | Customer Communication Plan
8 | High | Propose recovery plans with revised dates | Process | Customer Communication Plan